## Weekly Update 20090407
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | Department of Defense
| Week End Date: | 2009-04-03
| Submitter Name: | Department of Defense
| Submitter Contact Info: | 703-428-0711
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 17 | 1116 |  | Operation and Maintenance, Marine Corps - Recovery Act (2009 \ 2010) | 113865000
2 | 17 | 1117 |  | Operation and Maintenance, Marine Corps Reserve - Recovery Act (2009 \ 2010) | 39909000 | 2700000
3 | 17 | 1206 |  | Military Construction, Navy - Recovery Act (2009 \ 2013) | 280000000 | 500000
4 | 17 | 1320 |  | Research, Development, Test, and Evaluation, Navy - Recovery Act (2009 \ 2010) | 75000000
5 | 17 | 1805 |  | Operation and Maintenance, Navy - Recovery Act (2009 \ 2010) | 657051000
6 | 17 | 1807 |  | Operation and Maintenance, Navy Reserve - Recovery Act (2009 \ 2010) | 55083000
7 | 21 | 721 |  | Family Housing Construction, Army - Recovery Act (2009 \ 2013) | 34507000
8 | 21 | 726 |  | Family Housing Operation and Maintenance, Army - Recovery Act (2009 \ 2010) | 3932000
9 | 21 | 2022 |  | Operation and Maintenance, Army - Recovery Act (2009 \ 2010) | 1474525000
10 | 21 | 2041 |  | Research, Development, Test, and Evaluation, Army - Recovery Act (2009 \ 2010) | 75000000
11 | 21 | 2051 |  | Military Construction, Army - Recovery Act (2009 \ 2013) | 180000000
12 | 21 | 2066 |  | Operation and Maintenance, Army National Guard - Recovery Act (2009 \ 2010) | 266304000
13 | 21 | 2081 |  | Operation and Maintenance, Army Reserve - Recovery Act (2009 \ 2010) | 98269000
14 | 21 | 2094 |  | Military Construction, Army National Guard - Recovery Act (2009 \ 2013) | 50000000
15 | 57 | 743 |  | Family Housing Construction, Air Force - Recovery Act (2009 \ 2013) | 80100000
16 | 57 | 748 |  | Family Housing Operation and Maintenance, Air Force - Recovery Act (2009 \ 2010) | 16461000
17 | 57 | 3307 |  | Military Construction, Air Force - Recovery Act (2009 \ 2013) | 180000000
18 | 57 | 3404 |  | Operation and Maintenance, Air Force - Recovery Act (2009 \ 2010) | 1095959000
19 | 57 | 3605 |  | Research, Development, Test, and Evaluation, Air Force - Recovery Act (2009 \ 2010) | 75000000
20 | 57 | 3744 |  | Operation and Maintenance, Air Force Reserve - Recovery Act (2009 \ 2010) | 13187000
21 | 57 | 3834 |  | Military Construction, Air National Guard - Recovery Act (2009 \ 2013) | 50000000
22 | 57 | 3844 |  | Operation and Maintenance, Air National Guard - Recovery Act (2009 \ 2010) | 25848000
23 | 97 | 112 |  | Office of the Inspector General - Recovery Act (2009 \ 2011) | 15000000
24 | 97 | 150 |  | Defense Health Program - Recovery Act (2009 \ 2010) | 400000000
25 | 97 | 401 |  | Research, Development, Test, and Evaluation, Defense-wide - Recovery Act (2009 \ 2010) | 75000000
26 | 97 | 501 |  | Military Construction, Defense-wide - Recovery Act (2009 \ 2013) | 1450000000
27 | 97 | 4091 |  | Homeowners Assistance Fund - Recovery Act (X) | 555000000 | 150621 | 105905
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | Contracting requirements for Recovery Act projects were published in the March 31, 2009 Federal Register. This allows DoD to begin awarding contracts for Recovery Act projects. | DoD will submit a report to the White House Council on Environmental Quality on National Environmental Protection Act and National Historic Preservation Act requirements by April 9.
2 | DoD awarded its first Recovery Act project contracts. Total DoD Obligations to date are $3.4 million, including $2.7 million for a Marine Corps Vehicle Maintenance Facility and Tactical Vehicle & Equipment Storage area in Cincinnati, OH; a $ 0.5 million Navy project for Steam Line Replacement in Norfolk VA; and $0.2 million for the Army Corps of Engineers for the management of the Homeowners Assistance program. | The Department is reviewing the updated guidance provided by OMB on April 3 and is working to ensure procedures are established to meet reporting requirements. This includes weekly financial data submissions as well as the Agency and Program plans due on May 1.
3 | DOD is finalizing the remaining Army and Army National Guard Facility Sustainment Restoration and Modernization (FSRM) project lists to submit to OMB for approval by April 18th . | The Navy plans to award at least 5 FSRM projects and 1 additional Military Construction project by April 10.
4 | DoD managers met with the DoD Inspector General to discuss details on Recovery Act financial data collection and reporting. | DoD continues to develop Homeowner's Assistance Program implementation guidance.
5 | The US Army Corps of Engineers and the Army have finalized fund transfer procedures for managing Facility Sustainment Restoration and Modernization (FSRM) projects which will ease the financial reporting process.
6
7
8
9
10
11
12
13
14
15
16
17
18
19