## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | US Department of State
| Week End Date: | 2009-03-13
| Submitter Name: | Patrick F. Kennedy
| Submitter Contact Info: | Rachel Arndt (202) 647-1068
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 19 | 112 |  | Diplomatic and Consular Programs | 90000000 | 0 | 0
2 | 19 | 1119 |  | Capital Investment Fund | 290000000 | 0 | 0
3 | 19 | 530 |  | Office of Inspector General | 2000000 | 0 | 0
4 | 19 | 1079 |  | International Boundary and Water Commission - Construction | 220000000 | 0 | 0
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | International Boundary and Water Commission (IBWC) - Concluded negotiations for geo-technical investigations under RFP 09-07 for Lower Rio Grande Valley Reach (Lateral A - Donna Pump) | IBWC - Complete Procurement Strategy for entire plan
2 | IBWC - Developed preliminary procurement strategy for entire project plan | IBWC - Issue award for Geo-Technical Investigations service contract of Lower Rio Grande Valley Reach (Lateral A - Donna Pump) on March 18, 2009
3 | IBWC - Completed selection for 1 Term Engineering position. On-board/starts date is 03/16/2009 | IBWC - Complete procurement packages by 03/31/2009 of all pre-construction activities (statements of work and estimates for geo-tech, environmental, and design work )
4 | IBWC - Completed selection for 2 Term Contract Specialist positions. On-board/start dates projected for 03/23/2009 | IBWC - Developing phased plan obligation plan of all planned levee work by procurement line item
5 | Consular Affairs - Met with General Services Administration (GSA) to discuss space issues in relation to passport facilities | IBWC - Complete selection of second Term Engineering position on 03/16/2009
6 | Office of the Inspector General (OIG) held discussions with GSA/OIG on tracking/oversight of construction-related funding transferred to GSA
7 | Foreign Service Institute started Vendor Pre-performance service survey for language classrooms and offices renovations for the purpose of establishing measurements, parts requirements and costs
8 | OIG provided initial plan for oversight to Rep. Darrell Issa (R-CA)
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29