Billing Code: 4163-18-P

DEPARTMENT OF HEALTH AND HUMAN SERVICES

Centers for Disease Control and Prevention

Childhood Lead Poisoning Prevention Program (CLPPP)

ALL AMENDMENTS CAN BE FOUND IN RED WITHIN THE DOCUMENT.

Announcement Type: New

Funding Opportunity Number: CDC-RFA-EH06-602

Catalog of Federal Domestic Assistance Number: 93.197

Key Dates:

Application Deadline: February 21, 2006

# I. Funding Opportunity Description

Authority: This program is authorized under Sections 317(k)(2), 317A and 317B of the Public Health Service Act, [42 U.S.C. 247b(k)(2), 247b-1, and 247b-3], as amended. Relevant provisions of the Project Grant for Preventive Health Services Regulations are set forth at 42 CFR Part 51b.

Background: From 1990 to 2005, CDC has appropriated funds to state and local health departments to support childhood lead poisoning prevention programs. During FY 2005 alone, CDC allocated nearly 30 million dollars to state and city health departments. As a result of the collaboration between Department of Housing and Urban Development (HUD), and Environmental Protection Agency (EPA) and the support of state and local activities, the geometric mean (GM) blood lead levels in children one through five years of age have dropped to an average of 1.9 micrograms per deciliter (µg/dL) from a high of 15 µg/dL in the early 1980s.

Childhood lead poisoning remains a major preventable environmental health problem. It is a serious illness with potential lifelong negative health effects for children in all socioeconomic strata, but it disproportionately affects poor, and minority children.

According to the National Health and Nutrition Survey (NHANES), during the 1999-2002 survey period, children aged one-five years had a prevalence of elevated blood lead levels of 1.6 percent.  An estimated 310,000 children in that age group remain at risk to lead levels that have been associated with decreased intelligence, behavioral disturbances, delayed development, and other adverse health effects.  Moreover, disparities in exposure remain: the geometric mean (GM) BLL of children enrolled in Medicaid is significantly higher than children who are not enrolled (2.5µg/dL vs 1.9 µg/dL, respectively).

According to the 1999 General Accounting Office (GAO) “Report on Lead Poisoning”, the majority (83%) of children with elevated blood lead levels (≥10µg/dL) were Medicaid eligible. Currently, less than half (43%) of Medicaid- eligible children ever receive a blood lead screening test. The sources of lead poisoning for most of these children are lead paint in homes and lead paint-contaminated dust and soil.

In recent years, with an increasing number of refugees and other immigrants entering the United States, a corresponding increase has been seen in non-paint lead exposure (e.g., lead has been found in some homeopathic remedies, candies, pottery and other dishes used in food storage, preparation and serving).

In 2004, newly arrived children in New Hampshire from Africa were identified with elevated blood lead levels.  The medical records indicated that the blood lead elevations, in some cases frank lead poisoning, occurred after the children were relocated to the United States.  The children also showed evidence of extreme chronic malnutrition (MMWR January 21, 2005).

Most U.S. children today who have lead poisoning or who are at high-risk for lead poisoning, including the recent arrivals are impoverished and live in older, deteriorating housing and children whose nutritional status is compromised are at an even greater risk.

CDC believes that with a continued concerted effort, especially in the area of primary prevention, lead poisoning will be virtually eliminated by 2010, and the nation’s health objective to "eliminate blood lead levels in children," as presented in the U.S. Department of Health and Human Services’ "Healthy People 2010” (objective no.8-11) will be achieved.

Program efforts need to increase focus in the area of housing-based primary prevention policy development and provide the necessary data to policy makers that will assure their support of those policies. Housing-based primary prevention policy will assure lead-safe housing is available for families with young children beyond 2010.

After 2010, program efforts will continue to focus on blood lead surveillance, however, other surveillance activities that reveal changes in housing risk status and non-paint exposure sources will likely be added.

Purpose: The purpose of the program is to assist state and local partners in building capacity to eliminate childhood lead poisoning as a major public health problem. The focus of the program is children under the age of six years with special emphasis on children under the age of three years. Special emphasis will be placed on building capacity for primary prevention of lead poisoning and on implementing protective housing-based policy that will remain in place beyond 2010.

All appendices and attachments posted with this announcement are also posted on the CDC Web site at: www.cdc.gov/od/pgo/funding/grantmain.htm

Measurable outcomes of the program will align with one (or more) of the following performance goal(s) for the National Lead Poisoning Prevention Branch (LPPB) of the National Center for Environmental Health (NCEH):

- To reduce the burden of lead poisoning in children,

- To improve the ability of state childhood lead poisoning prevention programs’ to monitor the burden of lead poisoning in children, and

- To assure implementation of systems to control/eliminate lead sources before children are exposed.

This announcement is only for non-research activities supported by CDC.  If research is proposed, the application will not be reviewed.  For the definition of research, please see the CDC Web site at: http://www.cdc.gov/od/ads/opspoll1.htm

Applicants must provide information related to the lead burden in their jurisdiction using blood lead testing data (see Appendix IX), population data, poverty status/Medicaid data, and age of housing or other housing-specific condition data and present data about non-paint sources of lead exposure in high-risk urban, suburban, and rural areas (if applicable) and describe populations living in those areas.

RECIPIENT ACTIVITIES: Awardee activities for this program are the following elements:

Note that the following elements are to be included as components of the Work Plan, including the goals, objectives and activities detailed under each element.  The goals, objectives and activities of the Evaluation Plan should also be included as a component of the Work Plan.

A) Elimination Plan

Applicants with an existing strategic elimination plan shall provide a copy of the plan as an attachment to the application.  The plan shall include activities for periodic meeting of the elimination advisory group (at least semiannually, preferably quarterly), indicate how data are used to assess progress, and to provide guidance to advance the plan.  The elimination advisory group is made up of stakeholders interested in childhood lead poisoning issues.  This advisory group is convened by the applicant for the purpose of seeking the stakeholders advice on the development and implementation of the jurisdiction’s lead poisoning elimination plan. The elimination plan shall include goals, objectives, and activities.  Applicants shall include activities to monitor/evaluate the elimination advisory group’s activities on a regular basis for the purpose of enhancing the overall plan.  In addition to the urban areas, the plan must include specific goals, objectives, and activities related to older suburban and rural areas, as applicable.

The elimination plan shall include a graphic representation (e.g., table, chart) of total projected numbers of children with elevated blood lead levels (≥10µg/dL) by budget year with projected reduction by budget year until elimination of elevated blood lead levels in children is achieved.

Applicants without an existing elimination plan will develop, publish and implement one by the end of the first budget period.  See Appendix V.

B) Screening/Case Management Plan

Applicants with an existing blood lead screening/case management plan shall provide a copy of the plan as an attachment to the application.  The applicants must include the following activities in their work plan or case management plan:

- Review of the plan, annually, including how the review outcome will be utilized to increase the number of high risk children who receive blood lead screening.

- Methodology used to measure screening performance of providers (including Medicaid providers).

- Provision of education and communication of risk information to the high-risk populations identified in the Need Section of the application.

- Assessment of the timeliness, quality and improvement of the provision of case management services in compliance with recommendations from Advisory Committee on Childhood Lead Poisoning Prevention, “Managing Elevated Blood Lead Levels Among Young Children” (CDC, March 2002).

- Provision of electronic case management data, including inspection data and hazard control/intervention data into an electronic database and sent to CDC, portions of which will be made available for public use.  Applicant must include written data quality assurance procedures.

- Enforcement, or a plan to develop, regulations within the state or jurisdiction requiring elimination or control of lead hazards in housing units occupied by children with an elevated blood lead level, in collaboration with state and local housing and environmental quality authorities.

- Enforcement, or plan to develop, regulations within the state or local jurisdiction that provide resident/tenant protection from retaliatory eviction or other discrimination related to disclosure of lead hazards or elevated blood lead levels.

- Requirement of the reduction of lead hazards, including performance of mandatory dust wipe testing to assure clearance standards are met after remediation work in accordance with EPA standards 40 CFR Part 745.227.  This citation can be accessed at http://www.access.gpo.gov/nara/cfr/waisidx_03/40cfr745_03.html

- Accessing information during environmental inspections related to the HUD Disclosure Rule (Section 1018 of the Residential Lead-Based Paint Hazard Reduction Act of 1992) and forward potential violations of federal regulations to HUD and EPA Regional Office for enforcement and potential violations of local ordinances to local housing enforcement authorities.

Sharing of unit-specific data obtained during environmental investigations with appropriate public agencies (e.g., state and local housing and environmental quality authorities, Medicaid, HUD and EPA Regional Offices). Applicants shall describe how elevated blood lead data will be provided quarterly to housing authorities of federally subsidized housing, as required under HUD 1012 Lead-Safe Housing Rule 24 CFR 35.1225.  This citation can be accessed at http://www.gpoaccess.gov/cfr/retrieve.html

Applicants without an existing screening/case management plan will provide activities with a timeline to ensure that the plan will be developed, published and implemented by the end of the first budget period.

C) Surveillance

Applicants with an existing surveillance system shall provide description of the system (e.g., what data are collected and how they are used by program) and a detailed flow chart for both individual and summary blood lead test data in the application as an appendix.  Applicants must include written data quality assurance procedures.

Applicants must include the following activities in their work plan:

- Enforcement, or a plan to develop regulations that require electronic reporting of all blood lead and environmental test results for children less than 72 months of age.   See Appendix I for definition of “Electronic Laboratory-Based Reporting (ELR)”.

- Maintenance of an existing, or development of an electronic data base to collect, compile and share blood lead and case management data, including environmental inspection, hazard identification, remediation, and clearance data.  These data shall integrate or interface with other maternal child and environmental public health databases (e.g., immunization registries, Adult Blood Lead Epidemiology and Surveillance [ABLES]; National Electronic Disease Surveillance System [NEDSS]; Medicaid; and Special Supplemental Nutrition Program for Women, Infants and Children [WIC]; state and local housing and environmental quality authorities).

- Identification of Medicaid-eligible children who have not received required blood lead testing (e.g., data sharing, data matching) in partnership with state Medicaid agency.

- Development and publishing of an annual report for stakeholders; include distribution plan for elimination planning group, HUD and EPA Regional Offices, state and local leaders of governing bodies, and Health Departments (e.g., Governor, Mayor, state and local legislators, Health Commissioner, and state and local Health Directors).  Applicants shall include in report the number of inspections, risk assessments, EBLL investigations, abatements, interim control applications, and similar lead hazard identification and control activities in its jurisdiction.

- Provision of public access to data without personal identifiers.

Applicants developing a new data system shall include in the application as an appendix, a complete listing of partners involved in the development, describe the planned data system and its resource requirements, including both development and maintenance costs and provide evidence (i.e., letters of support) that partners include, but are not limited to the following: state epidemiology group, state information technology department and state EPHTP (Environmental Public Health Tracking Program, if one exists).  See list of state and city EPHTPs at  http://www.cdc.gov/nceh/tracking/projects/home.htm.

Applicants without an existing surveillance system shall include specific activities describing the surveillance system that will be designed and implemented by the end of the first budget period.  Applicants must include written data quality assurance procedures.  See Appendix VI for guidance.

D) Primary Prevention

Applicants shall provide specific goals and objectives that include primary prevention objectives for families: those who live in pre-1978 housing (prioritized to pre-1950), pregnant women, women of childbearing age, families with young children and others at risk for lead exposure.

Applicants shall include in their work plan the following specific activities:

- Systematic standardized assessment of housing in the jurisdiction; inspections shall include testing of deteriorated paint, dust wipe testing and testing of bare soil to locate all lead-based paint hazards, as defined in EPA 40 CFR Part 745.226.  This citation can be accessed at http://www.access.gpo.gov/nara/cfr/waisidx_03/40cfr745_03.html

- Performance of inspection activities in housing where a child with an elevated blood lead level lives, where the child spends a significant amount of time, secondary residences, and other areas where the child (or other children) may be exposed to lead hazards (e.g., in buildings with more than one housing unit, conduct inspection not only in the elevated blood lead child’s residence, but also in adjacent units where children could be at risk.

- Development of primary prevention activities that are consistent with the Preventing Lead Exposure In Young Children: A Housing-Based Approach to Primary Prevention of Lead Poisoning (CDC, October 2004).  See Appendix IV for examples of primary prevention activities.

- Assurance of lead-safe work practices, conduct lead-safe work practice training, provision of resources to help families, building owners, maintenance and housing rehabilitation workers, and others to reduce lead hazards (in accordance with Sections 1012-1013 of Title X of the Residential Lead-Based Paint Hazard Reduction Act of 1992, as implemented in 24 CFR Part 35). Guidance on this Rule can be found http://www.hud.gov/offices/lead/leadsaferule/LSHRGuidance21June04.rtf

- Ensure dust wipe test clearance standards are met after abatement work, remediation, or other hazard control work is completed, consistent with EPA 40 CFR Part 745.227.  This citation can be found at http://www.access.gpo.gov/nara/cfr/waisidx_03/40cfr745_03.html

- Enforcement, or a plan to develop, regulations within the state or jurisdiction requiring elimination or control of lead hazards in housing units occupied by children and based on the existence of the lead hazard alone in housing units that could be occupied by children, with the exception of housing where a child is not expected to reside, such as elderly housing.

●	Risk communication/health education activities that support primary prevention activities and are targeted to the high-risk populations identified in the Need section of the application.

E) Strategic Partnerships

- State Health Commissioner/local Health Director ensures that child health data will be used to facilitate development of child health and housing-based legislative policy and that those policies will be supported through implementation.

- The state Health Commissioner/local Health Director shall endorse CLPPP participation in emerging health situations related to lead exposure (e.g., African refugee lead exposure).

Applicants shall include in their application as appendices, evidence of partnership, collaboration or planned partnership or collaboration with:

- Appropriate stakeholders via letters of support or MOUs with housing agencies, financial institutions, CBOs, Medicaid, WIC, landlord groups, lead inspectors, hazard control and/or construction and/or maintenance contractors, etc.  Note: letters of support or MOUs shall include meeting frequency, roles, and specific responsibilities/activities for each partner.

- EPHTP (if one exists).  See list of state and city EPHTPs at http://www.cdc.gov/nceh/tracking/projects/home.htm.

- State’s Office of Rural Health.  See list of state contacts at

http://ruralhealth.hrsa.gov/funding/50sorh.htm

- State refugee coordinator.  See list of state contacts at

http://www.acf.hhs.gov/programs/orr/partners/coordina.htm

- Cooperative State Research Education and Extension Service.  See list of state contacts at

http://www.csrees.usda.gov/qlinks/partners/state_partners.html

Applicants will establish effective, well-defined working relationships within public health agencies and other agencies and organizations at national, state, and community levels and include the following activities in their work plan:

- Collaboration with local housing agencies in the development of the lead poisoning prevention aspect of the jurisdiction’s annual action and 5-year consolidated housing plan.

- Collaboration and integration of lead services into existing maternal-child health home visitation, other environmental programs and/or housing subsidy program (e.g., Section 8 Housing Choice Voucher program).

- Collaboration with regional HUD and EPA Offices in targeting enforcement of Section 1018 of Title X Lead Disclosure Rule.  More information regarding this Rule can be found at   http://www.epa.gov/opptintr/lead/leadbase.htm

- Development of EPA Supplemental Environmental Projects (SEPs) and/or HUD Child Health Improvement Projects (CHIPs).

WORKPLAN

Applicants shall submit a work plan for the current budget period that includes specific, measurable, achievable, realistic, and time-phased goals, objectives and activities. Applicants must include the activities provided in the program elements: A) elimination plan, B) screening/case management plan, C) surveillance, D) primary prevention, and E) strategic partnerships. Those objectives and activities must be in alignment with the applicant’s existing or proposed elimination plan and targeted to those populations and areas identified as high-risk in the Need section of the application.

Applicants shall include supporting activities of 1) local programs and other organizations that are sub-grantees of funds awarded under this announcement and 2) activities of other communities that have been identified as high risk in the Need section of this application, but which are not necessarily sub-grantees of funds awarded under this announcement.

Include with the application as an appendix, a tentative work plan outline for years two through five of the project period that is in alignment with the elimination plan tentative goals and objectives for years two through five of the project period.  See Appendix VII.

EVALUATION PLAN

An evaluation plan must be included with the application and part of the Work Plan. The evaluation plan must include:

- Measures related to each goal in the elimination plan.

- Measures that evaluate the objectives and activities of the annual work plan.

- Includes the name or, if person has not been hired, position (include job description) responsible for conducting the evaluation.

- Indicates evaluation frequency.

- Indicates how the results will be used to improve the program.

Applicants must include in the application as an appendix, a logic model that addresses the program as a whole, including inputs and activities of staff, and strategic partners; and activities, objectives, process, and outcome/impact indicators that are consistent with the elimination plan and the annual work plan.  See Appendix VIII.

PROJECT MANAGMENET, STAFFING AND RESOURCES

Applicants must provide information that demonstrates their agency’s commitment to the elimination of childhood lead poisoning.  Applicant provides curriculum vitae for existing key personnel (job descriptions for planned key personnel). As determined by the Grants Project Officer, key personnel must have the level of education, experience and/or skills necessary to successfully implement and complete the project.  In accordance with 45 CRF part 92.30(d)(3), found at  http://frwebgate.access.gpo.gov/cgi-bin/get-cfr.cgi?TITLE=45&PART=92&SECTION=30&YEAR=2001&TYPE=TEXT

key personnel that require prior approval are the following: Program Manager/Director, Principal Investigator, and Surveillance Manager/Epidemiologist. Applicants must provide commitment that key staff vacancies will be filled by end of first quarter, first budget period and within one quarter when they become vacant during the project period.

In a cooperative agreement, CDC staff is substantially involved in the program activities, above and beyond routine grant monitoring.  CDC activities include, but are not limited to the following:

- Foster collaboration with other federal, state, and local health; environmental; and housing agencies by initiating contacts, conference calls, and on-site visits to discuss programmatic issues.

- To ensure program success, CDC will be an equal partner with programmatic involvement throughout the project period by provision of technical assistance, advice, and coordination.

- Within first twelve (12) months, provide advice on the project’s design/existing data collection approach to ensure that it is reasonable to achieve the goals of the program.

- Provide technical advice about integrating blood lead and environmental data systems, including coordination of required quarterly or annual data submission to CDC.

- Provide technical assistance in implementing activities and identifying major childhood lead poisoning prevention program issues, effective strategies, and priorities related to the cooperative agreement.

- Advise on planning, development, implementation, and evaluation of elimination plan, including policy development and revisions to the plan, and approve the plan.

- Facilitate and assist selected projects in the development and implementation of housing-based primary prevention surveillance activities.

- Regularly review the literature to ensure that partners are being provided technical assistance and consultation that reflects the most current science and practice.

- Advise on the development of an appropriate evaluation plan that measures the effectiveness of project activities and approve the plan within twelve (12) months of grant award.

- Annually review screening/case management plans, and elimination plans including evaluation reports for the purpose of identifying opportunities for the provision of technical assistance.

- Provide approval for key personnel.

# II. Award Information

Type of Award: Cooperative Agreement. CDC’s involvement in this program is listed in the Activities Section above.

Fiscal Year Funds: 2006

Approximate Current Fiscal Year Funding: $30,000,000

Approximate Number of Awards: Up to 45 awards are expected to be awarded.

Approximate Average Award: The average award is expected to be $667,000. (This amount is for the first 12-month budget period, and includes both direct and indirect costs.)

Floor of Individual Award Range: None

Ceiling of Individual Award Range: The first year budget period ceiling for an individual award is $1,700,000.

Anticipated Award Date: July 1, 2006

Budget Period Length: 12 months

Project Period Length: Five years

Throughout the project period, CDC’s commitment to continuation of awards will be conditioned on the availability of funds, evidence of satisfactory progress by the recipient as documented by actual program performance, and the determination that continued funding is in the best interest of the Federal government.

# III. Eligibility Information

III.1. Eligible applicants - Eligible applicants that can apply for this funding opportunity are as follows:

Applications may be submitted by state health departments, or their bona fide agents and the local health departments of the following five jurisdictions:

New York, NY; Chicago, IL; Detroit, MI; Los Angeles County, CA; and Philadelphia, PA.  CDC will give funding preference to these five local jurisdictions with the highest estimated number of children with elevated blood lead levels.

CDC will also give funding preference to state programs that have significant estimated numbers of children with elevated blood lead levels, and that direct federal funds to localities with high concentrations of children at risk for childhood lead poisoning.

State health departments or their bona fide agents include the District of Columbia, the Commonwealth of Puerto Rico, the Virgin Islands, the Commonwealth of the Northern Marianna Islands, American Samoa, Guam, the Federated States of Micronesia, the Republic of the Marshall Islands, the Republic of Palau and federally recognized Indian tribal governments.  Competition is limited to these entities by authorizing legislation.

A bona fide agent is an agency or organization identified by the state as eligible to submit an application under the state eligibility in lieu of a state application.  If applying as a bona fide agent of a state or local government, a letter from the state or local government as documentation of the status is required.  Place this documentation behind the first page of the application form.  The bona fide agent documentation will not be counted towards the 40-page limit.

III.2. Cost Sharing or Matching

- Applicants must assure that income earned by the CLPPP will be returned to the program to support lead poisoning prevention activities.

- In accordance with Section 2501 (a) of the Children’s Health Act of 2000,[42 U.S.C. Section 247b-16], the state agrees to expend (through state or local funds) $1 for every $2 provided under the grant. (States may include in-kind contributions and state share of Medicaid reimbursement funds for this match).

- Preference will be given to those applicants that demonstrate detailed significant in-kind contributions.  Significant in-kind contributions are those contributions in excess of the match requirement (i.e.,>50%).  This funding preference is given in accordance with Departmental policy in that,

  - The project or activities will have a greater likelihood of success if there are other contributors to the costs of the project, and

  - the likelihood that the project will become self-sustaining when CDC funding ends will be increased, and

  - the cooperative agreement support is only one of a number of known potential sources for the funding of an activity.

- Costs and third party in-kind contributions counting towards satisfying a cost sharing or matching requirement must be verifiable from the records of grantees and sub-grantee or cost-type contractors. These records must show how the value placed on third party in-kind contributions was derived. To the extent feasible, volunteer services will be supported by the same methods that the organization uses to support the allocability of regular personnel costs.  All in-kind contributions identified in the application must be reported on form 424A and tracked by the recipient.

III.3. Other

If a funding amount greater than the ceiling of the award range is requested, the application will be considered non-responsive and will not be entered into the review process.  The applicant will be notified that the application did not meet the submission requirements.

Special Requirements:

If the application is incomplete or nonresponsive to the special requirements listed in this section, it will not be entered into the review process.  The applicant will be notified the application did not meet submission requirements.

- Late applications will be considered non-responsive.  See Section “IV.3. Submission Dates and Times” for more information on deadlines.

- Applicants must show evidence of collaboration with housing agency and/or environmental quality authority in jurisdiction (i.e., letter of support or MOU).

- Applicants must present letter of commitment from state Health Commissioner/local Health Department Director that assures child health data will be used to develop and support protective child health policy.

- Applicants directly providing services must be enrolled with their state Medicaid agency as a Medicaid provider.  Providers entering into agreements with the applicants to provide such services must be enrolled with their state Medicaid agency as a Medicaid provider.  To satisfy this program requirement, applicants must present a copy of Medicaid Provider Certification/Statement as proof that this requirement is met.  Failure to include this information will result in the application being returned.  This information shall be placed immediately behind the Resource Worksheet pages and will not be counted towards the 40-page limit.

- Applicants shall provide in the appendix, assurance that authorization for travel for CDC-funded personnel to attend CDC sponsored grantee meetings, conferences and trainings will be provided. (See section IV.5. Funding Restrictions)

- Note: Title 2 of the United States Code Section 1611 states that an organization described in Section 501(c)(4) of the Internal Revenue Code that engages in lobbying activities is not eligible to receive Federal funds constituting a grant, loan, or an award.

# IV. Application and Submission Information

IV.1. Address to Request Application Package

To apply for this funding opportunity, use application form PHS 5161-1.

Electronic Submission:

CDC strongly encourages the applicant to submit the application electronically by utilizing the forms and instructions posted for this announcement on www.Grants.gov, the official Federal agency wide E-grant Web site.  Only applicants who apply on-line are permitted to forego paper copy submission of all application forms.

Registering your organization through www.Grants.gov is the first step in submitting applications online. Registration information is located in the “Get Started” screen of www.Grants.gov. While application submission through www.Grants.gov is optional, we strongly encourage you to use this online tool.

Please visit www.Grants.gov at least 30 days prior to filing your application to familiarize yourself with the registration and submission processes. Under “Get Started”, the one-time registration process will take three to five days to complete. We suggest submitting electronic applications prior to the closing date so if difficulties are encountered, you can submit a hard copy of the application prior to the deadline.

Paper Submission:

Application forms and instructions are available on the CDC Web site, at the following Internet address: www.cdc.gov/od/pgo/forminfo.htm

If access to the Internet is not available, or if there is difficulty accessing the forms on-line, contact the CDC Procurement and Grants Office Technical Information Management Section (PGO-TIM) staff at 770-488-2700 and the application forms can be mailed

IV.2. Content and Form of Submission

Application: A project narrative must be submitted with the application forms.  The narrative must be submitted in the following format:

- Maximum number of pages for narrative: 40 pages. This includes the Need, Capacity, Work plan (include all program element activities), and Evaluation Plan.  If your narrative exceeds the page limit, only the first pages within the page limit will be reviewed.

- Font size: 12 point unreduced

- Double-spaced

- Paper size: 8.5 by 11 inches

- Page margin size: One inch

- Number all pages of the application sequentially from page 1 (Application Face Page) to the end of the application, including charts, figures, tables, and appendices.

- Printed only on one side of page

- Held together only by rubber bands or metal clips, not bound in any other way.

The narrative shall address specific goals, objectives, and activities of the specific elements as the first budget period work plan, including the evaluation plan.  An outline of goals and objectives for years two through five of the project period should be included as an appendix.  The application must include the following items in the order listed:

Cover letter *

Project Abstract – not to exceed 2 pages single spaced *

SF424 *

Bona fide agent documentation (if applicable) *

Narrative includes: Need, Capacity, Work Plan and Evaluation Plan (not to exceed 40 pages).

Budget narrative *

Resource spreadsheet *

Medicaid Provider Certification *

Checklist *

Assurances *

Other Certifications *

Disclosure Forms *

Appendices *

* NOT included in 40-page limit

Information to be included in the application appendices:

- Curriculum Vitas, Resumes, Organizational Charts, Letters of Support, MOUs, copies of elimination, screening/case management plans, matrix of work plan, logic model, outline of goals and objectives for years two through five of the project period, etc.

The agency or organization is required to have a Dun and Bradstreet Data Universal Numbering System (DUNS) number to apply for a grant or cooperative agreement from the Federal government.  The DUNS number is a nine-digit identification number, which uniquely identifies business entities.  Obtaining a DUNS number is easy and there is no charge.  To obtain a DUNS number, access www.dunandbradstreet.com or call 1-866-705-5711.

For more information, see the CDC Web site at: http://www.cdc.gov/od/pgo/funding/grantmain.htm.

If the application form does not have a DUNS number field, please write the DUNS number at the top of the first page of the application, and/or include the DUNS number in the application cover letter.

Additional requirements that may require submittal of additional documentation with the application are listed in section “VI.2.  Administrative and National Policy Requirements.”

# IV.3. Submission Dates and Times

Application Deadline Date: February 21, 2006

Explanation of Deadlines: Applications must be received in the CDC Procurement and Grants Office by 4:00 p.m. Eastern Time on the deadline date.

Applications may be submitted electronically at www.grants.gov.  Applications completed on-line through Grants.gov are considered formally submitted when the applicant organization’s Authorizing Official electronically submits the application to www.grants.gov.  Electronic applications will be considered as having met the deadline if the application has been submitted electronically by the applicant organization’s Authorizing Official to Grants.gov on or before the deadline date and time.

If submittal of the application is done electronically through Grants.gov (http://www.grants.gov), the application will be electronically time/date stamped, which will serve as receipt of submission.  Applicants will receive an e-mail notice of receipt when CDC receives the application.

If submittal of the application is by the United States Postal Service or commercial delivery service, the applicant must ensure that the carrier will be able to guarantee delivery by the closing date and time.  If CDC receives the submission after the closing date due to: (1) carrier error, when the carrier accepted the package with a guarantee for delivery by the closing date and time, or (2) significant weather delays or natural disasters, the applicant will be given the opportunity to submit documentation of the carrier’s guarantee.  If the documentation verifies a carrier problem, CDC will consider the submission as having been received by the deadline.

If a hard copy application is submitted, CDC will not notify the applicant upon receipt of the submission.  If questions arise on the receipt of the application, the applicant should first contact the carrier.  If the applicant still has questions, contact the PGO-TIM staff at (770)488-2700.  The applicant should wait two to three days after the submission deadline before calling.  This will allow time for submissions to be processed and logged.

This announcement is the definitive guide on application content, submission address, and deadline.  It supersedes information provided in the application instructions.  If the application submission does not meet the deadline above, it will not be eligible for review, and will be discarded.  The applicant will be notified the application did not meet the submission requirements.

IV.4. Intergovernmental Review of Applications

Executive Order 12372 does not apply to this program.

IV.5. Funding restrictions

Restrictions, which must be taken into account while writing your budget, are as follows:

- Funds may not be used for research.

- Reimbursement of pre-award costs is not allowed.

- Funds may not be used to pay for reimbursable Medicaid services for Medicaid-eligible children.

- Funds may not be used for medical care and treatment, or for environmental remediation of lead hazards.  However, the applicant must provide a plan to ensure that these program activities are carried out and demonstrate the program’s appropriate involvement with medical care, treatment and remediation efforts.

- Not more than 10 percent (exclusive of direct assistance) of any cooperative agreement or contract (subgrantee or consultant) funded through the cooperative agreement may be obligated for administrative costs.  This 10 percent limitation is in lieu of, and replaces, the indirect cost rate.

- A resource spreadsheet must be submitted with this application. The resource worksheet should be placed after the budget narrative and will not be counted towards the 40-page limit. See Resource Worksheet Appendix II and IIA.

- Applicants should include costs for up to two people to travel to Atlanta, GA (three-overnight stays) to attend a CDC sponsored Lead Poisoning Prevention Partners Conference.

- Applicants should include costs for an appropriate number of CDC-funded staff to travel to Alexandria, VA (five overnight stays) to attend the CDC sponsored National Lead Poisoning Prevention Training Center (LPPTC).  The appropriate number of staff to attend the LPPTC should be determined by each applicant’s staff turnover rate.

Guidance for completing the budget can be found on the CDC Web site, at

http://www.cdc.gov/od/pgo/funding/budgetguide.htm

IV.6. Other Submission Requirements

Application Submission Address:

Electronic Submission:

CDC strongly encourages applicants to submit applications electronically at www.grants.gov.  The application package can be downloaded from www.grants.gov.  Applicants are able to complete it off-line, then upload and submit the application via the grants.gov Web site.  E-mail submissions will not be accepted.  If the applicant has technical difficulties in grants.gov, costumer service can be reached by E-mail at http://www.grants.gov/CustomerSupport or by phone at 1-800-518-4726 (1-800-518-GRANTS).  The Customer Support Center is open from 7:00 a.m. to 9:00 p.m. Eastern Time, Monday through Friday.

CDC recommends that submittal of the application to grants.gov shall be early to avoid any unanticipated difficulties before to the deadline.  Applicants may also submit a back-up paper submission of the application.  Any such paper submission must be received in accordance with the requirements for timely submission detailed in Section IV.3. of the grant announcement. The paper submission must be clearly marked “BACK-UP FOR ELECTRONIC SUBMISSION.”  The paper submission must conform to all requirements for non-electronic submissions.  If both electronic and back-up paper submissions are received by the deadline, the electronic version will be considered the official submission.

The applicant must submit all application attachments using a PDF file format when submitting via Grants.gov.  Directions for creating PDF files can be found on the grants.gov Web site.  Use of file formats other than PDF may result in the file being unreadable by staff.

OR

Paper Submission:

Applicants shall submit the original and two hard copies of the application by mail or express delivery service to:

Technical Information Management- CDC-RFA-EH06-602

CDC Procurement and Grants Office

2920 Brandywine Road

Atlanta, GA 30341

# V. Application Review Information

V.1. Criteria

Applicants are required to provide measures of effectiveness that will demonstrate the accomplishment of the various identified objectives of the cooperative agreement.  Measures of effectiveness must relate to the performance goals stated in the “Purpose” section of this announcement.  Measures must be objective and quantitative and must measure the intended outcome.  The measures of effectiveness must be submitted with the application and will be an element of evaluation.

An independent review group appointed by CDC will evaluate each application against the following criteria:

NEED (Total of 25 points)

The announcement is focused on the elimination of childhood lead poisoning as a major public health problem, therefore, the assessment of need within the applicant’s jurisdiction should include focus on communities and populations where there is significant evidence of high numbers of children under six years old who are at high risk for lead poisoning. The applicant should:

- Describe the program or planned program, including the number of years in existence and/or funded by CDC (if applicable). (2 points)

- Extent of the problem as determined by blood lead testing evidence. Programs in existence since 1997 provide evidence for calendar years 1997-2004 by year (Appendix IX includes 1997-2003 data).  The data should include the number of children 0-36 months and 37-72 months tested and the number with confirmed blood lead levels ≥ 10 micrograms per deciliter (µg/dL).

- The applicant should also use:

    - population data; (5 points)

    - poverty/Medicaid data; (5 points)

    - age of housing or housing-specific  condition data; (5 points)

    - describe high-risk urban, suburban, and rural areas (if applicable) and the at- risk populations living in those areas; (5 points)

    - non-paint sources of lead exposure. (3 points)

Program Elements - CAPACITY TO ELIMINATE CHILDHOOD LEAD POISONING as a PUBLIC HEALTH PROBLEM (Total of 32 points to be distributed as follows):

- Elimination Plan (Total of 8 points)

The applicant provides evidence that they have implemented an elimination plan or will implement such a plan by the end of the first budget period. A copy of the plan should be included as an appendix in the application. An elimination plan should include:

  - A mission. (1 point)

  - Describes lead burden as consistent with those populations and areas identified in the NEED section. (1 point)

  - Clear, measurable goals, objectives, and activities in the proposed work plan; outline for years 2-5.  (1 point)

  - Person(s) or positions responsible for completion of objectives are named. (1 point)

  - Using data to evaluate and guide the plan. (1 point)

  - Describes activities that assure the advisory group members stayed engaged in the process to monitor and refine the plan. (1 point)

  - Provides supporting evidence, meeting agendas/minutes and list of attendees by name, title, and organization. (1 point)

  - Includes a graphic representation (e.g., chart, graph) of total projected numbers of children with elevated blood lead levels by year with projected reduction by year until elimination of elevated blood lead levels. (1 point)

2.   Screening/Case Management Plan (Total of 5 points)

The applicant provides evidence that they have implemented a screening/case management plan that targets resources to children at highest risk or will implement such a plan by the end of the first budget period.

A copy of the screening/case management plan is included as an appendix and clearly describes:

- Blood lead testing of children less than 6 years is consistent with those identified as high-risk in the Need section. (1 point)

- Electronic case management data systems are in place or planned to be in place by the end of the first budget period to identify and track children who receive timely and appropriate case management services and data are used, at least annually, to evaluate the case management process for key aspects: timeliness, written care plan, environmental inspections and lead hazard remediation, decrease in blood lead levels, and rates of case closure. (1 point)

- Minimally be consistent with recommendations from the Advisory Committee on Childhood Lead Poisoning Prevention, “Managing Elevated Blood Lead Levels Among Young Children” (CDC, March 2002). (1 point)

- Enforcement, or a plan to develop, regulations within the state or jurisdiction that require elimination or control of lead hazards in housing units occupied by children with an elevated blood lead level and resident/tenant protection from retaliatory eviction or other lead-related discrimination. (1 point)

- Current Medicaid reimbursement methodology or specific proposed reimbursement planned by end of first budget year for environmental inspections and case management services for Medicaid-eligible children and that the reimbursement plan will be reviewed at least annually, and updated as costs increase. (1 point)

3. Surveillance (Total of 10 points)

The extent to which the applicant describes their current, or planned childhood blood lead surveillance system in the following areas:

- Describes existing or plan for developing a child-specific data collection and management system allowing for multiple lab tests and multiple addresses to be related to a single child over multiple years. (1 point)

- Describes enforcement, or plan to develop, regulations within the state or jurisdiction requiring the electronic reporting of all blood lead and environmental test results for children less than 72 months of age. (1 point)

- Describes an electronic connection to other child health and environmental public health data (e.g., Medicaid, immunization, National Electronic Disease Surveillance System [NEDSS], Adult Blood Lead Epidemiology and Surveillance [ABLES], and Special Supplemental Nutrition Program for Women, Infants, and Children [WIC], state and/or local housing and environmental quality authority, or other Web-based public health data system) or if not using NEDSS, NEDSS-based, or other compatible system, applicant shows evidence of partnership through specific activities and describes what new surveillance system they are developing and evidence (through letters of support) they are working with state epidemiology  group, information technology group, and state Environmental Health Tracking Program.  Applicant also describes ongoing maintenance needs of such system and source of funding for non-NEDSS system.  If planning to use CDC Lead Program Area Module (PAM) with NBS, applicant shows evidence of communication with state NEDSS Coordinator or other NEDSS personnel (through letter of support). (2 points)

- Describes current or planned data system for identification of Medicaid-eligible children. (2 points)

- Describes adequate electronic database is in place to identify and track children who receive case management services. (1 point)

- Describes plan to report all required data elements to CDC quarterly (1 point)

- Describes plan to publish and distribute an annual data report for stakeholders.  Stakeholders to include elimination planning group, HUD and EPA Regional Offices, state and local leaders of governing bodies, (e.g., Governor, Mayor, state and local legislators, state Health Commissioner, and local Health Directors). (1 point)

- Presents a detailed flow chart in appendix of the surveillance system for both individual and summary data.  The flow chart should minimally include:  data entry, quality controls points, data usage/report generation and data transfer linkages. (1 point)

4.   Primary Prevention (Total of 5 points)

The extent in which the applicant describes and demonstrates primary prevention efforts in their jurisdiction and includes:

- Electronically collect unit-specific housing inspection data and systematic assessment of lead-safe housing status in jurisdiction by performance of environmental investigation activities such as, lead dust screening, visual inspections, paint chip, and soil testing. (1 point)

- Environmental screening for lead hazards of other high-risk housing (i.e., house next door, apartments nearby), as well as any secondary residences or day care is conducted when a child is identified with an elevated blood lead level. (1 point)

- Build community capacity to conduct lead-safe training and provide resources to help families reduce lead hazards in their homes. (1 point)

- Health education plan, including various communications and trainings to increase awareness of lead poisoning prevention, includes medical providers in this educational plan and targets the plan to high-risk populations identified in Need section of application. (1 point)

- Enforcement, or plan to develop, regulations within the state or local jurisdiction requiring the elimination or control of lead hazards in homes where children live or could live. (1 point)

5.   Strategic Partnerships (Total of 7 points)

- Applicant provides evidence of strategic partnerships via letters of support, MOUs, or contracts. Examples of key partners include housing agencies; Medicaid; Special Supplemental Nutrition for Women Infant and Children (WIC) Program; community-based organizations; landlord groups; realtors; banking; maintenance and construction contractors;  Office of Rural Health; state Environmental Public Health Tracking Program (if one exists); the state refugee coordinator, and the Cooperative State Research Education and Extension Service. (1 point)

- Letters and/or MOUs describe meeting frequency, roles, responsibilities, and activities for each partner. (1 point)

- Applicant presents a letter of commitment from state Health Commissioner/Health Department Director that assures child health data will be used to develop and support protective child health policy and endorses CLPPP response to emerging situations (e.g., African refugee lead exposure). (1 point)

- Applicant provides letter of support from jurisdiction’s housing agency and/or housing authority and/or community development agency that specifies collaborative activities related to the development of the lead poisoning prevention element of the jurisdiction’s annual and 5-year consolidated plan for housing. (1 point)

- Applicant describes partnerships involving HUD and EPA Regional Offices in the targeting of Title X enforcement in jurisdiction. Describes current (or planned) protocol to access 1018 Disclosure Rule information during environmental inspections and forward potential violations to HUD and EPA for enforcement. (1 point)

- Describes a plan for the development of EPA Supplemental Environmental Projects (SEPs) and/or HUD Children’s Health Improvement Projects (CHIPs). (1 point)

- Provides evidence that the program is collaborating with or plans to collaborate with other healthy home program issues, such as, asthma prevention, injury prevention and improvement in indoor air quality. (1 point)

WORK PLAN (Total of 20 points to be distributed as follows)

Applicant provides a work plan in this application that includes specific, measurable, achievable, realistic, and time-phased goals, objectives and activities for the first budget year.   Applicant goals, objectives, and activities must relate to elimination, screening & case management, surveillance, primary prevention, and strategic partnerships. Applicant should include evaluation measures for each proposed objective and identify the program staff responsible for accomplishing each objective.

Activities are targeted or prioritized to high-risk populations identified in the Need section of application.  (10 points)

Applicant provides work plans for potential sub-grantees awarded under this announcement that are consistent with the applicant’s work plan and elimination plan.  Activities of high-risk communities that are not potential direct sub-grantees awarded under this announcement shall also be included in objectives and/or supporting activities of the proposed work plan and shall be consistent with the elimination plan. (5 points)

Applicant provides a tentative work plan outline for years two through five of the project period.  (5 points)

Evaluation Plan (Total of 10 points)

Applicant presents an evaluation plan that is consistent with goals and objectives in work plan, indicates what data will be used to evaluate program, names person(s) (or positions if not yet hired) responsible for overall program evaluation, and indicates how results will be used to enhance program success. Outcomes/impact indicators are tied to elimination, represent substantial incremental progress leading to elimination of elevated blood lead levels by 2010, and are supported by surveillance and/or other data. (5 points)

Applicant presents a logic model that is reasonable, clear, and consistent with objectives and activities identified in the work plan and elimination plan. (5 points)

PROJECT MANAGEMENT, STAFFING and RESOURCES

(Total of 8 points)

The extent to which the applicant describes the proposed staffing, includes job descriptions and curriculum vitae that indicates the applicant’s ability to carry out the recipient activities identified in the program requirements section of this announcement.   Descriptions should include the position titles, education and experience, the staff roles with their specific responsibilities, and their level of effort and percentage of time each person will devote to the program and if key positions are vacant provides commitment that those vacancies will be filled by end of first quarter, first budget period. (5 points)

Applicants includes activities to seek reimbursement from third-party payors, including Medicaid, for those case management and environmental inspection and hazard control/intervention services that are reimbursable. (3 points)

Matching (2 points)

Preference will be given to those applicants that demonstrate detailed significant (i.e., > 50% of the funds requested in this application) in-kind contributions.

V.2. Review and Selection Process

Applications will be reviewed for completeness by the Procurement and Grants Office (PGO) staff, and for responsiveness jointly by National Center for Environmental Health/Lead Poisoning Prevention Branch and PGO.  Incomplete applications and applications that are nonresponsive to the eligibility criteria will not advance through the review process.  Applicants will be notified the application did not meet submission requirements.

An independent objective review panel appointed by CDC will evaluate complete and responsive applications according to the criteria listed in the “V.1.  Criteria” section above.  The review is generally conduced by committee or groups of field readers or by a combination of those methods.  The review of the applications is intended to be advisory and not to replace the authority of the Public Health Service authority to decide whether a grant shall be awarded.

In addition, the following factors may affect the funding decision:

- Maintaining geographic diversity.

- Preference to jurisdictions with high numbers of children under the age of 6 years with elevated blood lead levels.

Funding Preference

- Funding preference will be given to applicants that demonstrate commitment through substantial in-kind contributions, as well as clear, active collaboration with other agencies, including environmental quality authorities and housing agencies engaged in childhood lead poisoning prevention.

V.3. Anticipated Announcement and Award Dates

Award announcement date is anticipated to be on or about March 24, 2006

# VI. Award Administration Information

VI.1. Award Notices

Successful applicants will receive a Notice of Award (NoA) from the CDC Procurement and Grants Office.  The NoA shall be the only binding, authorizing document between the recipient and CDC.  The NoA will be signed by an authorized Grants Management Officer, and mailed to the recipient fiscal officer identified in the application.

Unsuccessful applicants will receive notification of the results of the application review by mail.

VI.2. Administrative and National Policy Requirements

- Successful applicants should comply with the Code of Federal Regulations and 45 CFR Parts 74 and 92. The following additional requirements apply to this project:

  - AR-9		Paperwork Reduction Act Requirements

  - AR-10 	Smoke-Free Workplace Requirements

  - AR-11 	Healthy People 2010

  - AR-12 	Lobbying Restrictions

  - AR-14 	Accounting System Requirements

  - AR-24 	Health Insurance Portability and    Accountability Act Requirements

  - AR-25	Release and Sharing of Data

Where to Obtain Additional Information

Two telephone conference calls for application technical assistance will be held during the application period.  Dates and times will be posted on www.cdc.gov/lead.  For further information please contact Paula Staley at 770-488-3300.  This and other CDC announcements, necessary applications and associated forms can be found at www.cdc.gov (click on “Funding”, then “Grants and Cooperative Agreements”).

Additional information on the requirements can be found on the CDC Web site at: http://www.cdc.gov/od/pgo/funding/ARs.htm.

For more information on the Code of Federal Regulations, see the National Archives and Records Administration at http://www.access.gpo.gov/nara/cfr/cfr-table-search.html

An additional Certification form from the PHS5161-1 application needs to be included in the grants.gov electronic submission only.  Applicants shall refer to

http://www.cdc.gov/od/pgo/funding/PHS5161-1-Certificates.pdf.  Once the applicant has filled out the form, it shall be attached to the grants.gov submission as Other Attachments Form.

VI.3. Reporting Requirements

The applicant must provide CDC with an original, plus two hard copies, of the following reports:

- Interim progress report, specifications of which will be provided under separate cover. The progress report will serve as the non-competing continuation application, and must contain the following elements:

  - Status of current budget period objectives (i.e., met, unmet, or partially met). If unmet or partially met, state why and when objective will be met or indicate how objective has been modified.

  - Programs that planned to develop an Elimination, Screening/Case Management and/or Surveillance Plans by the end of the first budget period must provide a draft copy of those plans as part of their first year interim progress report.  Programs that do not submit a draft copy of proposed plans may be subject to increased reporting requirements, or other discipline, up to and including termination of the cooperative agreement.

  - Interim financial status report projected to the end of budget period, and indicates specifically those funds that are anticipated to be unobligated.

  - New budget period proposed objectives and activities and measures of evaluation (i.e., work plan).

  - Budget.

  - Additional Requested Information.

- Final financial status report due no more than 90 days after the end of the budget period.

- Final narrative performance reports, due no more than 90 days after the end of the budget period.  Programs that planned to develop an Elimination, Screening/Case Management and/or Surveillance Plan by the end of the first budget period must provide a final copy of those plans as part of their final narrative performance report for the first budget year.  Programs that do not submit a final copy of the plans proposed to be developed in the first budget year may be subject to increased reporting requirements, or other discipline, up to and including termination of the cooperative agreement.

- Quarterly data submissions are required.  Additional information regarding data submissions will be provided to successful applicants. Data collection initiated under this cooperative agreement program has been approved by OMB under OMB number 0920-0337 “National Blood Lead Surveillance System” Expiration Date: 5/31/2008.  See Appendix VI for listing of required data elements.

The reports must be mailed to the Grants Management Specialist listed in the “Agency Contacts” section of this announcement.

Programs that fail to submit timely reports as determined by the Grant Project Officer may be subject to discipline, up to and including, termination of the cooperative agreement, as determined by the Grants Management Officer.

Programs who exhibit poor performance through lack of significant progress or completion of program goals, objectives and activities as determined by the Grant Project Officer may be subject to more frequent reporting or other discipline, up to and including termination of the cooperative agreement as determined by the Grants Management Officer.

# VII. Agency Contacts

CDC encourages inquiries about this announcement.

For general questions, contact:

Technical Information Management Section

CDC Procurement and Grants Office

2920 Brandywine Road

Atlanta, GA 30341

Telephone: 770-488-2700

For program technical assistance, contact:

Paula Staley, Project Officer

4770 Buford Highway, MS F-40

Atlanta, GA 30341

Telephone: 770-488-3300

E-mail: bgx3@cdc.gov

For financial, grants management, or budget assistance, contact:

Gary R. Teague, Grants Management Specialist

CDC Procurement and Grants Office

2920 Brandywine Road, MS E-14

Atlanta, GA 30341

Telephone: 770-488-1981

E-mail: GTeague@cdc.gov

VIII. Other Information

Other CDC funding opportunity announcements can be found on the CDC Web site at: http://www.cdc.gov/od/pgo/funding/grantmain.htm

Appendix I

Glossary of Terms

Activities: Major tasks that must be done to accomplish each objective.

Assessment: Activities organized by a public health agency to regularly and systematically collect, assemble, analyze, and make available information about the health of the community, including statistics on childhood lead poisoning risk status, community health needs, and epidemiologic and other information related to childhood lead poisoning.

Assurance: Activities organized by a health department that services necessary to achieve agreed-upon goals related to childhood lead poisoning are provided, either by encouraging actions by other entities (private or public sector), by requiring such action through regulations, or by providing services directly.

CDC – Centers for Disease Control and Prevention.

Childhood Lead Poisoning Prevention Program (CLPPP): A designated unit within an agency responsible for implementing or coordinating a systematic and comprehensive approach to childhood lead poisoning prevention.

Consolidated Housing Plan – A required document that local housing agencies submit to HUD to receive certain HUD funding for housing and community development purposes. One element of the consolidated plan involves lead poisoning prevention. For more information about the consolidated planning process, see http://www.hud.gov/offices/cpd/about/conplan/index.cfm

Confirmed Elevated Blood Lead Level: One venous blood specimen with a lead concentration greater than or equal to 10 micrograms per deciliter (µg/dL), or two capillary blood specimens drawn within 12 weeks of each other, both containing a lead concentration greater than or equal to 10 µg/dL. [Source: Council of State and Territorial Epidemiologist (CSTE) Position Statement #EH1.]

De minimus - De minimis levels. Safe work practices are not required when maintenance or hazard reduction activities do not disturb painted surfaces that total more than:

(1) 20 square feet (2 square meters) on exterior surfaces;

(2) 2 square feet (0.2 square meters) in any one interior room or space; or

(3) 10 percent of the total surface area on an interior or exterior type of component with a small surface area. Examples include window sills, baseboards, and trim.

Electronic Laboratory-Based Reporting (ELR): The transmission of data of public health importance from clinical laboratories to public health agencies in electronic format. Data transmitted by ELR should be automated and use standardized codes for tests and results allowing for more timely and complete reporting. (Source: "HISSB Archives" http://www.cdc.gov/CIC/HISSB_Archive/HISSB--Activities--Electronic_Laboratory-Based_Reporting.htm.)

Elimination (of childhood lead poisoning as a public health problem): The National Health and Nutritional Examination Survey (NHANES), a population-based survey designed to oversample children at greatest risk for elevated blood lead levels (EBLLs), reports only a five percent probability that the survey, as currently conducted, will identify any children with EBLLs when there are fewer than 12,000 nationwide. At that point, lead poisoning can no longer be considered a public health problem (i.e., public health survey instruments cannot detect cases).

EPA – U.S. Environmental Protection Agency.

Evaluation Measure: An indicator a program uses to determine achievement of a goal, objective, or activity. It can be process or outcome/impact based. Evaluation measures can be drawn from a wide range of data sources, such as blood lead surveillance, housing and other public data, Medicaid data, program documentation, special surveys, etc. The data source(s) used for evaluation should be clearly described.

Goals: An outcome a program intends to accomplish during the program period.

Healthy People 2010 goal (Objective 8-11): Eliminate elevated blood lead levels in children. Target is zero percent.

High-risk: A term used to designate areas, populations, and individuals with higher than average risk for lead exposure.

HUD – U.S. Department of Housing and Urban Development.

Human Subjects: Interaction with living people for the purpose of collecting data or specimens; use of identifiable data about living people.

Lead Hazard: Accessible paint, dust, soil, water, or other source or pathway that contains lead or lead compounds that can contribute to or cause elevated blood lead levels.

Lead hazard remediation: The elimination, reduction, or containment of known and accessible lead sources.

Logic Model – A visual presentation of inputs, activities, impacts, and outcomes that demonstrates how activities in the work plan relate to the program’s goals and objectives. Logic models are useful for project planning, management, and evaluation. Measures of evaluation can be drawn by monitoring the relations among the activities, objectives, and goals and the overall outcome.

Measure of Evaluation: A comparison between actual and planned progress in achieving programmatic goals and objectives. The measure must be objective and quantitative and must measure the intended outcome. The measure should be identified in the evaluation plan aspect of the work plan.

Objectives: The steps a program will take to achieve the goal. They are specific (identify who/what/where/when), measurable (define how much/many), achievable, realistic, and time-phased. Objectives typically include action verbs such as "identify," "develop," "increase," "apply," or "perform."

Outcome (or Impact) Evaluation: A measurement tool addressing whether distal effects are changing in your jurisdiction, and/or if your activity is responsible. Outcome/impact evaluation should be used to measure both the success of an activity in moving toward elimination of childhood lead poisoning and the comparative effectiveness of different activities toward this goal. Note: "Outcome" tends to be used when addressing whether an activity had the intended outcome, and "Impact" when addressing if an activity had the intended impact on the community.

Policy Development: A public health agency responsibility to serve the public interest in the development of comprehensive public health policies related to childhood lead poisoning prevention and treatment by promoting use of the scientific knowledge base in decision-making about public health and by leading using a strategic approach, developed on the basis of a positive appreciation for the democratic political process.

Primary Prevention: The prevention of an adverse health effect in an individual or population. Regarding lead poisoning prevention, this is reducing or eliminating a lead hazard in the environment before the exposure of an individual or population. (Source: Screening Young Children for Lead Poisoning: Guidance for State and Local Public Health Officials. CDC, November 1997.) For housing-based primary prevention recommendations, see Preventing Lead Exposure In Young Children: A Housing-Based Approach to Primary Prevention of Lead Poisoning. CDC, October 2004.

Process Evaluation Measures: A measurement that addresses whether activities are being implemented as intended.

Program Staff Responsible: Team member(s) who have primary responsibility for each activity.

Secondary Prevention – Identifying and treating individuals with established/confirmed lead poisoning. This includes those with lead poisoning as well as those at high risk for developing lead poisoning. Note that blood lead testing will determine the presence of or high risk for developing lead poisoning and, as such, is a secondary prevention activity.

Surveillance: A process that 1) systematically collects information over time about children’s blood lead levels using laboratory reports as the primary data source; 2) is used to trigger follow-up of cases, including medical and environmental field investigations, when necessary; 3) collects data for timely analysis and 4) uses data to guide planning, implementation, and evaluation of a program.

Time Frame for Completion: A projected time period recorded for each goal, objective, and activity.

Work Plan: A program management tool that provides direction and guidance for the overall program, as well as for each program component. It is designed to be used for program planning, implementation, and monitoring progress made toward program goals.

Appendix II

Resource Worksheet iNSTRUCTIONS

This guidance is offered for the preparation of a resource tool. This resource tool is a valuable addition and will be used by both the awardees and the CDC Project Officers to easily observe where agency and other resources are allocated and in what amounts, as well as identify where resources should be shifted to accomplish the Healthy People 2010 goal of elimination of lead poisoning. The CDC Project Officers will provide technical assistance to the awardees in the use of this tool during the project period. Place the Resource Worksheet after the Budget Narrative in the application. The Worksheet is not included in the maximum number of pages and is not scored.

Refer to the following numbers on the spreadsheets for definitions of required information.

Column:

  - Salaries/Position

  - Fringe

  - Consultant

  - Equipment

  - Supplies

  - Travel

  - Other

  - Contractual

  - Total Direct Costs

  - Indirect

  - Program Income (include third party reimbursements). Include financial donations, etc. Can be estimate.

  - TOTAL

- CDC Requested funds for this application

- Federal funds (other than CDC)

  - HUD

  - EPA

  - Title V

- Specify type and amount of in-kind (non-financial) contributions. Include community-based organizations (CBOs); private foundation; and other state or local contributions, such as percent of time a state or city housing inspector performs primary prevention activities, etc.

- State financial funding with source (certification fees or dedicated fee fund, paint tax, general fund, Medicaid matching, etc.)

- Total funding for elimination of lead poisoning within the jurisdiction

- Program categories - indicate percent of effort (not amount of funding).

  - Elimination planning

  - Screening/case management

  - Surveillance

  - Primary prevention (include regulatory enforcement)

  - Strategic partnerships

  - Program evaluation

Appendix IIA

| Appendix IIA |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RESOURCE WORKSHEET |  |  |  |  |  | (7) Program categories- indicate percent of effort |  |  |  |  |  |
| (1) | (2) Requested from CDC (this application) | (3) Other federal funds | (4) Other in-kind | (5) State funding | (6) Total funding for lead program | (a) Elimination Planning | (b) Screening/case management | ( c) Surveillance | (d) Primary prevention (includes regulatory enforcement | (e) Strategic partnership | (f) Program evaluation |
| Salaries/Positions |  |  |  |  |  |  |  |  |  |  |  |
| Fringe |  |  |  |  |  |  |  |  |  |  |  |
| Consultant |  |  |  |  |  |  |  |  |  |  |  |
| Equipment |  |  |  |  |  |  |  |  |  |  |  |
| Supplies |  |  |  |  |  |  |  |  |  |  |  |
| Travel |  |  |  |  |  |  |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |  |  |
| Contractual |  |  |  |  |  |  |  |  |  |  |  |
| Total Direct Costs |  |  |  |  |  |  |  |  |  |  |  |
| Indirect |  |  |  |  |  |  |  |  |  |  |  |
| Program Income |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |

Appendix III

Selected U.S. Census information indicating estimated number of children at highest risk for elevated blood lead, based on poverty and housing, states and funded cities or counties.

| State/Funded City or County | Number of children ages 5 years and younger, 2000* | Number of children ages 5 years and younger living in poverty in 1999† | Estimated number of children ages 1-5 years in poverty living in pre-1950 housing units, 2003‡ | Number of pre-1950 housing units, 2000† |
| --- | --- | --- | --- | --- |
| Alabama | 356,676 | 82,914 | 8,235 | 261,970 |
| Alaska | 57,620 | 7,718 | 370 | 12,472 |
| Arizona | 459,141 | 94,187 | 2,560 | 99,986 |
| Arkansas | 217,545 | 53,196 | 5,620 | 153,008 |
| California | 3,018,386 | 596,765 | 83,255 | 2,092,267 |
| Colorado | 357,202 | 44,237 | 12,635 | 261,751 |
| Connecticut | 270,187 | 29,348 | 10,605 | 435,884 |
| Delaware | 62,122 | 8,536 | 2,605 | 59,008 |
| District of Columbia | 39,326 | 12,696 | 3,710 | 141,138 |
| Florida | 1,142,293 | 208,747 | 17,635 | 433,564 |
| Georgia | 714,090 | 127,351 | 14,230 | 337,036 |
| Hawaii | 94,446 | 13,940 | 920 | 45,073 |
| Idaho | 116,942 | 19,341 | 3,995 | 95,144 |
| Illinois | 1,059,514 | 161,727 | 66,550 | 1,555,079 |
| Indiana | 508,845 | 73,230 | 25,065 | 717,111 |
| Iowa | 227,062 | 29,202 | 9,975 | 483,849 |
| Kansas | 226,862 | 32,253 | 9,790 | 320,648 |
| Kentucky | 320,380 | 71,871 | 10,965 | 335,067 |
| Louisiana | 381,826 | 108,795 | 18,020 | 285,831 |
| Maine | 85,915 | 13,338 | 1,960 | 233,187 |
| Maryland | 427,939 | 48,656 | 9,820 | 439,180 |
| Massachusetts | 480,422 | 58,454 | 36,900 | 1,121,552 |
| Michigan | 814,505 | 123,830 | 51,135 | 1,131,959 |
| Minnesota | 397,581 | 41,403 | 9,010 | 560,322 |
| Mississippi | 246,122 | 69,506 | 5,455 | 135,350 |
| Missouri | 445,566 | 77,253 | 13,645 | 577,060 |
| Montana | 66,452 | 14,358 | 3,175 | 101,166 |
| Nebraska | 141,081 | 19,380 | 5,620 | 233,764 |
| Nevada | 175,408 | 27,287 | 3,335 | 28,525 |
| New Hampshire | 92,378 | 8,190 | 1,530 | 157,121 |
| New Jersey | 681,609 | 76,446 | 22,390 | 998,852 |
| New Mexico | 157,439 | 42,736 | 2,185 | 90,327 |
| New York | 1,500,961 | 308,272 | 122,640 | 3,309,770 |
| North Carolina | 647,879 | 113,199 | 17,795 | 449,819 |
| North Dakota | 47,613 | 8,173 | 780 | 77,231 |
| Ohio | 911,072 | 152,373 | 49,005 | 1,502,331 |
| Oklahoma | 283,208 | 63,051 | 13,590 | 272,451 |
| Oregon | 268,083 | 44,662 | 6,895 | 299,403 |
| Pennsylvania | 884,030 | 141,187 | 57,595 | 2,113,422 |
| Rhode Island | 77,648 | 14,548 | 7,425 | 172,412 |
| South Carolina | 318,543 | 62,856 | 7,505 | 194,461 |
| South Dakota | 61,352 | 11,948 | 2,510 | 98,826 |
| Tennessee | 451,520 | 89,329 | 14,595 | 349,462 |
| Texas | 1,948,297 | 425,138 | 45,655 | 878,981 |
| Utah | 248,430 | 28,442 | 4,065 | 120,546 |
| Vermont | 41,709 | 5,448 | 1,935 | 101,489 |
| Virginia | 557,736 | 71,726 | 12,065 | 453,297 |
| Washington | 475,456 | 73,029 | 12,360 | 475,191 |
| West Virginia | 122,919 | 32,491 | 8,720 | 243,886 |
| Wisconsin | 414,337 | 52,607 | 28,035 | 722,078 |
| Wyoming | 37,226 | 6,319 | 330 | 46,514 |
| Chicago, IL | 263,486 | 74,071 | 35,555 | 602,934 |
| Detroit, MI | 93,365 | 33,217 | 28,870 | 210,588 |
| Los Angeles County, CA | 896,143 | 221,882 | 36,270 | 822,456 |
| New York, NY | 652,423 | 188,213 | 77,920 | 1,642,098 |
| Philadelphia, PA | 119,359 | 38,114 | 16,190 | 386,382 |
| United States | 23,140,901 | 4,101,689 | 886,415 | 25,815,821 |

*	Source: 2000 U.S. Census, Summary File 1 (SF1).

†	Source: 2000 U.S. Census, Summary File 3 (SF3).

‡	Source: American Community Survey (ACS), 2003. Further information regarding the ACS is available at http://www.census.gov/acs/www/

Appendix IV

Examples of Primary Prevention Activities

- Link families with young children at high risk for lead poisoning to housing inspection and environmental intervention resources before a child’s blood lead level becomes elevated.

- Evaluate lead-safe housing status of the community by conducting systematic environmental investigation activities (such as lead dust wipes, visual inspections, paint chip and soil analysis) based on the high-risk status of the housing (i.e., pre-1950 housing in poor condition), compiling those data in an electronic format, and developing an ongoing evaluation component.

- Strengthen regulatory infrastructure to create lead-safe housing. Develop and codify specifications for lead-safe housing treatments.

- Partner with housing agencies to incorporate lead hazard identification into ongoing housing code or other inspections.

- Assure that policy changes needed to promote childhood lead poisoning prevention and lead-safe environments are recommended and supported with data.

- Collaborate with other agencies and organizations and incorporate lead poisoning educational information into other health, housing, and community services that reach high-risk families. Use data to expand resources and motivate action for primary prevention.

- Conduct family and community education that support primary prevention activities.

- Conduct professional and public health education, risk communication, and training activities to increase lead poisoning prevention awareness.

- When a child is identified with an elevated blood lead level, assure that environmental testing of nearby units is conducted.

- Assure that housing units identified previously as sources for lead exposure for a child are prioritized for remediation, so that the units do not remain a source for poisoning subsequent children.

- Provide and/or build community capacity to conduct lead-safe training and provide resources to help families reduce lead hazards in their homes.

- Assure that all lead abatement contractors are certified and that all renovation and other contractors who work in pre-1978 housing are trained in lead-safe work practices.

Appendix V

Strategic Elimination Plan Guidance

The development of a strategic elimination plan to eliminate childhood lead poisoning as a public health problem by 2010 is an important tool in helping communities focus efforts and resources toward this goal. It is also instrumental in measuring progress and determining midpoint adjustments necessary to ensure success.

I. The applicant must establish an advisory committee (or expand the scope of its current advisory group) to develop and implement a jurisdiction-wide strategic elimination plan. This committee should also monitor the progress of the elimination plan, leverage resources, and have the ability to enhance cooperative efforts needed to attain the goal.

This committee should include representation from the various stakeholders who will be involved in eliminating the jurisdiction’s lead poisoning problem. They must have sufficient authority (i.e.,mid to upper management) to commit staff and resources to the plan.

The representatives should include, but are not limited to, the following:

Regional HUD Office, state and local housing program and/or environmental quality management staff.

EPA regional staff.

Real estate and landlord organizations.

Community representatives such as parents, concerned citizens, child advocates, etc.

State and local elected officials.

State Medicaid agency and managed care organizations (MCOs) management staff.

Physicians, physician organizations and/or other health care providers and organizations.

Community banking representatives.

Public health department maternal-child health and environmental management staff.

State office of rural health representative.

State refugee coordinator.

Cooperative state research education and extension service representative.

Grassroots advocacy groups focused on the jurisdiction’s most at-risk populations and community-based organizations (CBOs) focused on children’s health issues.

Other maternal-child health programs whose participants are likely to be at high risk for lead poisoning (e.g., WIC, Immunization, Asthma Prevention, Injury Prevention, Head Start and Healthy Start).

II. At a minimum, strategic elimination plan should contain:

A.	Mission Statement.

B.	Statement of Purpose.

C.	Statement of historical context and assessment of the current lead poisoning problem specific to the jurisdiction. The assessment should be based on all available data sources (e.g., blood lead tests and housing surveillance, Medicaid eligibility, tax assessor, census) that may assist the committee in determining goals, objectives, and activities. Data will also be used to measure the progress made in terms of both children (e.g., the number of children with elevated blood levels and the number of those children who remain at risk) and housing (e.g. the increase in the number of lead-safe housing units) as the applicant moves toward elimination.

D. Goals, Objectives, and Activities.

1. Develop annual goals, objectives, and activities that address, at a minimum, primary prevention, including regulatory infrastructure; screening/case management services, including environmental inspection and remediation; and surveillance data, including blood lead and housing.

2. Support each goal with 12-month (annual) objectives. The goals, objectives, and activities for first budget period should be included as part of the annual program work plan. Potential awardees should include specific annual goals, objectives, and activities from existing elimination plan (if applicable) in the first budget year of this project period and briefly describe progress on objectives and activities and clearly demonstrate “next steps” to be taken in elimination plan. If no prior elimination plan exists potential awardee must include  specific activities for first budget year of this project period as part of their work plan. See Appendix VII.

- The goals and objectives for years two through five should be provided in outline format only, because they may change based on the outcomes of the first year. Activities may change as well.

4. Annual objectives of the strategic elimination plan should be included in the annual program evaluation. See Appendix VIII.

E. The application should include letters of support from key elimination planning group participants. Letters of support should identify specific activities of the participant, including commitment of agency resources to the goal of eliminating childhood lead poisoning by 2010.

Appendix VI

SURVEILLANCE SYSTEM GUIDANCE

A childhood blood lead surveillance system should include case management and environmental inspection data as well as program monitoring capabilities, and should provide data needed to determine screening and elevated blood lead level (EBLL) rates among specific high-risk populations including Medicaid-eligible children. The system should be based on laboratory reports of blood lead test results to the state and/or local childhood lead poisoning prevention program (CLPPP). The system should use and plan to increase electronic transfer of data from laboratories, WIC, immunizations, and birth certificates, and between local and state health departments.

The system should contain unique identifiers within a jurisdiction for each child and address, and should have minimum built-in data entry and import edit checks. The system should be Web-based to obtain real-time information. The system should collect core/standard data elements including at least the following:

Patient Data

CHILD ID

Name: Last, First, Middle

Address: Street, City, State, Zip

County Code: FIPS

Home phone number

Date of birth

Sex

Gender

Race

Ethnicity

## Guardian Name: Last, First

Health Care Provider

Provider ID – assigned by CLPPP

Provider Name

Provider Address: Street, City, County, State, Zip

Follow-up Data

Case Management

Home visit date(s)

Referrals, including type, date referred, and date  completed

Date case closed

Reason: Complete, incomplete, administrative

Environmental Information:

Investigation Start Date

Investigation Reason

Investigation Completion Date

Investigation Closure Reason

Date Remediation or Abatement Completed

Investigation Findings/Source(s)Identification

Clearance Testing Results

Date Clearance Testing Completed

Laboratory/Sample Data

LAB ID

Laboratory Name

Laboratory Address: Street, City, State, Zip

Date Sample Drawn

Date Sample Analyzed

Requisition number

Accession number

Type of test (lead, EP, etc.)

Result (with Units)

Sample type (venous, capillary, unknown)

Sample purpose

The system should have the capability to send quarterly data extractions to CDC.

Core Surveillance:

The core of the surveillance system should be a child-specific, relational database that allows for multiple lab tests and multiple addresses to be followed over time. The system should allow for tracking inspections and remediation activities.

The surveillance system should have the technologic capability to receive and report all blood lead tests performed on children in the applicant’s jurisdiction. Applicants should describe plans and methods to achieve complete reporting for all children tested for lead and for all blood lead levels in their jurisdiction and entering all of these results into the surveillance system, where programmatic or legislative barriers have not been resolved.

Applicants should provide current baseline percentage of tests reported electronically by laboratories, other heath departments, and/or other sources and describe plans to increase the yearly percentage by at least 10% each year until overall electronic reporting reaches at least 90% of all tests. To be considered electronic reporting, the data must be imported into the system rather than entered manually by a user. (For example, if data are sent on a diskette as an Excel spreadsheet, but the program is not capable of manipulating the spreadsheet to import it into the system, and instead prints out the spreadsheet for the data entry operator to type into the system, this is not electronic reporting.) [See Appendix I for definition of Electronic Laboratory-Based Reporting (ELR)].

Goals for increased electronic reporting should be higher than 10% per year until 85%-90% is reached, where appropriate and based on the need for improvement.

System should have a detailed flow chart of the surveillance system for both individual test data and summary information. The flow chart should minimally include, but not be limited to, data entry, quality control points, data usage/report generation, and data transfer/linkages.

The flow chart should be included in the application appendix. CLPPP staff, including administrative, surveillance, case management, environmental, and other CLPPP or health department staff, should meet regularly to discuss improving the quality and utility of surveillance and other data to best meet CLPPP needs and the goal of eliminating lead poisoning as a public health problem. This should be recorded as part of permanent surveillance system management documentation. This documentation should include how improvements in surveillance are being made based on this input.

Programs should submit quality assurance protocols for data process for cleaning and editing data. Applicants should demonstrate use of the surveillance system to guide, monitor, and evaluate CLPPP components and activities, minimally to include:

o Use of surveillance data for development and evaluation of the jurisdiction-wide targeted screening plan.

o Assessment of effectiveness of case management within the CLPPP jurisdiction, minimally including time between key control points such as how long it takes after a child is identified as a case to conduct the investigation and remediation compared to standards set by the CLPPP and current best public health practices.

o Assessment of rates of screening and EBLLs among Medicaid eligible children. (See "Medicaid and Other Linkages" below for additional requirements in this area.)

o Assessment of comparative effectiveness of interventions or activities intended to reduce the case burden in the applicant’s jurisdiction.

Program should produce an annual report for the CLPPP’s internal and external stakeholders. The report should include the number and percentage of children screened and elevated by specific demographic variables. It should include analysis and interpretation of jurisdictional surveillance data, and present trends and important public health findings.

The program should produce periodic supplementary reports targeted for specific internal and/or external use on a more frequent basis.

The program should identify standard core reports with frequency and target audience. The applicant should identify their ability to respond to information requests and produce reports as needed.

State applicants should demonstrate collaboration with the National Electronic Disease Surveillance System (NEDSS) contact(s) in their state to work toward incorporation of childhood lead poisoning surveillance into an integrated statewide surveillance system. Non-state applicants should demonstrate collaboration with the NEDSS contact in their state and/or with their state CLPPP to work toward incorporation of local childhood lead poisoning surveillance into an integrated statewide surveillance system.

Until approved by the Lead Poisoning Prevention Branch to submit quarterly data extractions, applicants should submit annual surveillance data to CDC as required by OMB No. 0920-0337. Please note recent changes to the specifications document, as required by OMB race coding changes.

Applicants should evaluate their surveillance system at least annually, including:

o A description of the surveillance system, how it is being used, and how data are disseminated

o Data Quality

o Acceptability

o Positive Predictive Value

o Representativeness

o Timeliness

Programs should also identify ongoing evaluation measures of their surveillance system. These ongoing measures and the activities designed for improving surveillance based on these measures should be recorded.

Medicaid and Other Linkages

Programs will have a system for ongoing identification of Medicaid-eligible children. The preferred method for achieving this objective would include performing data linkages or matches between surveillance and Medicaid enrollment data sets; however, alternative methods are acceptable, with justification, if valid estimates can be made.

Programs will use the system described above to produce and share with the state and local Medicaid agencies annual reports that describe the following:

o The number and percent of all Medicaid-eligible children less than 72 months of age who receive a blood lead screening test by age and the number and percent of all Medicaid-eligible children with elevated blood lead levels by age.

o If the program cannot conduct these activities electronically at the time of the application, the applicant will submit a measurable, time-phased work plan for being able to accomplish this task within 1 year of award.

Programs will establish a substantial target for the annual reduction in percent of Medicaid children with elevated blood lead levels using the above data and estimates. This target should be included in the elimination plan and annual work plan.

Programs will conduct other data linking as consistent with the intent of the Children’s Health Act of 2000, as amended.

Appendix VII

Work Plan Guidance

A work plan is a program management tool that provides program direction and guidance. It is designed for program planning and implementation as well as monitoring progress made toward reaching program goals and objectives. Each program requirement described within the application: [A) Elimination Plan; B) Screening/Case Management Plan; C) Surveillance; D) Primary Prevention; E) Strategic Partnerships; F) Program Evaluation] must be a part of the work plan.

The portion of the work plan addressing the elimination plan describes implementation of annual goals and objectives for the strategic elimination plan.

Applicants must have work plan goals and objectives that include specific activities for high-risk populations identified in the Need section of application and that are aligned with the elimination plan goals and objectives. In addition to those high-risk communities that are subgrantees of cooperative agreement funds awarded under this announcement, high-risk communities that are not direct subrecipients of cooperative agreement funds awarded under this announcement should be included in objectives and supporting activities in the proposed work plan.

Each work plan should include the following in matrix format: 1) goals, 2) objectives, 3) activities planned to achieve objectives, 4) a timeline to assess progress or completion, 5) named person(s) responsible for activities, and 6) description of data to assess activities (process indicators) and overall measures of effectiveness (impact/outcome).

Applicants are required to provide measures of effectiveness that will demonstrate the accomplishment of the various identified objectives of the cooperative agreement. Measures must be quantifiable, and must measure the intended outcome/impact.

Suggested Work Plan matrix format:

| Goal (A statement or outcome) | Objective (Steps to achieve the goal) | Activity (Major task to accomplish objective) | Timeframe (Projected time to complete activity) | Person(s) Responsible (Lead person for activity) | Evaluation Measure (Indicator that measures achievement of goal or objective) |
| --- | --- | --- | --- | --- | --- |
| Adequate number of lead safe housing units will be available for occupancy by families with young children. | Increase the number of high-risk homes where lead hazards are identified and controlled before children are poisoned from x to x. | CLPPP will partner with housing program to integrate lead hazard inspection into existing housing inspection protocols. | December 2005 | Mary Smith, CLPPP Manager | Number of housing units identified with lead hazards during routine housing inspections and remediated before a child is poisoned. |

Goal(s) should be presented for each of program element.

Objective(s) in support of each program element goal.

Activities planned to achieve each objective.

Timeframe for completion for each objective and activity.

Person(s) responsible for completion, by name and/or position.

Evaluation indicator(s) addressing both activities (process) and objectives (impact/outcome) describing data that will be used.

Appendix VIII

PROGRAM EVALUATION GUIDANCE

Program evaluation is the art and science of collecting and using data to improve performance of your program activities. It is used to determine how specific activities are contributing to the overall goals and objectives of your program. Program evaluation answers two key questions:

- Are we doing things right? (Process evaluation)

- Are we doing the right things? (Outcome/impact evaluation)

It is necessary to do program evaluation so you can assess whether a program activity or element is having the desired effect to the extent intended (outcome/impact evaluation). It is also crucial in understanding whether program activities are implemented and functioning as planned, or whether certain aspects should be altered to improve overall efficiency (process evaluation).

Program evaluation is more than a summary of activities; it is a comparison that explains what is working well or what could be made better. The comparison is the key element of program evaluation that determines how well the activity or element is faring compared to another option, plan, or time period. The comparison could be between two or more types of activities, or between the work plan or benchmarks and the implementation in the field, or between baseline data and data collected at time intervals during an activity.

Evaluation measures are selected indicators used to make these comparisons. They are collected from a wide variety of data sources. Creating a logic model is useful when designing an evaluation framework.

LOGIC MODEL

A logic model demonstrates how activities included in the work plan relate to goals and objectives. In addition, the logic model includes all inputs into the program, even those not funded by the cooperative agreement. These visual presentations can be especially useful for relating the work of the program to the overall goal of elimination of childhood lead poisoning by 2010, including incremental annual progress.

Logic models can also be used as a project planning, management, and as an evaluation tool by relating the specifics to the big picture. Evaluation measures can be drawn from the logic models by examining the relations among the goals, objectives, and activities, as well as the overall outcomes of the program. The following resources are provided to assist you in the development of a logic model:

Resources

1. CDC. Framework for program evaluation in public health. MMWR 1999;48(No. RR-11). Available from URL: http://www.cdc.gov/mmwr/preview/mmwrhtml/rr4811a1.htm.

2. CDC Public Health Training Network. Practical evaluation of public health programs. Available from URL: http://www.phppo.cdc.gov/phtn/Pract-Eval/workbook.asp.

3.CDC Evaluation Workgroup Resources. Available from URL: http://www.cdc.gov/eval/. (Click on resources and you will find different methods and books on step-by-step methods, including logic models.)

4. CDC. Updated guidelines for evaluating public health surveillance systems. MMWR 2001;50(No. RR-13). Available from URL: http://www.cdc.gov/mmwr/preview/mmwrhtml/rr5013a1.htm.

5.United Way. Outcome Measurement Resource Network. Available from URL: http://national.unitedway.org/outcomes/library/. (Portions are on the Web site for free. The book, videotape, and train the trainer package cost about $40.)

6. Taylor-Powell E, Jones L, Henert E. Enhancing program performance with logic models. University of Wisconsin-Extension; 2002. Available from URL:  http://www1.uwex.edu/ces/lmcourse/.

7. US Department of Housing and Urban Development. Logic model broadcast materials. Available from URL: http://www.hud.gov/offices/adm/grants/nofa05/logicmodelfiles.cfm.

Appendix IX

Children ages < 72 months for whom blood lead surveillance data were reported to CDC with confirmed blood lead levels (BLLs) ≥ 10 µg/dL by state, county or city, year and BLL group — selected U.S. sites, 1997-2003.  Table represents data present in the Childhood Lead Surveillance (CLS) database as of October 1, 2005.

| State/County/City | Year | Number of children tested | Total number of children with confirmed* BLLs ≥10 µg/dL | Confirmed EBLLs as % of children tested | Number of confirmed children by highest blood lead level (µg/dL) at or after confirmation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 10-14 | 15-19 | 20-24 | 25-44 | 45-69 | ≥70 |
|  | 1997 | 22,875 | 1,501 | 6.56% | 890 | 410 | 120 | 76 | 5 | 0 |
|  | 1998 | 17,827 | 988 | 5.54% | 586 | 250 | 85 | 61 | 6 | 0 |
|  | 1999 | 17,660 | 549 | 3.11% | 344 | 114 | 44 | 41 | 6 | 0 |
| Alabama | 2000 | 13,719 | 315 | 2.30% | 205 | 62 | 20 | 21 | 7 | 0 |
|  | 2001 | 12,107 | 642 | 5.30% | 392 | 129 | 62 | 54 | 5 | 0 |
|  | 2002 | 22,495 | 454 | 2.02% | 257 | 103 | 51 | 38 | 4 | 1 |
|  | 2003 | 21,307 | 503 | 2.36% | 299 | 107 | 50 | 42 | 4 | 1 |
|  | 1997 | 142 | 2 | 1.41% | 1 | 1 | 0 | 0 | 0 | 0 |
|  | 1998 | 242 | 2 | 0.83% | 2 | 0 | 0 | 0 | 0 | 0 |
|  | 1999 | 103 | 1 | 0.97% | 1 | 0 | 0 | 0 | 0 | 0 |
| Alaska | 2000 | 73 | 1 | 1.37% | 0 | 1 | 0 | 0 | 0 | 0 |
|  | 2001 | 52 | 3 | 5.77% | 3 | 0 | 0 | 0 | 0 | 0 |
|  | 2002 | 115 | 2 | 1.74% | 1 | 0 | 1 | 0 | 0 | 0 |
|  | 2003 | 77 | 2 | 2.60% | 0 | 1 | 1 | 0 | 0 | 0 |
|  | 1997 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
|  | 1998 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
|  | 1999§ | 1,929 | 168 | 8.71% | 93 | 42 | 12 | 18 | 3 | 0 |
| Arizona | 2000 | 7,249 | 181 | 2.50% | 105 | 35 | 19 | 20 | 2 | 0 |
|  | 2001 | 8,026 | 170 | 2.12% | 109 | 34 | 10 | 17 | 0 | 0 |
|  | 2002 | 12,005 | 227 | 1.89% | 159 | 42 | 16 | 9 | 1 | 0 |
|  | 2003¶ | — | 229 | — | 165 | 35 | 13 | 15 | 1 | 0 |
|  | 1997¶ | 11,462 | 1,764 | 15.39% | 397 | 509 | 448 | 362 | 41 | 7 |
|  | 1998¶ | 11,257 | 1,649 | 14.65% | 420 | 481 | 393 | 316 | 34 | 5 |
| California† | 1999¶ | 4,638 | 919 | 19.81% | 247 | 279 | 190 | 181 | 18 | 4 |
| (excluding Los | 2000¶ | 5,350 | 878 | 16.41% | 253 | 261 | 162 | 181 | 16 | 5 |
| Angeles County) | 2001¶ | 6,783 | 877 | 12.93% | 229 | 281 | 165 | 178 | 21 | 3 |
|  | 2002¶ | 20,089 | 1,394 | 6.94% | 390 | 467 | 260 | 250 | 25 | 2 |
|  | 2003¶ | 154,043 | 1,525 | 0.99% | 857 | 319 | 167 | 156 | 24 | 2 |
|  | 1997¶ | 948 | 511 | 53.90% | 165 | 169 | 94 | 72 | 11 | 0 |
|  | 1998¶ | 541 | 198 | 36.60% | 69 | 65 | 36 | 25 | 3 | 0 |
| Los Angeles | 1999¶ | 5,416 | 630 | 11.63% | 117 | 191 | 166 | 133 | 19 | 4 |
| County, CA† | 2000¶ | 7,367 | 598 | 8.12% | 147 | 150 | 145 | 138 | 16 | 2 |
|  | 2001¶ | 8,260 | 525 | 6.36% | 95 | 162 | 116 | 144 | 6 | 2 |
|  | 2002¶ | 1,800 | 176 | 9.78% | 72 | 52 | 26 | 25 | 1 | 0 |
|  | 2003¶ | 79,499 | 1,033 | 1.30% | 698 | 171 | 80 | 77 | 7 | 0 |
|  | 1997 | 5,077 | 180 | 3.55% | 108 | 36 | 16 | 17 | 2 | 1 |
|  | 1998 | 4,151 | 125 | 3.01% | 78 | 24 | 6 | 14 | 3 | 0 |
|  | 1999 | 3,815 | 102 | 2.67% | 64 | 20 | 10 | 7 | 1 | 0 |
| Colorado | 2000 | 6,606 | 112 | 1.70% | 71 | 21 | 7 | 12 | 1 | 0 |
|  | 2001 | 8,984 | 113 | 1.26% | 62 | 20 | 18 | 12 | 1 | 0 |
|  | 2002$ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 2003$ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 1997 | 22,435 | 298 | 1.33% | 196 | 54 | 26 | 20 | 2 | 0 |
|  | 1998 | 60,725 | 2,410 | 3.97% | 1,284 | 523 | 293 | 275 | 31 | 4 |
|  | 1999 | 65,603 | 2,155 | 3.28% | 1,246 | 460 | 219 | 196 | 31 | 3 |
| Connecticut | 2000 | 64,685 | 2,371 | 3.67% | 1,353 | 514 | 258 | 218 | 26 | 2 |
|  | 2001 | 67,512 | 2,026 | 3.00% | 1,206 | 449 | 191 | 156 | 22 | 2 |
|  | 2002 | 69,670 | 1,813 | 2.60% | 1,059 | 392 | 186 | 157 | 14 | 5 |
|  | 2003 | 68,038 | 1,551 | 2.28% | 951 | 308 | 129 | 141 | 17 | 5 |
|  | 1997 | 28 | 15 | 53.57% | 1 | 1 | 6 | 4 | 3 | 0 |
|  | 1998 | 8,881 | 245 | 2.76% | 118 | 57 | 34 | 34 | 1 | 1 |
|  | 1999 | 10,343 | 245 | 2.37% | 109 | 56 | 36 | 40 | 4 | 0 |
| Delaware | 2000 | 9,648 | 231 | 2.39% | 102 | 50 | 42 | 33 | 4 | 0 |
|  | 2001 | 14,555 | 254 | 1.75% | 127 | 80 | 20 | 25 | 2 | 0 |
|  | 2002 | 13,008 | 253 | 1.94% | 158 | 59 | 10 | 25 | 1 | 0 |
|  | 2003¶ | 7,277 | 131 | 1.80% | 88 | 20 | 13 | 9 | 1 | 0 |
|  | 1997 | 183 | 131 | 71.58% | 10 | 23 | 51 | 43 | 4 | 0 |
|  | 1998 | 6,810 | 225 | 3.30% | 71 | 67 | 40 | 39 | 8 | 0 |
| District of | 1999 | 11,777 | 215 | 1.83% | 84 | 57 | 35 | 37 | 2 | 0 |
| Columbia | 2000 | 14,040 | 175 | 1.25% | 100 | 35 | 21 | 15 | 3 | 1 |
|  | 2001 | 16,042 | 156 | 0.97% | 73 | 33 | 15 | 33 | 2 | 0 |
|  | 2002 | 15,755 | 122 | 0.77% | 49 | 27 | 21 | 20 | 5 | 0 |
|  | 2003 | 9,229 | 193 | 2.09% | 87 | 70 | 16 | 18 | 1 | 1 |
|  | 1997 | 38,803 | 2,347 | 6.05% | 1,592 | 486 | 142 | 109 | 13 | 5 |
|  | 1998 | 33,803 | 2,146 | 6.35% | 1,495 | 396 | 138 | 110 | 7 | 0 |
|  | 1999 | 34,389 | 1,509 | 4.39% | 967 | 347 | 108 | 75 | 10 | 2 |
| Florida | 2000 | 45,896 | 723 | 1.58% | 467 | 149 | 40 | 58 | 9 | 0 |
|  | 2001 | 63,382 | 643 | 1.01% | 397 | 137 | 56 | 50 | 3 | 0 |
|  | 2002 | 70,550 | 827 | 1.17% | 526 | 158 | 71 | 60 | 9 | 3 |
|  | 2003 | 105,831 | 774 | 0.73% | 478 | 147 | 78 | 55 | 11 | 5 |
|  | 1997 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
|  | 1998 | 22,496 | 445 | 1.98% | 246 | 122 | 41 | 36 | 0 | 0 |
|  | 1999 | 20,588 | 512 | 2.49% | 283 | 131 | 42 | 49 | 7 | 0 |
| Georgia | 2000 | 27,609 | 466 | 1.69% | 276 | 108 | 35 | 43 | 3 | 1 |
|  | 2001 | 33,097 | 422 | 1.28% | 267 | 90 | 26 | 38 | 0 | 1 |
|  | 2002 | 33,620 | 295 | 0.88% | 184 | 58 | 24 | 24 | 4 | 1 |
|  | 2003 | 53,530 | 381 | 0.71% | 221 | 86 | 37 | 33 | 1 | 3 |
|  | 1997 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
|  | 1998§ | 15 | 13 | 86.67% | 3 | 6 | 2 | 2 | 0 | 0 |
|  | 1999 | 3,736 | 92 | 2.46% | 51 | 28 | 11 | 2 | 0 | 0 |
| Hawaii | 2000 | 4,897 | 93 | 1.90% | 63 | 19 | 6 | 5 | 0 | 0 |
|  | 2001 | 7,391 | 88 | 1.19% | 48 | 22 | 8 | 6 | 4 | 0 |
|  | 2002 | 9,171 | 100 | 1.09% | 62 | 18 | 12 | 7 | 1 | 0 |
|  | 2003 | 7,967 | 81 | 1.02% | 48 | 16 | 6 | 10 | 1 | 0 |
|  | 1997 | 75,035 | 6,192 | 8.25% | 3,588 | 1,401 | 570 | 575 | 50 | 8 |
|  | 1998 | 71,067 | 4,649 | 6.54% | 2,813 | 959 | 412 | 410 | 46 | 9 |
| Illinois | 1999 | 81,297 | 3,676 | 4.52% | 2,202 | 799 | 321 | 320 | 30 | 4 |
| (excluding | 2000 | 90,167 | 3,697 | 4.10% | 2,237 | 752 | 360 | 301 | 40 | 7 |
| Chicago) | 2001 | 82,714 | 3,120 | 3.77% | 1,825 | 636 | 316 | 312 | 28 | 3 |
|  | 2002 | 87,903 | 2,938 | 3.34% | 1,726 | 620 | 298 | 256 | 31 | 7 |
|  | 2003 | 92,695 | 2,688 | 2.90% | 1,570 | 599 | 233 | 257 | 27 | 2 |
|  | 1997 | 96,140 | 23,800 | 24.76% | 13,255 | 5,804 | 2,257 | 2,189 | 249 | 46 |
|  | 1998 | 95,263 | 19,616 | 20.59% | 11,907 | 4,137 | 1,783 | 1,555 | 196 | 38 |
|  | 1999 | 91,947 | 15,960 | 17.36% | 9,919 | 3,241 | 1,343 | 1,291 | 139 | 27 |
| Chicago, IL | 2000 | 96,569 | 13,872 | 14.36% | 8,561 | 2,855 | 1,232 | 1,078 | 116 | 30 |
|  | 2001 | 104,501 | 11,645 | 11.14% | 7,207 | 2,502 | 946 | 860 | 111 | 19 |
|  | 2002 | 104,264 | 9,302 | 8.92% | 5,840 | 1,898 | 767 | 703 | 82 | 12 |
|  | 2003 | 103,701 | 6,691 | 6.45% | 4,317 | 1,312 | 503 | 505 | 41 | 13 |
|  | 1997 | 28,640 | 894 | 3.12% | 534 | 181 | 88 | 72 | 16 | 3 |
|  | 1998 | 26,563 | 733 | 2.76% | 387 | 179 | 88 | 70 | 9 | 0 |
|  | 1999 | 26,030 | 755 | 2.90% | 436 | 177 | 73 | 66 | 2 | 1 |
| Indiana | 2000 | 25,307 | 567 | 2.24% | 343 | 117 | 60 | 41 | 5 | 1 |
|  | 2001 | 27,442 | 599 | 2.18% | 347 | 140 | 66 | 42 | 4 | 0 |
|  | 2002 | 29,105 | 604 | 2.08% | 351 | 138 | 48 | 58 | 6 | 3 |
|  | 2003 | 38,944 | 654 | 1.68% | 373 | 145 | 71 | 60 | 5 | 0 |
|  | 1997 | 25,335 | 1,422 | 5.61% | 755 | 355 | 158 | 136 | 16 | 2 |
|  | 1998 | 26,254 | 1,299 | 4.95% | 696 | 289 | 130 | 163 | 16 | 5 |
|  | 1999 | 27,823 | 1,061 | 3.81% | 552 | 236 | 128 | 130 | 14 | 1 |
| Iowa | 2000 | 30,031 | 1,054 | 3.51% | 556 | 251 | 121 | 105 | 19 | 2 |
|  | 2001 | 37,085 | 1,071 | 2.89% | 578 | 239 | 116 | 111 | 23 | 4 |
|  | 2002 | 42,534 | 1,135 | 2.67% | 619 | 262 | 110 | 130 | 9 | 5 |
|  | 2003 | 43,824 | 1,035 | 2.36% | 565 | 231 | 106 | 115 | 16 | 2 |
|  | 1997§ | 36 | 3 | 8.33% | 1 | 0 | 0 | 2 | 0 | 0 |
|  | 1998 | 3,485 | 71 | 2.04% | 24 | 24 | 7 | 14 | 2 | 0 |
|  | 1999 | 4,010 | 224 | 5.59% | 108 | 61 | 26 | 27 | 2 | 0 |
| Kansas | 2000 | 7,244 | 222 | 3.06% | 120 | 50 | 16 | 31 | 5 | 0 |
|  | 2001 | 10,715 | 322 | 3.01% | 191 | 61 | 33 | 32 | 4 | 1 |
|  | 2002 | 15,564 | 354 | 2.27% | 198 | 82 | 31 | 36 | 7 | 0 |
|  | 2003 | 26,037 | 365 | 1.40% | 220 | 79 | 41 | 21 | 4 | 0 |
|  | 1997 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
|  | 1998 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
|  | 1999 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
| Kentucky† | 2000§ | 16,346 | 145 | 0.89% | 65 | 30 | 20 | 27 | 3 | 0 |
|  | 2001 | 27,022 | 351 | 1.30% | 177 | 69 | 46 | 52 | 3 | 4 |
|  | 2002¶ | 3,956 | 44 | 1.11% | 23 | 6 | 7 | 8 | 0 | 0 |
|  | 2003 | 28,225 | 190 | 0.67% | 99 | 35 | 25 | 24 | 6 | 1 |
|  | 1997 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
|  | 1998§ | 23,168 | 551 | 2.38% | 227 | 152 | 82 | 81 | 6 | 3 |
|  | 1999 | 21,587 | 690 | 3.20% | 318 | 191 | 94 | 76 | 10 | 1 |
| Louisiana | 2000 | 30,805 | 1,023 | 3.32% | 484 | 270 | 137 | 122 | 8 | 2 |
|  | 2001 | 44,458 | 1,061 | 2.39% | 563 | 249 | 118 | 125 | 3 | 3 |
|  | 2002 | 54,205 | 1,044 | 1.93% | 542 | 255 | 115 | 121 | 9 | 2 |
|  | 2003 | 61,668 | 982 | 1.59% | 526 | 222 | 131 | 100 | 3 | 0 |
|  | 1997 | 10,414 | 412 | 3.96% | 255 | 89 | 33 | 29 | 4 | 2 |
|  | 1998 | 10,025 | 398 | 3.97% | 262 | 78 | 26 | 31 | 1 | 0 |
|  | 1999 | 9,608 | 336 | 3.50% | 192 | 86 | 28 | 28 | 2 | 0 |
| Maine† | 2000 | 10,107 | 330 | 3.27% | 205 | 68 | 29 | 20 | 8 | 0 |
|  | 2001 | 11,381 | 327 | 2.87% | 209 | 62 | 29 | 23 | 2 | 2 |
|  | 2002 | 14,390 | 292 | 2.03% | 196 | 62 | 19 | 11 | 3 | 1 |
|  | 2003 | 14,571 | 253 | 1.74% | 182 | 38 | 17 | 15 | 1 | 0 |
|  | 1997¶ | 2,051 | 1,807 | 88.10% | 345 | 455 | 568 | 409 | 25 | 5 |
|  | 1998¶ | 2,189 | 1,914 | 87.44% | 363 | 763 | 470 | 286 | 28 | 4 |
|  | 1999¶ | 2,040 | 1,427 | 69.95% | 346 | 524 | 327 | 209 | 18 | 3 |
| Maryland | 2000 | 69,582 | 3,742 | 5.38% | 1,963 | 1,009 | 415 | 322 | 25 | 8 |
|  | 2001 | 82,093 | 3,478 | 4.24% | 2,032 | 875 | 278 | 263 | 28 | 2 |
|  | 2002 | 66,795 | 1,795 | 2.69% | 1,101 | 376 | 175 | 135 | 8 | 0 |
|  | 2003 | 64,506 | 1,551 | 2.40% | 1,006 | 306 | 122 | 104 | 13 | 0 |
|  | 1997 | 241,872 | 7,810 | 3.23% | 5,197 | 1,531 | 629 | 423 | 27 | 3 |
|  | 1998 | 253,513 | 5,905 | 2.33% | 3,954 | 1,199 | 408 | 317 | 27 | 0 |
|  | 1999 | 260,588 | 5,279 | 2.03% | 3,607 | 980 | 395 | 267 | 27 | 3 |
| Massachusetts† | 2000 | 255,247 | 4,334 | 1.70% | 3,028 | 759 | 274 | 244 | 23 | 6 |
|  | 2001 | 246,363 | 3,644 | 1.48% | 2,520 | 652 | 251 | 204 | 12 | 5 |
|  | 2002 | 242,915 | 3,211 | 1.32% | 2,176 | 614 | 217 | 182 | 21 | 1 |
|  | 2003 | 235,222 | 2,219 | 0.94% | 1,527 | 415 | 139 | 128 | 10 | 0 |
|  | 1997 | 8,699 | 796 | 9.15% | 418 | 203 | 85 | 87 | 3 | 0 |
|  | 1998 | 35,647 | 1,732 | 4.86% | 1,030 | 356 | 166 | 152 | 27 | 1 |
| Michigan | 1999 | 51,316 | 2,225 | 4.34% | 1,248 | 531 | 240 | 189 | 17 | 0 |
| (excluding | 2000 | 54,942 | 2,031 | 3.70% | 1,253 | 452 | 171 | 144 | 9 | 2 |
| Detroit) | 2001 | 57,928 | 1,857 | 3.21% | 1,174 | 369 | 166 | 120 | 24 | 4 |
|  | 2002 | 59,095 | 1,394 | 2.36% | 850 | 301 | 124 | 101 | 17 | 1 |
|  | 2003 | 58,734 | 1,144 | 1.95% | 700 | 226 | 122 | 81 | 12 | 3 |
|  | 1997 | 14,892 | 3,228 | 21.68% | 1,630 | 703 | 461 | 395 | 36 | 3 |
|  | 1998 | 26,304 | 5,086 | 19.34% | 3,077 | 1,105 | 447 | 414 | 38 | 5 |
|  | 1999 | 24,622 | 3,824 | 15.53% | 2,329 | 794 | 371 | 296 | 29 | 5 |
| Detroit, MI | 2000 | 24,213 | 2,691 | 11.11% | 1,692 | 545 | 219 | 211 | 22 | 2 |
|  | 2001 | 30,815 | 3,398 | 11.03% | 2,174 | 694 | 263 | 236 | 26 | 5 |
|  | 2002 | 32,786 | 3,016 | 9.20% | 1,883 | 667 | 233 | 191 | 38 | 4 |
|  | 2003 | 31,596 | 2,155 | 6.82% | 1,314 | 452 | 180 | 184 | 21 | 4 |
|  | 1997 | 37,404 | 1,871 | 5.00% | 1,098 | 398 | 201 | 151 | 18 | 5 |
|  | 1998 | 35,654 | 1,551 | 4.35% | 917 | 340 | 138 | 134 | 16 | 6 |
|  | 1999 | 36,724 | 1,214 | 3.31% | 733 | 258 | 111 | 94 | 15 | 3 |
| Minnesota | 2000 | 41,176 | 1,018 | 2.47% | 584 | 218 | 96 | 105 | 12 | 3 |
|  | 2001 | 47,098 | 1,079 | 2.29% | 638 | 221 | 104 | 100 | 11 | 5 |
|  | 2002 | 53,136 | 868 | 1.63% | 505 | 161 | 80 | 109 | 10 | 3 |
|  | 2003 | 61,826 | 807 | 1.31% | 468 | 174 | 75 | 77 | 10 | 3 |
|  | 1997 | 545 | 520 | 95.41% | 111 | 269 | 83 | 53 | 4 | 0 |
|  | 1998 | 890 | 485 | 54.49% | 115 | 259 | 61 | 47 | 3 | 0 |
|  | 1999 | 7,945 | 767 | 9.65% | 501 | 180 | 47 | 38 | 1 | 0 |
| Mississippi | 2000 | 11,107 | 169 | 1.52% | 99 | 40 | 18 | 11 | 0 | 1 |
|  | 2001 | 16,771 | 435 | 2.59% | 306 | 74 | 29 | 23 | 3 | 0 |
|  | 2002 | 26,258 | 525 | 2.00% | 329 | 113 | 45 | 35 | 1 | 2 |
|  | 2003 | 36,882 | 520 | 1.41% | 353 | 104 | 25 | 36 | 2 | 0 |
|  | 1997 | 41,747 | 5,060 | 12.12% | 2,827 | 1,200 | 542 | 441 | 42 | 8 |
|  | 1998 | 44,459 | 5,045 | 11.35% | 2,933 | 1,168 | 448 | 434 | 56 | 6 |
|  | 1999 | 49,004 | 4,790 | 9.77% | 2,788 | 1,150 | 418 | 385 | 46 | 3 |
| Missouri | 2000 | 56,987 | 4,946 | 8.68% | 2,903 | 1,149 | 390 | 460 | 41 | 3 |
|  | 2001 | 65,137 | 3,352 | 5.15% | 2,087 | 710 | 278 | 241 | 34 | 2 |
|  | 2002 | 66,606 | 2,838 | 4.26% | 1,735 | 652 | 223 | 206 | 17 | 5 |
|  | 2003 | 72,166 | 2,744 | 3.80% | 1,777 | 574 | 186 | 186 | 21 | 0 |
|  | 1997 | 856 | 40 | 4.67% | 28 | 7 | 4 | 0 | 1 | 0 |
|  | 1998 | 1,126 | 30 | 2.66% | 24 | 5 | 1 | 0 | 0 | 0 |
|  | 1999 | 3,400 | 19 | 0.56% | 16 | 2 | 0 | 1 | 0 | 0 |
| Montana | 2000 | 2,394 | 18 | 0.75% | 13 | 4 | 1 | 0 | 0 | 0 |
|  | 2001 | 2,210 | 6 | 0.27% | 4 | 1 | 1 | 0 | 0 | 0 |
|  | 2002$ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 2003$ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 1997 | 5,190 | 318 | 6.13% | 165 | 64 | 33 | 49 | 6 | 1 |
|  | 1998 | 8,510 | 357 | 4.20% | 190 | 78 | 37 | 40 | 10 | 2 |
|  | 1999 | 11,117 | 390 | 3.51% | 202 | 84 | 51 | 46 | 6 | 1 |
| Nebraska | 2000 | 13,881 | 312 | 2.25% | 160 | 61 | 40 | 41 | 6 | 4 |
|  | 2001 | 14,530 | 296 | 2.04% | 162 | 66 | 31 | 33 | 4 | 0 |
|  | 2002 | 17,867 | 246 | 1.38% | 136 | 56 | 16 | 32 | 6 | 0 |
|  | 2003 | 17,602 | 271 | 1.54% | 137 | 57 | 37 | 36 | 4 | 0 |
|  | 1997 | 15,775 | 503 | 3.19% | 269 | 118 | 54 | 57 | 4 | 1 |
|  | 1998 | 15,243 | 538 | 3.53% | 301 | 123 | 64 | 46 | 4 | 0 |
| New | 1999 | 14,350 | 555 | 3.87% | 319 | 138 | 51 | 41 | 4 | 2 |
| Hampshire | 2000 | 13,977 | 501 | 3.58% | 317 | 117 | 38 | 27 | 1 | 1 |
|  | 2001 | 13,509 | 390 | 2.89% | 246 | 84 | 24 | 34 | 2 | 0 |
|  | 2002 | 14,551 | 397 | 2.73% | 248 | 82 | 38 | 25 | 3 | 1 |
|  | 2003 | 14,353 | 412 | 2.87% | 256 | 89 | 36 | 26 | 5 | 0 |
|  | 1997¶ | 12,336 | 2,865 | 23.22% | 824 | 500 | 765 | 687 | 75 | 14 |
|  | 1998¶ | 11,193 | 2,350 | 21.00% | 685 | 389 | 617 | 586 | 67 | 6 |
|  | 1999¶ | 8,249 | 1,716 | 20.80% | 494 | 302 | 466 | 389 | 60 | 5 |
| New Jersey | 2000 | 135,297 | 3,823 | 2.83% | 1,438 | 667 | 790 | 801 | 105 | 22 |
|  | 2001 | 146,950 | 3,025 | 2.06% | 1,206 | 591 | 533 | 584 | 103 | 8 |
|  | 2002 | 153,290 | 1,936 | 1.26% | 999 | 453 | 190 | 257 | 35 | 2 |
|  | 2003 | 151,584 | 2,919 | 1.93% | 1,542 | 616 | 337 | 379 | 40 | 5 |
|  | 1997 | 5,936 | 71 | 1.20% | 43 | 12 | 4 | 10 | 1 | 1 |
|  | 1998 | 4,525 | 24 | 0.53% | 9 | 9 | 5 | 1 | 0 | 0 |
|  | 1999 | 4,488 | 28 | 0.62% | 16 | 7 | 5 | 0 | 0 | 0 |
| New Mexico | 2000 | 3,253 | 23 | 0.71% | 18 | 3 | 1 | 1 | 0 | 0 |
|  | 2001 | 2,695 | 39 | 1.45% | 24 | 9 | 2 | 4 | 0 | 0 |
|  | 2002$ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 2003$ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 1997 | 206,547 | 13,026 | 6.31% | 7,810 | 2,967 | 1,165 | 1,009 | 66 | 9 |
|  | 1998 | 194,784 | 10,664 | 5.47% | 6,435 | 2,520 | 915 | 715 | 71 | 8 |
|  | 1999 | 181,768 | 8,281 | 4.56% | 5,123 | 1,844 | 663 | 592 | 49 | 10 |
| New York | 2000 | 181,036 | 6,171 | 3.41% | 3,854 | 1,308 | 521 | 427 | 52 | 9 |
| (excluding New | 2001 | 183,201 | 5,166 | 2.82% | 3,229 | 1,122 | 403 | 368 | 37 | 7 |
| York City) | 2002 | 179,769 | 4,493 | 2.50% | 2,842 | 946 | 356 | 309 | 36 | 4 |
|  | 2003 | 160,825 | 3,767 | 2.34% | 2,286 | 845 | 318 | 285 | 28 | 5 |
|  | 1997 | 297,531 | 9,906 | 3.33% | 6,873 | 1,565 | 728 | 648 | 76 | 16 |
|  | 1998 | 303,710 | 10,370 | 3.41% | 7,229 | 1,808 | 652 | 610 | 62 | 9 |
|  | 1999 | 295,584 | 7,990 | 2.70% | 5,627 | 1,362 | 492 | 450 | 53 | 6 |
| New York, NY | 2000 | 319,312 | 6,734 | 2.11% | 4,764 | 1,223 | 360 | 340 | 43 | 4 |
|  | 2001 | 306,389 | 4,914 | 1.60% | 3,344 | 937 | 291 | 302 | 34 | 6 |
|  | 2002 | 297,177 | 4,128 | 1.39% | 2,839 | 753 | 240 | 268 | 25 | 3 |
|  | 2003 | 304,130 | 3,526 | 1.16% | 2,270 | 690 | 261 | 260 | 41 | 4 |
|  | 1997 | 97,167 | 1,259 | 1.30% | 718 | 313 | 120 | 95 | 11 | 2 |
|  | 1998 | 96,729 | 1,067 | 1.10% | 641 | 257 | 78 | 83 | 8 | 0 |
|  | 1999 | 107,096 | 1,039 | 0.97% | 628 | 235 | 100 | 72 | 4 | 0 |
| North Carolina | 2000 | 116,947 | 1,261 | 1.08% | 772 | 287 | 108 | 83 | 8 | 3 |
|  | 2001 | 121,940 | 995 | 0.82% | 616 | 215 | 79 | 78 | 5 | 2 |
|  | 2002 | 122,501 | 921 | 0.75% | 584 | 196 | 75 | 62 | 3 | 1 |
|  | 2003 | 122,911 | 908 | 0.74% | 611 | 187 | 57 | 47 | 5 | 1 |
|  | 1997 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
|  | 1998 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
|  | 1999 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
| North Dakota | 2000§ | 24 | 1 | 4.17% | 0 | 1 | 0 | 0 | 0 | 0 |
|  | 2001 | 1,089 | 4 | 0.37% | 1 | 1 | 0 | 2 | 0 | 0 |
|  | 2002 | 1,271 | 13 | 1.02% | 4 | 3 | 3 | 3 | 0 | 0 |
|  | 2003 | 1,054 | 17 | 1.61% | 11 | 3 | 1 | 2 | 0 | 0 |
|  | 1997 | 75,193 | 12,445 | 16.55% | 6,832 | 2,790 | 1,395 | 1,258 | 149 | 21 |
|  | 1998 | 76,279 | 11,859 | 15.55% | 6,717 | 2,670 | 1,318 | 1,027 | 113 | 14 |
|  | 1999 | 106,151 | 9,346 | 8.80% | 5,417 | 2,123 | 985 | 739 | 74 | 8 |
| Ohio | 2000 | 96,322 | 7,360 | 7.64% | 4,149 | 1,695 | 812 | 636 | 60 | 8 |
|  | 2001 | 103,659 | 6,604 | 6.37% | 3,878 | 1,449 | 657 | 541 | 68 | 11 |
|  | 2002 | 114,446 | 5,949 | 5.20% | 3,500 | 1,314 | 557 | 501 | 64 | 13 |
|  | 2003 | 115,844 | 4,978 | 4.30% | 2,973 | 1,038 | 460 | 440 | 64 | 3 |
|  | 1997 | 9,183 | 342 | 3.72% | 233 | 57 | 20 | 31 | 1 | 0 |
|  | 1998 | 7,550 | 164 | 2.17% | 107 | 28 | 16 | 10 | 3 | 0 |
|  | 1999 | 8,630 | 127 | 1.47% | 81 | 20 | 8 | 17 | 1 | 0 |
| Oklahoma | 2000 | 9,483 | 154 | 1.62% | 103 | 36 | 9 | 6 | 0 | 0 |
|  | 2001 | 11,842 | 145 | 1.22% | 88 | 32 | 11 | 13 | 1 | 0 |
|  | 2002 | 12,781 | 145 | 1.13% | 80 | 39 | 11 | 12 | 2 | 1 |
|  | 2003 | 12,969 | 145 | 1.12% | 92 | 31 | 11 | 11 | 0 | 0 |
|  | 1997 | 4,928 | 80 | 1.62% | 51 | 11 | 10 | 7 | 1 | 0 |
|  | 1998 | 5,766 | 100 | 1.73% | 59 | 23 | 10 | 8 | 0 | 0 |
|  | 1999 | 6,166 | 112 | 1.82% | 71 | 26 | 9 | 5 | 1 | 0 |
| Oregon | 2000 | 6,887 | 108 | 1.57% | 71 | 20 | 6 | 9 | 0 | 2 |
|  | 2001 | 8,817 | 96 | 1.09% | 57 | 21 | 10 | 7 | 0 | 1 |
|  | 2002 | 10,917 | 94 | 0.86% | 50 | 25 | 8 | 9 | 2 | 0 |
|  | 2003 | 11,028 | 98 | 0.89% | 56 | 23 | 10 | 7 | 0 | 2 |
|  | 1997 | 8,626 | 1,399 | 16.22% | 351 | 539 | 232 | 250 | 21 | 6 |
|  | 1998 | 15,239 | 1,773 | 11.63% | 727 | 518 | 240 | 253 | 29 | 6 |
| Pennsylvania | 1999 | 39,797 | 2,199 | 5.53% | 881 | 662 | 289 | 335 | 27 | 5 |
| (excluding | 2000 | 42,488 | 2,020 | 4.75% | 819 | 567 | 291 | 316 | 26 | 1 |
| Philadelphia) | 2001 | 24,639 | 1,468 | 5.96% | 615 | 356 | 177 | 248 | 62 | 10 |
|  | 2002 | 23,436 | 1,278 | 5.45% | 554 | 392 | 167 | 146 | 15 | 4 |
|  | 2003 | 33,625 | 1,102 | 3.28% | 491 | 310 | 130 | 146 | 22 | 3 |
|  | 1997 | 26,941 | 7,203 | 26.74% | 3,307 | 2,007 | 1,026 | 773 | 78 | 12 |
|  | 1998 | 29,781 | 7,238 | 24.30% | 3,974 | 1,778 | 798 | 639 | 42 | 7 |
|  | 1999 | 25,197 | 4,110 | 16.31% | 2,368 | 972 | 421 | 314 | 34 | 1 |
| Philadelphia, PA | 2000 | 33,389 | 4,916 | 14.72% | 2,874 | 1,154 | 475 | 384 | 29 | 0 |
|  | 2001 | 22,509 | 2,970 | 13.19% | 1,797 | 651 | 269 | 229 | 23 | 1 |
|  | 2002 | 31,549 | 4,133 | 13.10% | 2,557 | 889 | 396 | 267 | 21 | 3 |
|  | 2003 | 11,970 | 1,650 | 13.78% | 1,216 | 273 | 93 | 61 | 6 | 1 |
|  | 1997 | 33,749 | 2,972 | 8.81% | 1,706 | 675 | 299 | 260 | 29 | 3 |
|  | 1998 | 34,000 | 2,526 | 7.43% | 1,558 | 521 | 215 | 196 | 23 | 13 |
|  | 1999 | 34,230 | 2,344 | 6.85% | 1,474 | 477 | 184 | 184 | 22 | 3 |
| Rhode Island | 2000 | 33,826 | 2,057 | 6.08% | 1,274 | 425 | 163 | 171 | 22 | 2 |
|  | 2001 | 34,751 | 2,029 | 5.84% | 1,267 | 404 | 178 | 167 | 11 | 2 |
|  | 2002 | 34,661 | 1,774 | 5.12% | 1,175 | 352 | 121 | 114 | 11 | 1 |
|  | 2003 | 33,813 | 1,312 | 3.88% | 863 | 271 | 91 | 81 | 6 | 0 |
|  | 1997 | 13,310 | 684 | 5.14% | 436 | 151 | 57 | 37 | 3 | 0 |
|  | 1998 | 9,307 | 457 | 4.91% | 292 | 92 | 46 | 25 | 2 | 0 |
|  | 1999 | 26,432 | 548 | 2.07% | 386 | 111 | 31 | 19 | 1 | 0 |
| South Carolina | 2000 | 33,528 | 680 | 2.03% | 439 | 157 | 38 | 45 | 1 | 0 |
|  | 2001 | 46,025 | 566 | 1.23% | 377 | 122 | 37 | 27 | 2 | 1 |
|  | 2002 | 49,158 | 512 | 1.04% | 350 | 106 | 32 | 21 | 3 | 0 |
|  | 2003 | 45,797 | 376 | 0.82% | 274 | 66 | 15 | 19 | 1 | 1 |
|  | 1997 | 6,351 | 374 | 5.89% | 240 | 82 | 26 | 25 | 1 | 0 |
|  | 1998 | 9,015 | 689 | 7.64% | 455 | 141 | 55 | 34 | 4 | 0 |
|  | 1999 | 9,555 | 644 | 6.74% | 447 | 123 | 34 | 34 | 6 | 0 |
| Tennessee | 2000 | 12,567 | 372 | 2.96% | 239 | 91 | 28 | 13 | 1 | 0 |
|  | 2001§ | 37,281 | 404 | 1.08% | 247 | 85 | 35 | 30 | 5 | 2 |
|  | 2002 | 57,040 | 477 | 0.84% | 310 | 96 | 21 | 46 | 2 | 2 |
|  | 2003 | 48,753 | 295 | 0.61% | 175 | 70 | 30 | 17 | 3 | 0 |
|  | 1997¶ | 1,286 | 50 | 3.89% | 36 | 9 | 3 | 0 | 2 | 0 |
|  | 1998¶ | 877 | 24 | 2.74% | 15 | 5 | 3 | 1 | 0 | 0 |
|  | 1999¶ | 960 | 61 | 6.35% | 16 | 8 | 18 | 17 | 1 | 1 |
| Texas | 2000¶ | 12,380 | 352 | 2.84% | 160 | 92 | 45 | 50 | 4 | 1 |
|  | 2001 | 172,397 | 1,741 | 1.01% | 1,070 | 346 | 158 | 151 | 12 | 4 |
|  | 2002¶ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 2003 | 252,036 | 1,798 | 0.71% | 1,121 | 351 | 156 | 153 | 16 | 1 |
|  | 1997 | 1,794 | 44 | 2.45% | 19 | 15 | 4 | 6 | 0 | 0 |
|  | 1998 | 2,493 | 53 | 2.13% | 33 | 15 | 3 | 2 | 0 | 0 |
|  | 1999 | 2,608 | 19 | 0.73% | 13 | 3 | 2 | 1 | 0 | 0 |
| Utah | 2000 | 3,583 | 22 | 0.61% | 12 | 8 | 1 | 1 | 0 | 0 |
|  | 2001 | 3,438 | 19 | 0.55% | 9 | 5 | 2 | 3 | 0 | 0 |
|  | 2002 | 4,343 | 25 | 0.58% | 16 | 4 | 0 | 5 | 0 | 0 |
|  | 2003¶ | 4,127 | 24 | 0.58% | 15 | 6 | 1 | 2 | 0 | 0 |
|  | 1997 | 6,744 | 306 | 4.54% | 186 | 74 | 23 | 22 | 1 | 0 |
|  | 1998 | 6,253 | 239 | 3.82% | 143 | 51 | 26 | 14 | 5 | 0 |
|  | 1999 | 6,181 | 170 | 2.75% | 94 | 37 | 24 | 15 | 0 | 0 |
| Vermont | 2000 | 6,428 | 179 | 2.78% | 105 | 48 | 12 | 13 | 1 | 0 |
|  | 2001 | 6,465 | 145 | 2.24% | 75 | 43 | 17 | 8 | 2 | 0 |
|  | 2002 | 6,731 | 149 | 2.21% | 91 | 30 | 14 | 12 | 1 | 1 |
|  | 2003 | 6,864 | 133 | 1.94% | 73 | 30 | 15 | 13 | 2 | 0 |
|  | 1997 | 12,905 | 868 | 6.73% | 415 | 226 | 115 | 103 | 6 | 3 |
|  | 1998 | 23,863 | 942 | 3.95% | 481 | 239 | 111 | 86 | 24 | 1 |
|  | 1999 | 24,388 | 501 | 2.05% | 266 | 143 | 58 | 29 | 5 | 0 |
| Virginia | 2000 | 25,786 | 617 | 2.39% | 369 | 141 | 47 | 57 | 3 | 0 |
|  | 2001 | 39,771 | 470 | 1.18% | 238 | 112 | 56 | 52 | 12 | 0 |
|  | 2002 | 51,459 | 560 | 1.09% | 314 | 123 | 51 | 62 | 10 | 0 |
|  | 2003$ | 51,444 | 411 | 0.80% | 222 | 96 | 46 | 41 | 5 | 1 |
|  | 1997 | 3,715 | 38 | 1.02% | 21 | 4 | 6 | 7 | 0 | 0 |
|  | 1998 | 3,278 | 40 | 1.22% | 25 | 8 | 2 | 5 | 0 | 0 |
|  | 1999 | 3,117 | 28 | 0.90% | 16 | 3 | 4 | 4 | 1 | 0 |
| Washington | 2000 | 3,617 | 40 | 1.11% | 19 | 4 | 9 | 6 | 1 | 1 |
|  | 2001 | 3,491 | 32 | 0.92% | 19 | 4 | 3 | 5 | 1 | 0 |
|  | 2002 | 6,606 | 42 | 0.64% | 20 | 15 | 1 | 6 | 0 | 0 |
|  | 2003 | 5,581 | 31 | 0.56% | 13 | 12 | 2 | 3 | 1 | 0 |
|  | 1997 | 11,637 | 263 | 2.26% | 169 | 53 | 23 | 15 | 3 | 0 |
|  | 1998 | 10,483 | 237 | 2.26% | 150 | 56 | 18 | 12 | 1 | 0 |
|  | 1999 | 9,571 | 167 | 1.74% | 112 | 35 | 13 | 6 | 1 | 0 |
| West Virginia | 2000 | 11,753 | 173 | 1.47% | 115 | 36 | 12 | 9 | 0 | 1 |
|  | 2001 | 12,194 | 147 | 1.21% | 89 | 33 | 15 | 9 | 1 | 0 |
|  | 2002 | 13,649 | 149 | 1.09% | 98 | 28 | 13 | 9 | 1 | 0 |
|  | 2003 | 14,664 | 161 | 1.10% | 93 | 26 | 22 | 18 | 1 | 1 |
|  | 1997 | 68,464 | 7,010 | 10.24% | 3,681 | 1,794 | 781 | 677 | 64 | 13 |
|  | 1998 | 69,590 | 5,334 | 7.66% | 2,972 | 1,299 | 532 | 480 | 44 | 7 |
|  | 1999 | 70,686 | 4,567 | 6.46% | 2,581 | 1,132 | 417 | 397 | 36 | 4 |
| Wisconsin | 2000 | 70,382 | 3,910 | 5.56% | 2,325 | 807 | 389 | 351 | 28 | 10 |
|  | 2001 | 79,225 | 3,659 | 4.62% | 2,159 | 823 | 344 | 295 | 33 | 5 |
|  | 2002 | 81,608 | 3,363 | 4.12% | 2,057 | 705 | 299 | 266 | 32 | 4 |
|  | 2003 | 81,077 | 2,820 | 3.48% | 1,669 | 654 | 242 | 233 | 20 | 2 |
|  | 1997 | 642 | 11 | 1.71% | 6 | 1 | 2 | 2 | 0 | 0 |
|  | 1998 | 851 | 15 | 1.76% | 6 | 4 | 2 | 3 | 0 | 0 |
|  | 1999 | 1,241 | 6 | 0.48% | 5 | 0 | 0 | 1 | 0 | 0 |
| Wyoming | 2000 | 1,191 | 3 | 0.25% | 2 | 0 | 0 | 0 | 0 | 1 |
|  | 2001 | 1,277 | 4 | 0.31% | 3 | 0 | 1 | 0 | 0 | 0 |
|  | 2002 | 1,581 | 4 | 0.25% | 2 | 1 | 0 | 0 | 1 | 0 |
|  | 2003 | 1,726 | 8 | 0.46% | 5 | 1 | 0 | 2 | 0 | 0 |
|  | 1997 | 1,611,569 | 122,641 | 7.61% | 67,793 | 28,312 | 13,473 | 11,693 | 1,170 | 200 |
|  | 1998 | 1,761,674 | 114,571 | 6.50% | 66,305 | 25,636 | 11,498 | 9,896 | 1,076 | 160 |
|  | 1999 | 1,891,870 | 94,438 | 4.99% | 55,603 | 20,813 | 9,140 | 7,930 | 842 | 110 |
| United States¶ | 2000 | 2,216,700 | 87,792 | 3.96% | 51,646 | 18,922 | 8,509 | 7,753 | 814 | 148 |
|  | 2001 | 2,538,008 | 76,992 | 3.03% | 45,856 | 16,502 | 7,060 | 6,647 | 800 | 127 |
|  | 2002 | 2,454,181 | 65,811 | 2.68% | 39,817 | 14,191 | 5,779 | 5,329 | 597 | 98 |
|  | 2003 | 2,729,136 | 55,765 | 2.04% | 34,232 | 11,586 | 4,781 | 4,578 | 514 | 74 |

Note: State data and analysis may vary from CDC data because of strict CDC guidelines for data acceptance

* Confirmed by either one elevated venous test or two elevated capillary tests <12 weeks apart

† BLLs between 10–24 μg/dL may be underreported – reporting requirements of BLLs within this range differ by state

§ Statewide surveillance start-up year

¶ Incomplete data: CDC does not have the state’s complete dataset

$ Not funded by CDC, so not required to report BLL data

N/A - State surveillance system not in place

Frequently Asked Questions (FAQs)

During technical assistance conference calls held on 12/15/05 and 12/19/05 questions were from potential applicants were posed, to which the following responses are presented in the form of frequently asked questions (FAQs).

Matching

What funds can be used for match? - State and local funds - State share of Medicaid reimbursement for lead screening and covered lead case management and environmental risk assessments. - Hardware costs for implementing Lead PAM - Software development costs for enhancements to non-NEDSS-based system. - Maintenance costs for non-NEDSS-based system. How to account for matching funds in the application? Matching funds can be detailed in Letters of Support. Are these matching funds a cash match? No, what we are looking for is a level of effort, not actual cash contribution to the program, however that level of effort has a cost associated with it. For example, the state share of Medicaid reimbursement goes to pay a claim for a lead service, not to the CLPPP to buy more pamphlets. In this example, use historical data to estimate the state share of the Medicaid reimbursement. Provide a Letter of Support from state Medicaid agency that indicates the estimated amount of state share for lead services in first budget year. Can Community Development Block Grants (CDBG) funds be used as match? No, CDBG are federal funds. Can community based organizations funding be used as match? Yes, the amount of funds that originate from state or local funds and are used to further the lead program goals and objectives. What accounting method is required for the match during the first budget year? Specific guidance will be provided to successful awardees.

Medicaid Provider Certificate/Statement

What must we include in the application? A Medicaid Provider Certificate or Statement that indicates that those entities that provide services to Medicaid eligible children are authorized as Medicaid providers to bill Medicaid for covered services. If a Medicaid Provider Certificate/Statement is not included with the application, will the application be returned? Yes.

Back to top

Partnerships with Housing Entities

Can you define housing entities and give some examples? Housing entities generally oversee and/or distribute HUD funds for housing in the state or locale and are responsible for completion of the state or local HUD Consolidated Plan for Housing. - State environmental quality agencies that are most often attached to the state health department. They generally oversee the EPA lead disciplines training and certification grant programs. - Regional or local housing authorities that oversee HUD subsidized housing. - Local housing agencies that enforce local housing codes.

Surveillance

Where are the environmental data elements that CDC will require to be reported as part of the quarterly data submission? The environmental data elements are listed in the Surveillance Appendix VI.

Environmental Public Health Tracking Programs

Where are existing programs located? Existing Public Health Tracking Programs are identified at http://www.cdc.gov/nceh/tracking/projects/home.htm.

Screening/Case Management

Are you expecting one plan to be submitted for both screening and case management? No, they are generally two separate plans, but we would like for them to be presented together as two parts of overall plan for secondary prevention. Will CDC provided funds for blood lead testing? Our policy remains unchanged regarding blood lead testing, we will not provide funds for blood lead testing.

Back to top

Primary Prevention

What activities are you looking for in the application with regard to women of childbearing age? Lead poisoning prevention educational activities.

Letters of Support

To whom should the Letters of Support be addressed? Gary Teague, Grant Management Specialist

Appendix IX

Appendix IX column heading appear to have shifted. Appendix IX will be reformatted and provided on Grants.gov in early January.

Data requested in NEED Section

Please clarify the age ranges for blood lead screening and elevated blood lead levels data requested. We are asking for number of children tested and number of children confirmed with BLL>=10 that are less than 6 years old (< 72 months). The age groups are 0 through 35 months (for children less than 3 years) and 0 through 71 months (for children less than 6 years).

Under Program Element Surveillance (C ), what is meant by activities that require enforcement or development of regulations that require electronic reporting of all environmental test results for children < 72 months of age? The applicant should provide evidence that they have the ability to, (or planning activities that will result in the ability to) assess the lead safe status of all target housing within their jurisdiction (not only housing occupied by a child with an EBLL). To assess the lead safe status of all target housing, requires the applicant to compile the results of all lead inspections/risk assessments performed within their jurisdiction. Not lead sample results (i.e., XRF readings, paint chip, soil, water analysis results), but results meaning whether lead hazards were identified or not. Follow up activities that take place (or not) in those target housing units where lead hazards are identified is also an integral aspect of that assessment. The regulatory aspect is related to the possibility of making the provision of these certain data from all lead inspections/risk assessments a condition of lead inspector/risk assessor state licensure or perhaps a local requirement.