eGovernment Initiatives

Integrated Acquisition Environment (IAE)

Project Charter

"Unify and Simplify

Through Shared Services"

Submitted by:

IAE Program Management Office

January 17, 2003

Version 2.0

Revision Chart

| Version | Primary Author(s) | Description of Version | Date Completed |
| --- | --- | --- | --- |
| 2.0 | D. Drews | Major revision/updated to Version 1 | 01/07/2003 |
| 2.1 | D. Drews | Review revisions | 01/13/2003 |
| 2.2 | T. Dumouchelle | Final revisions | 01/16/2003 |
| 2.3 | D. Drews | Additional module descriptions | 01/17/2003 |

APPROVALS

We, the undersigned, accept this document as a stable work product to be placed under formal change control as described by the Change Control Procedure document.

Signed:	Date:

Function Sponsor

Signed:	Date:

Organization Sponsor

Signed:	Date:

Project Manager

Table of Contents

Revision Chart	2

1.	Introduction	4

2.	Detailed Section Definitions	4

2.1	Background	4

2.2	The Issue	5

2.2.1	Problem Statement	5

2.2.2	Scope	6

2.3	Goals of project	9

2.3.1	Goals	9

2.3.2	Date for Completion of Project	10

2.3.3	Impact of Goal Achievement	10

2.4	Key Objectives and Timeline	11

2.5	Roles	12

2.5.1	E-Gov Leadership Team	14

2.5.2	Sponsors	14

2.5.3	Project Managers	14

2.5.4	Team Leads	15

2.5.5	Team Members	15

2.5.6	Project Stakeholders	18

2.6	Resources/Constraints	18

2.7	Assumptions and Risks	18

2.7.1	Assumptions	18

2.7.2	Risks	20

2.8	Linkages/Dependencies	21

2.8.1	Internal	21

2.8.2	External	22

2.9	Decision Making	23

2.9.1	Internal	23

2.9.2	External	24

2.10	Communication	25

2.10.1	Internal	25

2.10.2	External	26

2.11	Knowledge Management	27

# 1.         Introduction

The Integrated Acquisition Environment (IAE) Project is a result of the Presidents Management Agenda as it relates to e-Government (e-Gov).  The emergence of the Internet as a platform for communication and the exchange of goods and services is transforming the way organizations interact and transact with their business partners.  These new technologies are making it possible for organizations to greatly reduce costs and streamline business processes while improving customer service.

The IAE will be built on the framework of a shared services model where no single organization has "ownership", rather the services are a constellation of capabilities built on standards and accessible over the Internet.  The IAE will serve as the access point for various services and will provide a set of tools and capabilities that can be leveraged by the acquisition community stakeholders to conduct business across the government.  The IAE will provide access to Internet-based software solutions, acquisition capabilities and value-added services required to support the entire acquisition lifecycle in a unified and fully integrated manner.  The IAE will leverage the Internet and the technology infrastructure currently existing in government agencies and will also leverage existing and emerging government capabilities such as FirstGov and the e-Authentication initiative.

The project charter summarizes the essential information for the Integrated Acquisition Environment Project team. The purpose of the charter is to ensure that the team members are aligned with the project sponsor as to the purpose, timeframe, support and key checkpoints.

# 2.         Detailed Section Definitions

## 2.1         Background

This document has been prepared in accordance with direction and guidance provided by the Office of Management and Budget.

The Federal Government spends approximately $200 billion on the acquisition of goods and services, making it the largest purchaser in the world.  Government agencies utilize multiple methods of acquisition, work with thousands of suppliers, and purchase millions of different products and services.  Given the size and complexity of federal acquisitions, legislation over the last decade, for example, the Information Technology Management Reform Act (ITMRA, or the Clinger Cohen Act), Federal Acquisition Reform Act (FARA), the Government Paperwork Elimination Act (GPEA) and Federal Acquisition Streamlining Act (FASA), have effectively mandated that acquisition functions be simplified, clear, and understandable.  The intent of these legislative initiatives is to improve the efficiency of the acquisition process by facilitating the acquisition of commercial products and services, and transforming the process to accommodate electronic commerce.

The Integrated Acquisition Environment Project was born out of the Quicksilver Task Force that was established to address performance gaps and redundancies in existing Government systems as they relate to e-Government, a key component of the President's Management Agenda.

Two acquisition environment alternatives were originally defined and analyzed: (1) retain the status quo with limited integration between the e-Procurement systems among participating partners and considerable duplication of data, and (2) provide the initial components of an Integrated Acquisition Environment with the technology, tools, services and operational capabilities to address the entire acquisition lifecycle in a fully integrated environment.  Subsequently, as a part of the OMB 300B process, a third alternative was considered. This third alternative considered a compromise environment:  proceed with the development of the Business Partner Network, the replacement of the Federal Procurement Data System with a modern management information system, the directory of interagency contracts and the Intra-governmental transaction exchange.  There would be no integration or standard interface development and no overarching portal to connect those files for the user.

The second alternative, the Integrated Acquisition Environment approach, was chosen because it provided the most significant improvements in effectiveness and efficiency. The IAE vision is to fully leverage the best available business services by integrating them to make them available to all stakeholders in a cost effective way.

## 2.2         The Issue

### 2.2.1        Problem Statement

Federal agencies have responded to the need to streamline acquisitions by undertaking various initiatives.   Agencies are increasingly leveraging electronic technologies to streamline acquisitions, reduce costs, and collaborate with suppliers.  However, as more and more agencies have undertaken initiatives, lack of coordination among Agencies has led to other inefficiencies, including:

-         Duplication of effort – In order to meet their individual needs, various initiatives have been undertaken often, with no coordination across Agencies and missed opportunities to partner with other Agencies.  This has resulted in many redundant initiatives with no standards across the government.  Also, many of these initiatives require expertise to be properly developed and managed, expertise that is often not available or too expensive to justify for each agency.  An example of duplication of effort is redundant eCatalogs.  Many agencies are implementing and maintaining eCatalogs at great cost.  Instead, these agencies should be looking to leverage government and commercial catalogs for integration.

-         Stove-piped information systems – Since many initiatives are being implemented without coordination, these systems are unable to "talk" to each other or exchange information.  This has resulted in multiple handoffs and manual data transfers, and an inability to exchange critical information.

-         No data/messaging standards – As described above, different, incompatible data/messaging methods are utilized making it impossible for systems to share information.  E-commerce at its core implies communication and exchange of information among business partners.   An example of lack of data/messaging standards is the ability to exchange files for BPN.

-         Lack of scale – Some initiatives, such as eCatalogs, require a minimum level of size and scale in order to deliver a positive ROI.  Since many agencies do not generate enough purchasing activity to reach the required size, they either cannot invest in these initiatives or invest and incur losses.  An example related to scale is eCatalogs or a supplier database.  Both require large investments and a great deal of expertise.

-         Cross-Agency leverage – There are many opportunities to better leverage the government buying power through better cross-agency coordination of acquisitions.

There are many common acquisition functions/needs, such as the ability to search for suppliers, which can and should be managed as a shared service. If these functions/needs are addressed as a government-wide shared service, agencies can focus on mission-specific needs such as strategy, operations, and management. The Integrated Acquisition Environment enables leveraging government-wide shared services for common functions.

### 2.2.2        Scope

The project scope falls under Internal Efficiency and Effectiveness  (IEE) to "improve the performance and reduce costs of Federal Government administration by using best practices in areas such as supply chain management, financial management, and knowledge management."  It is not intended to create a new central system, nor to replace current business tools used in those functional areas.  The vision is to provide "a secure business environment that facilitates and supports cost effective acquisition of goods and services in support of mission performance".

Many of the building blocks for the IAE exist today but need to be further developed and unified, based on common standards, in order to provide the open access, standards-based functionality, interoperability and scalable capability needed for the acquisition process.

The first five modules selected to develop the initial capabilities of an IAE will serve as the foundation for the fully implemented IAE.  The five modules that pertain to this project charter are:

- e-Catalogs will provide a common on-line access to current interagency contracts and electronic catalogs for goods and services to all federal customers and establish a common framework for development of future eCatalogs.  				                                                               This initiative will establish a government e-Catalog directory of existing interagency contracts, to facilitate discovery and enable smarter business decisions.  It will enable future analysis of business duplication to improve leverage.  The intra-governmental sources for supplies and services will also be listed within e-Catalogs, providing users access to all government sources in one place. The longer-term vision is to move towards integration of e-catalogs in an effort to eliminate duplicate requirements on our vendors and facilitate integration with back office finance and acquisition systems.

- Business Partner Network (BPN), initially identified as the Integrated Vendor Profile Network (IVPN), will provide a single point of registration, validation, and access for all trading partner data. 						          The DoD's Central Contractor Registration (CCR) system is the core for the new system to be used by all government agencies.  As it expands to include grantees and intra-governmental sources, it will be renamed the Business Partner Network (BPN).   It replaces the multiple, manual, redundant, and often inconsistent vendor data collection systems with a single data entry system for vendor information collection and validation that will be shared with agency contract writing systems.  It will also be enhanced to

-         Add Annual Representations and Certifications for vendors

-         Validate data with third parties wherever possible such as Taxpayer Identification Number with IRS; DUNS numbers with Dun and Bradstreet, and 8(a), HubZone, and Small Disadvantaged Business status validation with SBA

-         Integrate with other vendor-based systems in the Government to provide a single source for all information on a vendor to improve competitive sourcing and enable better business decisions.  Examples include past performance information from the Government-Wide PPIRS (Past Performance Retrieval System)  (fed by the NIH, NASA, and DoD), FedBizOpps, FMS Treasury Offset Program, and the Excluded Parties Listing System.

- Federal Procurement Data System – Next Generation (FPDS-NG), initially identified as the Federal Acquisition Management Information System (FAMIS), redesigns the existing Federal Procurement Data System (FPDS) and provides for better integration with agency legacy procurement systems.                                      A government-wide procurement reporting system is critical to understanding purchasing activity across the government. This allows the government to develop sourcing strategies including opportunities to pool spend, negotiate government-wide contracts, and identify purchasing trends. The current government-wide procurement reporting system, FPDS or the Federal Procurement Data System, has become outdated and in need of enhancements. Specifically, the system is not integrated with agency procurement systems, and only captures limited historical data.  FPDS-NG will be the central point for consolidated collection of statistical and management information related to government acquisitions. It will provide timely management data and tailored reporting capability of real-time information in an automated environment. It will also eliminate the need for agency feeder systems.

- Intra-governmental Transactions Exchange redesigns the process for government-to-government transactions in order to streamline ordering, billing and collection and to improve the financial settlement process.                            Ordering, billings, and collections between federal agencies, and between organizations within some agencies, are extremely inefficient. Additionally, matching or reconciling these transactions is extremely difficult because there is no standardized process.  The new standardized approach will unify the process and introduce and enforce data stewardship roles and responsibilities. This will streamline the data handling processes, reduce workload, improve billing accuracy, and reduce payment errors. It will also significantly improve the ability to identify matching intra-governmental revenues and expenses for elimination purposes in the preparation of consolidated financial statements. Finally, the buyer generated order number and the seller generated invoice number will provide agencies links to the data to create accounting entries within their systems.

- Standard eTransactions establishes standard data elements, business definitions, interfaces, and roles and responsibilities for government acquisition data.               At their core, e-commerce applications are about sharing information between multiple partners.  Standardized electronic transactions enhance information sharing among systems and agencies and support the "enter once, use many times" concept.  This begins by mapping the process, which is currently underway, and establishing standard business definitions, ownership, behaviors, and roles and responsibilities.  The process is building upon existing work done by the Joint Financial Management Improvement Program (JFMIP) document detailing touch-points among procurement and financial functional areas, and the DoD end-to-end activity, which mapped the acquisition process and identified touch points where data is transferred between functions. Commercial standards will be used to develop standard interfaces between each shared system, between shared systems and agency systems, and between shared systems and vendor partners.

- Other extensions of the IAE The IAE team has identified many other systems and databases that can be shared to further unify the process. While many of these exist today, their integration into the IAE through standard interfaces will enhance the initiative. Integration will also allow unified governance through one Configuration Control Board and funding from a central account accrued by a surcharge on all users as proposed later in this document.  Some of these are:

-         Maintenance and integration of current systems such as:  FedBizOpps (FBO), Excluded Parties Listing System (EPLS), Past Performance Information Retrieval System (PPIRS) and the past performance collection systems.

-         Integrated access to DOL electronic wage rate determinations data and

-         Expansion of DOD's Technical Data System (TeDS) government wide to improve monitoring of vendor access to secured drawings.

-         Development of an electronic means for accessing subcontracting opportunities and reporting data. Online access to contract documents as required and appropriate.

In addition to the original five modules, an additional module, the IAE Portal and Integration Broker, will deliver the integration capability that will provide a single, common, on-line user interface to the IAE and set of common interfaces to the Agency back-office systems.

## 2.3         Goals of project

### 2.3.1        Goals

●        Create a simpler, common, integrated business process for buyers and sellers that promotes competition, transparency and integrity

●        Increase data sharing to enable better business decisions in procurement, logistics, payment and performance assessment

●        Take a unified approach to obtaining modern tools to leverage investment costs for business related processes

### 2.3.2        Date for Completion of Project

The date of completion for the Planning and Acquisition phases of this project is anticipated to be 30 September 2004, with Operations & Maintenance continuing through 30 September 2011.

### 2.3.3        Impact of Goal Achievement

The U. S. Federal Government is the largest purchasing organization in the world.  As such, the government can benefit substantially from streamlining acquisition processes and leveraging its buying power to reduce the cost of goods purchased.  The IAE promises to quickly and efficiently provide the government acquisition community the tools to begin taking advantage of new state-of-the-art technologies.  As use of these technologies grows over time, the government will be able to substantially reduce costs of acquisitions and use taxpayer dollars for other programs.

## 2.4         Key Objectives and Timeline

The key objectives, milestones, and completion dates are as follows:

| Objective | Milestone | Completion Date |
| --- | --- | --- |
| Reduce the cost and make transparent the ordering, billing, and collections of intergovernmental transactions by increasing the visibility and beginning to integrate those transactions into the acquisition process | Develop intra-governmental transaction exchange | September 30, 2003 |
| Implement a directory of interagency contracts to simplify selection and facilitate leverage of Government buying | Initial operational capability (Identify GWAC, MAC and other interagency contracts and limited ordering information) | July 15, 2002 |
|  | Final rule (Requires backfill of information on existing contracts) | December 31, 2002 |
|  | Available for full data entry | December 31, 2002 |
|  | Fully populated database | June 30, 2003 |
| Develop a standard glossary and vocabulary to facilitate exchange of data between and within agencies | Final comments on JFMIP exposure document (Defines procurement and finance touch points) | February 28, 2002, complete |
|  | Define data for synopses and solicitations | September 30, 2003 |
| Deploy a single point of registration and validation of trading partner data accessed by all agencies | Initial operational capability | June 30, 2002 |
|  | Full operational capability | October 1, 2003 |
| Implement a central point for consolidated collection and access of statistical and management information related to government acquisitions | Initial operational capability | December 31, 2003 |

## 2.5         Roles

Implementation of a government-wide, integrated acquisition environment is a complex process, the success of which relies heavily on cooperation amongst all stakeholders.  The multi-tiered management structure for the IAE implementation, as depicted below, reflects two separate management needs: strategic and operational.  At a strategic level, oversight is provided by the Internal Efficiency and Effectiveness (IE&E) Portfolio Steering Group.  On a tactical level, program management rests with the Program Manager, the IAE Program Management Office (PMO), and the agency partners.

Since the IAE is envisioned as a shared services model, specific capabilities will be built by participating organizations, championed by the Procurement Executive Council's Electronic Commerce Chair.  Under the general management of the IAE PMO, the participating organization will stand up the analysis, design, development and testing capability.  Once a specific capability is ready for implementation, IAE PMO will coordinate implementation activities throughout the agencies.

The IAE Module team members from the Partner Agencies and Participating Agencies play a critical role in the definition, design, testing, and implementation of the IAE.  These teams provide hands-on support to the various IAE projects, while serving as the primary liaison and communication channel between the designated government agencies and the IAE PMO.  The module teams consists of representatives from various government agencies.  The team lead, an IAE PMO representative, will be responsible for driving recommendations from the teams through the IAE PMO to the Internal Efficiency and Effectiveness Portfolio Steering Group for eGov Initiatives.

The module teams' overriding objective is to ensure that stakeholder agencies' interests are represented throughout the acquisition and implementation of the IAE.  To meet this objective, the team representative will:

-         Accept charters to design, develop and test the IAE

-         Keep the agency "in the loop" regarding IAE status and developments

-         Serve as a two-way communications agent between the agency and the IAE PMO

-         Reach out to functional experts within the agency to identify issues and concerns associated with IAE

-         Prioritize and communicate these concerns to the IAE PMO

-         Maintain open lines of communication with team counterparts to consolidate and resolve conflicting interests and requirements

-         Work with team counterparts to resolve issues and problems identified throughout the process and provide recommendations for solution to PMO

-         Manage implementation activities in their organization and support other organizations in their implementation

Consulting Partners will be brought into the IAE program to provide subject matter expertise on emerging government initiatives, policy, privacy and other administrative issues needed to steer IAE to a successful implementation.  Consulting Partners relationships will be maintained throughout implementation.  Close interaction between these organizations and the IAE PMO will be critical.

### 2.5.1        E-Gov Leadership Team

| Name | Title | Comments |
| --- | --- | --- |
| Stephen Perry | Administrator, GSA |  |
| Michael Carleton | E-Gov Lead/CIO, GSA |  |
| Donna Bennett | Commissioner, FSS |  |
| Sandra Bates | Commissioner, FTS |  |
| F. Joseph Moravec | Commissioner, PBS |  |
| G. Martin Wagner | Associate Administrator, Office of Government-wide Policy (OGP) |  |
| M. J. Jameson | Associate Administrator, Office of Citizen Services |  |
| Lewis Sanford | GSA PMO Manager, Architect | Coordinates the five GSA initiatives |

### 2.5.2        Sponsors

| Name | Title | Comments |
| --- | --- | --- |
| Donna Bennett | Commissioner, FSS | Organizational sponsor |
| Michael Sade | Procurement Executive, Department of Commerce | Functional sponsor (Chair, Procurement Executive Council E-Commerce Committee) |

### 2.5.3        Project Managers

The IAE Project Managers are responsible for defining and meeting the specific measurable objectives for the project in terms of performance, cost and schedule goals.

| Name | Title | Comments |
| --- | --- | --- |
| Teresa Sorrenti | Project Manager |  |
| Earl Warrington | Deputy Project Manager |  |

### 2.5.4        Team Leads

The IAE Project is logically separated into five initiatives, each with a team and team lead.

| Name | Title | Comments |
| --- | --- | --- |
| Linda Burgher, DOD | Lead, Team A - BPN | Business Partner Network (BPN) |
| Pat Brooks, GSA | Lead, Team B - FPDS | Federal Procurement Data System – Next Generation (FPDS-NG) |
| Vacant | Lead, Team C | e-Catalogs |
| Vacant | Lead, Team D | Standard e-Transactions |
| Janet McBride, OFFM | Lead, Team E | Intra-governmental Transactions |
| Vacant | Lead, Team F | IAE Integration Broker and Portal |

### 2.5.5        Team Members

#### 2.5.5.1       Team A: BPN

| Name | Agency | Comments |
| --- | --- | --- |
| Vacant | Commerce | Partner |
| Lisa Romney | Defense | Partner |
| Bruce Propert | Defense |  |
| Terry Hunt | Defense |  |
| Linda Burgher | Defense | Partner Lead |
| Lilly Valoree | DHS | (Formerly, EPA) |
| Gay Prejean | EPA |  |
| Ron Taylor | GSA | Member until 1/3/03 |
| Ed Loeb | GSA |  |
| J. K. Peterson | Interior | Partner |
| Karl Beisel | NASA | Partner |
| Arthur Collins | SBA | Partner / Virtual Member |
| Pam Campbell | Transportation | Partner |
| Richard Miller | Treasury |  |
| Debbie Banks | USAID |  |
| Linh Lam | USAID |  |
| Dwight Ford | VA | Partner |

#### 2.5.5.2       Team B: FPDS-NG

| Name | Agency | Comments |
| --- | --- | --- |
| Debbie Streufert | Defense | Partner |
| Philip Degen | Defense |  |
| Bernice Bealle | EPA | Former member |
| John Cochran | GSA |  |
| Margaret Neary | GSA |  |
| Pat Brooks | GSA |  |
| Barbara Levy | HHS |  |
| Barry McVay | HUD |  |
| Ed Girovasi | HUD |  |
| Bill Childs | NASA | Partner |
| Sue Hopkins | NRC |  |
| Linda Williams | SBA | Partner / virtual member |
| Neil Wensel | SBA |  |
| Bonnie Hangar | Treasury |  |
| Lou Masciocchi | Treasury |  |
| Joe Daragan | USDA | Partner |

#### 2.5.5.3       Team C: e-Catalogs

| Name | Agency | Comments |
| --- | --- | --- |
| Jack Stem | Defense | Partner |
| Liz Howard | EPA |  |
| Bill Morgan | GSA |  |
| Sarah Harris | GSA FTS |  |
| Steve Mahaney | HHS | Virtual observer |
| Pete Brownell | Interior | Partner |
| Ron Crider | NASA | Partner |
| Linda Williams | SBA | Partner / virtual member |
| Stan March | SSA |  |
| Lisa Maass | Transportation | Partner |
| Richard Sites | Transportation | Partner |
| Patricia Hoover | Treasury |  |
| Dwight Ford | VA | Partner |
| Ron Jones | VA | Partner/ Virtual member |

#### 2.5.5.4       Team D: Standard e-Transactions

| Name | Agency | Comments |
| --- | --- | --- |
| Vacant | Commerce |  |
| Steve Slavsky | Defense | Partner |
| Cedric Vessel | Defense |  |
| Rosemary Evans-Finley | Education |  |
| Judy Madden | EPA |  |
| Ron Taylor | GSA | Retired 1/3/03 |
| Paul Marsden | Interior | Partner |
| Anne D. Hudson | Justice |  |
| Ken Stepka | NASA | Partner |
| Arthur Collins | SBA | Partner / virtual member |
| Dan Walt | State |  |
| Lee Kair | USCG |  |
| Linh Lam | USAID |  |
| Dwight Ford | VA | Partner |

#### 2.5.5.5       Team E: Intra-governmental Transactions

| Name | Agency | Comments |
| --- | --- | --- |
| Eileen Parlow | Defense |  |
| Jackie Carter | Defense |  |
| Denny Daniel | EPA | Retired 1/3/03 |
| Ofelia Moore | EPA |  |
| Ron Taylor | GSA | Retired 1/3/03 |
| Paul Weinberger | HHS | Finance |
| Joan Kimmel-Frantz | Interior | Partner |
| Janet McBride | OMB | Lead |
| Brian Wolfe | Transportation | Partner |
| Jeff Hoge | Treasury |  |
| Linh Lam | USAID |  |
| Larry Jackson | VA |  |

#### 2.5.5.6       Team F: IAE Integration Broker and Portal

| Name | Agency | Comments |
| --- | --- | --- |
| Lisa Romney | Defense |  |
| Bruce Propert | Defense |  |
| Linda Burgher | Defense |  |
| Jack Stem | Defense |  |
| Anne D Hudson | DOJ |  |
| Gay Prejean | EPA |  |
| Elizabeth Howard | EPA |  |
| Ronald Taylor | GSA | Retired 1/3/03 |
| Sarah Harris | GSA |  |
| John Cochran | GSA |  |
| Pat Brooks | GSA |  |
| Edward C. Loeb | GSA |  |
| Peter H. Brownell | Interior |  |
| J. K. Peterson | Interior |  |
| Patricia V. Hoover | IRS |  |
| Ron Crider | NASA |  |
| Ken Stepka | NASA |  |
| Julie Basile | OMB |  |
| Linda Williams | SBA |  |
| Stan March | SSA |  |
| Richard Miller | Treasury |  |
| Lee Kair | USCG |  |
| Howard G Price | USDA |  |
| Dwight Ford | VA |  |

#### 2.5.5.7       Cross-team Observers / Virtual Members

| Name | Agency | Comments |
| --- | --- | --- |
| Dan Cassil | GSA |  |
| John Geist | GSA |  |
| Vonia Ashton-Grigsby | GSA |  |
| Edward Leary | HUD |  |
| Karin Kurz | Labor |  |
| Patrick Mullen | USAID |  |
| Tish Tucker | USDA |  |
| Lois Russell | VA |  |

### 2.5.6        Project Stakeholders

| Stakeholder | Stake | Consultation Approach | Representative | Title |
| --- | --- | --- | --- | --- |
| Procurement Executive Council | Must implement and integrate results | Status briefings | Gary Krump / Mike Sade | Vice Chair |
| Office of Federal Procurement Policy | Must make some regulatory or procedural changes | Status briefings | Angela Styles | Administrator |
| Office of e Government, OMB | Responsible for e-Gov projects as a whole | Regular meetings | Stephen Galvan | IEE Portfolio Manager |
| Quad Council | Steering Committee | Inform after | Stephen Galvan | Chair |
| COTS software providers | Must be able to incorporate changes | Meetings to discuss | varies |  |

## 2.6         Resources/Constraints

| Resources | Constraints |
| --- | --- |
| Personnel | Key positions are vacant. Other positions have "light" participation due to transient or inconsistent agency representation. |
| Funding | Long term costs are unknown at present |
| Requirements | Requirements are unverified and expanding (potentially) |
| Commitment | Agency willingness to use unknown |
| Funding | Reimbursement model proposed for sustaining funding |

## 2.7         Assumptions and Risks

### 2.7.1        Assumptions

The following table contains assumptions defined by the five project initiative teams for the IAE Project:

| Assumptions | Team A: BPN | Team B: FPDS | Team C: Catalogs | Team D: Std Data | Team E: Intra-gov. |
| --- | --- | --- | --- | --- | --- |
| FAR changes will be made | X |  | X |  |  |
| Other policy changes will be made | X |  | X |  | X |
| FPDS will populate the interagency contracts directory long term |  | X | X |  |  |
| BPN will populate FPDS long term | X | X | X | X |  |
| FPDS will have more leading indicators in the future, not just historical data |  | X |  | X |  |
| Some vocabulary exists and must be normalized |  |  |  | X |  |
| Funding will be available | X | X | X | X | X |
| Information and visibility will improve leverage |  | X | X |  | X |
| Store and reuse knowledge | X | X | X | X | X |
| Direct interface with contract writing systems is preferred | X | X | X | X | X |
| Focus must be on user: simplicity will increase and improve use | X | X | X |  | X |
| BPN will absorb PRONET registration function | X |  |  |  |  |
| Wage determination process will be integrated into the IAE but not in BPN | X |  |  |  |  |
| Cannot use BPN as the source for vendor data in FPDS until all agencies use BPN | X | X |  |  |  |
| Government buyers and sellers (customers/providers will be in BPN | X |  |  |  | X |
| Purchase card transactions are excluded |  | X |  |  | X |
| Interfaces should be multi-channel: web/batch transmitted | X | X | X | X | X |
| XML will eventually be used | X | X | X | X | X |
| Intra-government. solution could also be used intra-agency |  |  |  |  | X |
| Will not revisit use of an internal Government purchase card |  |  |  |  | X |

### 2.7.2        Risks

The following risks, impacts and mitigation strategies, updated to agree with the 300B, are defined for the IAE Project:

| Risk | Impact/Effect if not mitigated | Mitigation Strategy |
| --- | --- | --- |
| Some contracts restrict use | Unauthorized orders | Build restrictions into business rules |
| User acceptance/culture change |  | Communication plan; Ensure simplicity; Ensure value-added |
| No one will give up control of own system/catalog/data | Chaos; Continued redundancy and increased costs | Tie to budget allocations so that agency unique systems that overlap IAE functionality are no longer funded. Ensure benefits are communicated to get buy-in early in the process. |
| Content management could be overwhelming for consolidated view of all catalogs | Increase resource requirement to manage centralized data | Industry Best Practices will be followed to adopt distributed catalogs technique when feasible from a technological and business point of view. |
| Insufficient funding | Cannot implement | Work with FSS, PEC, OMB, QUAD Council |
| Insufficient funding for agency integration | IAE without users | Ensure that PMC, OMB, and CIOs are aware of internal agency requirements related to the e-Gov agenda |
| COTS providers of back office systems do not make required changes | Agencies cannot implement | Build requirements into FAR and JFMIP which are baseline requirements for COTS packages. Meet with COTS providers to ensure awareness and get early buy-in |
| Not all agencies have a contract writing system | Agencies cannot implement, have varied implementation timeframes | Ensure they either modify home grown systems or decide to purchase a COTS product; develop method for cross-agency servicing |
| FAR changes are not issued | Cannot implement | Work with OFPP/OMB/FAR Council to ensure issuance |
| Other Policy changes are not issued | Cannot implement | Work with OMB, FMS, etc. to ensure prompt issuance |
| IRS will not validate TINs | Erroneous 1099s continue | Meet with IRS to get BPN declared an authorized user or get law changed |
| Several business systems do not use DUNS numbers, especially financial systems | Difficulty sharing data and implementing BPN | Policy change; Cross-walk internal systems |
| No funding model set for long term | Inability to maintain the IAE after initial implementation | OMB/Congress determine how to fund cross-agency shared projects; Alternatively, subscription model would require early and consistent budgeting |
| Remote locations (and others in emergency conditions) may not be able to access | Inability to conduct acquisitions | Ensure redundant systems. Ensure multiple channels. Ensure alternate procedures. |
| Vendor socio-economic status can change | Risk of overwriting contract data | Ensure that critical data in BPN has effective dates |
| No standard source, format, or process for Intra-governmental transactions | Difficulty in automating | Begin with the business process and data and write a FAR-like procedure. |

## 2.8         Linkages/Dependencies

### 2.8.1        Internal

The following table contains the linkages and dependencies between the IAE Project modules and current or planned internal projects or work.

|  | Team A: BPN | Team B: FPDS-NG | Team C: Catalogs | Team D: Std Data | Team E: Intra-govt | e-Authen | e-Grants | HRDN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Team A: BPN |  |  |  | X | X | X | X |  |
| Team B: FPDS-NG | X |  |  | X |  | X |  | X |
| Team C: Catalogs |  | X |  | X |  | X |  | X |
| Team D: Std Data | X | X |  |  |  | X |  | X |
| Team E: Intra-govt | X |  |  | X |  | X |  | X |

### 2.8.2        External

The following table contains the linkages and dependencies between the IAE Project initiatives and current or potential relevant external trends.

|  | Team A: BPN | Team B: FPDS-NG | Team C: Catalogs | Team D: Std Data | Team E: Intra-Gov |
| --- | --- | --- | --- | --- | --- |
| Technology |  | Ability to send changes via metadata to agencies | Ability to search multiple catalogs | ebXML |  |
| JFMIP | Require registration not just value-added |  |  | Glossary of Finance touch points | New document on revenue systems |
| Past performance info retrieval | Ability to link |  |  | Vocabulary |  |
| Excluded parties listing | Must use DUNS |  |  | Vocabulary |  |
| Legal requirements | X | X |  |  | X |
| PEC |  | Rqmts and funding | Rqmts and funding |  |  |
| Legacy system integration | X | X | X | X | X |
| COTS package integration | X | X | X | X | X |
| Financial systems requirements |  | X |  |  | X |
| Transition/migration | X | X | X | X | X |
| NATO | CAGE for foreign firms |  |  |  |  |
| IRS | Validate TIN |  |  |  |  |
| SBA | PRONET business rules |  |  |  |  |
| FAR changes | •Require registration • Centralize Reps & Certs | Standard contract number | Require population of directory |  |  |
| Other Policy changes | •Require registration for payment •Accept banking RTN updates | Eliminate $ threshold for detailed reporting Data elements changing. |  |  | •Create procedures •Require registration •Require a "yellow pages" |
| DOL | EEO compliance business rules |  |  |  |  |
| NARA | Archive and audit trail rqmts | Archive and audit trail rqmts |  |  |  |
| Funding availability | X | X | X | X | X |

## 2.9         Decision Making

Decision-making, communication and knowledge management are made extremely complex by the distributed nature and time constraints of this initiative.  This initiative's members are not only people from across organizational boundaries, but agency and department boundaries.  Furthermore, it is expected that as the initiative matures, citizens, businesses, and Federal employees from across the country, if not the world, will play a vital part in its success.  Therefore, it is recognized that decision-making, communication and knowledge management are not separate and distinct processes of this initiative.  Rather, they are interwoven components of a complex whole.

When business and technical decisions need action, all GSA initiatives are supported by designated 'solution architects', Lew Sanford and Mark Raiffa, to promote consistency across initiatives and to seek opportunities to leverage investments.

### 2.9.1        Internal

Team meetings will be held weekly and will be the principal method of disseminating project information.  Within the initiative team, the program manager will work to arrive at consensus through open lines of communications at all times.    When team consensus cannot be reached, the issue will be brought before the appropriate level for adjudication and disposition.

Given that time and other resources are in short supply, the following decision-making procedures will be utilized when necessary.  However, these will be used for administrative actions as opposed to substantial issues with government-wide impact.

| Majority Control | Used when sufficient time is lacking for decision by consensus or when the decision is not so important that consensus needs to be used and when complete member commitment is not necessary for implementing the decision. |
| --- | --- |
| Average of members' opinions | Used when it is difficult to get group members together to discuss, when the decision is so urgent that there is not time for group discussion, when member commitment is not necessary for implementing the decision, etc. This method is applicable to simple, routing decisions. |
| Expert member | Used when the expertise of one person is so far superior to that of all other group members that little is to be gained by discussion. Used only when the need for membership action in implementing the decision is slight. |
| Decision by authority without discussion | Used for simple routine decisions, when very little time is available to make the decision, when group members expect the designated leader to make the decision, and when group members lack the information to make the decision any other way. |

### 2.9.2        External

Issues that reach beyond the team and require a deeper consideration of government-wide impact (reference Figure 1 below) will be approached in two ways:

- 1.      The decision-making channels for GSA acting as the managing partner is represented on the left in the figure below.  The program manager will consult with the designated GSA service commissioner who will, if need be, further consult with the GSA Administrator, Commissioners of the other GSA services, the Associate Administrator of the Office of Government-wide Policy and the GSA CIO.

- 2.      Decision-making channels for OMB, acting as the coordinating entity on issues requiring broader coordination, legislative changes, etc., is represented on the right in the figure below.  The program manager will consult with the designated portfolio manager who will, if need be, further consult with the portfolio steering committee, Quad Council, and the OMB Portfolio Management Office.

Figure 1.  Decision-Making and Communication Channels

## 2.10     Communication

As a foundation to communication, staff meetings will be held weekly and they will be the principal method of disseminating project information.  The OMB IEE Portfolio Manager is updated every two (2) weeks. The program manager also meets monthly with the GSA Executive Committee to keep them informed.  Quarterly, the program manager will brief the GSA Administrator.  The program manager may meet more often with the OGP Associate Administrator and the OMB IEE Portfolio Manager according to the importance and impact of actions by the initiative team members.  In addition, the program manager and the IAE staff will participate in weekly meetings of the GSA Program Management Office to ensure cross-pollination of ideas among the other GSA-sponsored initiatives and eliminate groupthink, defensive avoidance, and other barriers to innovation.

### 2.10.1    Internal

Staff meetings will be held at least once a week, and they will be the principal means of interaction and communication.

Through the knowledge management support of the GSA E-Gov Program Office, asynchronous team communications will be sustained through IBM QuickPlace software that resides on a GSA extranet server.  Discussions, decisions, documents, tasks, and events will be posted to the team's area within the E-Gov QuickPlace.  Synchronous communications will be supported either through the aforementioned weekly face-to-face meetings or by virtual meetings sustained through IBM Sametime that also resides on a GSA extranet server.  On-line awareness, chat, white-boarding or document sharing/collaboration will be performed through Sametime, as required.

### 2.10.2    External

Communication external to the team will follow a similar path as that for decision-making outlined above.  Within the GSA structure, communication will be maintained with the sponsoring service commissioner or the Associate Administrator of the Office of Government-wide Policy through to the Administrator as shown on the left-side in Figure 1 . Decision-Making and Communication Channels diagram.

Communication will incorporate direct consultation with OMB through the portfolio managers, portfolio steering committees, and the Portfolio Management Office on issues requiring broader coordination, legislative changes, etc.

Communication will also be maintained with the President's Management Council,

Federal CIO Council,

Quad Council,

Procurement Executive Council, partners, stakeholders and others vital

to the initiative, with support from the GSA E-Gov Program Management Office.

The following is how the IAE team will address stakeholders to build customer and user understanding and support:

-         Industry Presentations

-         Press Releases

-         Stakeholder meetings

-         Website

-         Standard theme, logo and format to communications

The IAE Communications Plan will provide more detailed communications information.

## 2.11     Knowledge Management

Organizations use information strategically to make sense of their environment and/or a change in that environment, to create new knowledge for innovation, and to make decisions about courses of action. Knowledge management activities enable knowledge for understanding, innovation and decision-making. These are supported by the GSA Program Management Office through team/meeting facilitation groupware support using a document management tool, IBM QuickPlace (http://ftswebteams.gsa.gov/e-gov),Sametime (http://fts-stnet-co.gsa.gov), and a new shared document storage and communication tool, called e-Gov Central (https://www.egovcentral.gov); and a series of quantitative and qualitative research methods cataloging best/smart practices, lessons learned or learning histories, after action reports, and other knowledge management methodologies.

| QuickPlace | Used to support asynchronous team collaboration. Team work spaces within the E-Gov QuickPlace will house discussions, decisions, reports, presentations, spreadsheets, project management plans, tasks, and events posted to the team's calendar. |
| --- | --- |
| Sametime | Used to synchronous, real time interactions. On-line awareness, chat, and web-based meetings and document collaboration are the tools available. |
| e-Gov Central | A new shared document storage and communication tool used by OMB for communication across all initiatives |
| Expert Location | Because the potential of QuickPlace to serve as an expert locator is limited, GSA is pursuing a dedicated solution for expertise location. If it can be implemented while E-Gov initiatives are pursued, expertise location will allow team members to more easily locate individuals with key expertise impacting team efforts. |
| Best/Smart Practices | The GSA knowledge manager will assist teams in assessing, capturing, and cataloging the smartest practices in the field of the initiative. |
| After Action Reviews | The GSA knowledge manager will hold periodic discussions to surface issues within the team after it completes objectives or milestones supporting initiative goals. This will serve to capture learning to enhance continued team efforts and strengthen team cohesion. |
| Lessons Learned / Learning Histories | The GSA knowledge manager will conduct structured and unstructured interviews with team members at the conclusion of the E-Gov project to assess their perspective of the team's efforts, its processes, its success in achieving the stated goals, and suggestions for improvements that future teams can follow. |