DEPARTMENT OF EDUCATION

HSPD-12 Implementation Status Report (March 31, 2009)

| Updated Date: | Number of Employees requiring PIV credentials | Number of Employees requiring a NACI (or at least equivalent) that have not previously undergone a background check | Number of Employees requiring a NACI (or at least equivalent) with background investigation in process | Number of Employees with completed/ adjudicated NACI (or equivalent background investigation) | Total Number of PIV credentials Issued to Employees |
| --- | --- | --- | --- | --- | --- |
| Mar 2009 | 4,031 | 17 | 5 | 4,019 | 4,019 |
| Dec. 2008 | 4,377 | 0 | 0 | 4,377 | 4,377 |

| Updated Date: | Number of Contractors requiring PIV credentials | Number of Contractors requiring NACI (or at least equivalent) that have not previously undergone a background check | Number of Contractors requiring a NACI (or at least equivalent) with background investigation in process | Number of Contractors with completed/ adjudicated NACI (or equivalent background investigation) | Total Number of PIV credentials Issued to Contractors |
| --- | --- | --- | --- | --- | --- |
| Mar 2009 | 274 | 2 | 0 | 272 | 272 |
| Dec. 2008 | 269 | 0 | 0 | 269 | 269 |

| Updated Date: 12/31/2008 | Number of other individuals (e.g. guest researchers) requiring PIV credentials | Number of other individuals (e.g. guest researchers) requiring NACI (or at least equivalent) that have not previously undergone a background check | Number of other individuals requiring a NACI (or at least equivalent) with background investigation in process | Number of other individuals with completed/ adjudicated NACI (or equivalent background investigation) | Total Number of PIV credentials issued to individuals other than employees or contractors (e.g. guest researchers) |
| --- | --- | --- | --- | --- | --- |
| Mar 2009 | 0 | 0 | 0 | 0 | 0 |
| Dec 2008 | 0 | 0 | 0 | 0 | 0 |

| Implementation Plan Summary |
| --- |
| [Planned Date of Full Implementation] |  | Next Major Milestone: ([MM/DD/YYYY] – “brief description of next major milestone”) |
| October 27, 2008 | [Planned Total Number of NACIs to be verified/completed for current employees and contractors by Oct. 27, 2007*] 4,363 Federal 255 contractors Total 4,618 | Milestones 4th Q FY 08: 10/27/08– total 4,618 cards issued 100% 12/31/08 – total of 4,646 (28 new cards since 10/27/08 employees and contractors) |
| March 20, 2009 | The number of employees requiring PIV IDs has decreased due to departures from administration changeover and a reevaluation of the temporary staff positions. 4,019 federal 272 contractors Total 4,291 Departments PIV credentials are integrated with the physical access systems | 3/31/09 – Total of 4,291 (45 new cards since 12/31/08 employees and contractors) 9/26/209 - Integration of PIV credentials with logical access systems |