Bureau of Land Management

#### Lessons Learned

Oregon/Washington Bureau of Land Management

Competitive Sourcing Standard Study

Maintenance Functions

September 24, 2004

TouchstoneGlobal

5335 Wisconsin Avenue NW Suite 440

Washington, D.C. 20015

(202) 274-4760

Under BLM Contract No. GS-10F-0086L

TABLE OF CONTENTS

Executive Summary	3

PRELIMINARY PLANNING	6

Study Budget and Schedule	6

Business Unit Definition	7

Generating Workload Data	7

Communication Plan	7

Relationship between BLM and Contractors	7

Inventory of GFP/GFE	7

PWS DEVELOPMENT	7

PWS Tasks	7

PWS Workload	7

PWS Performance Measures	7

Performance-based Contract	7

MEO DEVELOPMENT	7

Starting Inventory	7

Study Sizing Strategy	7

Management of MEO Design	7

Technical Performance Planning	7

Control of Quality in MEO Operations	7

Transition Planning	7

Costing Issues	7

COST COMPARISON	7

PROCUREMENT PROCESS	7

# Executive Summary

From November 2002 through April 2004, the Oregon/Washington (OR/WA) State Office of the Bureau of Land Management conducted an Office of Management and Budget (OMB) A-76 standard competitive sourcing study of maintenance functions.  The functions included facilities, road, and recreation site maintenance.  This report addresses lessons learned during the study and what those lessons might mean for the design and conduct of future studies.

The OR/WA study is the largest competitive sourcing study conducted within the Department of Interior to-date.  It was also probably the first standard study in Government that followed the revised A-76 Circular.  The size of the study contains some important lessons.  The maintenance organization studied in OR/WA is large, diverse, and dispersed.  The determining factors for a successful study of large organizations and multiple functions are not only whether vendors exist with the capability to perform these functions or whether we can expect to find efficiencies and improve performance of scale across the entire organization.  The determining factors for a successful study lie within the organization itself.  These internal determining factors include:

- Recognizing the existing cultural context around the group or function being studied and the readiness to undertake change,

- Readiness of management structures, policies, and geographical requirements to being integrated along the functional lines required by the PWS,

- Ability of integrated functional planning at the regional scale to replace work planning designed to flexibly respond to multiple demands at the local level,

- Ability of integrated functional planning at the regional scale to deliver similar or better service, and

- Capacity of the organization to meet the challenges of a large reorganization, redesign, and implementation effort.

As this report is being finalized, the OR/WA State Office is actively implementing the Most Efficient Organization (MEO).  BLM’s ability to meet the challenges reflected above will be more evident over the next six-twelve months.

Related to the above discussion is the significance of the business unit identified for study.   OR/WA identified its business unit with the assistance of a support contractor, who emphasized the need to define the business unit as everything required to perform the activity being studied.  Unfortunately, BLM learned that defining appropriate business units sometimes can be exceedingly difficult, because there can be more than one option in drawing the line between the MEO and the residual governmental organization. And each option will produce its own set of issues.  For this study, especially, issues such as geographic differences and complexities inherent in the manner in which maintenance activities are performed within BLM introduced problems that were not wholly predictable and that are still being managed as OR/WA implements the MEO. For example, in the MEO, OR/WA has integrated its maintenance activities along functional lines rather than geographic areas.  In some geographic areas there is a greater percent of maintenance work integrated with other activities, and thus a higher percent of part-time FTE dedicated to maintenance. In these areas, the MEO and the residual governmental organization will be especially challenged to perform the work efficiently.

Another set of lessons is associated with monitoring performance-based organizations.  If the study results in an in-house win, the government executes a Letter of Obligation (LOO).  A private sector win results in a contract award.  Both the LOO and the contract are performance-based documents. Performance-based contracts and LOOs focus on performance results, and require measurable workload data and performance standards.  BLM found that quantifiable workload data at the level required in a competitive sourcing study are often not available.  In the preliminary planning phase, it is essential to develop a system for tracking workload that, at a minimum, identifies tasks performed, task frequency, and hours expended per task.  An on-going tracking system will be required to monitor performance and control costs if an LOO is put in place.

Competitive sourcing studies are conducted by workforce teams, guided by study support contractors, if possible.  The makeup of these teams influences how readily they can accomplish their tasks. For example, the MEO Team is usually composed of persons familiar with and assigned to the organization under study. The MEO team can tend to resist the notion that serious organizational change is needed or even desired. Strong facilitation is needed to ensure effectiveness of the MEO Team and to develop a commitment to success. The MEO Team needs to continually collaborate with affected managers, to ensure that all MEO design features are vetted as much and as often as necessary with key managers

A competitive sourcing standard study has a significant impact on the workforce, no matter what its outcome. Attention to continuous communication throughout the study is critical.  Unfortunately, once a performance decision has been made, there is a period of at least 30 days before specifics on the decision’s impact can be shared.  This time period allows for challenges to the decision.   In the OR/WA study, there was an additional delay due to the fact that the Voluntary Separation Incentive Pay (VSIP) and Voluntary Early Retirement (VERA) authorities had not been approved by the Office of Personnel Management (OPM).  The delay in being able to provide VSIP/VERA offers to impacted employees lengthened the time of anxiety for BLM employees.  The Department of the Interior is working with the Office of Management and Budget and OPM to secure provisional VSIP/VERA authority for future competitive sourcing studies, which would provide a bit more certainty to BLM employees.

The remainder of this report covers what has been learned in five areas – Preliminary Planning, Performance Work Statement (PWS) Development, MEO Development, Procurement Process and Cost Comparison.  Several practical findings that relate to the above discussion are summarized below and discussed in more detail in the report.

- The time allowed for this standard study was not adequate; a problem which was aggravated by the time elapsed between the announcement of the study and its initiation.  More time was needed to meet with managers and workers on PWS tasks. Workshops were not an effective means to gather information/data.

- Early involvement of experts on the A-76 process can save time and alleviate problems in design of the PWS.  A costing specialist needs to be available to the team working on the MEO, to assist in accurately capturing costs without overstating them.  Early and periodic involvement of procurement expertise assists in coping with the complicated and unique nature of a large A-76 study.

- Identification of lead individuals to evaluate progress, ensure reporting of results, monitor data quality, and identify trends or concerns is necessary.

- Development of a business unit needs to include the necessary components of the function, including management and supervision.

- BLM systems for collecting and auditing information on workload generally do not fit the A-76 process.  Where tracking systems for individual job or task orders for employees are lacking, asking employees to record tasks over time could substitute.

- Definitive sideboards and early/periodic management review of workload data submitted are needed quality control steps to promote consistency.  The inclusion of a “20% rule” (if you spend less than 20% of your time, don’t include it) meant some work and some tasks were not in the PWS.

- The A-76 process requires changes in how BLM thinks about relationships with contractors (e.g. use of equipment, interface with the public, scheduling work).

- Inventory of Government furnished property to be assigned to, or shared with, the contractor could be developed in advance of the study process.

- Unresolved issues over the management of some functions or tasks (e.g. supervision of volunteers, inclusion of currently contracted work) lead to frequent revisions to the PWS.

- Development of the Technical Performance Plan should begin early in MEO design and development.

- The Quality Control Plan (used to monitor MEO effectiveness) needs to be a practical tool with a limited set of measures that are well understood.

- Transition planning should address important details like equipment inventory, facility handoff and training, while avoiding excessive detail on minor requirements.

- In an interagency setting, regular coordination and communication across agency lines is essential.  Even with a carefully implemented communication plan, there will be continued concern and need for additional communication

# PRELIMINARY PLANNING

The original approach for the FY03 Oregon/Washington competitive sourcing program was to conduct a series of express and streamlined studies for the recreation site and facilities maintenance functions (primarily based on a District breakdown) and conduct a single statewide standard study for the road maintenance function.  However, following an on-site review of each district plus discussions with senior functional and procurement managers, it was decided a more logical approach, with a potential for increased economic benefits, was to combine recreation site, facilities, and road maintenance into a single statewide (Oregon and Washington) standard study.  The following observations relate to the early planning effort for the study.

### Study Budget and Schedule

The study budget and schedule didn’t anticipate the vast and complex nature of the organization and the work performed.  The diversity of the effort (in terms of both geography and work performed) in Oregon and Washington made it very difficult to generate a common approach to maintenance work and prevented a “one-size-fits-all” approach to PWS and MEO development.  As a result, the effort expended by both the support Contractor and the Government was more than initially anticipated and planned for in the Project Management Plan.

Lesson Learned:  The initial study schedule was forced to fit the time available.  Without preliminary planning, this was an unrealistic timeframe for completing a standard study.  Too much time elapsed between the formal announcement of the study and the beginning of the effort to develop the required study documentation.

- Meeting with BLM Personnel

More time was needed to meet with the workers and managers responsible for the accomplishing the PWS tasks.  The original plan was to minimize travel costs by conducting short visits to each District and then holding a few centralized workshops to develop both the PWS and the MEO.  The District visits weren’t long enough to complete the data capture process and we had to spend considerable time in the workshops gathering missing data from each District.  Workshops are not effective means for gathering individual District information because they are meant for group participation, consensus, and compromise.  Thus, we wasted a lot of everyone’s time during the workshops and were forced to conduct more workshops than planned to complete both the PWS and MEO.

Lesson Learned:  The process requires that we plan for and utilize realistic time frames to capture workload data at the local sites.

- Understanding the impact of early decisions and guidance provided for the study.

The lack of understanding of how certain decisions would be impacted by the A-76 process caused some initial decisions to be re-evaluated during the PWS development process.  These included:

- 20% task rule.

- Use of volunteers.

- Decision on whether to include Government Furnished Property (GFP) as part of the PWS.

- Use of current contracts.

Lesson Learned:  Key policy decisions need to be discussed and evaluated in the Preliminary Planning phase of the A-76 process.  Earlier involvement of a support contractor and other A-76 experts should eliminate the need for the PWS Team to make changes to the PWS, PWS workload, and re-examine previously done work.

### Business Unit Definition

A business unit should include everything needed to accomplish the function under study.   Given the geographic differences and the complexities inherent in the way maintenance is performed in BLM, it was difficult to decide how best to define the business unit to be studied.  Also, much of the management, supervision, and those functions that accounted for less than 20% of a person’s time were excluded from the study.  As a result, a rather large residual organization had to be retained by the Government, which will likely reduce the efficiency of the overall organization.

Lesson Learned:  Development of a business unit must incorporate an entire entity.  A business unit should function independently and thus include management and supervision along with the functional workforce.  In the future, BLM must define everything required to perform the function being studied.

- Use of USFS personnel

The use of USFS personnel and their tasks caused some problems; mainly in the cases where USFS personnel were not informed their tasks were included in the study scope.

Lesson Learned: Better coordination between agencies is needed to ensure all affected employees are aware of their status under the A-76 rules.

### Generating Workload Data

We didn’t establish a basis for defining and collecting workload data before we started the PWS effort.  Where the same function is performed in multiple Districts, a definition of what constitutes measurable workload and a standardized method of collecting it would have added consistency to the PWS.  Program Element (PE) codes were used early in the process to determine the historical scope of the work required in terms of staff hours and FTEs.  However, PE codes were not designed for this purpose and they did not provide the level of detail needed.  It was also determined that the accuracy of PE code reporting is questionable due to differing guidance within the workforce on how and when to report time against a PE code.

Lesson Learned:  Since BLM does not have a work management system that tracks maintenance job orders, it would have made sense to ask the maintenance workers to manually keep track of what they did (type of work and how long it takes) for a period of time leading up to the study.  This would have provided a stronger basis for documenting the amount of work to be accomplished.

### Communication Plan

The communications plan prepared by ORSO provided an excellent approach to keeping employees, internal groups, and external groups informed of events in the competitive sourcing process.  The plan, which was integrated into the Project Management Plan, assigned responsibilities for continuous communications with unions, human resource managers, and other stakeholders.  The competitive sourcing team did a good job of coordinating information and providing information to stakeholders.

### Relationship between BLM and Contractors

The A-76 process requires a change in the way an organization like BLM views contractor support.  This culture change was most noticeable in areas such as contractors using Government equipment, contractors interfacing with the public, contractors setting their own daily work schedule, and using a performance rather than process orientation as the basis for defining what a contractor is to accomplish.

### Inventory of GFP/GFE

GFP has to be inventoried, whether or not it is offered in the PWS.  If it is offered, it has to appear as a Technical Exhibit in the PWS.  If it is not offered, it still needs to be inventoried so the Agency Tender Team can know how much of what type of equipment and supplies to include in the Tender.

Lesson Learned:  Inventory GFP during the Preliminary Planning phase when time is not an issue.  This includes identifying GFP that will remain with the residual governmental organization and any equipment that may have to be shared between the residual governmental organization and the service provider.

# PWS DEVELOPMENT

Creating a Performance Work Statement (PWS) can be a challenging and complex process.   However, the basic requirements of any PWS are fairly simple:

- Identification of the tasks to be performed.

- Identification of task workload (the frequency each task is performed).

- Identification of the performance measures against which task completion is evaluated.

- Identification of guidance and/or regulations that provide additional direction in performing the tasks.

The first three items are vital in the development of a performance-based work statement since they quantify “what” needs to be performed, as opposed to “how” it should be done.  The last item provides additional regulatory or agency guidance that may be needed to fully understand the scope of the task and task requirements.  As such, the last item is not required for every task, but should be provided when necessary.

While the PWS Team for Roads, Facilities, and Recreation Site Maintenance did an excellent job in preparing a performance-based document, there were several areas that could be improved prior to any future competitive sourcing studies.  These are addressed in the sections below.

### PWS Tasks

The absolute first step in developing any work statement is to identify the tasks to be performed. The biggest challenge that had to be overcome was the fact there were 10 separate districts whose task requirements varied greatly (e.g., fighting range fires in the east forest fires in the west; or maintaining water guzzlers in the east vs. supporting logging operations in the west).  However, this was mitigated by the use of Subject Matter Experts (SME) from each district.  The experience and “corporate memory” of these SMEs was invaluable in identifying common tasks each district performed as well as tasks that were specific to their district.

Other issues:

- None of the districts had a system (automated or manual) for tracking tasks, task completion, or task frequency.

- Most districts did not have written SOPs or other documents to assist in task identification.

- There was little task standardization, due to the varied type of equipment used in the districts.  This meant the PWS had to identify tasks common to all districts as well as exceptions for specific districts.

- The type of equipment to be maintained varied widely between districts.  This meant the task frequency also varied widely (see Paragraph 2, PWS Workload, below).

Lesson Learned:  Implement a system for identifying and tracking tasks.  Many organizations outside of BLM use an automated management information system to provide historical information on tasks and task workload.  These systems can usually provide other useful management information, such as funds, supplies and materials, and hours expended in accomplishing each task.  In addition, automated systems can provide data to differentiate routine maintenance from repair requirements, since these actions typically have different resource requirements.  The use of an automated system is a valuable asset, both in the preliminary planning phase of an A-76 study as well as during the actual development of the PWS.  At a minimum, in the preliminary planning phase, develop a spreadsheet-based system for each district that identifies tasks performed, task frequency, and hours expended per task.

### PWS Workload

After a PWS task is identified, the next step is to identify how often the task is performed.  The main challenge in this step was that the districts did not have a system for tracking tasks or task frequency.  Once again, the SMEs were crucial in providing technical estimates of workload.

Other issues:

- There was no system in place for collecting and auditing workload.  This meant that there was no independent means for establishing historical workload.  The significant amount of special project work and fire assignments made the collection of workload data more difficult.

- The use of volunteer labor was not resolved prior to writing the PWS.  This meant PWS workload had to be repeatedly revised to remove volunteer workload and supervision of volunteer labor.

- The inclusion of workload for PWS tasks currently being performed by contractors.  This issue was not resolved until the PWS was almost complete.  The late decision to allow each district to decide which contracts to continue and which to include in the PWS meant last minute changes to PWS workload.

- The “20% task rule” excluded PWS work performed by personnel less than 20% of their productive time.  This affected the PWS since not all workload for PWS tasks would be accounted for in the PWS.

- There was little management engagement at the local and state level for oversight of the workload information and data.   Despite two field visits and e-mail verifications of the workload data, it was not until the MEO reviewed the workload data that errors, omissions, and padding became evident.

- The PWS workload generation did not have definitive sideboards.  Workload levels appeared to be reported as “should do” instead of meeting a realistic level based on past and future budget scenarios.

- Some Districts purposely omitted workload that should have been included in the PWS.

Lesson Learned:  Implement a system for tracking workload.  This can be part of the same system recommended for in Paragraph 1, PWS Tasks, above.  Overestimating or underestimating the amount of workload has a direct impact on determining the number of personnel actually required to perform the PWS tasks and must be as accurate as possible.  A budgeting level should be used in guiding the workload estimates.

The system for tracking workload should also track the time required to perform the task so that cycle times can be established for each task.  While this is not a PWS requirement, it would be very helpful to the personnel developing the Agency Tender.

All employees performing PWS tasks (no matter how small) report the workload so that it can be included in the PWS.  The emphasis should be on the PWS tasks being performed, not the position performing them.

Finally, an independent review of the workload data should be performed by a management official or team knowledgeable in the activity being studied at draft and final stage to assure workload integrity.

### PWS Performance Measures

The main difficulty with developing performance evaluation measures was that there were no consistent performance measures across the districts, or even within districts.  This situation is not unique to the BLM study – most Government agencies are not used to formally evaluating task performance or enforcing a quality control program.  However, quantifiable performance measures are a critical part of any performance-based work statement, for obvious reasons.  Again, the SMEs were a great resource in developing PWS performance measures that they felt were realistic and achievable.

The use of decentralized execution is a real advantage across all the districts.  This, coupled with the customer-oriented attitude of most of the employees we met, meant a lot of good things were getting accomplished in the districts.  However, it appeared that most work was accomplished based on “knowing what needs to be done” with little emphasis placed on formally evaluating quality.  This lack of a feedback system could pose problems in monitoring and achieving PWS task standards.

Lesson Learned:  Developing a Quality Control Plan is relatively easy.  The hard part is actually implementing the plan and monitoring the quality metrics to ensure PWS standards are being met.  This is where many agencies have difficulties.

Evaluating performance requires a two-step process.  First, a system must be developed for evaluating task performance per PWS standards.  This includes designating who will evaluate performance and developing a process for reporting the results.  Second, an overall quality improvement process must be developed to monitor overall task performance against PWS standards.  This includes designating an individual(s) who will identify trends as well as investigate the causes for sub-par performance and recommend corrective measures.  The bottom line is that a qualified individual must be responsible for monitoring compliance with PWS standards.

### Performance-based Contract

The inability to specifically tie down workload and standards made it extremely difficult to create a performance-based contract.  When standards were not available, “as directed by the authorized representative” was placed in the PWS.   Not until the Contracting Officers review, was it determined that the PWS was written as a personal services contract and was unacceptable to the Government.  A change in Contracting Officers during the review and acceptance phase further complicated and delayed the PWS.

Lesson Learned: Full understanding between the contractor providing support and Contracting Officer on what constitutes a performance-based contract would have prevented the delay and re-write of the PWS.

# MEO DEVELOPMENT

### Starting Inventory

The solicitation, PWS, and A-76 rules require that a valid response (industry bid or Agency Tender) must include the cost of all labor associated with the function under study.  The MEO Team began their analysis with an inventory of positions that did not include everyone who was impacted by the maintenance functions being studied.  Management, supervisory, and critical support staff were excluded from the starting inventory given to the MEO team.  As a result, considerable extra time and effort was spent identifying the deficiencies and correcting the inventory.  An accurate starting inventory is important because it is the basis for the public announcement of what is to be studied; it is the basis for determining any savings resulting from the study; and personnel impacted by the study (included in the inventory) need to be notified.

Lesson Learned:  A complete business unit for a starting inventory is extremely critical.  Adhere to OMB A-76 guidance to define a complete business unit of positions and functions for study in order to ensure optimal MEO results and for an efficient MEO development process. The concept of a well-defined business unit as the basis for the study is also addressed in paragraph 1.3.  This should take place during preliminary planning in order to avoid problems like those encountered by the MEO Team.

### Study Sizing Strategy

If the organization being studied is too large, too diverse, or too dispersed, MEO designers are faced with extremely difficult and possibly intractable MEO design decisions.  The determining factors for a successful study of large organizations and multiple functions are not whether vendors exist with the capability and reach to perform functions or whether it makes sense to expect to find efficiencies of scale across the entire organization.  The determining factors for a successful study lie within the organization itself.  These internal determining factors include:

- Can the existing organization culture adjust to thinking of itself as a more integrated entity?

- Can the diversity of the functional and management structures as well as policies and geographical differences be integrated as required by the PWS?

- Can the lack of integrated and adaptive planning be compensated for by automation or by imposing a planning integration?

- Can the organization rise to the challenge of a massive reorganization, redesign, and implementation effort?

Lesson Learned:  Studies should be sized to recognize cultural differences across the organization, diversity in operational practices, capability to achieve the economies of scale that are desired and experience with and commitment to change (automation adoption experience, understanding and skill in using procedural and operational change mechanisms, ability and willingness of management to encourage, motivate, and promote change across the organization).  These considerations must be weighed for the study size being recommended.  Based on the reasons mentioned above, the recommendation of the support contractor to consolidate the streamlined, express, and standard studies originally envisioned into a single standard study may not have been the best approach.

### Management of MEO Design

MEO design must be managed at each step to ensure timely and successful development.  This management requires facilitation, collaboration, and continuous communication.  Strong facilitation of the MEO Team by the support contractor is necessary.  Mere support contractor collaboration and willingness to assist is not adequate.  MEO Teams are composed of persons usually familiar with and assigned to the organization under study.  They tend to reflect the agendas and desires of their managers for study outcomes and can tend to remain in denial of the notion that serious organizational change is needed or even desired. Strong facilitation is needed to ensure early buy-in by the MEO Team and development of a commitment to success.  Much collaboration is usually needed across the organization but especially with managers who can influence the level of buy-in and commitment of the MEO Team members.  Communications often break down with other key stakeholders including union representatives, human resource managers, and others.

Lesson Leaned:  Begin every study with strong facilitation aimed at early buy-in and commitment to success by the MEO Team.  Collaborate often with affected managers.  Generally, this should be in the format of one-to-one meetings by MEO Team Leads with all managers affected as often as required.  No MEO design features should be taken for granted but should be vetted as much and as often as necessary with key managers.  Feedback should be integrated by the support contractor and indexed back to final MEO design features.  These concepts must then be documented in the appropriate plan (Technical Performance Plan, Quality Control Plan, and Transition Plan).

MEO Team membership was heavily weighted toward subject matter experts.  More management officials would have been helpful when considering the organizational impacts.  The resulting MEO organization bore a strong resemblance to the originally existing organization.  A different balance on the team may have resulted in a more innovative MEO.

### Technical Performance Planning

The TPP is the operational tool to get the MEO into action.  The tendency is to delay development of the Technical Performance Plan (TPP) until it is too late to produce a fully viable operational tool.  If it is not begun early enough in the study, the MEO Team will let the support contractor develop the TPP without their full involvement in the TPP development process.  The TPP is the single most critical document for assuring a successful MEO.

Lesson Learned:  The TPP planning effort should begin early in the MEO design and development stages.  Linkages between design features and future implementation mechanisms often surface early in the design phase.  The TPP must provide specific steps to achieve organizational synchronization in all aspects of the new MEO (structure, procedures operational policy, and planning).

### Control of Quality in MEO Operations

The Quality Control Plan (QCP) is the plan that will allow the MEO manager to assess how well the MEO is measuring up to PWS and internal MEO performance standards and how to take action if a function is not meeting the standard.   In preparing the QCP, the tendency was to provide too much detail on how to measure every PWS task.  This view of the QCP will assure its failure as a quality control device due to the sheer volume of work to be performed.  Instead, the QCP must address how quality of performance is to be measured and specify only those PWS areas of critical importance.  Also, during development of the QCP, there was a desire to use it as a quality assurance tool and view it from the Government’s perspective as an inspection document.  .

Lessons Learned:  The QCP must be understood by all stakeholders to be the tool of the MEO manager, not the Residual Organization or the Government.  The QCP must be developed to sample in a uniform and effective way PWS tasks without becoming an impossible measure of everything at once.

### Transition Planning

The Transition Plan (TP) must address key features and major timelines while leaving the responsibility for detailed transition planning to the appropriate Government activity (HR, Contracting, etc,).  The tendency is to forget important transition planning actions while being overly specific about minor requirements.  This results in the TP getting messy with details without being complete.

Lesson Learned:  At a minimum the TP should address the following:

- Equipment inventory and equipment handoff and control.

- Facility handoff, key control, and special security issues.

- Training or new qualifications specified by the MEO

- Planning for recruitment actions and other staffing issues

- Special one-time costs.

- Staff orientation and assembly.

- Automation and system innovation setup, training, and implementation.

### Costing Issues

The diverse and complex nature of the functions being studied and the required personnel and equipment in this study made it very difficult to develop accurate costs.  It was more time-consuming than expected to achieve a full accounting for all MEO costs and enter them into COMPARE.    Staffing plans across two agencies (BLM and USFS) and over 10 Districts are difficult to stabilize and thus require frequent changes.  This leads to costing questions, ambiguities, and unnecessary work.  The support contractor did not fully appreciate this and take it into consideration when preparing the project schedule and budget.

Lesson Learned:  A costing specialist needs to be available to consult with the MEO Team about identification, capture, and proper documentation of all costs.  It is important for costs to be captured, but just as important, that costs not be overstated.  Doing both takes skill.  Final staffing needs to be locked in before costing begins; not to do so results in multiple changes as grades, titles, and numbers are adjusted on the fly.  Costing associated with special programs like the Working Capital Fund must be analyzed as completely as possible since these integrated programs tend to hide real costs.

# COST COMPARISON

Due to the agency’s lack of accurate historical accomplishment and costing data performing a cost comparison in strict accordance with the Circular was problematic.   The total value of what the various studied functions cost the agency in past years was not accurately ascertainable since myriad fund codes were used and overhead and other program work was at times intermingled and adjusted to meet various needs.

Cost savings could only be demonstrated by analyzing differences in personnel and equipment costs between the in-place organization at the time of the studies initiation and the organization proposed by the MEO.  Equipment costs were also reduced due to downward changes in the Working Capital Fund rate charged the agency.

Special projects which would be initiated by the agency on an indefinite-delivery-indefinite-quantity basis were better subject to analysis since historical pricing was available to establish fully loaded equipment rates to be used as a starting point for future task order pricing.

Cost comparison between the private sector and MEO was not performed as no private sector offers were received.

# PROCUREMENT PROCESS

The procurement process was complicated by the unique nature of such a large, full, A-76 study and the fact that no in-house experience existed.  The time and energy that went into studying and understanding the process was felt, by some, to be too extensive to be effectively performed by an existing organization as an additional assigned duty.

Lesson Learned:  The use of knowledgeable procurement specialists would be a valuable asset, especially in the early planning stages, to provide timely planning input and guidance to better assure good up front decision making and the timely delivery of products like the PWS.

The implementation of Revisions to the A-76 Circular complicated the process by changing such things as rights of employees and GAO’s involvement in the handling of protests.  This created uncertainty and confusion in interpreting the regulations or deciding which elements of a regulation to follow.

Some activities such as proposal evaluation and negotiation which are regular activities carried out by the procurement function proceeded in a timely and efficient manner.