The ARS Project Peer Review Process

Procedures for NP and Area Program Analysts

March 2005

Developed from Program Analyst Workshop

(rev. 2/06)

Table of Contents

Page

Acronyms – Abbreviations	3

The Process

Stage 1 – Identification of Projects to be Reviewed	4

Stage 2 – Prospectus and COI Development	9

Stage 3 – Project Plan Development	11

Stage 4 – Peer Review	12

Stage 5 – Revision and Response – PostPlan	13

Stage 5a – Revision and Response – ReReview	14

Stage 5b – Revision and Response – Postpone	17

Stage 5c – Revision and Response – Terminate/Redirect	18

Stage 5d – Revision and Response – Disapproved Postpone or

Terminate/Redirect Request	19

Stage 6 – Implementation	20

Formats

Tracking Documents and Document Transfer	21

Conflict of Interest	23

Prospectus	24

Project Plan	27

Templates

COI Template	33

Signature Page Templates	34

Request for Postponement Memo Templates	39

Request for Termination/Redirection Memo Template	42

Concurrence Template	43

Review Schedule Template	44

Milestone Table Template	45

Examples

Milestone Table	46

PDRAM	48

Additional Information

ARS’s Categories for Professional Scientific Positions	52

Hypothesis-Driven vs. Non-Hypothesis Driven Research	53

Requirements for Letters of Collaboration	55

Scanning and Editing Adobe File Tips	56

Bulletin on Requesting Postponements	57

Useful Websites	61

Acronyms – Abbreviations

CD/LD/ID – Center Director/Laboratory Director/Institute Director

COI – Conflicts of Interest

NP – National Program

NPS – National Program Staff

NPT – National Program Team

PA – Program Analyst

PDRAM – Program Direction and Resource Allocation Memo

PI/RL – Principal Investigator/Research Leader

OSQR – Office of Scientific Quality Review

SCA – Specific Cooperative Agreement

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Identify projects to be peer reviewed (ad-hoc and Panel) and assign to panels | NPS |  | Using Peer Review Tracking system and OSQR schedule, PAs generate list of projects to be reviewed. |  |  |  |
|  |  |  | NPLs review; request AD concurrence on projects to be reviewed. |  |  |  |
|  |  |  |  | Initial concurrence; coordinate any postpone actions from PI/RL. |  |  |
|  |  |  | Develop final lists, identify proposed number of panels needed, assign projects to proposed panels; forward to OSQR for approval, copy Area. |  |  | NPS |
|  |  |  |  | Request PI to begin work on COI. |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Program Planning Meeting or Teleconference | NPS |  | Announce Planning and Coordination Workshop (or teleconference) to: Review NP mission, components, action plan problem areas, and relationship of NP to other national programs. Review progress made by each project; identify gaps and needs in research; identify cooperators and collaborators; review projects to avoid duplication of efforts. Request PIs to prepare project planning documentation. Reminder on COI development. CC Area on invitation memo. |  |  |  |
|  |  |  |  | Instruct PI/RL on routing of project planning document. Request COI to be submitted to Area at same time as project planning document submitted. |  |  |
|  |  |  |  |  | Prepare project planning document prior to workshop; forward to NPS, through or cc Area, as directed. |  |
| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| Program Planning Meeting or Teleconference (continued) |  |  |  |  | Submit initial COI lists to Area |  |
|  |  |  | Host Workshop or Teleconference. |  | Participate in Workshop or Teleconference |  |
|  |  |  | Provide OSQR with list of potential panel chairs. Submit final panel assignment of projects for OSQR approval, copy Areas. |  |  |  |
|  |  | Notify NPS of approved panel assignment of projects, copy Areas. Update website. Begin panel selection and scheduling process |  |  |  |  |
|  |  |  |  | Within 2 weeks of receipt of approved panel assignments, submit initial COI lists to OSQR, copy NPS |  | Area |
|  |  | Use COI to develop list of potential panelists |  |  |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Develop Schedule |  | Provide dates due to OSQR. |  |  |  |  |
|  |  |  | Develop schedule(s) of dates due to NPS and OSQR; forward to Areas with PDRAMs. |  |  |  |
|  |  |  |  | Add Area due dates; provide to PI/RL with PDRAMs. |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| PDRAM | NPS |  | Develop and issue PDRAMs to Areas, cc OSQR, with schedule and panel assignments. If project objectives are revised after PDRAM is issued, a new PDRAM is required. |  |  | NPS |
|  |  |  |  | Review PDRAM; implemention memo to PI/RL, with schedule |  | Area |
|  |  |  |  |  | Begin developing prospectus. |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Final COI List | Area |  |  | Request updated COI list from PI, due with prospectus |  |  |
|  |  |  |  |  | Forward updated COI lists to Area |  |
|  |  |  |  | Forward updated COI lists to OSQR, copy NPS |  | Area |
|  |  | Use updated COI to develop/confirm list of potential panelists |  |  |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Prospectus Approval | NPS |  |  |  | Upon receipt of PDRAM, develop prospectus; obtain local approvals; forward to Area. If objectives are revised after PDRAM is issued, a new PDRAM is required. |  |
|  |  |  |  | Review; request revision as necessary, approve; forward to NPS |  | Area |
|  |  |  | Review; request revision as necessary, approve; forward to OSQR, copy Area |  |  | NPS |
|  |  |  |  | Copy to PI/RL; request project plan development |  |  |
|  |  |  |  |  | Begin developing project plan |  |
|  |  | Provide prospectus to Panel Chair for selection of panel team |  |  |  |  |
|  |  |  | NPS Panel Chair briefing |  |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Project Plan Approval | Area |  |  |  | Develop project plan; obtain local approvals; forward to Area |  |
|  |  |  |  | Review, request revision as necessary, approve; forward to OSQR, copy NPS and PI/RL |  | Area |
|  |  | Provide project plans to panelists |  |  |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Panel Review Schedule | OSQR | Notify NPS and Area of panel dates |  |  |  |  |
| Panel Briefing | OSQR | Arrange for briefing of panel by OSQR and NP Team | Participate in panel briefing |  |  |  |
| Panel Meeting | OSQR | OSQR does not participate in the panel meeting; OSQR is only available to assist as necessary. |  |  |  |  |
| Report Review Results | OSQR | Establish action due dates; send project review results to Area, copy NPS |  |  |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Report Review Results | Area |  |  | Review results; forward to PI/RL, with Area due date. If significant change to objectives required, request new PDRAM from NPS. |  | Area |
| Revision and Response | Area |  |  |  | Revise for PostPlan as necessary, exchange signature page, and prepare responses; obtain local approvals; forward to Area |  |
|  |  |  |  | Review, request revision as necessary, approve; forward to OSQR, copy NPS and PI/RL |  | Area |
|  |  | Review; request revision if necessary; approve |  |  |  |  |
|  |  | Once projects are certified, provide information copies of PostPlans and Responses to Panel. |  |  |  |  |
| Certification | OSQR | Provide Certification to Area, copy NPS |  |  |  |  |
|  |  |  |  | Forward Certification to PI/RL, with instructions for implementation of new project. |  | Area |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Report Review Results | Area |  |  | Review results; forward to PI/RL for discussion of options with NPS, PI/RL, Area. If significant change to objectives required, request new PDRAM from NPS. Provide guidance and due dates. |  | Area |
|  |  |  |  | Notify OSQR that project will be rereviewed. |  |  |
| Revision and Response | Area |  |  |  | Revise for ReReview as necessary, exchange signature page, and prepare responses; obtain local approvals; forward to Area |  |
|  |  |  |  | Review, request revision as necessary, approve; forward to OSQR, copy NPS and PI/RL |  | Area |
|  |  | Review; request revision if necessary |  |  |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| ReReview | OSQR | Provide ReReview copies to selected Panel members for second review |  |  |  |  |
|  |  | Obtain completed ReReviews and consolidate into one Recommendation form |  |  |  |  |
| Report Review Results |  | Establish action due dates; send project review result to Area, copy NPS |  |  |  |  |
|  |  |  |  | Review results; forward to PI/RL, with Area due date. If significant change to objectives required, request new PDRAM from NPS. Plans can be reviewed only twice; if NF or Major score, see Stage 5b or 5c. |  | Area |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Revision and Response | Area |  |  |  | Revise for PostPlan as necessary, exchange signature page, and prepare responses; obtain local approvals; forward to Area |  |
|  |  |  |  | Review, request revision as necessary, approve; forward to OSQR, copy NPS and PI/RL |  | Area |
|  |  | Review, request revision if necessary; approve |  |  |  |  |
|  |  | Once projects are certified, provide information copies of PostPlans and Responses to Panel. |  |  |  |  |
| Certification | OSQR | Provide Certification to Area, copy NPS |  |  |  |  |
|  |  |  |  | Forward Certification to PI/RL, with instructions for implementation of new project. |  | Area |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Report Review Results | Area |  |  | Review results; forward to PI/RL for discussion of options with NPS, PI/RL, Area. |  |  |
|  |  |  |  | Coordinate postpone request from PI/RL. |  | Area note intention |
|  |  |  |  | Notify OSQR of intention to postpone. |  |  |
| Rescheduling | OSQR | Upon approval of postpone request, schedule project into ad hoc session; provide schedule information to NPS and Area |  |  |  | NPS |
|  |  |  |  | Provide schedule information to PI/RL |  |  |
| PDRAM | NPS |  | At startup of ad hoc session, develop and issue PDRAM to Area, cc OSQR. If project objectives are revised after PDRAM is issued, a new PDRAM is required. |  |  | NPS |
|  |  |  |  | Review PDRAM; implementation memo to PI/RL. |  | Area |
|  |  |  |  |  | Begin developing prospectus |  |
| Continue with Stage 2 |  |  |  |  |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Report Review Results | Area |  |  | Review results; forward to PI/RL for discussion of options with NPS, PI/RL, Area. |  |  |
|  |  |  |  | Initiate memo requesting termination/redirection |  | Area note intention |
|  |  |  |  | Notify OSQR of intent to terminate/redirect |  |  |
| Redirection | NPS |  | Upon approval of termination/redirection, develop and issue PDRAM to Area, copy OSQR, to redirect resources, and if necessary to request scheduling of ad hoc sessions for resulting projects, |  |  | NPS to show disposition of project |
|  |  |  |  | Review PDRAM; implementation memo to PI/RL |  |  |
|  |  |  |  |  | Initiate necessary ARIS actions required by PDRAM |  |
|  |  | Per PDRAM, schedule project(s) into ad hoc session(s) as necessary; provide schedule information to NPS and Area |  |  |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Report Review Results | Area |  |  | Review results; forward to PI/RL for discussion of options with NPS, PI/RL, Area. |  |  |
|  |  |  |  | Coordinate postpone or terminate/redirect request from PI/RL |  | Area notes intention |
|  |  |  |  | Notify OSQR of intention to request postpone or terminate/redirect; cc NPS |  |  |
| Recovery and schedule adjustment | Area |  |  | Upon notification of disapproval of postpone or terminate/redirect request, verify 2-week schedule adjustment with OSQR. If significant change to objectives required, request new PDRAM from NPS. Notify PI/RL to begin revision process with adjusted schedule. |  | Area |
| Continue with Stage 5a |  |  |  |  |  |  |

| Step | Lead Office | OSQR Role | NPS Role | Area Role | PI/RL Role | ARIS Tracking |
| --- | --- | --- | --- | --- | --- | --- |
| Implementation of New Project | Area |  |  |  | Initiate ARIS action to establish new 416/417 based on information in certified project plan; review; obtain local approvals; approve to Area |  |
|  |  |  |  | Review to assure information reflects project plan, termination date and coding are appropriate; approve to NPS |  | Area |
|  |  |  | Review to assure information reflects project plan, appropriate termination date. Review coding and add NPS-entered codes as necessary. Expire old project when funds have been transferred. |  |  | NPS - new project info |
| Reports | OSQR | Provide NPS and Area with copies of panel summary report for session. |  |  |  |  |

Tracking Documents

Naming files:

NPS PDRAM: NP# Lead Scientist Project # PDRAM

303 Oscar 1234-56789-000-00D PDRAM

Prospectus: NP# Lead Scientist Project # P

303 Oscar 1234-56789-000-00D P

Conflicts of Interest List: NP# Lead Scientist Project # COI

303 Oscar 1234-56789-000-00D COI

Project PrePlan: NP# Lead Scientist Project # PrePlan

303 Oscar 1234-56789-000-00D PrePlan

Project PrePlan Appendix:  NP # Lead Scientist Project # PrePlan-App

303 Oscar 1234-56789-000-00D PrePlan-App

Project PostPlan: NP# Lead Scientist Project # PostPlan

303 Oscar 1234-56789-000-00D PostPlan

Project PostPlan Appendix:  NP # Lead Scientist Project # PostPlan-App

303 Oscar 1234-56789-000-00D PostPlan-App

Project Re-Review Plan:  NP# Lead Scientist Project # RRPlan

303 Oscar 1234-56789-000-00D RRPlan

Project Re-Review Plan Appendix:  NP # Lead Scientist Project # RRPlan-App

303 Oscar 1234-567879-000-00D RRPlan-App

ARS Response: NP# Lead Scientist Project # Response

303 Oscar 1234-56789-000-00D Response

Certification:  NP# Lead Scientist Project # Certification

303 Oscar 1234-56789-000-00D Certification

Note: Use complete project number in file names.

When the panel recommendations form is completed with the ARS responses, replace the words “Panel Recommendations” with “Response”.  Example: 303 Oscar 1234-56789-000-00D PanelRecommendations with 303 Oscar 1234-56789-000-00D Response.

If the scientist updates the COI, then follow the file name as above but insert the current date.  Example:  303 Oscar 1234-56789-000-00D COI (Updated 9-16-04)

No dates in the file names unless it is the updated COI list.

Document Transfer:

Transfer of peer review documents to OSQR from Area Offices.  All versions of the project plans should be sent electronically to OSQR as PDF files (preferred) or Word documents.  If PDF files are provided, no hard copies are required, except that for the Post-Project Plan, a hard copy of the signature page only, with the original Area Director signature, must be sent by FedEx or certified mail. If Word documents are provided, a hard copy of the entire project plan, including appendices, must be sent by FedEx or certified mail.  Wherever possible, the project plan file should include all appendices and letters of collaboration.  If this is not possible, these items can be included in a second, separate PDF or Word file, named as noted above.  Submit each document to OSQR attached to separate e-mails; add the note “1 of 2” or “2 of 2” as part of the e-mail subject line to assure that OSQR can retrieve both e-mails at the same time. The COI lists and the Response to Reviewer Recommendations must be sent to OSQR as Word documents, e-mail attachments.  Conflicts of Interest lists for a single project should be combined into one separate file.  Information copies of Requests for Postponement or Termination/Redirection will be sent electronically to OSQR as Word files.

Transfer of peer review documents to OSQR from the National Program Staff.  Approved prospectus must be sent electronically as Word documents to OSQR and the appropriate Area Offices.

Transfer of peer review documents to National Program Staff from Area Offices. Prospectus and information copies of the COI lists and ARS Response forms must be sent electronically to NPS as Word documents.  Copies of all versions of project plans may be sent electronically to NPS as PDF files or Word documents.  Requests for Postponement or Termination/Redirection must be sent electronically to NPS as Word documents.

Transfer of peer review documents to Area Offices from the National Program Staff.  PDRAMs will be sent electronically to Area Offices as PDF files.  Schedules will be sent electronically to Area Offices as Word documents.  Approvals or Disapprovals of Requests for Postponement or Termination/Redirection will be sent electronically to Area Offices as Word documents.

Transfer of peer reviews from the OSQR.  Peer reviews are electronically sent as Word documents to the appropriate Area Director and Area Program Analyst.  Copies are sent to the National Program Team and Program Analyst.

Electronic mail: All electronic mail pertaining to the peer review process should note the name of the review session or the National Program on the subject line.  If the message pertains to a specific project, the subject line should include the lead scientist’s name and research project number.  For split project plan files, attach each document to separate e-mails; add the note “1 of 2” or “2 of 2” as part of the e-mail subject line to assure that both e-mails can be retrieved at the same time.

Conflicts of Interest Format

Use the template or create a separate two-column table for each Category 1 or 4 scientist on the project, as well as any cooperating investigators not employed by ARS who will be considered an investigator on the project.  Each investigator listed on the cover sheet of the prospectus must provide a Conflicts of Interest list.  The tables should have one column for the full name and the other column for defining relationship with the individual.  Lists should include those individuals with which the SY has co-authored papers, conducted or planned research (including that planned in grant proposals), or supervised or been supervised in the past four years (all student and postdoctoral relationships apply that occurred during the past eight years).  Other possible conflicts of interest such as individuals who have a financial stake in the research, should be discussed with the OSQR.  Please state each person's FULL name (include middle initial or name, as appropriate).  If the individual has no middle initials, insert (NMI) where the initial would normally appear (e.g., John (NMI) Smith).  If the individual’s legal name is initials and not a name, insert (IO) into the name (e.g., J J (IO) Smith).  This will indicate to OSQR that the entry has been checked for accuracy.

The Conflicts of Interest lists are contained in one combined file for the project and are submitted separately from other documents.

The COI lists should have a header on all pages, with lead scientist's name at the left and page numbers placed flush right.  It should also have a footer on all pages, with version date at the left and filename placed flush right.

Prospectus Format

Create a file in MS Word and submit electronically through supervisory channels. Example file name: 303 Oscar 1234-56789-000-00D P

- The prospectus should be formatted as follows:

  - 8.5x11 letter portrait

  - Single spaced

  - 11-pt Arial or Helvetica font

  - 1" margins all around

  - Left justified

  - No end-of-line hyphens

  - Header on all pages with lead scientist's name at the left and page numbers placed flush right, excluding the cover page.  Begin page numbering with page 1 for the cover page, but do not show page number on the cover page.

  - Footer on all pages with version date at the left and filename placed flush right

- For tables, omit all vertical lines; place single horizontal lines under the title, under the column headings, and at the bottom of the table, just above any footnotes. Do not enclose tables or figures with lines or other borders.

- This short document (no more than five (5) pages, excluding the cover page) should describe the proposed project in terms of objectives, need for research, and approach and research procedures.

- As much as possible, the information should be abbreviated in the form of bullet statements and flow charts.

- The prospectus should flow from one section to the next without new page breaks.

Prospectus Outline

Cover Page

National Program —Title of the National Program under which the research described below is conducted.

Dates — General period in which the research project will be peer reviewed.

Old Research Project Number — Project number for the expiring project. If projects are being combined, list those that are being combined. If a project is being split, note that the old project is being split during this process.

Research Management Unit — Name of Research Management Unit (e.g., Areawide Pest Management)

Location — City and State.

Title — A brief, clear, specific description of the proposed project. Used alone, it should provide an indication of what the project is about. It should not contain more that 140 characters including letters, symbols and spaces. It is preferred that the new project be titled differently from the old project.

Investigator(s) — List all scientists assigned to conduct the research being planned and their percent commitment to the project, shown in decimal format (e.g., 0.50, 1.00). This will include all ARS Category 1 or 4 scientists assigned to the project and possibly non-ARS scientists. Any non-ARS scientist must function in a role equivalent to an ARS Category 1 or 4 scientist.  Identify the Lead Scientist. All scientists not employed by ARS need to be identified as 'non-ARS' scientists. The investigator list should reflect what is proposed for the new project, and need not match the SY listing of the current project in ARIS. Everyone on the list must prepare a Conflicts of Interest list.

Scientific Staff Years — List as a decimal, i.e., 2.75.

Planned Duration — List in terms of total months, i.e., 60 months.

Signatures — On the electronic copy of the Cover Page, submit electronic signatures using /s/ as the standard. OSQR only accepts prospectuses that demonstrate all approvals by the 1) the Research Leader; 2) Lab, Institute, or Center Director; 3) Area Director, and 4) the National Program Leader. For labs that have a 3-tier organizational structure (vs. the 4-tier organization that is implied on the coversheet), you may combine the first and second signature block. If your lab uses a different title for the Research Leader or Center Director, you may edit the titles accordingly. The National Program Staff turns in the final versions of prospectuses to OSQR and the appropriate Area Offices.

******Begin the first of your 5-page prospectus here. ******

Key Words

Provide a list of 6-10 keywords that describe the project.

Objectives

A clear statement of the specific objectives of the project that are attainable within the time period (not to exceed 5 years) and resources committed to the project. The statement should be complete enough to be used as the basis for scientific review.

Need for Research

List each of the following briefly:

-Description of the problem to be solved.
-Relevance to ARS National Program Action Plan.
-Potential benefits expected from attaining objectives.
-Anticipated products of the research.

-Customers of the research and their involvement.

The section describing 'customers' now requires that specific statements about the customers be made.  Avoid general comments such as "Our key customer is the pork industry."  Explain other characteristics that help reviewers understand the scope of the customers, such as:

1. Regional

2. Farm size

3. Environmental or ecological

4. Specific government agencies (federal, state, or local)

5. Business types, including business associations

It's a good idea to give the reviewers a few examples of the typical customers and if possible, new customers who might unexpectedly benefit from the success of the research.

Scientific Background

For the Prospectus, only describe how your project is coordinated with other projects (list them) to form a larger effort that addresses some aspect of the National Program. Also of relevance here are projects that do similar work, but you are not directly collaborating with them to attain your stated objectives. List those projects and describe how you are coordinating your efforts.

Approach and Research Procedures

For each objective, identify the hypothesis to be tested (if any.  See section on hypothesis-driven research and non-hypothesis-driven research, page X), the experimental approaches, and the specific research procedures that will be used. List contingency approaches and experimental options that will be considered if the initial research plan is unsuccessful in evaluating hypotheses or attaining objectives.

Collaborations

Collaborations with scientists outside of this project (ARS and external to ARS) that are necessary to attaining the objectives should be listed here.

Project Plan Format

Create a Word file according to these instructions.  Example file name: 303 Oscar 1234-56789-000-00D PrePlan

- The project plan should be formatted as follows:

  - 8.5x11 letter portrait

  - Single spaced

  - 11-pt Arial or Helvetica font

  - 1" margins all around

  - Left justified

  - No end-of-line hyphens

  - Header on all pages with lead scientist's name at the left and page numbers placed flush right, excluding the cover page.  Begin page numbering with page 1 for the cover page, but do not show page number on the cover page.

  - Footer on all pages with version date at the left and filename placed flush right

- For tables (excluding Milestone table), omit all vertical lines; place single horizontal lines under the title, under the column headings, and at the bottom of the table, just above any footnotes. Do not enclose tables or figures with lines or other borders.

- Avoid creating color graphics, unless necessary to thoroughly describe your plan or demonstrate scientific analyses. If color graphics are included and considered necessary, a note must accompany the plan stating that it must be printed in color. However, do not type on the plan "Please print in color."

- Do not create attachments.  Wherever possible, the project plan file should include all appendices and letters of collaboration.  If this is not possible, these items can be included in a second, separate PDF or Word file, named in the convention 303 Oscar 1234-56789-000-00D PrePlan-App, with page numbers continuing in sequence from main file.

The plan should not exceed:      <2 Scientific Years = 15 pages
                                            2-3.9 Scientific Years = 20 pages
                                            4-6.9 Scientific Years = 25 pages
                                                >7 Scientific Years = 30 pages
from Objectives through Project Management and Evaluation. Up to two pages of schemes, figures, and diagrams can be included in the text and will not be counted against the page limit. This first part should flow from one section to the next without new page breaks.

The Cover Page, Signature Page, Table of Contents, Project Summary, Objectives, Accomplishments from Prior Project Period, Literature Cited, Past Accomplishments of Each Investigator, Health, Safety, and Other Issues of Concern Statement, and Appendices should all be started on new pages.

Project Plan Outline

Cover Page  (same as cover for prospectus, without signature blocks)

National Program -- Title of the National Program under which the research described below is conducted.
Dates -- General period in which the research project will be peer reviewed. 
Old Research Project Number -- The project number for the expiring project. If projects are being combined, list those that are being combined. If a project is being split, note that the old project is being split during this process.
Research Management Unit -- Name of Research Management Unit (e.g., Areawide Pest Management)

Location -- City and State.
Title -- A brief, clear, specific description of the proposed project. Used alone, it should provide a clear indication of what the project is specifically about. It should not contain more than 140 characters including letters, symbols and spaces.  This should match the title used on the prospectus.
Investigator(s) -- List all scientists assigned to conduct the research being planned and their percent commitment to the project, shown in decimal format (e.g., 0.50, 1.00). This will include all ARS Category 1 or 4 scientists assigned to the project and possibly non-ARS scientists. Identify the Lead Scientist. All scientists not employed by ARS need to be identified as 'non-ARS' scientists. The investigator list should reflect what is proposed for the new project, and need not match the SY listing of the current project in ARIS. Everyone on the list must have an accomplishments section in the back of the plan. 
Scientific Staff Years -- List as a decimal, i.e., 2.75. (Does not include scientists not employed by the ARS. However to determine the page limit, calculate an equivalent scientific year for non-ARS scientists.)
Planned Duration -- List in terms of total months, i.e., 60 months.

Signatures (new page)

Insert the appropriate Signature Page template, depending on whether the plan is the PrePlan, a ReReview, or the PostPlan.

Table of Contents (new page)

Insert a table of contents.

Project Summary (new page)

The objectives and research approaches of the project plan should be summarized in 250 words or less on the second page. The first four pages of the project plan are not counted against the page limit.

Objectives (new page)

A clear statement must be given of the specific objectives of the project that are attainable within the project time period (not to exceed 5 years) and with the physical resources committed to the project as discussed in the Approach and Research Procedures section. The statement should be complete enough to be used as the basis for scientific review. Elaborate, in paragraph form, the bullet statements from the Prospectus.

Need for Research

A statement that provides information necessary for the review of the project based on its relevance to ARS National Program action plans. Use subsections to denote the following, which must be covered:

· Description of the problem to be solved.
· Relevance to ARS National Program Action Plan.
· Potential benefits expected from attaining objectives.
· Anticipated products of the research.

· Customers of the research and their involvement. (Be specific)

The section describing 'customers' now requires that specific statements about the customers be made.  Avoid general comments such as "Our key customer is the pork industry."  Explain other characteristics that help reviewers understand the scope of the customers, such as:

1. Regional

2. Farm size

3. Environmental or ecological

4. Specific government agencies (federal, state, or local)

5. Business types, including business associations

Scientific Background

Try to avoid repeating information already provided in the "Need for Research" section. The "Scientific Background" section should mainly focus on presenting and discussing relevant literature and technology relating to the stated objectives and scientific feasibility of the project plan. This section should cite relevant literature and key papers in the field, only. It is not intended to serve as a comprehensive bibliography. The literature cited should be sufficient to allow peer reviewers to conclude the investigators have current knowledge and understanding of the field of study. Results of past projects or other preliminary results of the investigators relevant to the current project plan should also be presented and discussed in this section. This section should also include information resulting from a CSREES-CRIS search. If applicable, try to show how the project is coordinated or associated with other ongoing research projects. For the CRIS search, cite the CRIS project number, title, location and describe in a few sentences its relationship to the project. It is not necessary to cite every CRIS project that is listed using the keywords for the search. Only include the truly relevant projects, perhaps five at most. If the investigator is aware of other, non ARS research relevant to the project it is also a good idea to refer to them in this section. Cite the lead investigator(s), institution, and briefly describe the relationship to the research outlined in your project plan. Some of these projects might be mentioned again under "collaborations" in the "Approaches and Procedures" section. It is important that peer reviewers can conclude the investigators are aware of and are forthright about others performing similar research.

Lastly, according to instructions from the National Program Leader and Area Director, describe Congressional mandates, if applicable, related to the project. Also, document patent searches if the project deals with product or technology development.

Approach and Research Procedures - Use three subsections under this heading to elaborate on the following:

Experimental Design - Describe in detail the scientific and experimental approach that is to be used and the research procedures that will be followed to attain objectives. For each objective or subobjective, if applicable, state what hypotheses will be tested and how the hypotheses will be tested. Hypotheses may not be appropriate for some research projects.  However, a clear statement of the information that is expected to be discovered/obtained and how this information will be used is required.  In either case, discuss how the experimental results will be evaluated.

Contingencies - Discuss approaches and experimental options that will be considered if the initial research plan is unsuccessful in evaluating hypotheses or attaining objectives.

Collaborations - Describe collaborations with scientists outside of this project (ARS and external to ARS) that are necessary to attaining the objectives. Necessary is meant to mean required for a successful project outcome. Necessary collaborations should be documented by an appended electronic letter from the scientist briefly detailing the collaboration. The letters of intent to collaborate must discuss what the collaborator will do and what level of commitment is anticipated.

If appropriate, sets of the above subsections may be used for each major objective.

Physical and Human Resources

Describe availability of major physical resources (i.e., facilities, major instrumentation and equipment, etc.) that are necessary to accomplish the research. Estimate the number (FTE) of non-Cat. I project personnel (postdocs, technicians, students, etc.) who will be available for this project.

Project Management and Evaluation

Projects composed of a number of investigators should describe the overall project management and evaluation process. The purpose of this section is to provide the panel with an overview of project management in terms of evaluating progress toward the objectives, changes in approaches, and documentation of these changes. This section would provide a basis for demonstrating to the panel how the project team functions and makes decisions about changes. The summary of this information during the lifecycle of the project would be linked to the Annual Report of Progress (AD-421). This section should be no longer than 1/2 page.

Milestones and Expected Outcomes (new page)

Insert a Milestone table (using this format: orientation: portrait; font: 9 pt Arial Narrow). Describe a series of milestones (points in the project where significant planned accomplishments can be documented) for the life of the project. These milestones are identified for each objective and hypothesis of the project along with the scientists responsible for each milestone. Milestones will be linked to the Annual Report of Progress (AD-421) to document the progress each year and the changes in milestones for the next year. This table can be exported from the project plan and maintained by the lead scientist for the project. Describe how progress will be documented through products (e.g., scientific papers, databases, germplasm releases, technology transfer, CRADAs).   The Milestone table template is included on page 45.  An example of a Milestone table is included in the Examples section, page 46.

Examples of Hypothesis Statement

Genetic background in elm influences the severity of leaf scorch symptoms.

Intensity of tillage does not affect soil organic matter distribution and carbon flux from the soil surface.

Diet composition in swine does not affect the composition of manure or the pathogen content in manure.

Examples of Milestone Statements

Evaluation of GC/MS method to quantify levels of volatile organic compounds in air samples.

Assessment of the validity of a rapid screening process for detection of nematodes in soil samples.

Evaluation of the performance of SWAT model to estimate water quality in corn-soybean watersheds.

Examples of Products

Research paper on variation in nitrogen mineralization rates across a combination of soils and manures.

Database that includes meteorological, plant growth, and soil carbon data from multiple crop rotations, soils, and climates.

Germplasm release.

Technology transfer agreement with a commercial company to market a widget developed from ARS research.

Accomplishments from Prior Project Period (new page)

This section summarizes the research accomplishments and impact from non-bridging research project(s) relevant to this project plan that is current or terminated within the last two years.  The purpose of this section is to provide the reviewers with a description of the accomplishments and impact from the previous efforts that are related to the project plan being reviewed.  The following information must be provided and should not exceed 2 pages.  These pages are not in the project plan page limit.

1.  Terminating research project number

2.  Title

3.  Project period (beginning and ending dates)

4.  Investigators and FTE

5.  Project accomplishments and impact

For each objective in the current or terminated project plan provide the following:

a. Summary of the most significant accomplishments and their related impact.  Cite most significant publications resulting from this research.  Mark all publications derived from this research project with asterisk in the Past Accomplishment section for each investigator.

b. If necessary, provide a synopsis of changes in the objectives and the reasons for the changes.

c. Describe how the objectives and accomplishments relate to the proposed objectives.

Literature Cited (new page)

Begin the Literature Cited on a new page. Literature can be listed alphabetically by author or in order of citation in the text. If papers are cited by author(s) and year, they must be listed alphabetically in the Literature Cited section. However, any citation format accepted by a scientific journal that includes all authors, article title, and complete page numbers may be used. Only material or papers that are published or in press should be provided in this section. Theses and dissertations, state and federal documents intended for professional distribution, and peer-reviewed proceedings of meetings generally are acceptable citations. Meeting abstracts, unpublished materials, and non-peer-reviewed materials are not acceptable as citable materials.

Past Accomplishments of Investigator(s) (new page)

All investigators listed on the project plan cover sheet must have a section for past accomplishments.  Begin each investigator's past accomplishments on a new page. In one single-spaced page or less per scientist, provide education and work experience, and describe accomplishments of the investigator(s) of this project over the past 10 years that are significant and pertinent to the proposed research.

Follow each investigator's past accomplishments with a list of the most relevant 20 peer-reviewed publications authored by the investigator.

Order the publications according to publication date, most recent last. Any citation format accepted by a scientific journal that includes all authors, complete article title, and complete page numbers may be used.

Health, Safety, and Other Issues of Concern Statement (new page)

Address the safety concerns for ten issues, including identification of necessary permits either in hand or requested. If not relevant, please state as such.
· Animal Care
· Endangered Species
· Environmental Impact Statement - Scientists and their Research Leaders shall make a determination on the potential environmental impact of the research. Many ARS research projects are conducted in contained facilities such as laboratories, greenhouses, or field plots. Such projects would be considered to the Categorically Excluded under ARS National Environmental Policy Act regulations. Project statements would then include the following statement: "THE RESEARCH PROJECT HAS BEEN EXAMINED FOR POTENTIAL IMPACTS ON THE ENVIRONMENT AND HAS BEEN FOUND TO BE CATEGORICALLY EXCLUDED UNDER ARS REGULATIONS FOR THE NATIONAL ENVIRONMENTAL POLICY ACT." The appropriate NPL(s), in discussion with the scientist about a replacement project, will decide whether it is Categorically Excluded.
· Human Study Procedure - Research teams under the Human Nutrition National Program should document how they have complied with the legal requirements for using human subject here.
· Laboratory Hazards
· Occupational Safety & Health
· Recombinant DNA Procedures - The IBC license number must be included in the project plan if there is work with recombinant DNA.
· Homeland Security
· Intellectual Property

· Existing SCAs - Describe any existing SCA in the collaboration section of the specific project objective and in the letter from the cooperator.

Appendix (new page)

On a new page, list appendices by page number.  If appendices cannot be included with the main text file, they may be combined as one file and submitted as a second PDF or Word file.  The appendices file should be set to begin numbering as continuation of the main text file, so that when assembled as one hardcopy document, the numbering will be consecutive.  Letters of collaboration should be included here, as well as any other supplementary materials that are essential to the plan. Scan or paste the collaborators letters into the project plan appendices after the list of appendices page.  Use of figures, schemes, and tables can greatly enhance the plan. Provide other explanatory material here.

Remember, up to two pages of figures, schemes, and tables will not be counted as part of the 15-30 page limit.

COI Template

CONFLICTS OF INTEREST

Project Plan Prospectus Addendum

NP Number, Research Project Number

___________________________________

List those individuals with which you (each investigator on the proposed project plan) have co-authored papers, conducted or planned research (including that planned in grant proposals), or supervised or been supervised in the past four years (All student and postdoctoral relationships apply that occurred during the past eight years).   Other possible conflicts of interest should be discussed with the OSQR.  You must spell out each person’s full name.

| Name | Relationship |
| --- | --- |

PrePlan Signature Page, with block for both RL and CD/LD/ID

Pre-Peer Review

(Signature and Dates Must Be Complete Prior to Distributing this Project Plan to Peer Reviewers)

Lead Scientist, Project Number and Title

This project plan was found to meet the peer review criteria, to be in compliance with the Project Plan Instructions and Format, and demonstrate how the research team will conduct research in a manner appropriate for this area of research. The funds committed toward this project are sufficient to support the planned research.

______________________________________		______________

Research Leader							Date

This project plan was prepared by a qualified research team and demonstrates the research team’s best effort towards achieving the assigned research objectives.

______________________________________		______________

Center, Institute or Lab Director					Date

This project plan was prepared by a qualified research team and demonstrates the research team’s best effort towards achieving the assigned research objectives.  All internal review and approval requirements have been met. This project plan is relevant to the Agricultural Research Service’s National Program [enter NP # and title] Action Plan and was prepared in accordance with the outlined objectives, experimental approach, and project duration previously agreed to by the National Program Team and Research Team. To validate the plan’s readiness for implementation and gain recommendations for improvement, the project plan is now available for peer review.

______________________________________		______________

Area Director								Date

These officials have not performed a scientific merit peer review. Their statements do not necessarily require expertise in the scientific subjects associated with this research. The approval to implement this project plan cannot be made without scientific peer review coordinated by the Office of Scientific Quality Review, ARS, USDA.

PostPlan Signature Page, with block for both RL and CD/LD/ID

Post-Peer Review Signature Page

Lead Scientist, Project Number and Title

This project plan was revised, as appropriate, according to the peer review recommendations and/or other insights developed while considering the peer review recommendations. A response to each peer review recommendation is attached. If recommendations were not adopted, a rationale is provided.

______________________________________		______________

Research Leader							Date

This final version of the project plan reflects the best efforts of the research team to consider the recommendations provided by peer reviewers. The responses to the peer review recommendations are satisfactory.

______________________________________		______________

Center, Institute or Lab Director					Date

The attached plan for the project identified above was created by a team of credible researchers and internally reviewed and recognized by the team’s management and National Program Leader to establish the project’s relevance and dedication to the Agricultural Research Service’s mission and Congressional mandates. It reflects the best efforts of the research team to consider the recommendations provided by peer reviewers.  The responses to the peer review recommendations are satisfactory. The project plan has completed a scientific merit peer review in accordance with the Research Title of the 1998 Farm Bill (PL105-185) and was deemed feasible for implementation. Reasonable consideration was given to each recommendation for improvement provided by the peer reviewers.

______________________________________		______________

Area Director (original signature required)			Date

ReReview Plan Signature Page, with block for both RL and CD/LD/ID

Re-Review Signature Page

(Signature and Dates Must Be Complete Prior to Distributing this Project Plan to Peer Reviewers)

Lead Scientist, Project Number and Title

This project plan was revised according to the recommendations made by the panel. It is found to meet the peer review criteria and to be in compliance with the project plan instructions and format, and demonstrate how the research team will conduct research in a manner appropriate for this area of research.  The funds committed toward this project are sufficient to support the planned research.

______________________________________		______________

Research Leader							Date

This project plan was prepared by a qualified research team and demonstrates the research team’s best effort towards achieving the assigned research objectives.

______________________________________		______________

Center, Institute or Lab Director					Date

This project plan was prepared by a qualified research team and demonstrates the research team’s best effort towards achieving the assigned research objectives.  All internal review and approval requirements have been met. This project plan is relevant to the Agricultural Research Service’s National Program [enter NP # and title] Action Plan and was prepared in accordance with the outlined objectives, experimental approach, and project duration previously agreed to by the National Program Team and Research Team. To validate the plan’s readiness for implementation and gain recommendations for improvement, the project plan is now available for peer review.

______________________________________		______________

Area Director								Date

These officials have not performed a scientific merit peer review. Their statements do not necessarily require expertise in the scientific subjects associated with this research. The approval to implement this project plan cannot be made without scientific peer review coordinated by the Office of Scientific Quality Review, ARS, USDA.

PrePlan Signature Page, combined RL and CD/LD/ID

Pre-Peer Review

(Signature and Dates Must Be Complete Prior to Distributing this Project Plan to Peer Reviewers)

Lead Scientist, Project Number and Title

This project plan was found to meet the peer review criteria, to be in compliance with the Project Plan Instructions and Format, and demonstrate how the research team will conduct research in a manner appropriate for this area of research. The funds committed toward this project are sufficient to support the planned research.  This project plan was prepared by a qualified research team and demonstrates the research team’s best effort towards achieving the assigned research objectives.

______________________________________		______________

RL or CD/LD								Date

This project plan was prepared by a qualified research team and demonstrates the research team’s best effort towards achieving the assigned research objectives.  All internal review and approval requirements have been met. This project plan is relevant to the Agricultural Research Service’s National Program [enter NP # and title] Action Plan and was prepared in accordance with the outlined objectives, experimental approach, and project duration previously agreed to by the National Program Team and Research Team. To validate the plan’s readiness for implementation and gain recommendations for improvement, the project plan is now available for peer review.

______________________________________		______________

Area Director								Date

These officials have not performed a scientific merit peer review.  Their statements do not necessarily require expertise in the specific subjects associated with this research.  The approval to implement this project plan cannot be made without scientific peer review coordinated by the Office of Scientific Quality Review, ARS, USDA.

ReReview Signature Page, combined RL and CD/LD/ID

Re-Review

Lead Scientist, Project Number and Title

This project plan was revised according to the recommendations made by the panel. It is found to meet the peer review criteria and to be in compliance with the project plan instructions and format, and demonstrate how the research team will conduct research in a manner appropriate for this area of research. The funds committed toward this project are sufficient to support the planned research.  This project plan was prepared by a qualified research team and demonstrates the research team’s best effort towards achieving the assigned research objectives.

______________________________________		______________

RL or CD/LD								Date

This project plan was prepared by a qualified research team and demonstrates the research team’s best effort towards achieving the assigned research objectives. All internal review and approval requirements have been met. This project plan is relevant to the Agricultural Research Service’s National Program [enter NP # and title] Action Plan and was prepared in accordance with the outlined objectives, experimental approach, and project duration previously agreed to by the National Program Team and Research Team. To validate the plan’s readiness for implementation and gain recommendations for improvement, the project plan is now available for peer review.

______________________________________		______________

Area Director								Date

These officials have not performed a scientific merit peer review.  Their statements do not necessarily require expertise in the specific subjects associated with this research.  The approval to implement this project plan cannot be made without scientific peer review coordinated by the Office of Scientific Quality Review, ARS, USDA.

PostPlan Signature Page, combined RL and CD/LD/ID

Post-Peer Review Signature Page

Lead Scientist, Project Number and Title

This project plan was revised, as appropriate, according to the peer review recommendations and/or other insights developed while considering the peer review recommendations.  A response to each peer review recommendation is attached.  If recommendations were not adopted, a rationale is provided. This final version of the project plan reflects the best efforts of the research team to consider the recommendations provided by peer reviewers. The responses to the peer review recommendations are satisfactory.

______________________________________		______________

RL or CD/LD								Date

The attached plan for the project identified above was created by a team of credible researchers and internally reviewed and recognized by the team’s management and National Program Leader to establish the project’s relevance and dedication to the Agricultural Research Service’s mission and Congressional mandates. It reflects the best efforts of the research team to consider the recommendations provided by peer reviewers.  The responses to the peer review recommendations are satisfactory. The project plan has completed a scientific merit peer review in accordance with the Research Title of the 1998 Farm Bill (PL105-185) and was deemed feasible for implementation. Reasonable consideration was given to each recommendation for improvement provided by the peer reviewers.

______________________________________		______________

Area Director (original signature required)			Date

Template for Request to Postpone Prior to Start of Review

Place on appropriate letterhead

[Date]

SUBJECT:	Postponement of Project 0000-00000-000-00D (Title) from NPXXX Peer Review Session

TO:	Antoinette A. Betschart

Associate Administrator

THROUGH:	_______________________

Deputy Administrator, Division

___________________________

Senior National Program Leader

_______________________

Area Director

_______________________

CD/LD/ID, Unit Name

_______________________

Research Leader, Unit Name

FROM:	_______________________

Lead Scientist, _____________ [Research Unit]

We request that the project listed below be postponed from the peer review presently scheduled for ________________.

This plan is presently scheduled for review by the NPXXX panel/ad hoc review/re-review*.

(*Plans postponed from re-review may be ad hoc reviewed by new reviewers but will NOT be allowed further re-review.)

National Program:  National Program for which plan is scheduled

Management Unit and Location:  Location

Lead Scientist:  Lead SY

Investigators:  List investigators with percent time, as shown on the project cover sheet

Reason for request: Provide a clear description of the circumstances that preclude review as scheduled. Include efforts considered or made to complete the plan without postponement.

Time period of the requested postponement: In months

Date plan will be reviewed:

cc:

OSQR

PA

Template for Request to Postpone After Receiving Unsatisfactory Review

Place on appropriate letterhead

[Date]

SUBJECT:	Postponement of Project 0000-00000-000-00D (Title) from NPXXX Peer Review Session

TO:	Antoinette A. Betschart

Associate Administrator

THROUGH:	_______________________

Deputy Administrator, Division

___________________________

Senior National Program Leader

_______________________

Area Director

_______________________

CD/LD/ID, Unit Name

_______________________

Research Leader, Unit Name

FROM:	_______________________

Lead Scientist, _____________ [Research Unit]

The project listed below received an unsatisfactory score in the recent NPXX Panel Review (insert panel session title).  We request that this project be postponed to a later ad hoc panel.

Project #:

Title:

National Program:

Management Unit and Location:

Lead Scientist:

Research Leader:

Center/Laboratory/Institute Director: (insert N/A if none)

Investigators:  list investigators with % time, as shown on the project cover sheet

Reason for request:  Justification why project should be postponed rather than ReReviewed.

Time period of the requested postponement:  Indicate intended ad hoc panel; if not earliest, justify.

cc:

OSQR

PA

Template for Request to Terminate/Redirect After Unsatisfactory Review

Place on appropriate letterhead

[Date]

SUBJECT:	Postponement of Project 0000-00000-000-00D (Title) from NPXXX Peer Review Session

TO:	Antoinette A. Betschart

Associate Administrator

THROUGH:	_______________________

Deputy Administrator, Division

___________________________

Senior National Program Leader

_______________________

Area Director

_______________________

CD/LD/ID, Unit Name

_______________________

Research Leader, Unit Name

FROM:	_______________________

Lead Scientist, _____________ [Research Unit]

The project listed below received an unsatisfactory score in the recent NPXX Panel Review (insert panel session title).  We request that this project be terminated, with resources redirected.

Project #:

Title:

National Program:

Management Unit and Location:

Lead Scientist:

Research Leader:

Center/Laboratory/Institute Director: (insert N/A if none)

Investigators:  list investigators with % time, as shown on the project cover sheet

Redirection Plan:  Indicate how resources will be redirected, how other projects will be affected, how National Program objectives can be accomplished without this project.

cc:

OSQR

PA

Concurrence Memo Template

Place on appropriate letterhead

Date

SUBJECT:	NP _____________ Concurrence List, (Panel Date)

TO:	________________, Director

__________________Area

THROUGH:	_________________/s/

Deputy Administrator

____________________________

FROM:	___________________/s/

National Program _____ Co-Leader

___________________ /s/

National Program ______ Co-Leader

The NP XXX Peer Review Panel is scheduled for ____________ ____, _____.  The following projects are proposed for inclusion.  Please review the list, indicate Area concurrence, and return it to _______________ by __________, ________.

Requests for postponements of a project from the scheduled review must be approved by the Associate Administrator, per the guidelines in the REE Bulletin #03-601, “Guidelines for the Postponement of Research Project Plan Peer Reviews.”

If you have any questions, please contact ___________ (phone: 301/504-____ or e-mail:      @ars.usda.gov).

| Research Project # | PI | Location | Area Concur | Request for Postponement |
| --- | --- | --- | --- | --- |
| 1265-22000-009-00D | Smith | Beltsville, MD |  | Memo forwarded to Dr. Betschart for approval 3/17/05 |

cc:

_______________, Area Program Analyst

Review Schedule Template

| NP ____ Panel Review Schedule, (Add Panel Date) NPS PA _______________ |
| --- |
|  | The National Program Team develops the list of projects to be reviewed, initiates the concurrence process and develops review schedule(s) | April 2006 – October 2006 |
|  | Final concurrence/assignment list due to OSQR and Area Director | June 1, 2006 |
|  | Area sends COI Lists to OSQR. | June 15, 2006 |
|  | The NPT prepares PDRAMS and forwards to Area Offices and OSQR | NLT November 1, 2006 |
|  | Research teams develop prospectus |  |
|  | Prospectus due to the Lab/Center/Institute Director |  |
|  | Prospectus due to the Area Office |  |
|  | Prospectus due to the NPT, | January 1, 2007 |
|  | Area re-submits COI List to OSQR if changes were made. | January 1, 2007 |
|  | Approved prospectus due to OSQR. The research teams will also receive direction to begin drafting their project plans. Also the deadline to submit suggestions for reviewers to OSQR. | February 1, 2007 |
|  | Project plans due to the Lab/Center/Institute Director |  |
|  | Project plans due to the Area Office |  |
|  | Approved project plans due to OSQR from the Area Office with copy to NPT | June 1, 2007 |
|  | OSQR processing and review period | June 2007 |
|  | Research teams receive and respond to reviews. Projects that receive a ‘major revision’ or ‘not feasible’ will receive separate direction. |  |
|  | Approved revised project plans and response to reviewers’ comments are due to OSQR from the Area Office with cc to NPT. About 2 weeks later, OSQR will issue a peer review certification and directions regarding the 416/417. The plan is then implemented for the period remaining until the next scheduled panel review in this National Program. |  |

Milestone Table Template

| Project Titlea |  | Project No.b |  |
| --- | --- | --- | --- |
| Objectivec |  |
| Performance Measured |  |
| Subobjectivee |  |
| Hypothesisf | SY Teamg | Monthsh | Milestonesi | Progress/ Changesj | Productsk |
|  |  | 12 |  |  |  |
|  |  | 24 |  |  |  |
|  |  | 36 |  |  |  |
|  |  | 48 |  |  |  |
|  |  | 60 |  |  |  |
| Hypothesis | SY Team | Months | Milestones | Progress/ Changes | Products |
|  |  | 12 |  |  |  |
|  |  | 24 |  |  |  |
|  |  | 36 |  |  |  |
|  |  | 48 |  |  |  |
|  |  | 60 |  |  |  |

The goal of the table is to present a summary of the project in a form that is easily used to link to Annual Report of Progress (421’s) and Performance Plans for each scientist.  The intent of the table is to be a dynamic representation of the project that captures over the project life cycle the important progress and products derived from the project.

Table can be expanded by copying any section below the project title line.

Explanation of Footnotes

a Project Title from the project plan (use new project title)

b Project Number from the ARS-416 (use old project number until new project is established)

c Objective from the project plan

d List the Performance Measure from the NP Action that the Objective Addresses

e Subobjective from project plan (if used, if not this line can be deleted)

f A statement of the hypothesis for the objective, if appropriate.  Otherwise the non-hypothesis statement

g Initials of the project team members contributing expertise to the specific hypothesis and significant collaborators (if a vacancy exists on the project, identify this position within the table)

h Milestones for the specific months of the project, be as specific as possible as to the measurable milestones

i The Progress/Changes section is completed at the end of each year by the project team as  part of the Project Management and Evaluation process and a summary of these are entered into the table and if there is a revised milestone or hypothesis this is entered for the next period of the project plan.

j Specific products of the project for each hypothesis line.

Example Milestone Table

| Project Title | Enhanced Adoption of Soil Conservation Practices and the Impact on Biological Stressors in Semiarid Agriculture | Project No. XXXX-12000-001-00D |
| --- | --- | --- |
| Objective | Quantify the response of insect populations to altered soil microclimate induced by conservation tillage |
| Performance Measure | 3.2.5: Provide fundamental and applied scientific information and technology to protect agriculturally important plants from pests and diseases. |

| Hypothesis | SY Team | Months | Milestones | Progress/ Changes | Products |
| --- | --- | --- | --- | --- | --- |
| Insect populations are not affected by conservation tillage practices. | SY1 SY2 | FY 07 (12) | Identify sampling sites for conservation tillage within production fields and establish monitoring sites for insects and soil microclimate Establish common database for insect populations and soil microclimate data |  | Website of experimental sites and data observations for project team to access Database format and structure developed |
|  |  | FY 08 (24) | Collect soil samples and agronomic data from field sites Collect aerial images across fields to determine spatial patterns of insect damage Collect insect population statistics for each field |  | Population of database with initial observations Initial comparison of differences among conservation tillage systems |
|  |  | FY 09 (36) | Collect soil samples and agronomic data from field sites Collect aerial images across fields to determine spatial patterns of insect damage Collect insect population statistics for each field |  | Database with 1st and 2nd year observations Prototype field assessment tool |
|  |  | FY 10 (48) | Collect soil samples and agronomic data from field sites Collect aerial images across fields to determine spatial patterns of insect damage Collect insect population statistics for each field |  | Database with 1st, 2nd, and 3rd results Evaluation of experimental observations in conjunction with cooperators |
|  |  | FY11 (60) | Summarize observations after 4th growing season |  | Evaluation of field-scale assessment tool Draft reports and manuscripts on the project summary |

Example PDRAM

January 7, 2005

SUBJECT:	Program Direction and Resource Allocation Memo for Project No. 6202-32000-018-00D “Microbial Competitive Exclusion to Reduce Epizootic Pathogenic Bacteria in Swine and Cattle”

TO:	C. Onstad, Director

Southern Plains Area

THROUGH:	J. Spence, Deputy Administrator  /s/

Nutrition, Food Safety and Quality

FROM:	J. Robens, National Program Leader  /s/

Food Safety

The Project Peer Review for National Program 108, Food Safety is scheduled for June 2005.  Project No. 6202-32000-018-00D “Microbial Competitive Exclusion to Reduce Epizootic Pathogenic Bacteria in Swine and Cattle” in the Food and Feed Safety Research Unit, College Station, Texas, is due to terminate May 31, 2006.  The new Project Prospectus is due to OSQR and NPS for review during February 2005, and the full Project Plan is due to OSQR during June 2005, for Panel Peer Review during July 2005.

The new Project Plan must be developed by the research team to meet the goals and objectives of the 2005-2009 National Program 108 Vision-Strategy Document/Action Plan recently provided. Both Prospectus and Project Plan should be written with relevance to the components and problem areas following the guidance given below.

Title: Interventions to Reduce Epizootic Pathogenic Bacteria in Swine and Cattle

Problem to be Addressed:

The gut of food producing animals can be a reservoir for human pathogens such as enterohemorrhagic Escherichia coli, Salmonella and Campylobacter; bacteria estimated to cause as many as 3.9 million cases of human disease in the United States each year.

Costs from human foodborne disease are estimated to exceed $4.5 billion dollars annually.  Carrier animals colonized by these bacteria rarely exhibit symptoms, thus their detection and exclusion from slaughter is difficult.  Numerous technologies have been developed to reduce the contamination of carcasses by these pathogens during and after slaughter but none are infallible, as evidenced by continued product recalls and outbreaks of human foodborne disease.  More recently, producers are under increasing pressure to reduce their use of antibiotics to control disease and enhance production due to concern of public health officials that such use is contributing to the emergence and proliferation of microbial populations resistant to antibiotics used to treat medically important diseases.  We need to understand the ecological factors limiting the competitiveness, survivability and virulence of foodborne pathogens in the environment and the gastrointestinal tract, and we need to develop environmentally compatible technologies to clear these pathogens from food animals during on-farm rearing. Where possible these interventions should contribute to the efficiency of animal production.

Objectives of Research:

- Identify ecological factors: a) affecting pathogen attachment to the host’s epithelial tissue, b) regulating respiratory and fermentative processes and c) determining seasonal patterns of E. coli O157:H7 shedding.

- Conduct FDA approved field trials to demonstrate efficacy of a rumen bypass chlorate product to control enteropathogens in cattle.

- Determine specific dosages and administration regimes needed to optimize the microbiological control activity of chlorate, competitive exclusion, nitroalkane and bacteriophage therapy to reduce carriage of zoonotic pathogens in cattle and swine immediately preharvest and to be used as new, more environmentally compatible alternatives to antibiotics

- Quantitatively model selective factors impacting the development, amplification, persistence and transfer of antibiotic resistance elements within mixed populations of commensal and pathogenic gut bacteria in the environment and the gastrointestinal tract

Cooperation/Collaboration with Other ARS and Outside Research Projects:

  - Dr. Lance H. Baumgard, Department of Animal Sciences, University of Arizona, Tuscon, Arizona

- Dr. Andrew D. Brabban, Biotechnology Research Lab, Evergreen State University, Olympia, Washington

- Dr. Gordon E. Carstens, Department of Animal Science, Texas A&M University

- Dr. Morgon H. Scott, Department of Public Health and Anatomy, Texas A&M University

- Dr. David J. Smith, USDA/ARS, Biosciences Research Laboratory, Fargo, North Dakota

- Dr. Chad H. Stahl, Department of Animal Science, Iowa State University, Ames, Iowa

Expected Outcomes with Relevance to Problem Areas and Components w/in the NP Action Plan (Technology Transfer/products):

Component 1.1 Preharvest Food Safety

Problem Statement 1.1.3 Ecology, Host Pathogen and Chemical Residue Relationships (45% of overall CRIS effort)

- Objective 1 - Identification of ecological factors: a) affecting pathogen attachment to the host’s epithelial tissue, b) regulating respiratory and fermentative processes and c) determining seasonal patterns of E. coli O157:H7 shedding.

- Information regarding: a) the effect of swainsonine on expression of host cell receptors utilized by pathogenic bacteria, b) the effects of electro-negative compounds on regulation of respiratory and fermentative processes of foodborne pathogens and c) the effects of melatonin, triiodothyronine and thyroxine on seasonal patterns of E. coli O157:H7 shedding in cattle

Problem Statement 1.1.4 Intervention Strategies (25% of overall CRIS effort)

- Objective 2 – Completion of FDA approved field trials to demonstrate efficacy and safety of a rumen bypass chlorate product to control enteropathogens in cattle.

  - Efficacy and safety data to support regulatory approval of chlorate technology.

    - Specific dosages and administration regimes needed to optimize the microbiological control activity of chlorate, competitive exclusion, nitroalkane and bacteriophage therapy to reduce carriage of zoonotic pathogens in cattle and swine immediately preharvest and to be used as new, more environmentally compatible alternatives to antibiotics.

- Practical, cost effective, user friendly interventions to reduce the carriage, shedding and environmental burden of epizootic pathogenic bacteria of food producing animals and targeted to specific metabolic processes or cellular components

Problem Statement 1.1.5 Antimicrobial Resistance (30% of overall CRIS effort)

  - A quantitative model incorporating selective factors impacting the development, amplification, persistence and transfer of resistance elements within mixed populations of commensal and pathogenic bacteria in the environment and the gastrointestinal tract.

    - Rates of acquisition and transfer of antimicrobial resistance under conditions of current or pending antimicrobial administration regimes.

    - An epidemiological model describing transmission dynamics of antibiotic resistance among enteric bacteria in an integrated, semi-closed population of swine and humans.

    - Phenotypic and genotypic antimicrobial resistance profiles among bacterial populations from watersheds downstream of concentrated dairy, beef and swine production systems, and an assessment of the environmental impact of composted and noncomposted manure on dissemination of foodborne pathogens and antimicrobial resistance when applied as a topsoil amendment.

Supplemental Information:  N/A

Scientific Personnel:

Robin C. Anderson, Lead Scientist………………………….100%

Ross C. Beier………………………………………………...100%

Todd R. Callaway……………………………………………100%

Thomas S. Edrington ………………………………………..100%

Roger B. Harvey……………………………………………..100%

Toni Poole …………………………………………………… 50%

David J. Nisbet……………………………………………….100%

Source of Funds and Funding Level:

$2,28,510 NTL.  $1,459,517 from CRIS Project No. 6202-32000-018-00D Microbial Competitive Exclusion to Reduce Epizootic Pathogenic Bacteria in Swine and Cattle, and $748,993 from CRIS No. 6202 - 32000-019 Antibiotic Resistance to Enteric Bacteria in Poultry or Food Producing animals.

National Program Information:

National Program Code:  NP 108 Food Safety

SOI   3310 Beef Cattle     50%

3410 Dairy Cattle   10%

3510 Swine             40%

Other Information: N/A

cc:

OSQR

Jill Stetka, NPS

PA, NFSQ

PA, SPA

ARS’s Categories for Professional Scientific Positions

Category. An ARS system of administrative designations for groups of positions having generally similar characteristics, primarily for personnel and budgetary tracking purposes.  Category has no legal or administrative significance outside of ARS. Some positions may perform duties from more than one category. ARS categories established for professional scientific positions are as follows:

Category 1 (Research Scientist). Permanent positions in which the highest level of work, for a major portion of time, involves personal conduct or conduct and leadership of theoretical and experimental investigations primarily of a basic or applied nature such as: determining the nature, magnitude, and interrelationships of physical, biological, and psychological phenomena and processes; creating or developing principles, criteria, methods, and a body of knowledge generally applicable for use by others. Category 1 positions are SY positions.

Category 2 (Nonpermanent Research/Service Scientist). Professional scientific positions which are established on a nonpermanent basis, are filled through temporary or term appointments, and entail research and/or service science work. Examples are Research Associate, Research Affiliate, Visiting Scientist, and individuals reemployed in ARS after having retired from Category 1 or Category 4 positions.

Category 3 (Support Scientist). Professional scientist positions which function to provide direct support or service to one or more Category 1 or 4 positions. The work of such positions is characterized by responsible involvement in one or more, but not all, phases of research (particularly not the problem selection and definition phases); responsible participation in analysis and preliminary interpretation of data (but not including responsibility for final interpretation and conclusion which relate the results to the field of research involved). Examples include but are not limited to: (1) conducting literature searches; (2) selecting procedures and conducting experiments; (3) collecting and analyzing data or specimens; or (4) preparing technical reports.

Category 4 (Service Scientist). Permanent positions whose incumbents either primarily or exclusively serve as project or program leaders over or personally perform, work assigned to ARS involving professional scientific services to the public or to other governmental agencies, such as: identification of animals, plants, or insects; diagnosis of diseases; mass production of plants, animals, or insects; collection, introduction, and maintenance of germplasm or specimens; vaccine production; education, extension, or technology transfer activities; or nutrient data and food intake surveys. Category 4 positions are SY positions.

Category 6 (Specialist). “Specialist" positions which perform scientific program management, administration and/or analytical duties and therefore require professional education and training. Examples are: Area Director, Center Director, Agricultural Administrator, and National Research Program Leader.

Hypothesis-Driven vs. Non-Hypothesis-Driven Research

Hypothesis-Driven Research:

Webster defines a hypothesis as a tentative assumption made in order to draw out and test its logical or empirical consequences. A hypothesis may be a conjecture or an unproved model. It often includes a prediction about what will happen and a possible explanation for why it will happen. A hypothesis is an integral part of the Scientific Method, which has four steps, as follows:

1. Observation and description of a phenomenon or group of phenomena.

2. Formulation of a hypothesis to explain the phenomena.

3. Use of the hypothesis to predict the existence of other phenomena, or to predict quantitatively the results of new observations.

4. Performance of experimental tests of the predictions by several independent experimenters and properly performed experiments.

Questions are asked concerning observations, followed by formulations of hypotheses. Then, predictions are made based on the hypothesis, and appropriately-controlled experiments are performed to test it, providing evidence to support or refute the hypothesis. Hypotheses are tested by doing experiments; thus, hypothesis-driven research is targeted.

Types of Hypotheses:

Non-directional hypothesis

• there is a difference or there is a relationship statement of expectation

• covers 2 of 3 possible outcomes

Directional hypothesis

• usually same as non-directional-- there are two possibilities as answers,

• usually better to use non-directional unless certain that relationship can only go one way

Null hypothesis

• no difference exists

Statistical hypothesis

• tests of statistical significance

• make a decision to reject or fail to reject the null hypothesis

Example (from http://www.selu.edu/Academics/Education/EDF600/Mod3/):

Question – Will students who attended at least two years of Montessori preschool have better reading comprehension abilities at the end of first grade than those students who did not attend preschool at all?

Non-directional hypothesis –

At the end of first grade, there will be a difference between reading comprehension abilities of children who attended at least two years of Montessori preschool and children who did not attend preschool at all.

Directional hypothesis –

At the end of first grade, children who attended at least two years of Montessori preschool will have higher reading comprehension abilities compared to children who did not attend preschool at all.

Null hypothesis –

At the end of first grade, there will be no difference between reading comprehension abilities of children who attended at least two years of Montessori preschool and children who did not attend preschool at all.

Additional Examples:

Hypothesis Statement

Genetic background in elm influences the severity of leaf scorch symptoms.

Intensity of tillage does not affect soil organic matter distribution and carbon flux from the soil surface.

Diet composition in swine does not affect the composition of manure or the pathogen content in manure.

Non-Hypothesis-Driven Research:

Note that there are research projects that are at step 1 of the Scientific Method—these projects may have no hypothesis. Many non-hypothesis-driven research projects can be characterized as descriptive, explorative, or discovery research. Such projects involve the study of a biological system or an aspect of a system about which we do not know enough to formulate hypotheses. The general approach is to gather large volumes of information about the particular system or biological function, then analyze the data to discover linkages or other significant characteristics that will provide insight into the mechanism and function of the system.

Examples of research that may not have hypotheses include:

√ Systems research…… NP 207

√ Model development

√ High throughput genomics and other “-omics” research and global gene expression research – this type of non-hypothesis-driven research is often called data-driven research.

√ Methods development for analyte detection -- excluded is comparing new methods to currently available methods.

√ Product development, although some hypotheses may be tested while conducting the research. This research is goal- or customer-oriented.

√ Service projects – taxonomy, IR-4, germplasm repository

Requirement for Letters of Collaboration

- If you cite the existence of a collaboration in your project plan the individual(s) with whom you are collaborating must provide you with a letter that clearly documents the collaboration.  This letter must accompany your project plan.  The Lead Scientist is responsible for making sure that all appropriate letters of collaboration are included with the Plan.  Request letters of collaboration as soon as possible in the Peer Review Process.

- The letter of collaboration must be written on the letterhead of the institution with which the collaborator is affiliated and signed by the collaborator.  (An e-mail should be used as a last resort and only for ARS collaborators.  It must be accompanied by the recipient-properties fields of the ARS lab’s e-mail software.)

- If you are sent a hardcopy of the letter, scan the letter and place it in your plan as a graphic insert (in the Appendix).

- The letter should clearly state the following:

  - The full name of the collaborator and his/her institution

  - A statement that explicitly describes the nature of what the collaborator will provide to the research.

  - A brief statement which describes the experience and expertise of collaborator in his/her field (citations of a few key papers would be helpful).

  - A statement acknowledging that facilities and equipment are available to the collaborator.

  - Acknowledgement of any prior or on-going collaboration with any members of the scientific team on the plan.

- Keep in mind, this letter is meant to show the peer review panel that the collaborator can provide the respective collaborative product.  The panelists may not be familiar with the collaborator or his/her level of expertise.  So, it is important that the letter provides this type of information.

Scanning and Editing Adobe File Tips

1. Try not to scan into a bitmap, tiff or other photographic file. Adobe does not compress them

as well and the file size is huge.

2. You can scan directly into an Adobe file (if you have purchased the distiller) and the letters

look beautiful! However it is harder to put the headers and footers in the documents. File size is

OK.

3. Scanning letters into a Word file. Scan them as a B&W drawing with resolution of 100 (to

keep file size down). However, this isn’t recommended for letters of collaboration with color

because you want to maintain the originality as much as possible. Crop the scan size to about

9" if letters are short. In Word, you can easily add headers and footers. The Word file

containing 38 letters (about half text and half scanned) was 11,000 kb which when distilled by

Adobe became a 1500kb file.

If you have the distiller Adobe package, Adobe files are editable. This should make it easy to

correct your signature pages or change page #'s. Here's how:

1. In Adobe, you should have 3 lines of toolbars. At the end of the 3rd line, there should be a

blue T button (Touchup Text Tool button) with an attached arrow button. If you don't see the big

T, bring down the menu by clicking on the arrow and then click on the T.

2. Click the big blue T (should stay depressed), and then move your cursor to the text you want

to edit and highlight it by left-clicking and dragging (as for any software). Type the new text over

the old text.

3. If you want to add text, it is best to move your cursor where you want the text to go. Hold

down the ctrl key on your keyboard as you click on the big blue T, then type.

4. If you want to move text, click on the text, and you should see a text box (like in PowerPoint),

but text should not be highlighted (unhighlight text if it is highlighted). Now go to the arrow

button attached to the big blue T and pull down the menu. Click the Touchup Object Tool button

just below the T button. Now go back to the highlighted text box and drag it to where you want it

to be.

5. If you want to change the font, go back up to the big blue T button. Highlight the text that

you want to change (left click and drag) and then right click and scroll down to attributes.

Designate font type and size.

6. To underline text, click and hold the highlight text tool and drag over to the underline text

tool. Drag your mouse over the text you want highlighted and the text will be underlined.

United States Department of Agriculture

Research, Education, and Economics

ARS  CSREES  ERS  NASS

Bulletin

Title: 	Guidelines for the Postponement of Research Project Plan Peer Reviews

Number: 	03-601

Date:	September 30, 2003	Expiration:  	September 30, 2004

Originating Office:	ARS Administrator’s Office

Replaces:	Related guidance in OA-0501; Peer Review Manual

Distribution: 	ARS-wide

The following guidance describes procedures required of lead scientists and research leaders to postpone an ARS CRIS project from its assigned panel peer review session.

References

For additional information on the ARS Peer Review Process, See Manual OA-0500.

Abbreviations

CRIS		-	Current Research Information System

NPS		-	National Program Staff

OSQR		-	Office of Scientific Quality Review

Definitions

Research Project Plan or Project Plan:  As used in this directive, means a 5-year plan of prospective research of which the Agricultural Research Service is responsible for conducting and/or funding.

Panel Peer Review or Panel Review: As used in this directive, refers to a panel of reviewers convened by the Office of Scientific Quality Review to evaluate and provide recommendations on research project plans.

Coverage

Affects all ARS CRIS Category D-project research teams unless exempted from the peer review requirements set forth in P.L. 104-185 (Section 103(d)).

Authorities

Title I--Priorities, Scope, Review, and Coordination of Agricultural Research, Extension, and Education Act of 1998 (P.L.104-185; Section 103(d)).

Policy and Procedure

The Office of Scientific Quality Review (OSQR) is responsible for managing the peer review of ARS research projects supported by in-house, base funds.  As mandated by law, these reviews are to take place every five years by peer review panels consisting of scientific experts from universities, private industry and state and federal governmental agencies.  New research projects and existing projects, which have undergone extensive reorganization, also must be reviewed soon after they are implemented by the National Program Staff (NPS).  Area Directors and National Program Leaders should ensure, where feasible, that new or reorganized projects are established prior to the start of the appropriate panel review session and no later than the start of the prospectus-development stage of the review process.

Cooperation at all administrative levels is needed to ensure timely review of new and existing research projects.  Assembling peer review panels to review project plans is one of the more important responsibilities of the OSQR staff.  Panel service requires a significant commitment of time by panel members. Once a peer review panel meeting is scheduled, it is difficult to alter the schedule.  Project plans not completed in time to be reviewed by a scheduled peer review panel are highly problematic.  Such tardy plans must be sent out later for ad hoc peer review, wherein additional scientific experts must be recruited to perform the review.  Also, tardiness or postponement in submission of project plans for review undermine the integrity of the peer review process for the Agency.

More importantly, tardy plans sent out for ad hoc review do not benefit from the face-to-face discussions by members of a peer review panel.  Panel discussions that are rigorous are integral to the peer review process, and result in the best evaluations of the quality of the proposed research and suggestions to improve the research.  Lead Scientists and Research Leaders/Laboratory Directors are responsible for ensuring that project plans are submitted to OSQR on schedule.  Postponement of peer review of a project plan will therefore be approved only under exceptional circumstances.

Two criteria that may allow postponement are listed below.

Key Scientific Leadership Vacancies and Long-Term Absences.  Critical leadership vacancies are typically generated when key incumbents leave existing project positions or when new appropriations provide for new projects and/or objectives.  Long-term absences include any factor such as family leave or major illness that would preclude a member of a project from performing their duties for more than two months.  Even when such vacancies or absences are expected to exist for several months, however, the Lead Scientist or Research Leader should consult with their supervisor and strive to develop creative solutions that will facilitate the completion of the project plan on schedule.

Significant Unanticipated Reorganization, Initiation, or Redirection of Research. Where feasible, planning for reorganization or redirection of research projects should   provide sufficient time for development of project plans that can be panel peer-reviewed at the time normally scheduled for the relevant National Program.  Scheduling information is available at the Schedule of Peer Reviews at the OSQR website .  Timely development and panel peer review of a research project plan is also desirable when unanticipated appropriations and/or instructions are received to initiate, reorganize, or redirect research in significantly new objective areas.

Before considering postponement, the Lead Scientist and Research Leader/Laboratory Director (or individuals acting in their capacity) are strongly encouraged to seek advice and guidance from sources, both inside and outside of the Agency, concerning research techniques and approaches not currently available in a project due to vacancies or absences but needed to carry out the proposed research.  Please note that the absence of a single scientist from a multiple-scientist project may not be sufficient to warrant postponement of a project plan review.

If, after considering the above criteria, the Lead Scientist or Research Leader have remaining concerns about the feasibility and quality of the pending research plan, they should raise their concerns informally with their Area Director and appropriate National Program Staff member to discuss whether a postponement is appropriate.  Following these informal discussions and concurrence, the Lead Scientist or Research Leader requesting a postponement of the peer review of their project plan must request the postponement in the form of a memo addressed to the Associate Administrator.  This formal request should be routed through, and be approved by, the Research Leader/Laboratory Director, Institute Director (when appropriate), Area Director and appropriate Associate Deputy Administrator.  A copy of the request must be sent to the OSQR’s Scientific Quality Review Officer.  It is strongly recommended that the Lead Scientist or Research Leader make their request for a postponement no later than one month prior to the start of the prospectus-development stage of the scheduled review process.

The memo to the Associate Administrator must contain the following information:

CRIS Project No.

Title of the Project.

National Program.

Management Unit and Location.

Name of the Lead Scientist.

Names of the Research Leader, Center/Institute/Laboratory Director (if applicable), Associate Deputy Administrator, and Area Director shown as, who the memo went “through” for final approval.

Investigators assigned to the project and percent time contribution by each.

Specific reason(s) for the requested postponement.

Time period of the requested postponement, to indicate the point in which a prospectus could be prepared.

Efforts considered or made to complete the project plan write-up, and why they are not feasible or have failed.  (Please note that it is the responsibility of the Lead Scientist, Research Leader and their Center/Institute/Laboratory Director to exhaust all options for writing the project plan before requesting a postponement).

Upon receiving documented concurrence (e-mails are acceptable) from the Research Leader, Center/Institute/Laboratory Director (if applicable), National Program Leader, and Area Director, the Lead Scientist or person acting in their capacity must forward the memo to the Associate Administrator’s Correspondence Unit at  .  The Correspondence Unit can also be reached at 301-504-4517.

Responsibilities

Associate Administrator, where applicable, through the OSQR, assures ARS is in compliance with P.L. 104-185; Section 103(d).  Considers recommendations for the postponement of peer reviews of research projects and makes a final decision.

Office of Scientific Quality Review, administers and provides guidance on the ARS Peer Review Process and advises the Associate Administrator.

Area Directors, discuss, review, and concur on requests for the postponement of peer reviews.  Considers input on the rationale for postponements from NPS and research teams.

National Program Leaders & Associate Deputy Administrators, review and make recommendations on requests for the postponement of peer reviews.

Research Leaders, review and make recommendations on requests for the postponement of peer reviews.  May also request postponements.

Lead Scientists (or individuals acting in their capacity), uses the above guidance to request a postponed peer review of their research project plan after other alternatives have been exhausted.

Approved by Dr. Caird Rexroad, Acting Associate Administrator		Date

Useful Websites

Office of Scientific Quality Review

http://www.ars.usda.gov/Research/docs.htm?docid=1286

ARS National Programs

http://www.ars.usda.gov/research/programs.htm

AFM Virtual Library – Administrative Issuances, P&P’s

http://www.afm.ars.usda.gov/ppweb/index.htm

Requirements for Letters of Collaboration

http://www.ars.usda.gov/Research/docs.htm?docid=1570
Helpful tips for preparing letters of collaboration.

CRIS Search

http://www.cris.csrees.usda.gov/
CRIS is the USDA's documentation and reporting system for ongoing and recently completed research projects in agriculture, food and nutrition, and forestry.

To Complete a Patent Search

http://www.cambiaip.org/Home/welcome.htm
CAMBIA offers free and friendly access to agricultural patents from the European Patent Office, applications provided under the Patent Cooperation Treaty, and the U.S. Patent Office. The site also offers some helpful information for novices, such as a tutorial on how to read a patent.

Homeland Security

http://www.arsnet.usda.gov/ohs, http://arsnet.usda.gov/OHS/biosafety/materials_toxins.htm#I, http://www.ars.net.usda.gov/OHS/biosafety/SelectAgents.doc