March 15, 2004

# INSPECTION MEMORANDUM

To:		Philip Maestri, Director

Management Improvement Team

From:		Cathy H. Lewis

Assistant Inspector General

Evaluation, Inspections, and Management Services

Subject: 	Completion of Blueprint for Management Excellence Numbers 153, 154 and 155 (ED/OIG I13E0013)

This memorandum provides the results of our inspection of three Action Items from the Department of Education’s (Department’s) Blueprint for Management Excellence. The EIMS group is examining several Action Items related to Human Capital.  Our objective is two-fold: 1) to determine if the item was completed as described; and, 2) as completed, does the action taken help the Department towards its stated Blueprint objective.  In this report, we examined items 153, 154, and 155 completed June 18, 2002, concerning organizational layers, supervisory ratio and improved citizen access.

## Background

All Executive agencies were required to submit to the Office of Management and Budget (OMB) a five-year restructuring plan as part of their FY 2003 budget submission and annual performance plan.  The Department submitted the One-ED plan as its answer to this request, which was accepted by OMB.  A Restructuring Team was established with three sub-teams: Cross-Cutting; Administrative Services and Program to answer the following questions: the current state; the future state; what gaps exist between the current state and the future state, and what would a Five-Year Plan for moving forward look like.  Their incomplete draft report is dated March 26, 2002.

The action item required for item 153 was:

The Department restructuring plan will address appropriate numbers of organizational layers.

The action item required for item 154 was:

The Department will address its supervisory ratio.

The action item required for item 155 was:

The Department’s restructuring plan will review positions to improve citizen access to services.

All three of these action items were listed as completed based upon the completion of the One-ED Report on June 18, 2002.  Because these actions items are so closely related, we are combining them for the purpose of this inspection.

### Objective 1:  Were the action items completed as described for Numbers 153, 154, and 155?

The One-ED report does not contain a restructuring plan that addresses appropriate numbers of organizational layers, it does not address the Department’s supervisory ratio and it does not review positions to determine how to improve citizen access to services.

The Assistant Secretary for the Office of Management (OM), responding to a request for documentation on these three action items, stated: “We decided not to develop a restructuring plan but rather focus on our work and the way we do it….the proper organizational structure will be what it ought to be to best support our work.”  Absent a five-year restructuring plan, we reviewed the business case analyses completed in Phase I of the One-ED process to determine the extent to which these three issues were addressed in those plans.

In One-ED, teams are guided through the Strategic Investment Process (SIP), which  culminates in the issuance of a written business case analysis.  The business case analysis format uses an all-inclusive template, touching on every aspect of a function.  There is, however, no particular focus on appropriate numbers of organizational layers, supervisory ratio or a review to improve citizen access to services.   According to team members, they were instructed to examine functions within their areas that needed improvement in order to propose reengineering solutions.  They did not examine overall organizational issues and they were not instructed to address the issues contained in items 153, 154 and 155.

Even if a comprehensive analysis had been included in the business cases, however, because of the methodology of the One-ED process, the result would not have been a comprehensive analysis of organizational layers, supervisory ratio or improving citizen access. Each of the nine business cases focused on only one business function, rather than the total mission of each office.  The One-ED strategic investment process, which will take some time to complete, will not result in a Department wide, strategic examination of any of these issues.

In response to the OMB request, other agencies undertook a comprehensive approach to workforce planning.  The U.S. Department of Commerce, for example, requested from each bureau a detailed plan responding to each point in the President’s Management Agenda.  Included in each bureau’s plan is a chart of the current organization and a chart showing the organization as it is projected to look at the end of fiscal year 2007.  The Internal Revenue Service’s response includes a multi-year staffing plan, which matches approved, funded positions and captures attrition, migration and programmatic change to project five-year hiring plans.

Objective 2: As completed, do the actions taken help the Department towards its stated Blueprint objective (advancing the strategic management of human capital)?

The Department did not develop a restructuring plan and did not address numbers of organizational layers, supervisory ratio or how to improve citizen access to services.  The individual One-ED business cases likewise did not develop plans to address these issues, and given their limited focus would not have a viable vehicle for such an analysis.  The Department does not have an overarching human capital strategy nor does it have a comprehensive Human Capital Plan that addresses these issues.

### Recommendations

- The Department should reconsider listing these action steps as “completed.” If the EMT believes that these actions are unnecessary, the action items should be designated as “closed.”

- The Department should re-examine its reliance on One-ED to address the Department’s need for a well-articulated human capital strategy and a comprehensive human capital plan.

## MIT Comments

The MIT acknowledged that not all of the activities outlined in One-ED have been accomplished.  As a result, the EMT is currently evaluating the issue of human capital and is identifying activities that need to be taken to address human capital issues throughout the Department.  In addition, the EMT is currently evaluating lessons learned from the original implementation of the Strategic Investment Process and is considering alternative approaches to implementation.  The MIT response is included as an attachment to this memorandum.

OIG Response

OIG has not modified its recommendations.