UNITED STATES

PATENT AND TRADEMARK OFFICE

LIFE CYCLE MANAGEMENT

for

AUTOMATED INFORMATION

SYSTEMS

LCM-AIS

April 2001

Washington, D.C.

|  |  | UNITED STATES DEPARTMENT OF COMMERCE Patent and Trademark Office ASSISTANT SECRETARY AND COMMISSIONER OF PATENTS AND TRADEMARKS Washington, D.C. 20231 |
| --- | --- | --- |

Executive Summary

Life-Cycle Management (LCM) emphasizes decision processes that influence system cost and usefulness.  These decisions must be based on full consideration of business functional requirements and economic and technical feasibility in order to produce an effective system.  The primary objectives of the LCM approach are to deliver quality systems that: 1) meet or exceed customer expectations when promised and within cost estimates, 2) work effectively and efficiently within the current and planned information technology infrastructure, and 3) are inexpensive to maintain and cost-effective to enhance.

This Manual establishes the policies, procedures, roles, and responsibilities governing the initiation, definition, design, development, deployment, operation, maintenance, management, and retirement of Automated Information Systems (AIS) within the United States Patent and Trademark Office.  This document is published by the Chief Information Officer, United States Patent and Trademark Office (USPTO) and applies to all USPTO personnel and contractors responsible for AIS projects.  Compliance with the provisions of this document is required unless specifically waived by the Chief Information Officer.

The primary audience for this Manual and the supporting Technical Standards and Guidelines (TSGs) are the functional and technical managers responsible for defining and delivering USPTO systems, their staff, and their support contractors.

Please forward recommendations for improving this publication to the Software Engineering  Process Group.

| Ronald P. Hack (Signed) |  | Date April 3, 2001 |
| --- | --- | --- |
| Acting Chief Information Officer |  |  |

Chapter 1

OVERVIEW OF LIFE CYCLE MANAGEMENT

1.1  Introduction	1-1

1.1.1 Purpose	1-1

1.1.2 Objectives	1-1

1.2  Intended Audience	1-2

1.3  Types of Projects	1-2

1.4  Life Cycle Management Phases	1-4

1.4.1 Initiation Phase	1-4

1.4.2 Concept Phase	1-4

1.4.3 Detailed Analysis Phase	1-5

1.4.4 Development Phase	1-6

1.4.5 Deployment Phase	1-6

1.4.6 Operations Phase	1-7

1.5  Tailoring the Life Cycle	1-8

1.6  System Development Methodology	1-9

1.6.1 General	1-9

1.6.2 System Development Methodology Criteria	1-9

1.7  Policies and Guidelines for the Management of Projects	1-10

1.7.1 Manage AIS Projects as Investments	1-10

1.7.2 Emphasize Evolutionary Development and Incremental Delivery  of Products	1-10

1.7.3 Improve End-User Productivity	1-10

1.7.4 Encourage End-User Involvement	1-11

1.7.5 Ensure that Adequate End-User Training is Provided	1-11

1.7.6 Employ Matrix Management Techniques	1-11

1.7.7 Comply with USPTO Information Technology Standards and   Guidelines	1-12

1.7.8 Use USPTO IT Infrastructure and Ensure  Compatibility With  USPTO TRM	1-12

1.7.9 Use USPTO Standard Data Definitions	1-12

1.7.10 Use USPTO Standard System Development Tools	1-13

1.7.11 Cost and Schedule Performance Must Be Planned and Reported	1-13

1.7.12 Each AIS Project Must Be Consistent with the USPTO SITP	1-13

1.7.13 Use of COTS Software is Encouraged	1-14

1.7.14 Business Process Reengineering Techniques May Be Applied	1-14

1.7.15 Secure and Protect All Sensitive Information	1-14

1.7.16 Apply Risk Management Techniques	1-14

1.7.17 Focus on Software Process Improvement	1-15

1.7.18 Manage AIS or Infrastructure system Baselines	1-15

1.7.19 Implement Key Software Management Processes	1-16

1.7.20 Conduct Peer Reviews	1-17

1.7.21 Establish A Technical Training Program	1-17

1.7.22 Encourage Prototyping	1-18

1.7.23 Reuse Software Whenever Practical	1-18

1.7.24 Help Ensure Software Independence	1-18

1.7.25 Using Contractor Support	1-19

1.7.26 Maintain Complete Project Records	1-19

1.8  AIS or infrastructure system Project Reviews	1-20

1.8.1 Purpose of Technical Reviews	1-20

1.8.2 Conducting Technical Reviews	1-21

1.8.3 In-Progress Reviews	1-23

1.9  Roles and Responsibilities for AIS or infrastructure system Project Management	1-23

1.9.1 Program Sponsor	1-23

1.9.2 Chief Information Officer (CIO)	1-24

1.9.3 Steering Committee	1-25

1.9.4 Project Manager	1-25

1.9.5 System Development Manager	1-26

1.9.6 System Architect	1-26

1.9.7 Production Manager	1-26

1.9.8 System Maintenance Manager	1-26

1.9.9 Technical Review Board	1-27

1.9.10 Software Engineering Process Group	1-27

Chapter 2

initiation phase

2.1  Introduction	2-1

2.1.1 Purpose	2-1

2.1.2 Overview	2-1

2.1.3 Tasks	2-1

2.1.4 Activities and Documentation	2-2

2.2  Project Management	2-2

2.2.1 Establishing Program Sponsorship	2-2

2.2.2 Appointing the Project Manager	2-3

2.3  Preparing the business case	2-3

2.3.1 Providing Background Information	2-4

2.3.2 Organizing the Business Case	2-4

Chapter 3

concept phase

3.1  Introduction	3-1

3.1.1 Purpose	3-1

3.1.2 Overview	3-2

3.1.3 Tasks	3-3

3.1.4 Activities and Documentation	3-4

3.2  Technical Management	3-7

3.3  System Boundary	3-7

3.4  Project Planning	3-8

3.4.1 Developing the Project Management Plan	3-8

3.4.2 Developing the Concept Of Operations	3-9

3.4.3 Developing High Level Requirements	3-9

3.4.4 Developing the Quality Assurance Plan	3-11

3.4.5 Developing Electronic Records Management Requirements 	3-11

3.5  DEFINING THE high level ARCHITECTURE	3-13

3.5.1 The System Architect’s Role	3-13

3.5.2 Evaluating Commercial Off-the-Shelf Software	3-13

3.5.3 Benefits of Using COTS Software	3-14

3.5.4 Disadvantages of Using COTS Software	3-15

3.5.5 Selecting an Approach	3-5

3.6  Assessing the Information Technology Investment	3-17

3.7  Project Risk Management	3-17

3.7.1 Project Risk Assessment	3-18

3.7.2 Risk Review and Mitigation	3-19

3.8  AIS Security	3-19

3.8.1 Concept Phase Security Activities	3-20

3.8.2 Sensitivity Assessment	3-20

3.9  Acquisition of Information Technology Resources	3-22

3.10  Project Management Plan Update	3-20

3.11  Concept Approval	3-21

3.11.1 Project Manager and System Development Manager Evaluate Documentation	3-23

3.11.2 High Level Requirements Review	3-24

Chapter 4

Detailed Analysis phase

DETAILED ANALYSIS PHASE	4-1

4.1  Introduction	4-1

4.1.1 Purpose	4-1

4.1.2 Overview	4-1

4.1.3 Tasks	4-2

4.1.4 Activities and Documentation	4-2

4.2  Detailed Requirements Analysis	4-6

4.2.1 Functional and Data Requirements Definition	4-6

4.2.2 Support Requirements	4-7

4.2.3 Requirements Traceability	4-8

4.2.4 Detailed Level Requirements Review	4-8

4.3  Business Transition Planning	4-9

4.3.1 Transition Activities	4-9

4.3.2 Preparing the Organization for Change	4-9

4.4  AIS Technical ArchitecturE AND DETAILED DESIGN	4-10

4.4.1 Use of Existing System Components or COTS Products	4-10

4.4.2 Design Characteristics	4-11

4.4.3 Prototyping	4-12

4.4.4 Peer Reviews	4-12

4.5  Subsystem Identification, Definition and Management	4-12

4.5.1 Evolutionary Development and Incremental Delivery of Capabilities	4-12

4.5.2 Subsystem Project Management	4-13

4.6  COTS Detailed Analysis and Design Considerations	4-14

4.7  Project Risk Management	4-14

4.8  AIS Security	4-15

4.8.1 Security Analysis and Design	4-15

4.8.2 Determining Security Requirements	4-15

4.8.3 Incorporating Security Requirements into Specifications	4-16

4.9  Logical Design Review	4-17

4.10  technical Design Review	4-17

4.11  analysis and design considerations	4-18

Chapter 5

DEvelopment phase

5.1  Introduction	5-1

5.1.1 Purpose	5-1

5.1.2 Overview	5-1

5.1.3 Tasks	5-1

5.1.4 Activities and Documentation	5-2

5.2  System Development	5-6

5.2.1 Software Development and Construction	5-6

5.2.2 Integration	5-7

5.3  Testing and Reviews	5-8

5.3.1 Design Characteristics	5-8

5.3.2 Independent Security Testing	5-8

5.3.3 Peer Reviews	5-9

5.3.4 Test Readiness Review	5-9

5.3.5 COTS Acceptance Testing	5-9

5.3.6 Integration Testing	5-9

5.3.7 Formal Qualification Testing (FQT)	5-10

5.3.8 Beta Readiness Review	5-10

5.3.9 Beta Testing	5-10

5.4  Project Risk Management	5-11

5.4.1 Project Risk Assessment	5-11

5.4.2 Project Risk Review and Mitigation	5-11

5.5  AIS and cots Security	5-12

5.6  Business Transition Planning	5-12

5.6.1 Transition Activities	5-13

5.6.2 Preparing the Organization for Change	5-13

5.9  Production Readiness Review	5-13

Chapter 6

dePLOYment phase

6.1  Introduction	6-1

6.1.1 Purpose	6-1

6.1.2 Overview	6-1

6.1.3 Tasks	6-2

6.2  Production Installation	6-2

6.3  Configuration Audits	6-3

6.3.1 Functional Configuration Audits	6-4

6.3.2 Physical Configuration Audits	6-4

6.4  AIS or infrastructure system Security (Accreditation)	6-4

6.5  Business Transition	6-5

6.6  Training	6-6

6.7  transfer of system management responsibility	6-6

Chapter 7

operations phase

7.1  Introduction	7-1

7.1.1 Purpose	7-1

7.1.2 Overview	7-1

7.1.3 Tasks	7-1

7.1.4 Activities and Documentation	7-2

7.2 post installation review	7-3

7.3  AIS or infrastructure system Operational Support	7-4

7.3.1 Operational Services	7-4

7.3.2 Problem Reporting and the Help Desk	7-4

7.4 meetings to obtain User Feedback 	7-5

7.5  Maintenance and Modification	7-6

7.5.1 Determination of Requirements	7-6

7.5.2 Change Requests	7-6

7.5.3 AIS or infrastructure system Modification Releases	7-7

7.5.4 Processing Change Requests	7-7

7.5.5 Estimating Change Resources and Impact	7-8

7.5.6 Prioritizing Change Requests	7-9

7.5.7 Change Request Procedures	7-9

7.5.8 AIS Change Documentation	7-10

7.6  AIS or infrastructure system Security	7-10

7.6.1 Security Operations and Administration	7-10

7.6.2 Operational Assurance	7-11

7.6.3 Periodic Re-Analysis of AIS or Infrastructure System Security	7-11

7.7 AIS or infrastructure system Retirement	7-12