## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | National Endowment for the Arts
| Week End Date: | 2009-03-13
| Submitter Name: | Larry Baden
| Submitter Contact Info: | badenl@arts.gov
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 59 | 102 |  | The National Endowment for the Arts: Grants and Administration, Recovery Act | 50000000 | 0 | 0
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | Recovery section approved by OMB and posted on NEA site | Complete matrix for tracking actions to implement Act
2 | Agency-wide plan approved by OMB | Complete agency-wide calendar to implement Act
3 | Paperwork Reduction Act clearance received from OMB | Recruit for Inspector General office position
4 | Apportionment submitted/approved | Recruit potential panelists
5 | Application guidelines developed | Continue exploring alternatives to Grants.gov
6 | Potential applicants identified | Fine tune review process
7 | Potential panelists identified | Develop award and post-award materials
8 | Intra-agency working group established | Develop program-specific plan for OMB and Congress
9 | Weekly meeting of working group initiated
10 | Press release submitted for approval
11 | Press release posted
12 | Panel review process finalized
13 | Agency-wide meeting held to orient staff
14 | Application guidelines posted on NEA Web site
15 | Synopses and application packages posted on Grants.gov
16 | Potential applicants notified
17 | Accounting codes established
18 | Reviewed/commented on draft OMB reporting requirements
19 | Agency-wide plan submitted to Congress and posted on NEA site
20 | Grants.gov contingency of operations plan submitted to OMB
21 | Received applications for state arts agencies and regional arts organizations
22
23
24
25
26
27
28
29