## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | US Department of State
| Week End Date: | 2009-04-03
| Submitter Name: | Patrick F. Kennedy
| Submitter Contact Info: | Rachel Arndt (202) 647-1068
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 19 | 112 |  | Diplomatic and Consular Programs | 90000000 | 0 | 0
2 | 19 | 1119 |  | Capital Investment Fund | 252000000 | 0 | 0
3 | 19 | 530 |  | Office of Inspector General | 2000000 | 0 | 0
4 | 19 | 1079 |  | International Boundary and Water Commission - Construction | 219650000 | 0 | 0
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | Resource Management met with key Department ARRA coordinators to discuss project financial coding to ensure transparency and accountability. | IBWC: Award Task Order for geo-technical services for Lateral A segment in the Lower Reach
2 | International Boundary and Water Commission (IBWC): Issued request for proposal for design of four segments in the Upper Reach (Canalization): Hatch West Levee, Mesilla East and West Levees, Canutillo East and West Levees and Anapra Levees | IBWC: Award Task Order for re-design for Hidalgo Phase I segment in the Lower Reach
3 | IBWC: Awarded Task Order for Historic Architect Investigations for Upper Reach (Canalization) | IBWC: Issue Task Order for aerial survey (lidar)
4 | IBWC: Issued Task Order for design for six segments in the Lower Reach: Main Floodway North and South Levees, Arroyo Colorado North Levee, North Floodway North and South Levees, Hidalgo Levee System | IBWC: Complete Scope of Work and submit procurement package for Lateral A to Retamal Dam in the Lower Reach
5 | IBWC: Awarded Task Order for Environmental Assessment for the Arroyo Colorado segment in the Lower Reach | CIF - Data Center - Finalize Statement of Work for RFP to engage Gov Rep Procurement - Architecture and Engineering firm
6 | IBWC: Pre-construction contracts are 83% issued
7 | CIF - Data Center - Continued RFP development with A/OPR for the engagement of an A&E firm to serve as the Govt Rep in future Data Center design and acq activities
8 | CIF - Data Center - Completed the preliminary assessment of the feasibility of acquiring land adjacent to an existing data center campus
9 | CIF - Data Center - Completed the preliminary assessment of the feasibility of contracting with the data center vendor to construct a turn-key solution
10 | CIF – IT Platform Modernization – GITM – Continued determination of specifications for upcoming equipment procurement
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29