## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | US Department of State
| Week End Date: | 2009-03-20
| Submitter Name: | Patrick F. Kennedy
| Submitter Contact Info: | Rachel Arndt (202) 647-1068
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 19 | 112 |  | Diplomatic and Consular Programs | 90000000 | 0 | 0
2 | 19 | 1119 |  | Capital Investment Fund | 252000000 | 0 | 0
3 | 19 | 530 |  | Office of Inspector General | 2000000 | 0 | 0
4 | 19 | 1079 |  | International Boundary and Water Commission - Construction | 219650000 | 0 | 0
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | International Boundary and Water Commission (IBWC): One term engineer started work 3/16/2009 | IBWC: Issue award for geo-technical investigations service contract for Lower Rio Grande Valley Reach (Lateral A - Donna Pump) upon receipt of allotment
2 | IBWC: Job offer made to one contracting specialist | IBWC: Complete procurement packages by 3/31/2009 (SOW & IGEs for pre-construction activities)
3 | Global IT Modernization Program (GITM) – Continued review of specifications for upcoming equipment procurement | IBWC: Complete selection process for 2nd engineering position
4 | Office of the Inspector General (OIG) responded to request from Rep. Daniel Issa on OIG oversight activities (provided 2/25/09 oversight) | GITM - Develop Contract Requirements for equipment procurement
5 |  | Cyber Security - Discuss project plans with internal and external stakeholders
6 |  | Consular Affairs - Meeting with the Department of Homeland Security to discuss possible passport facilities
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29