Unify and Simplify through Shared Services

Integrated Acquisition

Environment Initiative

IAE Monthly Update  April 24, 2003

MO Update—April 24, 2003

Vision:

A secure business environment that facilitates and supports cost-effective acquisition of goods and services in support of mission performance

IAE Initial Modules:

•  Business Partner Network (BPN)-Deploy a single point of registration and validation of supplier data accessed by all agencies

•  Federal Procurement Data System—Next Generation—(FPDS-NG)-Implement a central point for consolidated collection and access of statistical and management information related to Government acquisitions.

•  eCatalogs—Create an online directory of GWAC and MAC contracts to simplify selection and facilitate leverage of Government buying.

•  Intra-government Transactions (IGT)- Transform intra-governmental ordering and billing, reduce payment and collection problems, and enable swift and accurate revenue and expense elimination processes for preparing consolidated financial statements.

•  Standard eTransactions– Develop a standard glossary and vocabulary to facilitate exchange of data between and within agencies.

Activities for the Next Month:

•  BPN

•  Complete transition to new database

•  Continue analysis of novation process

•  Training for FedTeDS users

•     FPDS-NG

•  Begin transition

•  eCatalogs

•  Phase in Interagency Contracts directory to obtain agency feedback

•  Continue certification and accreditation for Interagency Contracts Direc- tory

•  Continue comparison of shopping cart and vendor data among gov- ernment catalog systems

•  Standard eTransactions

•  Normalization of transactions/mapping of associated data elements

•  Intra-governmental Transactions

•  Launch IGT exchange prototype and conduct testing with Treasury’s

Intra-governmental Payment and Collection (IPAC) system

•  Implement second version of Federal Registration system (FedReg)

•  IAE PMO

•  Add both additional government and contractor staffing support

•  Continue development of acquisition strategy and requirements analysis for message broker/portal

•  Validate actual O&M requirements using detailed cost structure from each system owner

Contact:

Teresa Sorrenti, IAE Program Manager               703-872-8610

Earl Warrington, IAE Deputy Program Manager   703-872-8609

Lew Sanford Jr., GSA eGov Program Manager   703-872-8600

Lisa Cliff, IAE Communications                            703-872-8593

Email: integrated.acquisition@gsa.gov

http://egov.gsa.gov

PMO Update—April 24, 2003

Key milestones:

BPN

•  Full BPN operational capability                                                October, 2003

FPDS-NG

•     Initial Full operational capability                                            October, 2003

eCatalogs

•     Interagency contracts directory (ICD) available                    May, 2003

for full data entry

•     Fully populate ICD database                                                October, 2003

•     Implement eCatalog capability                                              June, 2004

Intra-governmental Transactions

•  Phase 1 deployment                                                                 October, 2003

Standard eTransactions

•  Publish data specifications                                                       September, 2003

IAE PMO

•  Portal implementation                                                               September, 2004

Additional Modules

•     WDOL— Wage Determination Online                                  October, 2003

•     eSRS — Electronic Subcontracting Reporting System

Initial operating capability                                              March 2004

Final operating capability                                               October, 2004

•     CADO — Contract Award Documents Online                      TBD

Accomplishments

•  BPN

•  Launched Past Performance Information Retrieval System (PPIRS)  July, 2002

•  Launched Federal Technical Document System (FedTeDS)      February, 2003

•  Merged SBA PRO-Net registration with CCR registration

•  Registered all agencies for intra-governmental transactions

•  FPDS-NG

•Awarded contract for new system

•  eCatalogs

•  Performed testing of Interagency Contracts Directory

•  Intra-governmental Transactions

•  OMB issued business rules including order and bill data elements

•  Registered CFO Act Agencies and 25 small agencies in new Federal Registra- tion database of BPN

•  Standard eTransactions

•  Process mapping of acquisition and its data exchanges

Governance:

•     Steering Committee—Quad Council (Chief Information Offi- cers, Chief Financial Officers, Federal Acquisition Council, and Human Resources Managers Council)

•     Internal Efficiency and Effective- ness Portfolio Manager

•     Sponsor—Federal Acquisition Council (formerly Procurement Executives Council

•     Managing Partner—General Ser- vices Administration/Federal Supply Service Partners—Department of Agri- culture, Department of Com- merce, Department of Defense, Department of the Interior, De- partment of Transportation, De- partment of Veterans Affairs, NASA, Small Business Admini- stration

•     Other Participating Agencies— Department of Education, De- partment of Energy, Department of Health and Human Services, Department of Homeland Secu- rity, Department of Housing and Urban Development, Department of Justice, Department of Labor, Department of the Treasury, En- vironmental Protection Agency, National Science Foundation, Nuclear Regulatory Commission, Office of Personnel Manage- ment, Social Security Administra- tion, State Department, USAID