| Acquisition Process Scenario: 13. Orders Against FSS Multiple Award Schedule |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Roles: PO, BO, FO, OSDBU, AT, SSA, Offerors, PO/BO |  |  | Systems: C = Current, F= Future, FP = Future Potential |  |  |  |  |  |  |
| PO | Program Office (Role performs: program management, sustainment/logistics, data, facility support, programmatics, end user) |  | #### BO |  | Buying Office (Role performs: contracting/purchasing functions) |  |  |  |  |
| FO | Finance Office (Role performs: accounting functions, budget functions) |  | #### OSDBU |  | Small Business |  |  |  |  |
| AT | Acquisition Team (Role performs: Defined by FAR 1.102-3) |  | #### SSA |  | Source Selection Authority- Determine Awardee |  |  |  |  |
| Offerors | Quoters, Bidders, or Offerors |  | #### PO/BO |  | Either or PO/ BO |  |  |  |  |
| # | Activity | #### Description | #### Role | Systems |  |  |  | Information Exchanges | Control / Business Rules |
|  |  |  |  | C |  | Name | F |  |  |
| 1. | ### Define Requirements |  |  |  |  |  |  |  |  |
| 1.1 | Determine Need | Draft requirement, establish budget, and seek budget approval. | PO |  |  |  |  |  | FAR 7.105(a), 7.107, 10.110(a), 11.002, 11.401, |
| 1.1.2 | Combine Requirements | Explore ability to combine requirements, explore best business arrangements (contract partnering). | BO |  |  |  |  |  |  |
| 1.3 | Acquisition Planning | Develop acquisition plan data if new FSS. | PO |  |  |  |  |  | FAR: 1.102-3, 7.103, 7.105; 7.4, 14.201(a), 15.100, 15.101, 15.201(c) FAR 19.202 |
| 1.3.1 | Acquisition Planning | Develop and Coordinate Acquisition Planning (Forecast and Acquisition Plan) for new FSS | BO |  |  |  |  |  | FAR: 1.102-3, 7.103; 7.105; 7.4, 14.201(a), 15.100, 15.101, 15.201(c), 19.202 |
| 1.3.2 | Validate Goals | Validates goals, publicize forecast. | OSDBU | X |  | Acqnet | X | - Publish goals and forecast |  |
| 1.5 | Assigned Buyer / Contract Specialist | Buying Office analyzes requirement; assigns to buyer / contract specialist. | BO |  |  |  | X |  | Agency policy; FAR 7.102(b) OMB Cir A-11 |
| 2. | Market Research |  |  |  |  |  |  |  |  |
| 2.1 | Follow Order of Required Sources | For new FSS. For supplies: internal first, warehouses, UNICOR, JWOD, schedules, and open market For services: JWOD, UNICOR, schedules, and open market | BO |  |  |  |  |  | FAR 8.001 |
| 2.1.3 | Check Required Sources | For new FSS or new product/ service submission. Check required sources i.e., JWOD & UNICOR sources. | BO | X |  | JWOD Website | X | - Check required source | FAR 8.7, 8.6 41 USC 46-48c; 18 USC 4121-4128 |
|  |  |  |  | X |  | UNICOR Website | X | - Check required source |  |
| 2.1.4. | Check Federal Supply Schedules/ Multiple Award Contracts | Check Federal Supply Schedules/ Multiple Award Contracts / GWAC. Ensure product / service not covered under another FSS. | PO/ BO |  |  | eCatalog | X | - Check Supply Schedules - Check GWACs | FAR 8.4; 16.505; 41 USC XXX (public contracts & fed property mgmt) |
|  |  |  |  | X |  | Advantage | X | - Check Supply Schedules |  |
|  |  |  |  | X |  | Buyers.gov | X | - Reverse auction for IT against FSS and FTS contracts |  |
|  |  |  |  | X |  | FBO | X | - Check for potential combining of requirements |  |
| 2.2 | Conduct Market Survey RFI | Determine industrial category (NAICS) and size standards. Gather market survey findings. | BO | X |  | Census Website | X | - Check for specific NAICS | FAR 6.102; 19.201; FAR 19.303 |
|  |  |  |  | X |  | CCR/BPN | X | - Use NAICS to find potential Offerors |  |
| 2.2.1 | Validate Market Survey Findings | Validate NAICS. Validate small business opportunities. | OSDBU | X |  | Census Website |  | - Check with a specific NAICS | FAR 6.102, 19.201, 19.303 |
|  |  |  |  | X |  | CCR/BPN | X | - Use NAICS to find potential Offerors |  |
| 2.3 | Issue Sources Sought Notice RFI | Posting in newspapers, single point of government entry, trade magazines, other specialized web sites. | BO | X |  | FBO | X | - Post Synopsis for Sources Sought | FAR 5.002, 5.101; 15 USC 637(e), 41 USC 416 |
| 2.3.1 | Establish Information Library | Drawings, specifications and other related documents. | BO | X |  | FBO | x | - Upload documents | FAR 15.201(f); 11.201; 5.102(b)(iii) 14.211(a) |
|  |  |  |  |  |  | FedTeds | X | - Upload documents |  |
| 2.3.2 | Assess Responses From Sources Sought RFI | Receive responses and coordinate evaluations by the Acquisition Team. | BO | X |  | CCR/BPN | X | - Validate NAICS - Assess capabilities – Validate interest in type of requirement | FAR 15.202 14.101(a), (b) |
|  |  |  |  | X |  | ProNET |  | - Assess capabilities – Validate business size |  |
|  |  |  |  | X |  | FPDS | X | - Assess capabilities – validate experience |  |
|  |  |  |  |  |  | PPIRS | X | - Assess capabilities – validate past performance |  |
| 2.4 | Negotiate set-aside | Prepare a position/recommendation document. | BO |  |  |  |  |  | FAR 19.5 |
| 2.4.1 | Review Recommendations | Review and resolve position/recommendation. | OSDBU |  |  |  |  |  |  |
| 3.0 | Issue Synopsis/RFQ/ RFP / Invitation for Bid (IFB) | Issue pre-solicitation synopsis advertising that requirements need to be filled; |  |  |  |  |  |  |  |
| 3.1 | Post Notice of Contract Action (Pre-solicitation Synopsis) | Post to Federal Single Point, newspapers, periodicals, trade journals, professional journals | BO | X |  | FBO | X | - Advertising requirement | FAR 5.201(a) |
| 3.2 | Modify Synopsis | Modify Synopsis. | BO | X |  | FBO |  | - Modify synopsis | FAR 5.201(a) |
| 3.2.1 | Amend Combined synopsis-Solicitation | Amend combined synopsis-solicitation. | BO | X |  | FBO |  | - Amend combined synopsis-solicitation | FAR: 12.102 (b), 13.105, 14.208, 15.206, |
| 3.3 | Pre-Solicitation Process | Pre-Solicitation Process. |  |  |  |  |  |  |  |
| 3.3.1 | Develop Selection Plan | Section L: Instructions to Offerors Section M: Evaluation Criteria (Price, Quality, Past Performance); Establishing evaluation factors and significant sub-factors, e.g. that would fall in to source selection plan Coordinate with PO, FO, OSDBU, and Legal | BO |  |  |  |  |  | FAR 12.203, 12.303, 13.106-1(a) (2), 13.106-2, 13.106-2(b), 13.106-3 (a), 14.201-5 (b) – (c), 14.201-8, 14.206-6, 15.1, 15.304, 15.305 10 USC 2305, 41 USC 253a |
| 3.3.2 | Build Solicitation | Develops and coordinates review of formal solicitation. This includes technical requirements provided and reviewed by the PO. The method of procurement (RFP, IFB, RFQ) is determined and the Legal Office reviews for legal sufficiency. | BO | X |  | DOL –Wage Determination (Davis-Bacon) | X | - Extract wage determination (post in the solicitation for construction) | FAR 15.203-204, 14.201, 12.303, FAR 12.04, 13.106-1, 2.101 definition of “best value” |
|  |  |  |  | X |  | NTIS / SCA Wage Determination | X | - Obtain service contract wage determinations |  |
| 3.4 | Solicitation Process |  |  |  |  |  |  |  |  |
| 3.4.1 | Pre-Solicitation Contact with Potential Offerors | Pre solicitation conferences, one-on-ones, draft solicitations, and other reviews by potential Offerors to obtain feedback and publicize. | BO | X |  | FBO | x | - Push page updates to IVs | FAR 12.102 (b), 15.201, 13.104, 14.207, 14.211 |
| 3.4.2 | Issue Solicitation | Issue solicitation. | BO | X |  | FBO | X | - Issue / post Solicitation | FAR 5.003, 5.102(a), 12.102 (b), 13.106-1, 14.203, 15.205, |
|  |  |  |  |  |  | FedTEDS | X | - Upload technical drawings |  |
| 3.4.3 | Solicitation Inquiries | Post solicitation Inquiries (Vendor questions, concerns, and clarifications) obtained either by written communication or from a pre-proposal conference go through Contracting Office. | BO | X |  | FBO | X | - Post responses to inquiries | FAR 12.102 (b), 13.106-1, 14.203, 15.206, 15.201(f); 15.303(c) |
| 3.4.5 | Respond to Solicitation Protest | Can happen at any time before receipt of proposals. Solicitation protests can go to: GAO, Federal Court, Contracting Officer. | BO |  |  |  |  |  | FAR 12.102 b, 13.106-3(c), 14.408-8, 15.507, 33.1 |
| 3.4.6 | Issue Refreshed Solicitation | Issue refreshed solicitation | BO |  |  |  |  |  |  |
| 4. | Evaluate Responses | Evaluate Responses activities based on RFP |  |  |  |  |  |  |  |
| 4.1 | Receive Response | Receive response. | BO |  |  |  | X | - Receive electronic vendor responses | FAR 15.207-208 |
| 4.2 | Conduct Initial Evaluation | Determine responsiveness. | BO | X |  | CCR |  | - Check for existence of registration | FAR 15.304-305 |
|  |  |  |  |  |  | BPN | X | - Validate vendor information |  |
|  |  |  |  |  |  | ORCA | X | - Retrieve representations and certifications (R&C) |  |
| 4.3 | Communicate Responses to Evaluators | Transmit documents to evaluators. | BO |  |  |  |  |  | Internal agency regulations |
| 4.4 | Evaluate Proposal | Buying Office requests evaluators; evaluate technical proposal, price/costs, terms and conditions; Contracting Officer brings in additional expertise as required for review. | BO |  |  |  |  |  | FAR 13.305(a)(1), 15.3, 15.303(a)(4), 15.305(a), 15.305(a)(3) |
| 4.4.1 | Evaluate Past Performance | Review both past and current performance utilizing online tools and telephone surveys of references | BO | x |  | PPIRS | x | - Check past performance information | FAR 15.305(a)(2) |
| 4.5 | Request Clarifications | Clarifications plus exchanges before establishment of competitive range, to determine relative ranking of Offerors absent discussion. | BO |  |  |  |  |  | FAR 15.306(a) and (b) |
| 4.6 | Determine Price Reasonableness | Award is to all with reasonable price that meets requirement. | BO |  |  |  |  |  |  |
| 4.6.1 | Notify Exclusions and Perform Pre-Award Debriefing | Notify vendors not awarded and perform pre-award debriefing if requested. | BO |  |  |  |  |  | FAR 15.306(c)(3) & (4), 15.505 (only for negotiated) |
| 4.7 | Address Pre-Award Protests | Protests can go to GAO, Fed Court, or Contracting Officer and may occur any time before award. | BO |  |  |  |  |  | FAR 12.102 (b), 13.106-3 (c), 14.408-8, 15.507, 33.1 |
| 4.8 | Exchanges with Offerors | At request of the contracting officer. Can include: requirements, resources, cost/price, schedule, place of delivery / performance, technical approach, and provide an opportunity to correct deficiencies and make clarifications. | BO | X |  | DOL Wage Determination Web Site (Davis-Bacon) | X | - Extract wage determination from Dept of Labor and post in the solicitation for construction | FAR 15.306(d) |
|  |  |  |  | X |  | NTIS / SCA Wage Determination | X | - Obtain Service Contract Wage Determinations |  |
| 4.8.1 | Receipt of Proposal Revisions | Receive proposal revisions as a result of ongoing exchange with Offerors. Reverse Auctions are a tool that can be used to conduct price and other discussions electronically including the receipt of revisions of the price or other factors. | BO |  |  |  |  |  | FAR 15.306d, 15.307 |
| 4.8.2 | Evaluation of Proposal Revisions | Evaluate technical proposal, price/costs, terms and conditions; Contracting Officer brings in additional expertise as required for review. This is an iterative process. | BO |  |  |  |  |  | FAR 15.305 |
| 4.8.3 | Conclusion of Exchanges | Common cut off date for final proposal revision. | BO |  |  |  |  |  | FAR 15.307(b) |
| 4.8.4 | Receipt of Final Proposal Revisions | Receive final proposal revisions as a result of conclusion of exchanges. | BO |  |  |  |  |  | FAR 15.307(b) |
| 4.9 | Pre-Award Surveys and Approvals | Verify eligibility of prospective awardee thru EEO clearance (as applicable), DCAA & DCMA | BO | X |  | DOL pre-award Website | x | - Check vendor EEO | FAR 9.1; 9.4; 22.805(a) |
|  |  |  |  | X |  | EPLS | X | - Obtain EPLS status |  |
|  |  |  |  |  |  | BPN | X | - Obtain EPLS status |  |
|  |  |  |  |  |  | D&B | X | - Check financials |  |
| 5.0 | Issue Award |  |  |  |  |  |  |  |  |
| 5.1 | Verify Funds Availability | Ensure sufficient funds are available for proposed award value. May be done for a guarantee minimum. | BO |  |  |  |  |  | FAR 32.702 |
| 5.2 | Prepare Award | Assemble and prepare award documentation. Execute procurement instrument. Multiple awards through a year /years off one single solicitation. | BO |  |  |  |  |  | FAR 14.408-1, 15.204, 15.504 |
| 5.3 | Prepare Management Award Information | Develop and submit federal procurement data regarding specific current award. | BO | X |  | FPDS | X | - Report Information | FAR 4.6 |
|  |  |  |  |  |  | GWAC Index | X | - Post award data |  |
| 5.4 | Issue Award Notices | Post required notices: - Pre-award notices under set- asides this is an intent to award to vendor (only for vendors in competitive range) - Congress (as applicable), - Post award notice (FBO); - Unsuccessful Offerors - DOL (as applicable) | BO | X |  | FBO | X | - Post award notice | FAR 5.303, 12.102 (b), 13.106-3(c) 14.409-1 (b), 15.503, DFARS 204.6; agency regs for reports to Congress |
|  |  |  |  | X |  | ECats | X | - Post vendor data to catalogs |  |
|  |  |  |  |  |  | DOL | X | - Inform Award of service based contract performance |  |
|  |  |  |  | X |  | Sub-net |  | - Post subcontracting opportunities |  |
|  |  |  |  | X |  | FACNET |  | - EDI Transaction |  |
| 5.5 | Distribute Award Document | Send document / notification to: - Finance office - OSDBU - Contractor - Contract Administration | BO | P |  | EDA | X | - Post all award documents to provide for internal notifications | FAR 4.201 |
|  |  |  |  |  |  | CADO | X | - Post contract award documents to provide for transparency and visibility |  |
| 5.6 | Perform Post Award Debriefing | One-on-one discussion with non-selected Offerors of the aspects of their proposal and top-level information of the winner only. Coordinate with Legal and Program Office | BO |  |  |  |  |  | FAR 14.409-1(b), 15.506 |
| 5.7 | Address Post-Award Protest | Resolve post award protests, thru Alternative Dispute resolution (ADR) or court. Rule 4 file is developed. This activity is coordinated with Legal Office. | BO | X |  | GAO website |  | - Conduct legal research | FAR 12.102(b), 13.106-3 (c), 14.408-8, 15.507, 33.1 |
|  |  |  |  | X |  | Court of Claims Web site |  | - Conduct legal research |  |
|  |  |  |  | X |  | Lexus/Nexus & Others |  | - Conduct legal research |  |
| 6. | Monitor Performance/Contract Administration |  |  |  |  |  |  |  |  |
| 6.1 | Conduct Post-Award Orientation | Conduct post award conferences exchanging information to verify baseline program performance, and to create consistent expectations between the contractor and government team. Activity may be worked in conjunction with PO and Administrative Contracting Officer (ACO). | BO |  |  |  |  |  | FAR 42.5 |
| 6.2 | Issue Notice to Proceed | Provide authority to proceed with contract performance. | BO |  |  |  |  |  | FAR 36.213(e) |
| 6.3 | Monitor & Document Performance | Communication and documentation between Government and Contractor regarding quality and timeliness. Accomplished by COTR under authority of Contracting Officer (PCO or ACO). | PO | x |  | DOD CPARS | x | - Post performance information | FAR 42, 46.4 |
|  |  |  |  | X |  | NIH CPS | x | - Post performance information |  |
|  |  |  |  | X |  | NASA PPDBS | x | - Post performance information |  |
|  |  |  |  | X |  | Army PPMIS |  | - Post performance information |  |
|  |  |  |  | X |  | FDIC |  | - Post performance information |  |
|  |  |  |  | X |  | Education |  | - Post performance information |  |
| 6.3.4 | Subcontracting Plans | This will include the 294/295 subsequent plans |  |  |  |  |  |  |  |
| 6.3.5 | Quarterly Sales Report | This is quarterly sales per company awarded |  |  |  |  | X | - Vendor Support Center |  |
| 6.3.6 | General Correspondence |  |  |  |  |  | X |  |  |
| 6.3.7 | Catalogs Data | There 3 possible types - Initial - Supplemental - Cumulative |  | X |  |  | X | - GSA Advantage |  |
| 6.4 | Process Contract Changes | Issue modifications or change orders. Contracting Officer working in coordination with PO, ACO, FO, & Legal. | BO |  |  |  |  |  | FAR 43 |
| 6.4.1 | Verify Funding | Ensure sufficient funds are available for proposed award value. | BO |  |  |  |  |  | FAR 32.702 |
| 6.4.2 | Prepare Management Award Information | Develop and submit federal procurement data regarding specific current award | BO | X |  | FPDS-NG | X | - Report Management Information | FAR 4.6 |
|  |  |  |  |  |  | GWAC Index | X | - Post award Management data on GWAC index as applicable |  |
| 6.4.3 | Issue Novation Agreements | Administrative modification to the contract due to changing contractor name, banking information, and addresses. ACO / PCO must approve name change. | BO |  |  | BPN | X | - Notification of name change | FAR 42.12 |
| 6.5 | Assignment of Claims | Re-designate remittance entity. | BO |  |  | BPN | X | - Change payee (EFT) | FAR 32.8 |
| 9. | Close Out |  |  |  |  |  |  |  |  |
| 9.1 | Certify All Work has been Completed | Check that all requirements under contract have been satisfactorily met and that there are no outstanding claims or judgments. | PO |  |  |  |  |  | FAR 4.804-5(a) |
| 9.2 | Settle Any Claims | Negotiate outstanding claims and obtain release of claims. | BO |  |  |  |  |  | FAR 4.804-5(a)(14) |
| 9.3 | Issue Final Past Performance Evaluation | Produce final performance evaluation identifying quality and timeliness throughout the history of the contract. | PO | X |  | DOD CPARS | X | - Update performance data for close-out | FAR 42.15 |
|  |  |  |  | x |  | NIH CPS | x | - Update performance data for close-out |  |
|  |  |  |  | x |  | NASA PPDBS | x | - Update performance data for close-out |  |
| 9.4. | Closeout based on IFF | Close out based on Industrial Funding Fee; last payment notice from vendor. |  |  |  |  |  |  |  |
| 9.5 | Maintain Archival Contract Files | Maintain official contract records in accordance agency procedures and NARA requirements. | BO |  |  | FPDS-NG | X | - Report close-out information (12c FPDS-NG requirement reason for modification “closed-out”) | FAR 4.805 |
|  |  |  |  |  |  |  | X | - Record Mgt per NARA |  |