Contract No:  _____________________________      Date:  _________________

Project Title:  ______________________________________________________

Project Location:  ___________________________________________________

NOTE TO THE CO AND EPM:

The Pre-Construction Conference Agenda must be discussed and agreed upon by all interested parties (CO, EPM, RPR, LM, AOE, A-E, and the Construction Contractor) before finalizing the document and conducting the Pre-Construction Conference.  The Pre-Construction Conference agenda must be edited for each project specific.  The CO will chair the conference or may delegate the chair to the EPM.

- 1.	PURPOSE/OBJECTIVE

The purpose of this meeting is to establish lines of communications, authority, and responsibilities, clarify procedures to be followed during construction, and discuss items of mutual interest as required by the Contract Documents.  Administration of the construction contract for this project will be performed by (A-E, name) with USDA.  The pre-construction conference will in no way change the contractor’s responsibility to follow the requirements of the contract documents.

2.	PRE-CONSTRUCTION MEETING AGENDA

2.1	Introductions and Sign In

- 2.2	Introductory Remarks, Project Acknowledgements, and Research Program 	Overview

- 2.3	Points of Contacts

- 2.3.1	Construction Contractor (CC)

- 2.3.2	Construction Management A-E and Construction Inspector:

- (CM &CI)

- 2.3.3	Design Architect-Engineer Firm (A-E)

- 2.3.4	Contracting Officer (CO)

- 2.3.5	Contracting Officer’s Representative (COR)

- 2.3.6	Engineering Project Manager (EPM)

- 2.3.7	Research Program Representative (RPR)

- 2.3.8	Location Monitor (LM)

- 2.3.9	Area Office Engineer/Facility Engineer (AOE/FE)

- 2.4	Roles and Responsibilities

- 2.4.1	Research Program Representative (RPR)	  (INSERT NAME)

The RPR serves as a resource to the Project Team, and is expected to notify the Contracting Officer (CO), the EPM and the Contracting Officer’s Representative (COR) if he/she becomes aware of unusual or important circumstances pertinent to the construction project.  The RPR has no responsibility for construction inspection or supervision.

- 2.4.2	Contracting Officer (CO)			  (INSERT NAME)

The CO is the legal Government representative to the Contractors. He/she is authorized to enter, administer, and terminate contracts on behalf of the Government.  The CO is the only member of the Project Team with the authority to obligate Government funds or change the contract.  The CO is responsible for ensuring that the contract performance complies with all contractual provisions, including, but not limited to, scope, budget, and schedule.  The CO is responsible for ensuring adequate contract performance and contract management, overseeing and conduct negotiations, and other actions necessary to protect the Government’s interest.

- 2.4.3	Engineering Project Manager (EPM)	  (INSERT NAME)

The EPM will serve as the lead point of contact and shall disseminate information to the appropriate Project Team members for their action and involvement, and also to the contractors for day-to-day business, working within the terms of the contract.  It is the responsibility of the EPM to see that all Project Team members are kept advised of the actions, plans, and progress of the project.

- 2.4.4	Contracting Officer’s Representative (COR)	  (INSERT NAME)

The assignment as COR is made at the beginning of the project by an official designation letter from the CO outlining the responsibilities, authority, and limitations.  The COR is responsible for interpreting technical data in the A-E, construction, and CIC contracts.  The COR is responsible for the review of progress and pay requests for these contracts and making acceptance/rejection recommendations to the CO.  The COR may approve minor changes to the project that do not affect the program requirements, price, scope, and performance time of the contracts.

- 2..4.5	Area Office Engineer (AOE)		  (INSERT NAME)

The AOE will provide assistance to the Project Team and is invited to participate in progress meetings, equipment testing, and final inspections.  The AOE may serve as the COR on some projects.

- 2.4.6	Design A-E, Construction Phase (A-E) 	  (INSERT FIRM)

The A-E firm is the principal interpreter of the technical intent of the drawings.  The A-E shall review and approve/disapprove shop drawings as meeting/not meeting the intent of the design, and provide recommendations for approval/disapproval for those items which require CO approval, and forwarding them to the CO and COR.  The A-E shall monitor and inspect construction as specified in their Task Order/Contract to assure conformity with the requirements of the design.  In the event any difference may arise between the A-E and the construction contractor, the A-E shall immediately inform the CO and the COR providing details of pertinent facts and his/her recommendation of actions to be taken.

- 2.4.7	Construction Inspector (CI)			  (INSERT NAME)

When CI is required, the A-E shall provide a qualified inspector for proper control during all times of the construction-monitoring phase as specified in the A-E’s contract, whether it be full-time or part time.  The inspector shall examine the construction to assure conformance to the design intent, perform quality assurance functions, witness tests and record results.  The function of the inspector is to observe, record, maintain requisite documentation, and refer actions to the A-E for interpretation of conformance to design intent and to the CO and COR for those items which require contract interpretation.

2.4.8	Location Monitor (LM)			  (INSERT NAME)

The LM is an ARS representative at the construction site and is formally designated by the CO, the LM serves as a point of contact for the A-E, Construction Inspection Contractor (CIC), or the Construction Contractor to provide information regarding location rules and regulations.

- 2.5	Team Remarks and Expectations

- 2.5.1	Project Overview:  The RPR will provide research program overview, program objectives, and expectations.

- 2.5.2	Design Architect-Engineer:  Design intent, design philosophy, and over all design overview.

- 2.5.3	A-E, Construction Phase:  Project Inspection, quality assurance, and commissioning.

- 2.5.4	Construction Contractor:  Contract execution, construction methodology, and sequence.

- 2.6	Contract Requirements

- 2.6.1	Regular work Hours ___A.M. to ___P.M. Monday-Friday, notify CO at least 7 calendar days prior to schedule any work outside regular work hours.

- 2.6.2	Severe weather (CO/EPM must edit as per location specific or delete the paragraph).

- 2.6.3	Contract Performance period, in accordance with the contract terms, this contract shall be completed within ___ calendar days after receipt of NTP.

- 2.6.4	Interruption to Government operation and schedule construction.

- 2.7	Notice To Proceed (NTP) will be issued after receipt and approval of:

- 2.7.1	Performance and Payment Bonds

- 2.7.2	Insurance Certificates, maintain the following insurance coverage as a minimum:

- 2.7.3	Comprehensive General liability:  $500,000 per occurrence

- 2.7.4	Automobile liability:  $200,000 per person, $500,000 per occurrence for bodily injury, $20,000 per occurrence for property damage.

- 2.7.5	Worker compensation in the amount required by Federal and State workers compensation and occupational disease laws.

- 2.7.6	Employer’s liability coverage of $100,000.

- 2.7.7	Progress and payment schedule:  The Schedule of Values may use ARS Form 371/372 or the AIA Document G702/G703, based on a cost loaded Network Analysis Schedule (NAS).  Three (3) copies shall be submitted to the A-E/CIC for review, and verification.  The A-E shall forward payment recommendations to the CO for final approval.  Information will come from the Contractor’s Schedule of Prices.  Subdivisions shall be mutually agreeable to by CO and A-E firm.

- 2.7.8	Statement and Acknowledgement (Form SF 1413) from each subcontractor.

- 2.7.9	NTP – (Date)

- 2.7.10	Groundbreaking Ceremony

- 2.7.11	Completion Date

- 2.8	On-Site Construction Start:  Prior to construction start the following 	submittals must be submitted to the CO for approval:

- 2.8.1	Quality Control Plan, Section 01XXX

- 2.8.2	Have a meeting on Quality Control mutual understanding,

- Section 01XXX

- 2.8.3	Obtain digging permit

- 2.8.4	Environmental Protection Plan, Section 01XXX

- 2.8.5	The Preliminary Network Analysis must be reviewed and approved.

- 2.8.6	Submit resumes for key personnel to the CO for approval:  Project Manager, Superintendent, Quality Control Manager, Scheduler, Safety Officer, etc. (review the contract document for personnel requirements).

- 2.8.7	Construction site plan showing construction trailer location, staging area and other major construction site components.

- 2.8.8	Accident Prevention Plan/Safety Plan, Section 01XXX.

- 2.8.9	Waste Management Plan, Section 01XXX

- 2.8.10	Storm Water Management and Sediment Control Permits,

- Section 01XXX.

- 2.8.11	The construction contractor (CC) shall provide to the CO a list of contract personnel of the general and subcontractors, who will be emergency contacts, including address, and telephone numbers for use in an emergency.  As changes occur and additional information becomes available, the CC shall update the list.

- 2.9	Contract Administration

- 2.9.1	The CO has the overall contract administration responsibility regarding contractual matters.  During his/her absence, this responsibility will be delegated to personnel designated to act in his/her capacity.

- 2.9.2	Correspondences relative to the interpretation of the contract documents shall be addressed to the CO with copies to the EPM, COR, and the A-E.  All questions pertaining to payrolls, labor provisions, bonds etc., shall be sent to the CO. (Sample list attached)

- 2.9.3	Superintendent:  Adequate full-time supervision of the contractor’s employees and subcontractors is required at all times.  The Government will not take the responsibility of acting for the prime contractor’s superintendent.

- 2.9.4	Housekeeping:  During construction, the contractor shall dispose of the resultant dirt and debris each workday and keep the premises clean.  Dust control measures will be enforced.

- 2.9.5	Utilities:  The contractor shall provide all temporary utilities required for construction and until beneficial occupancy or Government accepting the facility.  If it is agreeable with the LM and the COR, the contractor may use location utilities; however, the contractor shall be responsible for connection and disconnection expenses.  Contractor shall coordinate through the LM and give 2 weeks notice.

- 2.9.6	Toilet Facilities:  The contractor shall provide toilet facilities for all his employees including subcontractors.  Toilet facilities shall comply with State and local regulations and shall be maintained in neat sanitary condition.  The location of such accommodations will be subject to the LM approval.

- 2.9.7	Responsibility of Subcontractors:  The prime Contractor is responsible for all actions of their subcontractors.  The Government has no contractual relationship with subcontractors or suppliers.

- 2.9.8	The Contractor shall keep an updated record drawings and specifications on site at all times.  The Contractor also shall keep all approved shop drawings and submittals on site at all the times.

- 2.9.9	Liquidated Damages:  Refer to Section xxx of the contract, $_____ per each calendar day.

- 2.9.10	Delays:  Any requests for time extensions shall be accompanied by an explanation with supporting proof.  The contractor is expected to complete the project for acceptance and occupancy within the contract period.  We emphasize the importance of completely documenting and notifying the CO of any cause for delay, before the delay actually occurs.

- 2.9.11	Project Sign and Construction Office Trailer or Building:  The contractor shall coordinate sign locations with the LM.  The construction office should be located as conveniently as possible, yet not interfering with the work progress.  A project sign is not a contract requirement and, if agreed to, shall be at the contractor's expense.

- 2.9.12	Construction Entrance and Staging Area:  The contractor shall coordinate construction entrance and staging area locations with the LM.  The construction entrance shall be constructed as per local/State codes and standards.

- 2.9.13	Request for Information Process (RFI):  All RFI’s will be numbered sequentially and submitted to the A-E with copies to the CO, EPM, and COR. Verbal communications for technical clarifications and field directions may be referred directly to the CI and the COR.  Discrepancies not readily resolved shall be referred to the CO, EPM, and COR.  Only the CO can make changes to the contract amount, period of performance, and specifications.

- 2.9.14	Field Conditions - Changes

- 2.9.14.1	Minor:  The COR is authorized to make minor changes to meet field conditions not involving price, scope, performance period, or other contract terms.  The CO shall be promptly notified if an emergency occurs.

- 2.9.14.2	Major:  Major changes, which affect the contract price, terms, or conditions, specifications, and performance period must be approved by the CO and documented by change order signed by the CO.

- 2.9.15.	Access to the Site:  Government engineers and contracting personnel shall be allowed access to the project at all times while work is in progress.  Others may visit the site only with permission of the COR or LM.  The CO, COR, or LM shall be informed of all suspected unauthorized Individuals or other suspicious activity.

- 2.9.16	EEO requirements and posters shall be Permanently displayed on job site.

- 2.9.17	Payrolls:  It is the responsibility of the prime contractor to review contractor and subcontractor's payrolls to ensure that they are properly prepared.  Payrolls are due weekly to the CI/A-E.  Final payment will not be made until all payrolls have been submitted.  The CI/A-E will perform a cursory review of payroll compliance with the DOL Wage Determination on a monthly basis, and perform cursory periodic labor interviews on monthly basis.   The CI/A-E will forward the reviewed payroll and associated documentation with recommendation to the CO for final approval and processing.

NOTE TO THE CO AND EPM:

Payment Procedures:  The CO and EPM must discuss the Schedule of Values (Section 01370). The Schedule of Values will subdivide the contract effort into defined phases or area of building, specification section, materials, equipment, labor, bond, and general conditions items.  The Schedule of Values may use ARS form 371/372, the AIA Document G702/G703, based on cost loaded Network Analysis Schedule (NAS).  Information will come from the Contractor’s Schedule of Values.  Subdivisions shall be mutually agreeable to by Contracting Officer and A-E firm.

- 2.10	Application for Payment Procedures

- 2.10.1	The Contractor shall complete and sign Contractor’s Request for Payment Transmittal ARS Form 371 or Application and Certificate for Payment AIA Document G702, along with a Schedule of Values identifying the work accomplished to date using ARS Form 372, AIA Document G703, or a cost loaded Network Analysis Schedule in sufficient detail to allow ease of verification.  Schedule of values must be tied to the work completed and schedule.  The CO prior to any payment being made shall approve the initial schedule of values and NAS.

- 2.10.2	A “draft“copy and backup will be prepared for A-E review on the first of the month.

- 2.10.3	The A-E shall review all requests for payment by the CC.

- 2.10.4	Upon review and agreement of the facts, a final application will be typed, including adjustments and signed by the Contractor.  Final application shall be submitted within three (3) calendar days after the draft is approved.  The subcontractors’ and suppliers’ applications will be attached.

- 2.10.5	The A-E shall review the CC’s certified payroll, and assure compliance with all wage and labor requirements.  The A-E shall immediately notify the CC and the CO through the EPM of delinquent payrolls or errors and omissions found during review.

- 2.10.6	The A-E will submit an approval recommendation within three (3) workdays and forward to the CO with copy concurrently to the COR.

- 2.10.7	The COR will review and recommend approval/disapproval and submits to the CO for approval.

- 2.10.8	The CO is responsible for approval and processing payment request.

- 2.10.9	The Government will make payment to the Contractor on a schedule consistent with the Prompt Payment Act.  Payments will be made by the Electronic Funds Transfer (EFT) procedure.  Upon award the contractor shall contact the Miscellaneous Payment Section at the National Finance Center (NFC) to initiate the enrollment process of the Vendor Express Program (VEP). The VEP will assign a number to contractor for payment under the EFT.  NFC can be reached at 1-800-421-0323.

- 2.10.10	Final payment

- 2.10.10.1	The final payment request shall be accompanied by the Final Release Form which shall contain the Contractor’s Corporate Seal.  A corporate officer shall sign the release and be certified by a corporate secretary.

- 2.10.10.2	Release of claims - Before final payment, the contractor must release the Government from claims.  This release states:

“For and in consideration of the receipt of final payment in the amount of $_____ under and pursuant to Contract No._________, the undersigned hereby releases the Government from any and all obligations whatsoever arising under said Contract.

Signature  _________________    Date  _________

- 2.10.10.3	Withholding Payments:

- 2.10.10.3.1	Contractor will not request any payment for work not in compliance with Contract Documents.

- 2.10.10.3.2	The Government may withhold payment if work is not in compliance with Contract Documents, Federal or State Laws/Regulations, or has reason to believe that the balance of the work will not be completed within the contract time.

- 2.10.11	Payment for Stored Material and Equipment

- 2.10.11.1	The CO must approve payment for material and equipment stored off-site in advance.  The CO will require certificates of property insurance or require items to be stored in a bonded or insured warehouse.  If the CO approves requests; amount may be included in Application for Payment.

- 2.10.11.2	The Government retains the right to enter the premises where the materials and equipment are stored for verification, inspection, checking, auditing, or for any purpose considered necessary to protect the Government interest.

- 2.10.11.3	The Contractor must also provide updated inventory indicating which items are still in storage, which items were removed from storage, and under which application payment it was included.

- 2.11	Contractor Quality Control (CQC) and Quality Control (QC) Personnel

- 2.11.1	The CQC plan shall be based on the three-point inspection procedure, initial, follow up, and final phases.

2.11.2	The CQC organization shall include Quality Control System Manager (QCSM) to ensure the safety and contract compliance.  The QCSM qualifications shall be submitted to the Government for approval.  The QCSM shall have a minimum of ____ year’s construction experience similar to the subject contract.  Failure to submit the appropriate experience will be the basis to stop the work on site until the contractor provides the appropriate experienced personnel.

2.12	A-E Construction Inspector and A-E Role

2.12.1	The CI shall conduct ____ visits weekly.

The CI will have a resident office located on the site.

2.12.2	The A-E shall provide submittal review, monitor and inspect work, note unsafe conditions to the contractor, maintain a project diary, make recommendations on time extensions and changes, and compare as built data and drawings.

2.13	Record Drawing and Specifications

2.13.1	As-Built Drawings

2.13.1.1	The Contractor’s QCSM is required to ensure the as-built drawings and specifications required by Section 01770 “Closeout Procedure,” are kept current on a daily basis and marked to show deviations, which have been made from the contract drawings.

2.13.1.2	The QCSM at the completion of the work shall furnish a certificate of compliance prior to submission to the CO.

2.13.2	Record Drawings and Specification

2.13.2.1	The A-E shall review the CC’s as-built drawings and specifications to assure accuracy.

2.13.2.2	The A-E shall provide a set of record drawings on mylar and a set of paper specifications, and also on electronic media CD, using the design documents and the as-built provided by the Contractor.  The A-E will stamp the term “Record Documents” and date and sign all sheets of the mylar and the title page of the specifications.

2.13.3	Operations and Maintenance Manuals

2.13.3.1	On or before completion of project construction, the

A-E shall give to the facility director/manager, a package of all operation and maintenance data, and manuals received from the Contractor, after first verifying their completeness and accuracy.

2.13.4	Contract Close Out Process.  Refer to Section C.8.3.10 and C.8.3.11 for construction close-out process, in accordance with

A-E Statement of Work version 2.7.