## Weekly Update 20090410
No. | Financial and Activity Report (sheet 1 of 2) Version 1.3
| Agency Name: | Department of Defense
| Week End Date: | 2009-04-10
| Submitter Name: | Department of Defense
Submitter Contact Info:
| Agency / Bureau | TAFS | Sub-Account Code (OPTIONAL) | Total Obligations | Total Gross Outlays
1 | (007-10) Department of Defense--Military: Operation and Maintenance | (17-1116 2009 \ 2010) Operation and Maintenance, Marine Corps - Recovery Act
2 | (007-10) Department of Defense--Military: Operation and Maintenance | (17-1117 2009 \ 2010) Operation and Maintenance, Marine Corps Reserve - Recovery Act |  | 2756000
3 | (007-25) Department of Defense--Military: Military Construction | (17-1206 2009 \ 2013) Military Construction, Navy - Recovery Act |  | 499916
4 | (007-20) Department of Defense--Military: Research, Development, Test, and Evaluation | (17-1320 2009 \ 2010) Research, Development, Test, and Evaluation, Navy - Recovery Act |  | 390400
5 | (007-10) Department of Defense--Military: Operation and Maintenance | (17-1805 2009 \ 2010) Operation and Maintenance, Navy - Recovery Act |  | 16526346
6 | (007-10) Department of Defense--Military: Operation and Maintenance | (17-1807 2009 \ 2010) Operation and Maintenance, Navy Reserve - Recovery Act
7 | (007-30) Department of Defense--Military: Family Housing | (21-0721 2009 \ 2013) Family Housing Construction, Army - Recovery Act
8 | (007-30) Department of Defense--Military: Family Housing | (21-0726 2009 \ 2010) Family Housing Operation and Maintenance, Army - Recovery Act
9 | (007-10) Department of Defense--Military: Operation and Maintenance | (21-2022 2009 \ 2010) Operation and Maintenance, Army - Recovery Act
10 | (007-20) Department of Defense--Military: Research, Development, Test, and Evaluation | (21-2041 2009 \ 2010) Research, Development, Test, and Evaluation, Army - Recovery Act
11 | (007-25) Department of Defense--Military: Military Construction | (21-2051 2009 \ 2013) Military Construction, Army - Recovery Act
12 | (007-10) Department of Defense--Military: Operation and Maintenance | (21-2066 2009 \ 2010) Operation and Maintenance, Army National Guard - Recovery Act
13 | (007-10) Department of Defense--Military: Operation and Maintenance | (21-2081 2009 \ 2010) Operation and Maintenance, Army Reserve - Recovery Act
14 | (007-25) Department of Defense--Military: Military Construction | (21-2094 2009 \ 2013) Military Construction, Army National Guard - Recovery Act
15 | (007-30) Department of Defense--Military: Family Housing | (57-0743 2009 \ 2013) Family Housing Construction, Air Force - Recovery Act
16 | (007-10) Department of Defense--Military: Operation and Maintenance | (57-0748 2009 \ 2010) Family Housing Operation and Maintenance, Air Force - Recovery Act
17 | (007-25) Department of Defense--Military: Military Construction | (57-3307 2009 \ 2013) Military Construction, Air Force - Recovery Act
18 | (007-10) Department of Defense--Military: Operation and Maintenance | (57-3404 2009 \ 2010) Operation and Maintenance, Air Force - Recovery Act |  | 1797929
19 | (007-20) Department of Defense--Military: Research, Development, Test, and Evaluation | (57-3605 2009 \ 2010) Research, Development, Test, and Evaluation, Air Force - Recovery Act
20 | (007-10) Department of Defense--Military: Operation and Maintenance | (57-3744 2009 \ 2010) Operation and Maintenance, Air Force Reserve - Recovery Act
21 | (007-25) Department of Defense--Military: Military Construction | (57-3834 2009 \ 2013) Military Construction, Air National Guard - Recovery Act
22 | (007-10) Department of Defense--Military: Operation and Maintenance | (57-3844 2009 \ 2010) Operation and Maintenance, Air National Guard - Recovery Act
23 | (007-XX) Department of Defense--Military - No Specific Bureau | (97-0112 2009 \ 2011) Office of the Inspector General - Recovery Act
24 | (007-XX) Department of Defense--Military - No Specific Bureau | (97-0150 2009 \ 2010) Defense Health Program - Recovery Act
25 | (007-20) Department of Defense--Military: Research, Development, Test, and Evaluation | (97-0401 2009 \ 2010) Research, Development, Test, and Evaluation, Defense-wide - Recovery Act
26 | (007-25) Department of Defense--Military: Military Construction | (97-0501 2009 \ 2013) Military Construction, Defense-wide - Recovery Act
27 | (007-30) Department of Defense--Military: Family Housing | (97-4091 \ X ) Homeowners Assistance Fund - Recovery Act |  | 155331 | 139388
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | Cumulatively DoD has obligated $22,125.9 thousand. | Navy plans to award at least 1 FSRM project next week. This project is for Parking Garage Repairs, NMIC, Suitland, MD, $5,600 thousand.
2 | This week Navy awarded five Facility Sustainment Restoration and Modernization (FSRM) projects totaling $7,880K. These include Replacing Roof Mounted Boilers on Bachelor Quarters (BQ) 3144 & 3150, Naval Station San Diego, CA, $884K; Replace Metal Roof, BQ, Naval Air Station North Island, CA, $637K; Replace Fire Detection Devices, BQ Building 72, NSA, Washington, DC, $1,024K; Replace Elevators #37 and #40 Building 171, Norfolk Navy Shipyard, VA, $1,835K; and Replace Heat, Ventilation and Air Conditioner and Modernize Boorda Hall BQ Complex, Buildings 3-34, Naval Station Great Lakes, IL $3,500K (in-house). | Air Force has 167 Military Family Housing Operations & Maintenance FSRM projects being readied for contract obligation award. Many of these projects will be awarded in the next 2 weeks.
3 | This week the first Air Force projects were awarded for $1,798K. These include $871K for Repair Asphalt Overruns at Gila Bend Air Force Auxiliary Field, AZ; $607K for Mill and Overlay overruns Runway 03R/21L at Luke AFB, AZ; $190K for Runway Repair at McChord AFB, WA; and $130K for correction of an airfield obstruction at Tyndall AFB, FL. | Army's first Military Construction project award (Ft Bliss, Warrior Transition Complexes, $57,000K) is in the final stages of the source selection process. Award is expected shortly.
4 | This week Navy obligated $8,647 thousand to the Naval Facilities Engineering Command for pre/post award contract support for 25 projects. | All services are gathering data in preparation for the 30 Apr submittal of the second report to the White House Council on Environmental Quality on National Environmental Protection Act/National Historic Preservation Act requirements.
5 |  | DoD is finalizing our Homeowner's Assistance Program guidance and expects to publicly announce those guidelines soon.
6 |  | DoD will submit our second FSRM project list for the balance of the remaining projects to Congress.
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34