| JURISDICTION (facility, agency, local, regional, state) | [2007 – 2008] |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Qtr 1 |  |  | Qtr 2 |  |  | Qtr 3 |  |  | Qtr 4 |  |  |
|  | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG |
| DSHS HQ – Statewide SNS exercises with Pan Flu components | Seminar to discuss exercise planning | Exercise scenario planning and coordination meeting |  | <--------- | Workshops and training in preparation for FY09 FS exercise | ---------- |  |  |  | <----- | Tabletop Exercises | ----- |
| DSHS HQ – Statewide Hurricane exercises | Seminar to discuss exercise planning |  |  | Seminar; workshop, training, and conference | Planning meetings | Workshops and Tabletop Exercises | Workshops and Tabletop Exercises | Evacuation Drills | Functional Exercise |  |  |  |
| DSHS HQ – Highly Pathogenic Avian Influenza (HPAI) Rapid Response | Seminar to conduct planning | Planning meetings | Planning meetings | Train the trainer, workshop, and tabletop exercise |  |  |  |  |  |  |  |  |
| DSHS HQ – Continuity of Operations (COOP) | Plan develop-ment meetings | Planning meetings | Planning meetings | Updates to COOP Plan |  | COOP pilot exercise – Tabletop Exercise |  | COOP Functional Exercise |  |  |  |  |
| DSHS HQ - participating with U.S. DOE and locals in WIPP TREX exercise (Radiological Incident) | *Planning, training, and Tabletop Exercise | Pre-exercise coordination meetings and Full Scale Exercise |  |  |  |  |  |  |  |  |  |  |
| DSHS Region 7 -participating with City of Waco and the U.S. Postal Service in BDS exercise | *Tabletop Exercise, Functional Exercise, and Full Scale Exercise |  |  |  |  |  |  |  |  |  |  |  |
| DSHS Region 2/3 -participating with the Governor’s Division of Emergency Management and the North Central Texas COG in Regional Tactical Communications Exercises |  | Tabletop Exercise | Functional Exercise | Tabletop Exercise |  |  |  |  |  |  |  |  |
| DSHS Region 2/3 - EOC and RSS exercises | Seminar to discuss exercise planning |  |  |  |  |  | March 11 – RSS staff training March 25 – Functional Exercise |  |  |  |  |  |
| DSHS Region 6/5S - Pan Flu Exercise |  | Training, Tabletop Exercise, and Drill |  |  |  |  |  |  |  |  |  |  |
| DSHS Region 7 - conducting SNS/Pan Flu exercise at a POD location | *Pre-exercise meeting and workshop | Functional Exercise |  |  |  |  |  |  |  |  |  |  |

*Planning, meetings, and ramp-up activities occurred during previous funding cycle (2006-2007)