U.S. Department of Health and Human Services, National Institutes of Health

National Institute of Allergy and Infectious Diseases (NIAID)

RFP-NIH-NIAID-DAIT-07-33

“Collaborative Network for Clinical Research on Immune Tolerance”

| - OFFERORS ARE RESPONSIBLE FOR ROUTINELY CHECKING THE FOLLOWING WEBSITE FOR ANY SOLICITATION AMENDMENTS. NO ADDITIONAL NOTIFICATION OF ANY AMENDMENTS WILL BE PROVIDED BY THIS OFFICE. http://www.Fedbizops.gov |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - SECTION A – SOLICITATION/CONTRACT FORM -- PURCHASE AUTHORITY: FAR 1.602-1 NOTE: The issuance of this solicitation does not commit the government to an award. |  |  |  |  |  |  |  |  |
| - Issue Date: February 3, 2006 | - Due Date: June 5, 2006 Time: 3:00 PM, EST |  |  |  |  |  |  | - Small Bus. Set-Aside: [ ]Yes [X] No 8(a) Set-Aside: [ ]Yes [X] No (See Part IV, Section L.) |
| - Mandatory Qualification Criteria: None |  | - Number of Awards: [X] Only 1 Award [ ] Multiple Awards |  |  |  |  | - Technical Proposal Page Limits: Total not-to-exceed 300 pages. See APPENDIX A and http://www.niaid.nih.gov/contract/eproposal.htm |  |
| - Issued By: Erin Goldstein Contracting Officer Office of Acquisitions (OA) DEA NIH, NIAID 6700-B Rockledge Drive Room 3214, MSC 7612 Bethesda, MD 20892-7612 |  |  |  | [X] NIAID reserves the right to make awards without discussion. |  |  |  |  |
|  |  |  |  | 11. Pre-proposal Conference Not Applicable |  | 12. Period of Performance: 7 years beginning on or about February 1, 2007. |  |  |
| 13. Primary Point of Contact: Name : Erin Goldstein Phone: 301-496-6423 Fax: 301-402-0972 E-Mail: EGoldstein@niaid.nih.gov |  |  | 14. Secondary Point of Contact: Name: Deborah Blyveis Phone: 301-594-7211 Fax: 301-402-4675 E-Mail: db539e@nih.gov |  |  |  |  | 15. Protest Officer: Charles W. Grewe Director, OA Address (see Block 9.) |
| - COLLECT CALLS WILL NOT BE ACCEPTED. FACSIMILE SUBMISSIONS ARE NOT ACCEPTABLE. |  |  |  |  |  |  |  |  |
| - Offers will be valid for 120 days unless a different period is specified by the Offeror on the form entitled “Proposal Summary and Data Record, NIH-2043" (See SECTION J – Attachments) |  |  |  |  |  |  |  |  |
| 18. DELIVERY ADDRESS INFORMATION |  |  |  |  |  |  |  |  |
| Hand Delivery or Overnight Service: Erin Goldstein Office of Acquisitions (OA), DEA NIAID, NIH 6700-B Rockledge Drive, Room 3214 Bethesda, MD 20817 |  |  |  |  | ### U.S. Postal Service or an Express Delivery Service Erin Goldstein Office of Acquisitions (OA), DEA NIAID, NIH 6700-B Rockledge Drive, Room 3214, MSC 7612 Bethesda, MD 20892-7612 |  |  |  |
| - The Official Point of Receipt for the purpose of determining timely delivery is the address provided in Block 18, above. The paper copy with original signatures is the official copy for recording timely receipt. If the paper copy of your proposal is not received by the Contracting Officer or Designee at the place and time specified, then it will be considered late and handled in accordance with HHSAR 352.215-70 entitled "Late Proposals and Revisions" located in this Solicitation. FACSIMILE SUBMISSION OF PROPOSALS IS NOT ACCEPTABLE. |  |  |  |  |  |  |  |  |

DETAILED TABLE OF RFP CONTENTS

PART I - THE SCHEDULE……………………………………………………….………………………………………..	 4

SECTION B - SUPPLIES OR SERVICES AND PRICES/COSTS…………………………………………………		 5

ARTICLE B.1.  BRIEF DESCRIPTION OF SUPPLIES OR SERVICES……………………………………….	 5

ARTICLE B.2.  PRICES/COSTS……………………………………………………………………………………	 5

ARTICLE B.3.  PROVISIONS APPLICABLE TO DIRECT COSTS……………………………………………..	 5

ARTICLE B.4.  ADVANCE UNDERSTANDINGS…………………………………………………………………	 5

SECTION C - DESCRIPTION/SPECIFICATIONS/WORK STATEMENT………………………………………   .	 5

ARTICLE C.1.  STATEMENT OF WORK………………………………………………………………………..…	 5

ARTICLE C.2.  REPORTING REQUIREMENTS AND DELIIVERABLES………………………………………	 6

SECTION D - PACKAGING, MARKING AND SHIPPING…………………………………………………………...	13

SECTION E - INSPECTION AND ACCEPTANCE…………………………………………………………………..	13

SECTION F - DELIVERIES OR PERFORMANCE………………………………………………………………….	.	14

ARTICLE F.1.  PERIOD OF PERFORMANCE…………………………………………………………………	12

ARTICLE F.2.  DELIVERIES………………………………………………………………………………………..	14

ARTICLE F.3.  CLAUSES INCORPORATED BY REFERENCE, FAR 52.252-2 (FEBRUARY 1998)……………………………………………………………………………………………………………………	18

SECTION G - CONTRACT ADMINISTRATION DATA………………………………………………………………	18

ARTICLE G.1.  PROJECT OFFICER……………………………………………………………………………….	18

ARTICLE G.2.  KEY PERSONNEL………………………………………………………………………………...	19

ARTICLE G.3.  INVOICE SUBMISSION/CONTRACT FINANCING REQUEST……………………………….	19

ARTICLE G.4.  INVOICE SUBMISSION/CONTRACT FINANCING REQUEST AND CONTRACT FINANCIAL REPORT………………………………………………………………………………………………..	20

ARTICLE G.5.  LETTER OF CREDIT PAYMENT INFORMATION……………………………………………..	20

ARTICLE G.6.  CONTRACT FINANCIAL REPORT………………………………………………………………	21

ARTICLE G.7.  INDIRECT COST RATES…………………………………………………………………………	22

ARTICLE G.8.  GOVERNMENT PROPERTY……………………………………………………………………..	23

ARTICLE G.9.  POST AWARD EVALUATION OF CONTRACTOR PERFORMANCE……………………….	23

SECTION H - SPECIAL CONTRACT REQUIREMENTS…………………………………………………………..		24

ARTICLE H.1.  HUMAN SUBJECTS………………………………………………………………………………..	24

ARTICLE H.2. REQUIRED EDUCATION IN THE PROTECTION OF HUMAN RESEARCH PARTICIPANTS………………………………………………………………………………………………………..	24

ARTICLE H.3. DATA AND SAFETY MONITORING IN CLINICAL TRIALS……………………………………. 22

ARTICLE H.4.  HUMAN MATERIALS (ASSURANCE OF OHRP COMPLIANCE………..……………………	25

ARTICLE H.5.  HUMAN EMBRYONIC GERM CELL (HEGC) RESEARCH …………………………………..	22

ARTICLE H.6.  HUMAN EMBRYONIC STEM CELL RESEARCH……………………………………............	23

ARTICLE H.7   CONTINUED BAN ON FUNDING OF HUMAN EMBRYO RESEARCH……………………	26

ARTICLE H.8.  NEEDLE EXCHANGE……………………………………………………………………………..	26

ARTICLE H.9.  PRIVACY ACT………………………………………  …………………………………………….	26

ARTICLE H.10  ANIMAL WELFARE…………………………………………………………………….…………	26

ARTICLE H.11.  INTRODUCTION OF RODENTS AND RODENT PRODUCTS………………………………	26

ARTICLE H.12.  RESEARCH INVOLVING HUMAN FETAL TISSUE……………………………………… …	27

ARTICLE H.13.  OPTION PROVISION  …………………………………………………………………………..	27

ARTICLE H.14.  SUBCONTRACTING PROVISIONS……………………………………………………………	27

ARTICLE H.15.  SALARY RATE LIMITATION LEGISLATION PROVISIONS…………………………………	28

ARTICLE H.16.  INFORMATION SECURITY………………………………………………………………………	29

ARTICLE H.17.  ENERGY STAR REQUIREMENTS……………………………………………………………...	33

ARTICLE H.18. PUBLICATION AND PUBLICITY…………………………………………………………………	33

ARTICLE H.19.  PRESS RELEASES……………………………………………………………………………….	33

ARTICLE H.20. REPORTING MATTERS INVOLVING FRAUD, WASTE AND ABUSE………………………	34

ARTICLE H.21. YEAR 2000 COMPLIANCE……………………………………………………………………….	34

ARTICLE H.22.  ANTI –LOBBYING…………………………………………………………………………………	35

ARTICLE H.23.  LIMITATION ON USE OF FUNDS FOR PROMOTION OF LEGALIZATION OF CONTROLLED SUBSTANCES……………………………………………………………………………………..	36

ARTICLE H.24.  SHARING RESEARCH DATA………………………………………… .………………………	36

ARTICLE H.25.  POSSESSION USE AND TRANSFER OF SELECT BIOLOGICAL AGENTS OR TOXINS…………………………………………………………………………………………………………………	36

ARTICLE H.26.  HOTEL AND MOTEL FIRE SAFETY ACT OF 1990 (P.L. 101-391)………………………..	36

ARTICLE H.27.  PROHIBITION ON CONTRACTOR INVOLVEMENT WITH TERRORIST ACTITIVITIES…………………………………………………………………………………………………………	36

ARTICLE H.28  NIH POLICY ON ENHANCING PUBLIC ACCESS TO ARCHIVED PUBLICATIONS RESULTING FROM NIH-FUNDED RESEARCH………………………………………………………………….	38

ARTICLE H.29.  CONSTITUTION DAY…………………………………………..………………………………..	38

ARTICLE H.30.  OBTAINING AND DISSEMINATING BIOMEDICAL RESEARCH RESOURCES…………	35

PART II - CONTRACT CLAUSES………………………………………………………………………………………...	38

SECTION I - CONTRACT CLAUSES……………………………………………………….………………………...	38

ARTICLE I.2.  AUTHORIZED SUBSTITUTIONS OF CLAUSES………………………………………………...	38

ARTICLE I.4.  ADDITIONAL FAR CONTRACT CLAUSES INCLUDED IN FULL TEXT………………………	40

PART III - LIST OF DOCUMENTS, EXHIBITS AND OTHER ATTACHMENTS…………………………………….	42

SECTION J - LIST OF ATTACHMENTS……………………………………………………………………………....	42

PART IV - REPRESENTATIONS AND INSTRUCTIONS………………………………………………………………	46

SECTION K - REPRESENTATIONS, CERTIFICATIONS AND OTHER STATEMENTS OF OFFERORS……………………………………………………………………………………………………………….	46

SECTION L - INSTRUCTIONS, CONDITIONS AND NOTICES TO OFFERORS………………………..………	47

1.  General Information……………………………………………………………………………………………	42

2.  Instructions to Offerors……………………………………………………………………………….............	48

a. General Instructions……………………………………………………………………………………….	48

b. Technical Proposal Instructions…………...………………………………………………………………	63

c. Business Proposal Instructions…….............……………………………………………......	80

SECTION M - EVALUATION FACTORS FOR AWARD  …………………………………………………………	92		1.  General……………………………………………………………………….………………………….……	92

2.  Human Subject Evaluation……………………………………………….……………….…………………	92

3.  Evaluation of Options…………………………………………………………..………………………..……	95

4.  Evaluation of Data Sharing Plan……………………………………………….……………………………	96

5.  Evaluation of Model Sharing Plan…………………………………………………………………………… 	96

6.  Technical Evaluation Criteria……………………………………… ………………………………………..	 96

6.  Past Performance Factor…………………………………………………………………………………….	.99

7.  Extent of Small Disadvantaged Business Participation…………………………………………………..	100

SOLICITATION ATTACHMENTS INCLUDED IN THIS RFP…………………………………………………………	100

PART I - THE SCHEDULE

THE CONTRACT SCHEDULE SET FORTH IN SECTIONS B THROUGH H, HEREIN, CONTAINS CONTRACTUAL INFORMATION PERTINENT TO THIS SOLICITATION. IT IS NOT AN EXACT REPRESENTATION OF THE PROPOSED CONTRACT DOCUMENT.  CONTRACTUAL PROVISIONS PERTINENT TO THE OFFEROR (I.E., THOSE RELATING TO THE ORGANIZATIONAL STRUCTURE [E.G., NON-PROFIT, COMMERCIAL] AND SPECIFIC COST AUTHORIZATIONS UNIQUE TO THE OFFEROR'S PROPOSAL AND REQUIRING CONTRACTING OFFICER PRIOR APPROVAL) WILL BE DISCUSSED IN THE NEGOTIATION PROCESS AND WILL BE INCLUDED IN THE RESULTANT CONTRACT.  HOWEVER, THE ENCLOSED CONTRACT SCHEDULE PROVIDES ALL THE NECESSARY INFORMATION FOR THE OFFEROR TO UNDERSTAND THE TERMS AND CONDITIONS OF THE RESULTANT CONTRACT.

SECTION B - SUPPLIES OR SERVICES AND PRICES/COSTS

ARTICLE B.1.  BRIEF DESCRIPTION OF SUPPLIES OR SERVICES

The purpose of this effort is to recompete the “Collaborative Network for Clinical Research on Immune Tolerance,” an international collaborative research effort coordinating clinical testing of new therapies to induce immune tolerance and improve treatments of autoimmune diseases, transplantation and allergies.  The Collaborative Network on Immune Tolerance hereafter called, “The Network “was first awarded in 1999.  The scope of work to be performed by the Network includes: 1) The design and conduct of Phase I-IV clinical trials of  investigational approaches intended to lead to a functional state of immune tolerance;  2) The design and conduct of mechanistic studies and the development of tolerance assays as integral components of these clinical trials;

3) Focused product development and nonclinical studies (e.g., toxicology, pharmacology, and pharmacokinetics, etc.) essential for the subsequent evaluation of experimental tolerance induction therapies in humans; and 4) the provision of bioinformatics, data management and analysis resources.

For this initiative, tolerance is broadly defined as specific lack of an immune response to targeted antigens (e.g. alloantigens, autoantigens, or allergens) by any of a variety of approaches including deletion, induction of anergy, immune deviation, sequestration, or suppression.  Approaches may target antigen specific receptors, molecules of the co-stimulation pathways, homing molecules, or other relevant approaches; and may use any of a variety of agents including antigen, peptides, altered peptides, monoclonal antibody blockade, cytokines, molecularly engineered cells or tissues, DNA vectors, or other relevant molecules.

ARTICLE B.2.  PRICES/COSTS

The final contract will contain the price/cost provisions agreed upon by the Government and the Offeror.  Options shall be priced separately.

ARTICLE B.3.  PROVISIONS APPLICABLE TO DIRECT COSTS

This article will prohibit or restrict the use of contract funds, unless otherwise approved by the Contracting Officer.  The following is a list of items that may be included in the resultant contract as applicable.   1) Acquisition, by purchase or lease, of any interest in real property; 2) Special rearrangement or alteration of facilities;  3) Purchase or lease of any item of general purpose office furniture or office equipment regardless of dollar value; 4) Travel Costs; 5) Consultant Costs; 6) Subcontract Costs; 7) Patient Care Costs; 8) Accountable Government Property; and 9) Research Funding.

ARTICLE B.4.  ADVANCE UNDERSTANDINGS

Specific elements of cost, which normally require prior written approval of the Contracting Officer before incurrence of the cost (e.g., foreign travel, consultant fees, subcontracts) will be included in this Article if the Contracting Officer has granted his/her approval prior to contract award.

SECTION C - DESCRIPTION/SPECIFICATIONS/WORK STATEMENT

ARTICLE C.1.  STATEMENT OF WORK

a.	Independently and not as an agent of the Government, the Contractor shall be required to furnish all the necessary services, qualified personnel, material, equipment, and facilities, not otherwise provided by the Government, as needed to perform the Statement of Work, dated January 30, 2006, attached hereto and made a part of this Solicitation  (See Section J - List of Attachments).

ARTICLE C.2.  REPORTING REQUIREMENTS AND DELIVERABLES

A.	Technical Progress Reports

In addition to the required reports set forth elsewhere in this Schedule, the preparation and submission of regularly recurring Technical Progress Reports will be required in any contract resulting from this solicitation.  These reports will require descriptive information about the activities undertaken during the reporting period and will require information about planned activities for future reporting periods.  The frequency and specific content of these reports will be determined prior to contract award.

For proposal preparation purposes only, it is estimated that 3 copies of these reports will be required as follows:

(X)	Quarterly

(X)	Annually

(X)	Final – Within 60 days prior to the expiration date of the contract

The requirements for the reports are described below:

1.	Quarterly Progress Report

The Contractor shall submit a Quarterly Progress Report within thirty (30) days of the close of each quarter.  The first reporting period consists of the first full three (3) calendar months of performance plus any fractional part of the initial month.  This report shall include a description of the activities during the reporting period, and the activities planned for the ensuing reporting period. A Quarterly Progress Report shall not be submitted when an Annual Progress Report is due.  Quarterly Progress Reports shall not exceed twenty (20) pages and shall include the following:

- Face page to include the contract number, contract title, performance period covered, Contractor’s name and address, telephone number, fax number, email address, and submission date.

- 4-6 page Executive Summary to include: a brief overview of the work completed and major accomplishments during the reporting period.

- Progress Report, to include a description of the following for each reporting period:

- The work performed and accomplishments achieved, including status of clinical trials and mechanistic studies (including those in development, active, on regulatory clinical hold, or completed);

- Technical, logistical, or financial problems encountered and how they were resolved;

- Lists of the clinical study final reports submitted within the quarter.  Formats of the reports to be compliant with ICH E6 guidelines.

- A list, description, and status report regarding all reagents produced or in production;

- A list, description, and status report regarding all nonclinical studies conducted;

- A list and description of laboratory facilities established;

- A list, description and justification of all subcontracts established or terminated;

- A list and brief description of all substantive partnerships involving industry, government-funded clinical research programs, or foundations.  The description must  outline the goals of the partnership, obligations of the individual partners, and progress in meeting the major objectives;

- A discussion of progress on the development and operations of bioinformatics activities; and

- Key personnel changes.

- Copies of manuscripts and abstracts published or submitted for publication completed for each quarter.

- A full disclosure of any inventions and patent or copyright applications submitted or in development.

- Annual Progress Report

The Contractor shall submit an Annual Progress Report thirty (30) days after the close of each annual performance period.  This report shall include a summation of the results of the entire contract work for the period covered.  An Annual Report shall not be required for the period when the Final Report is due.      Annual Progress reports shall not exceed one hundred (100) pages and shall include the following for each performance period:

  - Face page to include the contract number, contract title, performance period covered, Contractor’s name and address, telephone number, fax number, email address, and submission date.

4-6 page Executive Summary to include: a brief overview of the work completed, and major accomplishments.

  - A description of:

    - The work performed and accomplishments achieved, including status of clinical trials and mechanistic studies (including those in development, active, on regulatory clinical hold, or completed);

    - Technical, logistical, or financial problems encountered and how they were resolved;

    - A list, description, and status report regarding all reagents produced or in production;

    - A list, description, and status report regarding all nonclinical studies completed, ongoing or in development;

    - A list, description and status of Final Study Reports for trials completed during the reporting period;

    - A list, description and justification of laboratory facilities established and current measures of quality assurance and quality control measures;

    - A list, description and status report of tolerance assays established or under development;

    - A list and description of standard operating procedures for the conduct of mechanistic studies;

    - A list and justification of all subcontracts established or terminated;

    - Key personnel changes;

    - A list and brief description of all substantive partnerships involving industry, government-funded clinical research programs, or foundations.  The description must outline the goals of the partnership, obligations of the individual partners, and progress in meeting the major objectives;

    - Documentation of bioinformatics system and software requirements and progress.  Requirements updates shall address all issues that may arise due to modified or newly discovered requirements, as well as software lifecycle issues. This section of the report shall also explain the benefits delivered by the system of databases and technical support work, discuss any barriers to implementation and how they have been addressed, discuss the current and needed functions of the platform based on a thorough understanding of end-user requirements, and include the annual Automated Information System Security Report; and

    - Documentation of computer and data system security. The documentation shall include:

      - A log or record of the results from testing the Continuity of Operations Plan (COOP), any existing plans and progress reports for implementing additional security safeguards and controls; and the system access authorization list.  The profile shall be kept up-to-date for review and potential inspection upon demand by NIH/DHHS authorized agents.  Upon request, copies of specified profile documents shall be presented to NIH/DHHS for its own system's security reporting purposes.

      - System Security Plan.  The preparation of the System Security Plan shall follow the instructions in OMB Bulletin 90-08 (http://irm.cit.nih.gov/itmra/omb90-08.html).

      - Describe revisions or proposed revisions to the Network Strategic Plan and Research Agenda.

    - Update of the scientific administration plan, including the plans and rationale for the redirection of Network resources.

    - Summary of Network progress toward identification of biomarkers of the induction, maintenance, and loss of tolerance.

    - List of Final Study Reports and Quarterly Progress Reports for the entire reporting period and as well as manuscripts and abstracts published or submitted for publication.

    - A status report on all clinical trials summarizing adherence to, and deviations from, projected timelines for protocol development, implementation, and completion.  The report must outline steps taken, or to be taken, in the next quarterly reporting period to address significant deviations.

    - A financial status report summarizing invoiced expenditures and the Contractor’s best estimates of actual costs incurred (invoiced plus those to be invoiced) and projected future costs.  The report must detail the relevant expenditures and projected expenditures for each clinical trial and mechanistic study, and those costs and cost projections for individual mechanistic laboratory facilities, taking into account deviations from projected timelines for completion of studies.

    - Full disclosure of any inventions, and patent or copyright applications submitted or in development.

    - A report summarizing the Network’s reporting and management of Conflict of Interest.  At a minimum, the report must provide anonymous summary data regarding real and potential conflicts of interest and the steps taken to address these issues.

3.	Annual Progress Report for Clinical Research Study Populations

The Contractor shall submit information about the inclusion of women and members of minority groups and their subpopulations for each study being performed under this contract.  The contractor shall submit this information in the format indicated in the attachment entitled, "Inclusion Enrollment Report," which is set forth in Section J of the contract.  The contractor also shall use this format, modified to indicate that it is a final report, for reporting purposes in the final report.  The contractor shall submit the report in accordance with ARTICLE F.1. DELIVERABLES of the contract. In addition, the NIH Policy and Guidelines on the Inclusion of Women and Minorities as Subjects in Clinical Research, Amended, October 2001 applies.  As the Statement of Work includes conduct of Phase III clinical trials, see II.B of these guidelines.  The Guidelines may be found at the following website: ().

Include a description of the plans to conduct analyses, as appropriate, by gender and/or racial/ethnic groups in the clinical trial protocols as approved by the IRB, and provide a description of the progress in the conduct of these analyses, as appropriate, in the annual progress report and in the final report.  If the analysis reveals no subset differences, a brief statement to that effect, indicating the subsets analyzed, will suffice.  The Government strongly encourages inclusion of the results of subset analyses in all publication submissions.  In the final report, the Contractor shall include all final analyses of the data on gender and race/ethnicity.

4.	Final Report

The Final Report shall consist of a description of the work performed and results obtained for the entire contract period of performance as stated in Section F of this contract.  This report shall be in sufficient detail to describe comprehensively the results achieved.  The Final Report shall be submitted sixty (60) calendar days prior to the contract performance end date.  The Final Report shall include the following;

  - Face page to include the contract number, contract title, performance period covered, Contractor’s name and address, telephone number, fax number, email address, and submission date.

  - Introduction covering the purpose and scope of the contract effort including a summary of the major accomplishments (not to exceed 500 words) during performance of the contract.

  - An Executive Summary to include fulfillment of the contract goals and specific activities set forth in the Statement of Work.  Executive Summary should not exceed 25 pages.

  - A detailed description of the work performed (as described for the Annual Reports), the results obtained, and the impact and implications of the results on the scientific community and the public health of the Nation.

  - A list of all manuscripts published and in preparation and abstracts presenting work performed under the contract.

  - A report outlining the status of all partnerships with industry, Government-funded clinical research programs, and foundations.

  - List of all Government-furnished property, including reagents that could be made available to the successor contractor or returned to the Government.

- Summary of Salient Results

The Contractor shall be required to prepare and submit, with the Final Report, a summary (not to exceed 200 words) of salient results achieved during the performance of the contract.  This report shall be required 60 days before the contract completion date.

C.	Other Reports/Deliverables

      - Human Subjects IRB Annual Report (Formerly form 310, currently OMB 0990-0263 or other)

      - Invention Report Requirement -

All reports and documentation required by FAR Clause 52.227-11 including, but not limited to, the invention disclosure report, the confirmatory license, and the government support certification, shall be directed to the Office of Extramural Inventions and Technology Resources Branch, OPERA, NIH, 6705 Rockledge Drive, Room 1040 A, MSC 7980, Bethesda, Maryland 20892-7980 (Telephone: 301-435-1986).  In addition, one copy of an annual utilization report, and a copy of the final invention statement, shall be submitted to the Contracting Officer.  The final invention statement (see FAR 27.303(a)(2)(ii)) shall be submitted on the expiration date of the contract to the Contracting Officer.

The final invention statement (see FAR 27.303(a)(2)(ii)) shall be submitted on the expiration date of the contract to the following address:

Contracting Officer

Office of Acquisitions

DEA, NIAID, NIH, DHHS

6700-B Rockledge Drive, Room 3214, MSC 7612

Bethesda, Maryland  20892-7612

(Express Mail: Bethesda, MD 20817)

If no invention is disclosed or no activity has occurred on a previously disclosed invention during the applicable reporting period, a negative report shall be submitted to the Contracting Officer at the address listed above.

To assist contractors in complying with invention reporting requirements of the clause, the NIH has developed "Interagency Edison," an electronic invention reporting system.  Use of Interagency Edison is encouraged as it streamlines the reporting process and greatly reduces paperwork.  Access to the system is through a secure interactive Web site to ensure that all information submitted is protected.  Interagency Edison and information relating to the capabilities of the system can be obtained from the Web (http://www.iedison.gov), or by contacting the Office of Extramural Inventions and Technology Resources Branch, OPERA, NIH.

      - Source Code and Object Code - Unless otherwise specified herein, the Contractor shall deliver to the Government, upon the expiration date of the contract, all source code and object code developed, modified, and/or enhanced under this contract.

      - Industry Liaison - Within two months of the award of the contract, the Contractor shall submit to the NIAID Project Officer a plan to identify and capitalize on opportunities for industry partnerships to accomplish the goals and objectives described in the Network Research Agenda for review and approval.

      - Strategic Plan and Research Agenda- Within two months of the award of the contract, the Contractor shall submit to the NIAID Project Officer a final Strategic Plan and Research Agenda addressing the requirements outlined in the Statement of Work for review and approval.

      - Network Executive and Steering Committees - Within 120 days after award, the Network Executive Committee shall submit to the NIAID Project Officer recommendations of appointees to the Executive and Protocol Review Committees.  In addition, the Network Executive Committee shall submit final proposed Network bylaws, policies, and standard operating procedures for all aspects of Network activities to the NIAID Project Officer for review and approval.

      - Nonclinical Research and Product Development Final Study Reports

        - The Contractor must prepare and submit Final Study Reports for the nonclinical studies (e.g., pharmacokinetics, metabolism and toxicology studies) conducted in support of the proposed clinical trials, to the NIAID Project Officer or designee in formats compliant with the International Conference on Harmonization (ICH) guidelines (see www.fda.gov).  Health Authority submission.  These reports must be submitted within ninety (90) days after study completion.

        - Provide to the NIAID Project Officer or designee documents concerning manufacture, release testing, and stability testing of drug substance and drug product in formats compliant with for FDA cGMP requirements.  These documents must be submitted within ninety (90) days after completion of testing.

- Clinical Research

          - Provide to the NIAID Project Officer or designee, revised Clinical Trial Protocols addressing comments and requirements of the NIAID DAIT Clinical Research Committee, NIAID Data Safety Monitory Boards (DSMBs), and the Health Authorities

          - Provide, in a timely manner, miscellaneous reports as required by the NIAID Project Officer, NIAID Regulatory Staff, and NIAID Medical Monitors to address regulatory and other project management requirements.

- Bioinformatics, Data Collection, and Validation

            - Two (2) months after contract award and every three (3) years thereafter, the Contractor shall provide documentation of a Risk Analysis Assessment following the guidance given in NIH Security Plan Template (http://irm.cit.nih.gov/security/secplantemp.doc).  The Risk Analysis Assessment is to be maintained and updated every three years, or in advance of implementing major system modifications or enhancements.

            - Two (2) months after contract award, the Contractor shall develop and submit a Continuity of Operations Plan (COOP) following the guidance in NIH Security Plan Template (http://irm.cit.nih.gov/security/secplantemp.doc).  At a minimum, the COOP shall cover emergency operations, backup operations, and recovery plans to assure continuous operations of the system’s facility.  COOP testing shall be conducted and results recorded at least every six (6) months.

            - Twelve (12) months after contract award, and every twelve (12) months thereafter, the Contractor shall provide a demonstration, to the NIAID Project Officer or his designee, of a fully operable system of databases including interfaces for data acquisition, data models, and ontologies or structured vocabularies, as well as initial documentation for all hardware and software.  The contractor shall regularly update and refine these deliverables in accordance with end user requirements.  These modifications and appropriate measures of their impact shall be reported in the Annual Progress Report to the NIAID Project Officer.

            - Six (6) months after contract award, develop and implement a long-range plan for the long-term maintenance and survival of the data and data system.

- Plan for Selection, Development and Validation of Assays and Laboratories

Within three (3) months after contract award, the Contractor shall provide a process for the selection of laboratories and the development and validation of assays.

- Plan for Collaborations with Clinical Research Programs and Organizations

  - Within six (6) months after contract award, the Contractor shall provide a plan to establish and maintain collaborations with government- or privately-sponsored research networks and with the pharmaceutical and biotechnology industries.

  - Within six (6) months of contract award, and annually thereafter, the Contractor shall provide a summary of current collaborations and plans for future collaborations with other clinical research programs and organizations.

12.	Final Clinical Study Reports

a.   Prepare and submit to the NIAID Project Officer or designee Final Clinical Study Reports for each completed clinical trial within six (6) months of the database freeze.  The individual Final Clinical Study Reports may be a component of suitably timed Quarterly Progress Reports or Annual Progress Reports.

13.	Initial and Final Transition Plans

  - Submit an Initial Transition Plan six (6) weeks after award of the contract.

  - Submit a Final Transition Plan six (6) months prior to the completion date of the contract.

- Software and Data

The contractor shall deliver to the Government, upon the expiration date of the contract, all software and data developed, modified, and/or enhanced under this contract.

SECTION D - PACKAGING, MARKING AND SHIPPING

SECTION D - PACKAGING, MARKING AND SHIPPING

All deliverables required under this contract shall be packaged, marked and shipped in accordance with Government specifications.  At a minimum, all deliverables shall be marked with the contract number and contractor name.  The Contractor shall guarantee that all required materials shall be delivered in immediate usable and acceptable condition.

SECTION E - INSPECTION AND ACCEPTANCE

a.	The Contracting Officer or the duly authorized representative will perform inspection and acceptance of materials and services to be provided.

b.	For the purpose of this SECTION, (to be specified before award) the authorized representative of the Contracting Officer.

c.	Inspection and acceptance will be performed at 6610 Rockledge Drive, Bethesda, MD.

Acceptance may be presumed unless otherwise indicated in writing by the Contracting Officer or the duly authorized representative within 30 days of receipt.

d.	This contract incorporates the following clause by reference, with the same force and effect as if it were given in full text.  Upon request, the Contracting Officer will make its full text available.

FAR Clause 52.246-9, Inspection of Research and Development (Short Form) (April 1984).

SECTION F - DELIVERIES OR PERFORMANCE

ARTICLE F.1.  PERIOD OF PERFORMANCE

The period of performance of this contract shall be from February 1, 2007 through January 31, 2014.

ARTICLE F.2.  DELIVERIES

Satisfactory performance of the final contract shall be deemed to occur upon performance of the work described in Article C.1. and upon delivery and acceptance by the Contracting Officer, or the duly authorized representative, of the following items in accordance with the stated delivery schedule:

a.	The items specified below as described in SECTION C, ARTICLE C.2. will be required to be delivered F.O.B. Destination as set forth in FAR Clause 52.247-35, F.O.B. Destination, Within Consignees Premises (April 1984), and in accordance with and by the date(s) specified below and any specifications stated in SECTION D, PACKAGING, MARKING AND SHIPPING, of the contract.

b. Technical Reports Delivery and Distribution Schedule:

| - Item | ### Type of Deliverable | ### Initial Report - Due | ### Recipients & ### Number of Copies | ### Subsequent Reports Due |
| --- | --- | --- | --- | --- |
| - 1. | - Quarterly Progress Report to include clinical, bioinformatics and mechanistic studies | - 30 days following completion of the first three full Calendar Months of the Contract | - 3 Copies to PO (1 copy to be sent electronically) - 2 Copies to CO - (1 copy to be sent electronically) | - Quarterly; due on or before 30 days following the end of - each 3 month period beginning with the start of the contract. - Quarterly report will not be due when an annual or final report is due. |
| - 2. | - Annual Progress Report | - 30 days following the Anniversary Date of Contract | - 3 Copies to PO (1 copy to be sent electronically) - 2 Copies to CO - (1 copy to be sent electronically) | - Annually; submitted 30 days after the anniversary date. An annual report is not due when a final report is due. |
| - 3. | - Annual Progress Report for Clinical Research Study Populations | - 30 days following the Anniversary Date of Contract | - 3 Copies to PO (1 copy to be sent electronically) - 1 Copy to CO - (copy to be sent electronically) | - Annually; submitted 30 days after the anniversary date. |
| - Item | ### Type of Deliverable | ### Initial Report - Due | ### Recipients & ### Number of Copies | ### Subsequent Reports Due |
| - 4. | - Final Report - To include a summary of salient results | - 60 days prior to the expiration date of the contract | - 3 Copies to PO ( 1 copy to be sent electronically) - 2 Copies to CO - (1 copy to be sent electronically) | - N/A |

c.   Other Reports Delivery Schedule

| - Item | ### Type of Deliverable | ### SOW Reference | ### Initial Report ### Due | ### Recipients & ### Number of Copies | ### Subsequent Reports Due |  |
| --- | --- | --- | --- | --- | --- | --- |
| - 1. | - Human Subjects IRB Annual Review |  | - With Annual/Final Reports | - 3 Copies to PO - (1 copy to be sent electronically) - 2 Copies to CO(1 copy to be sent electronically | - Annually; submitted 30 days after the anniversary date. |  |
| - 2. | - Invention Report |  | - As required | - 3 Copies to PO - (1 copy to be sent electronically) - 1 Copy to CO | - As required |  |
| - 3. | - Source Code and Object Code |  | - On expiration date of contract | - 2 Copies to PO (1 copy to be sent electronically.) CO copied on transmission letter. | - N/A |  |
| - 4. | - Industry Liaison Plan |  | - Within 2 months of award of contract | - 3 Copies to PO (1 copy to be sent electronically) - 2 Copies to CO - (1 copy to be sent electronically | - N/A |  |
| - 5. | - Strategic Plan and Research Agenda | - SOW Task I | - Within 2 months of award of the contract | - 3 Copies to PO (1 copy to be sent electronically) - 2 Copies to CO - (copy to be sent electronically | - Annually, as a component of the Annual Progress Report |  |
| - 6. | - Network Executive and Steering Committee Membership | - SOW Task II | - Within 120 days of award of the contract | - 3 Copies to PO (1 copy to be sent electronically) - 2 Copies to CO - (copy to be sent electronically | - As required |  |
| - 7. | - Nonclinical Study and Product Development Reports | - SOW Task III | - Within 90 days of completion of the study or product manufacture | - 3 Copies to PO (1 copy to be sent electronically) - 1 Copy to CO | - As required; Within 90 days of completion of the study or product manufacture |  |
| - 8a. | - Clinical Trial Protocols | - SOW Task IV, item A | - As required | - 3 Copies to PO (1 copy to be sent electronically) - 2 Copies to CO - (1 copy to be sent electronically) | - As required |  |
| - 8b. | - Clinical Research Miscellaneous reports |  | - As required | - 3 Copies to PO or designee(1 copy to be sent electronically - 1 Copy to CO | - As required |  |
| - 9a. | - Risk Analysis Assessment |  | - 2 months after contract award | - 2 Copies to PO (1 copy to be sent electronically) - 2 Copies to CO - (copy to be sent electronically | - Every 3 years after contract award |  |
| - 9b. | - Continuity of Operations Plan |  | - 2 months after contract award | - 2 Copies to PO (1 copy to be sent electronically) - 2 Copies to CO - (copy to be sent electronically | - Test results due every 6 months |  |
| - 9c. | - Demonstration and documentation to PO of fully operable system of databases |  | - 12 months after contract award | - 2 Copies of documentation to PO (1 copy to be sent electronically) - 2 Copies to CO - (1 copy to be sent electronically | - Demonstration and update of documentation - every 12 months. |  |
| - 9d. | - Long Range Plan for Long-term maintenance and survival of data and data system |  | - 6 months after contract award | - 2 Copies to PO (1 copy to be sent electronically) - 2 Copies to CO - (1 copy to be sent electronically | - N/A |  |
| - 10. | - Plan for Selection, Development and Validation of Assays and Laboratories | - SOW Task V, item B | - Within 3 months of contract award | - 3 Copies to PO (1 copy to be sent electronically) - 1 Copy to CO |  | - As required |
| - 11a. | - Plan for Clinical Research - Collaborations | - SOW Task VII | - Within 2 months of award of the contract | - 3 Copies to PO (1 copy to be sent electronically) - 1 Copy to CO | - As required |  |
| - 11b. | - Summary of Collaborations | - SOW Task VII | - 6 months after award of the Contract | - 3 Copies to PO (1 copy to be sent electronically) - 1 Copy to CO | - Annually, may be submitted as part of the Annual Report or a suitably timed Quarterly Report |  |
| - 12. | - Final Clinical Study Reports | - SOW Task IV. | - 6 months after database-freeze | - 4 Copies to PO - (1 copy to be sent electronically) - 1 Copy to CO | - As required by completion of studies; 6 months after each database-freeze |  |
| - 13a. | - Initial Transition Plan | - SOW Task IX, item A | - 6 weeks after award of contract | - 3 Copies to PO - (1 copy to be sent electronically) - 1 Copy to CO | - N/A |  |
| - 13b. | - Final Transition Plan | - SOW Task IX, item B | - 6 months prior to expiration of the contract | - 3 Copies to PO - (1 copy to be sent electronically) - 2 Copies to CO - (1 copy to be sent electronically | - N/A |  |
| - 14. | - Data and Software |  | - On completion of contract | - 3 Copies to PO - (1 copy to be sent electronically) - 1 Copy to CO | - N/A |  |
| - 15. | - Other Deliverables - TBD |  | - As required. | - As required | - As Required. |  |

Copies of reports and deliverables shall be sent to the following addresses:

NIAID Project Officer:  	   National Institutes of Health, DHHS

Address: 	National Institute of Allergy and Infectious Diseases

Division of Allergy, Immunology and Transplantation

6610 Rockledge Drive, Room 3049

Bethesda, MD 20892

NIAID Contracting Officer:   	   National Institute of Allergy and Infectious Diseases

Office of Acquisitions,

DEA, NIAID, NIH, DHHS
6700B Rockledge Drive, Room 3214,  MSC 7612 
Bethesda, MD  20892-7612 
(Express Mail:  Bethesda, MD  20817)

ARTICLE F.3.  CLAUSES INCORPORATED BY REFERENCE, FAR 52.252-2 (FEBRUARY 1998)

This contract incorporates the following clause by reference, with the same force and effect as if it were given in full text.  Upon request, the Contracting Officer will make its full text available.  Also, the full text of a clause may be accessed electronically at this address: http://www.arnet.gov/far/.

FEDERAL ACQUISITION REGULATION (48 CFR CHAPTER 1) CLAUSE:

52.242-15, Stop Work Order (August 1989) with Alternate I (April 1984).

SECTION G - CONTRACT ADMINISTRATION DATA

Any contract awarded from this RFP will contain the following:

ARTICLE G.1.  PROJECT OFFICER

The following Project Officer(s) will represent the Government for the purpose of this contract:

[To be specified prior to award]

The Project Officer is responsible for: (1) monitoring the Contractor's technical progress, including the surveillance and assessment of performance and recommending to the Contracting Officer changes in requirements; (2) interpreting the statement of work and any other technical performance requirements; (3) performing technical evaluation as required; (4) performing technical inspections and acceptances required by this contract; and (5) assisting in the resolution of technical problems encountered during performance.

The Contracting Officer is the only person with authority to act as agent of the Government under this contract.  Only the Contracting Officer has authority to: (1) direct or negotiate any changes in the statement of work; (2) modify or extend the period of performance; (3) change the delivery schedule; (4) authorize reimbursement to the Contractor any costs incurred during the performance of this contract; or (5) otherwise change any terms and conditions of this contract.

The Government may unilaterally change its Project Officer designation.

ARTICLE G.2.  KEY PERSONNEL

Pursuant to the Key Personnel clause incorporated in this contract, the following individual(s) is/are considered to be essential to the work being performed hereunder:

| NAME |  | TITLE |
| --- | --- | --- |
|  | [To be specified prior to award] |  |

Note:  Invoicing Clauses will depend on type of awardee

ARTICLE G.3.  INVOICE SUBMISSION/CONTRACT FINANCING REQUEST

a.	Invoice/Financing Request Instructions for NIH Cost-Reimbursement Type Contracts NIH(RC)-1 are attached and made part of this contract.  The instructions and the following directions for the submission of invoices/financing request must be followed to meet the requirements of a "proper" payment request pursuant to FAR 32.9.

(1)	Invoices/financing requests shall be submitted as follows:

(a) 	To be considered a "proper" invoice in accordance with FAR 32.9, Prompt Payment, each invoice shall clearly identify the two contract numbers that appear on the face page of the contract as follows:

Contract No.  (This is the 17 digit number that appears in Block 2 of the SF-26, i.e. HHSN266200711000C.)

ADB Contract No.  (This is the 10 digit number that appears in the upper left hand corner of the SF-26, i.e.  N01-AI-71234.)

(b)	An original and two copies to the following designated billing office:

Contracting Officer

Office of Acquisitions

DEA, NIAID, NIH, DHHS

6700-B Rockledge Drive, Room 3214, MSC 7612

Bethesda, Maryland  20892-7612

(Express Mail: Bethesda, MD 20817)

(2)	Inquiries regarding payment of invoices should be directed to the designated billing office, (301) 496-0612.

ARTICLE G.3.  INVOICE SUBMISSION/CONTRACT FINANCING REQUEST AND CONTRACT FINANCIAL REPORT

a.	Invoice/Financing Request Instructions and Contract Financial Reporting for NIH Cost-Reimbursement Type Contracts NIH(RC)-4 are attached and made part of this contract.  The instructions and the following directions for the submission of invoices/financing request must be followed to meet the requirements of a "proper" payment request pursuant to FAR 32.9.

These instructions also provide for the submission of financial and personnel reporting required by HHSAR 342.7002.

(1)	Invoices/financing requests shall be submitted as follows:

(a) 	To be considered a "proper" invoice in accordance with FAR 32.9, Prompt Payment, each invoice shall clearly identify the two contract numbers that appear on the face page of the contract as follows:

Contract No.  (This is the 17 digit number that appears in Block 2 of the SF-26, i.e. HHSN266200701234C.)

ADB Contract No.  (This is the 10 digit number that appears in the upper left hand corner of the SF-26, i.e.  N01-AI-71234.)

(b)	An original and two copies to the following designated billing office:

Contracting Officer

Office of Acquisitions

DEA, NIAID, NIH, DHHS

6700-B Rockledge Drive, Room 3214, MSC 7612

Bethesda, Maryland  20892-7612

(Express Mail: Bethesda, MD 20817)

(2)	Inquiries regarding payment of invoices should be directed to the designated billing office, (301) 496-0612.

ARTICLE G.4.  LETTER OF CREDIT PAYMENT INFORMATION

a.	Advance payments will be provided under Letter of Credit Number                                    in accordance with Alternate V, Advance Payments Without Special Bank Account, of FAR Clause 52.232-12, Advance Payments.  This clause is provided in full text in Article I.4. of this contract.

The contractor shall withdraw funds pursuant to Department of Treasury Circular 1075 (31 CFR Part 205, http://www.access.gpo.gov/nara/cfr/waisidx_00/31cfr205_00.html ).

(1)	Invoice/Financing Request Instructions for NIH Cost-Reimbursement Type Contracts, NIH(RC)-1, are attached and made a part of this contract for the submission of completion and/or final invoices.  The invoice instructions and the following directions for the submission of invoices/financing requests must be followed to meet the requirements of a "proper" invoice, pursuant to FAR 32.9.  The completion and/or final invoice shall be submitted as follows:

An original and two copies to the following office:

Contracting Officer

Office of Acquisitions

DEA, NIAID, NIH, DHHS

6700-B Rockledge Drive, Room 3214, MSC 7612

Bethesda, Maryland  20892-7612

(Express Mail: Bethesda, MD 20817)

(2)	Inquiries regarding payments should be directed to the following office administering advance payments:

Division of Payment Management

11400 Rockville Pike

Rockwall Building #1, Suite 700

Rockville, MD 20852

(http://www.dpm.psc.gov/ under Contacts)

b.	The Contractor shall include the following certification on every invoice for reimbursable costs incurred with Fiscal Year funds subject to the salary rate limitation provisions as specified in ARTICLE H.  . of this contract.  For billing purposes, certified invoices are required for the billing period during which the applicable Fiscal Year funds were initially charged through the final billing period utilizing the applicable Fiscal Year funds:

"I hereby certify that the salaries charged in this invoice are in compliance with P.L. [cite the applicable Public Law Number for the a/applicable Fiscal Year as stated in ARTICLE H.  .] and ARTICLE H.  . of the above referenced contract."

ARTICLE G.5.  CONTRACT FINANCIAL REPORT

a.	Financial reports on the attached Form NIH 2706, Financial Report of Individual Project/Contract, shall be submitted by the Contractor in accordance with the Instructions for Completing Form NIH 2706, which accompany the form, in an original and two copies, not later than the 30th working day after the close of the reporting period.  The line entries for subdivisions of work and elements of cost (expenditure categories) which shall be reported within the total contract are listed in paragraph e., below.  Subsequent changes and/or additions in the line entries shall be made in writing.

b.	Unless otherwise stated in that part of the Instructions for Completing Form NIH 2706, entitled "PREPARATION INSTRUCTIONS," all columns A through J, shall be completed for each report submitted.

c.	The first financial report shall cover the period consisting of the (FIRST FULL CALENDAR MONTH/FIRST FULL THREE CALENDAR MONTHS) following the date of the contract, in addition to any fractional part of the initial month.  Thereafter, reports will be on a (monthly/quarterly) basis.

d.	The Contracting Officer may require the Contractor to submit detailed support for costs contained in one or more interim financial reports.  This clause does not supersede the record retention requirements in FAR Part 4.7.

e.	The following is a listing of expenditure categories to be reported:

| Expenditure Category A |  |  | Percentage of Effort/Hours |
| --- | --- | --- | --- |
| (1) Direct Labor |  |  |  |
|  | (a) Principal Investigator |  |  |
|  | (b) Co-Principal Investigator |  |  |
|  | (c) Key Personnel |  |  |
|  |  | (i) |  |
|  |  | (ii) |  |
|  |  | (iii) |  |
| (2) Other Professional Personnel |  |  |  |
| (3) Personnel - Other |  |  |  |
| (4) Fringe Benefits |  |  |  |
| (5) Accountable Personal Property |  |  |  |
| (6) Materials/Supplies |  |  |  |
| (7) Patient Care Costs |  |  |  |
| (8) Travel |  |  |  |
| (9) Consultant Costs |  |  |  |
| (10) Premium Pay |  |  |  |
| (11) Computer Costs |  |  |  |
| (12) Subcontract Costs |  |  |  |
| (13) Other Direct Costs |  |  |  |
| (14) Indirect Costs |  |  |  |
| (15) G&A Expense |  |  |  |
| (16) Total Cost |  |  |  |
| (17) Fee |  |  |  |
| (18) Total Cost Plus Fixed Fee |  |  |  |

f.	The Government may unilaterally revise the NIH 2706 to reflect the allotment of  additional funds.

ARTICLE G.6.  INDIRECT COST RATES

In accordance with Federal Acquisition Regulation (FAR) (48 CFR Chapter 1) Clause 52.216-7(d)(2), "Allowable Cost and Payment" incorporated by reference in this contract in Part II, Section I, the cognizant Contracting Officer representative responsible for negotiating provisional and/or final indirect cost rates is identified as follows:

Director, Division of Financial Advisory Services

Office of Contracts Management

National Institutes of Health

6100 Building, Room 6B05

6100 EXECUTIVE BLVD  MSC 7540

BETHESDA MD  20892-7540

These rates are hereby incorporated without further action of the Contracting Officer.

ARTICLE G.7.  GOVERNMENT PROPERTY

If this RFP will result in the acquisition or use of Government Property provided by the contracting agency or if the Contracting Officer authorizes in the preaward negotiation process, the acquisition of property (other than real property), this ARTICLE will include applicable provisions and incorporate the DHHS Publication (OS) 686, entitled, Contractor's Guide for Control of Government Property, (1990) which can be found at:

http://knownet.hhs.gov/log/AgencyPolicy/HHSLogPolicy/contractorsguide.htm

ARTICLE G.8.  POST AWARD EVALUATION OF CONTRACTOR PERFORMANCE

a.	Contractor Performance Evaluations

Interim and final evaluations of contractor performance will be prepared on this contract in accordance with FAR 42.15.  The final performance evaluation will be prepared at the time of completion of work.  In addition to the final evaluation, interim evaluations will be prepared semi-annually to coincide with the anniversary date of the contract.

Interim and final evaluations will be provided  to the Contractor as soon as practicable after completion of the evaluation.  The Contractor will be permitted thirty days to review the document and to submit additional information or a rebutting statement.  If agreement cannot be reached between the parties, the matter will be referred to an individual one level above the Contracting Officer, whose decision will be final.

Copies of the evaluations, contractor responses, and review comments, if any, will be retained as part of the contract file, and may be used to support future award decisions.

b.	Electronic Access to Contractor Performance Evaluations

Contractors that have Internet capability may access evaluations through a secure Web site for review and comment by completing the registration form that can be obtained at the following address:

http://oamp.od.nih.gov/OD/CPS/cps.asp

The registration process requires the contractor to identify an individual that will serve as a primary contact and who will be authorized access to the evaluation for review and comment.  In addition, the contractor will be required to identify an alternate contact who will be responsible for notifying the cognizant contracting official in the event the primary contact is unavailable to process the evaluation within the required 30-day time frame.

SECTION H - SPECIAL CONTRACT REQUIREMENTS

ARTICLE H.1.  HUMAN SUBJECTS

Research involving human subjects shall not be conducted under this contract until the protocol developed in Phase I has been approved by NIAID, written notice of such approval has been provided by the Contracting Officer, and the Contractor has provided to the Contracting Officer a properly completed "Protection of Human Subjects Assurance Identification/IRB Certification/Declaration of Exemption", Form OMB No. 0990-0263(formerly Optional Form 310), certifying IRB review and approval of the protocol.  The human subject certification can be met by submission of the Contractor's self designated form, provided that it contains the information required by the "Protection of Human Subjects Assurance Identification/IRB Certification/Declaration of Exemption", Form OMB No. 0990-0263(formerly Optional Form 310).

ARTICLE H.2. REQUIRED EDUCATION IN THE PROTECTION OF HUMAN RESEARCH PARTICIPANTS

NIH policy requires education on the protection of human subject participants for all investigators receiving NIH contract awards for research involving human subjects. For a complete description of the NIH Policy announcement on required education in the protection of human subject participants, the contractor should access the NIH Guide for Grants and Contracts Announcement dated June 5, 2000 at the following website: http://grants.nih.gov/grants/guide/notice-files/NOT-OD-00-039.html.  The information below is a summary of the NIH Policy Announcement:

The contractor shall maintain the following information:  (1) a list of the names and titles of the principal investigator and any other individuals working under the contract who are responsible for the design and/or conduct of the research; (2) the title of the education program(s) in the protection of human subjects that has been completed for each named personnel and; (3) a one sentence description of the educational program(s) listed in (2) above.  This requirement extends to investigators and all individuals responsible for the design and/or conduct of the research who are working as subcontractors or consultants under the contract.

Prior to any substitution of the Principal Investigator or any other individuals responsible for the design and/or conduct of the research under the contract, the contractor shall provide the following written information to the Contracting Officer:  the title of the education program and a one sentence description of the program that has been completed by the replacement.

ARTICLE H.3. DATA AND SAFETY MONITORING IN CLINICAL TRIALS

The contractor is directed to the full text of the NIH Policy regarding Data and Safety Monitoring and Reporting of Adverse Events, which may be found at the following web sites:

http://grants.nih.gov/grants/guide/notice-files/not98-084.html

http://grants.nih.gov/grants/guide/notice-files/not99-107.html

http://grants.nih.gov/grants/guide/notice-files/NOT-OD-00-038.html

The contractor must comply with the NIH Policy cited in these NIH Announcements and any other data and safety monitoring requirements found elsewhere in this contract.

Data and Safety Monitoring shall be performed in accordance with the approved Data and Safety Monitoring Plan.

The Data and Safety Monitoring Board and Plan shall be established and approved prior to beginning the conduct of the clinical trial.

ARTICLE H.4.  HUMAN MATERIALS (ASSURANCE OF OHRP COMPLIANCE)

The acquisition and supply of all human specimen material (including fetal material) used under this contract shall be obtained by the Contractor in full compliance with applicable State and Local laws and the provisions of the Uniform Anatomical Gift Act in the United States, and no undue inducements, monetary or otherwise, will be offered to any person to influence their donation of human material.

The Contractor shall provide written documentation that all human materials obtained as a result of research involving human subjects conducted under this contract, by collaborating sites, or by subcontractors identified under this contract, were obtained with prior approval by the Office for Human Research Protections (OHRP) of an Assurance to comply with the requirements of 45 CFR 46 to protect human research subjects.  This restriction applies to all collaborating sites without OHRP-approved Assurances, whether domestic or foreign, and compliance must be ensured by the Contractor.

Provision by the Contractor to the Contracting Officer of a properly completed "Protection of Human Subjects Assurance Identification/IRB Certification/Declaration of Exemption", Form OMB No. 0990-0263(formerly Optional Form 310),  certifying IRB review and approval of the protocol from which the human materials were obtained constitutes the written documentation required.  The human subject certification can be met by submission of a self designated form, provided that it contains the information required by the "Protection of Human Subjects Assurance Identification/IRB Certification/Declaration of Exemption", Form OMB No. 0990-0263(formerly Optional Form 310).

Note: One of the following two clauses will be included in the contract depending on the status of HPSCRG approval at contract award.

ARTICLE H.5.  HUMAN EMBRYONIC GERM CELL (HEGC) RESEARCH

All HPSCRG (Human Pluripotent Stem Cell Review Group) approved research involving human embryonic germ cells shall be conducted in accordance with the NIH Guidelines for Research Using Human Pluripotent Stem Cells ()

ARTICLE H.5.  HUMAN EMBRYONIC GERM CELL (HEGC) RESEARCH

Federally funded research involving the use of human embryonic germ cells derived from fetal tissue shall not be conducted under this contract until Human Pluripotent Stem Cell Review Group (HPSCRG) review and approval has been obtained.  Once approved by the HPSCRG, all research shall be conducted in accordance with the NIH Guidelines for Research Using Human Pluripotent Stem Cells ().

Phase(s)/Option Period(s) ___________which require(s) research involving the use of human embryonic germ cells shall not be conducted under this contract until the HPSCRG review and approval have been obtained, and documented by written notice of such approval by the contracting officer.  If the HPSCRG disapproves the documentation presented by the contractor, the contract may be terminated in accordance with the Termination of Convenience Clause referenced in Article I.1. of this contract/ OR the Contracting Officer may elect not to exercise Option(s) _________ of this contract in accordance with the Option Clause referenced in Article I.3. of this contract. In addition, it may be necessary for the Contracting Officer to invoke FAR Clause 52.242-15, Stop Work Order, referenced in Article F.3 Clauses Incorporated by Reference, of this contract if the review and approval process cannot be accomplished in a time frame that allows for continuity of this research effort.

ARTICLE H.6.  HUMAN EMBRYONIC STEM CELL (HESC) RESEARCH

All research conducted under this contract shall involve the use of existing human embryonic stem cells established under the NIH Embryonic Stem Cell Registry only.

ARTICLE H.7.  CONTINUED BAN ON FUNDING OF HUMAN EMBRYO RESEARCH

a.	Pursuant to Public Law(s) cited in paragraph b. below, NIH is prohibited from using appropriated funds to support human embryo research.  Contract funds may not be used for (1) the creation of a human embryo or embryos for research purposes; or (2) research in which a human embryo or embryos are destroyed, discarded, or knowingly subjected to risk of injury or death greater than that allowed for research on fetuses in utero under 45 CFR 46.208(a)(2) and Section 498(b) of the Public Health Service Act (42 U.S.C. 289g(b)).  The term "human embryo or embryos" includes any organism, not protected as a human subject under 45 CFR 46 as of the date of the enactment of this Act, that is derived by fertilization, parthenogenesis, cloning, or any other means from one or more human gametes or human diploid cells.

Additionally, in accordance with a March 4, 1997 Presidential Memorandum, Federal funds may not be used for cloning of human beings.

| b. Public Law and Section No. | Fiscal Year | Period Covered |
| --- | --- | --- |

[Applicable information to be included at award]

ARTICLE H.8.  NEEDLE EXCHANGE

a.	Pursuant to Public Law(s) cited in paragraph b., below, contract funds shall not be used to carry out any program of distributing sterile needles or syringes for the hypodermic injection of any illegal drug.

| b. Public Law and Section No. | Fiscal Year | Period Covered |
| --- | --- | --- |

[Applicable information to be included at award]

ARTICLE H.9.  PRIVACY ACT

This procurement action requires the Contractor to do one or more of the following: design, develop, or operate a system of records on individuals to accomplish an agency function in accordance with the Privacy Act of 1974, Public Law 93-579, December 31, 1974 (5 USC 552a) and applicable agency regulations.  Violation of the Act may involve the imposition of criminal penalties.

The Privacy Act System of Records applicable to this project is Number 09-25-0200.  This document is incorporated into this contract as Attachment 23.

ARTICLE H.10.  ANIMAL WELFARE

All research involving live, vertebrate animals shall be conducted in accordance with the Public Health Service Policy on Humane Care and Use of Laboratory Animals.  This policy may be accessed at:

http://grants1.nih.gov/grants/olaw/references/phspol.htm

ARTICLE H.11.  INTRODUCTION OF RODENTS AND RODENT PRODUCTS

No rodent or rodent product shall be delivered into the NIH, NIAID environment (NIH) directly, or through collaborative research or holding facilities under contract to NIAID except by permit.  Direct shipments to NIH from a Division of Veterinary Resources (DVR), Office of Research Services (ORS) approved source will be considered exempt.  Non-exempt sources must be approved by permit issued through the DVR, ORS.  The permit must be obtained by the Contractor prior to the shipment to NIH of the rodents and/or rodent products.  The Contractor must be sure that this permit exists and is current before transferring rodents or rodent products into the NIH, NIAID environment.  Refusal or negligence to do so will be considered a material breach of contract and may be treated as any other such material breach.  Applications for permits should be submitted by facsimile not less than 30 days prior (60 days in situations where quarantine is likely) to shipping date to:  NIH Division of Veterinary Resources (DVR), Office of Research Services (ORS), Building 14G, Service Rd. South, Room 102, BETHESDA  MD 20892-5210, (301)496-2527, FAX:  (301) 402-0352.

ARTICLE H.12.  RESEARCH INVOLVING HUMAN FETAL TISSUE

All research involving human fetal tissue shall be in conducted in accordance with the Public Health Service Act, 42 U.S.C. 289g-1 and 289g-2.  Implementing regulations and guidance for conducting research on human fetal tissue may be found at 45 CFR 46, Subpart B and  any subsequent revisions to this NIH Guide to Grants and Contracts ("Guide") Notice.

The contractor shall make available, for audit by the Secretary, DHHS, the physician statements and informed consents required by 42 USC 289g-1(b) and (c), or ensure DHHS access to those records, if maintained by an entity other than the contractor.

ARTICLE H.13.  OPTION PROVISION

Unless the Government exercises its option pursuant to the Option Clause set forth in ARTICLE I.3., the contract will consist only of (Phase I or Year I) of the Statement of Work as defined in Sections C and F of the contract.  Pursuant to clause 52.217- 6 set forth in ARTICLE I.3. of this contract, the Government may, by unilateral contract modification, require the Contractor to perform the options in the Statement of Work as also defined in Sections C and F of this contract.  If the Government exercises this option, notice must be given at least 60 days prior to the expiration date of this contract, and the estimated cost [plus fixed fee] of the contract will be increased as set forth in Article B.3.

ARTICLE H.14.  SUBCONTRACTING PROVISIONS

a.	Small  Business Subcontracting Plan

(1)	The Small Business Subcontracting Plan, dated TBD is attached hereto and made a part of this contract.

(2)	The failure of any Contractor or subcontractor to comply in good faith with FAR Clause 52.219-8, entitled "Utilization of Small Business Concerns" incorporated in this contract and the attached Subcontracting Plan, will be a material breach of such contract or subcontract and subject to the remedies reserved to the Government under FAR Clause 52.219-16 entitled, "Liquidated Damages-Subcontracting Plan."

b.	Subcontracting Reports

(1)	Subcontracting Report for Individual Contracts, SF-294

The Contractor shall submit the original and one (1) copy of Subcontracting Report for Individual Contracts, SF-294 in accordance with the instructions on the report as referenced in Public Law 95-507, Section 211.  In addition to the information contained in the General Instructions on the back of this form for Block 17, "Remarks," the Contractor shall provide an explanation for any category of small business subcontracting for which there were no dollars reported since the last reporting period.

Regardless of the effective date of this contract, the Report shall be submitted on the following dates for the entire life of this contract:

April 30th

October 30th

The Report shall be sent to the Contracting Officer at following address:

Contracting Officer

Office of Acquisitions

DEA, NIAID, NIH, DHHS

6700-B Rockledge Drive, Room 3214, MSC 7612

Bethesda, Maryland  20892-7612

(Express Mail: Bethesda, MD 20817)

(2)	Summary Subcontract Report, SF-295

The Contractor shall submit two (2) copies of Summary Subcontract Report, SF-295 in accordance with the instructions on the report as referenced in Public Law 95-507, Section 211.  Regardless of the effective date of this contract, the Summary Subcontract Report shall be submitted annually on the following date for the entire life of this contract:

October 30th

One copy of this report shall be sent to the Contracting Officer at the address above.  One copy of this Report shall be mailed to the Office of Small and Disadvantaged Business Utilization, DHHS at the following addresses:

Office of Small and Disadvantaged Business Utilization

Department of Health and Human Services

Hubert H. Humphrey Bldg., Room 360G

200 Independence Avenue, S.W.

Washington, D.C.  20201

(3)	The contractor shall also send an "Information Copy" of the SF-295 to the Cognizant Commercial Representative (CMR) at the address provided by the SBA.  The Contractor should call SBA Headquarters in Washington, DC at (202) 690-7235, for the correct address if unknown.

ARTICLE H.15.  SALARY RATE LIMITATION LEGISLATION PROVISIONS

a.	Pursuant to the P.L.(s) cited in paragraph b., below, no NIH Fiscal Year funds may be used to pay the direct salary of an individual through this contract at a rate in excess of the applicable amount shown or the applicable Executive Level for the fiscal year covered. Direct salary is exclusive of fringe benefits, overhead and general and administrative expenses (also referred to as “indirect costs” or “facilities and administrative (F&A) costs”). Direct salary has the same meaning as the term “institutional base salary.”  An individual's direct salary (or institutional base salary) is the annual compensation that the contractor pays for an individual's appointment whether that individual's time is spent on research, teaching, patient care or other activities.  Direct salary (or institutional base salary) excludes any income that an individual may be permitted to earn outside of duties to the contractor.  The per year salary rate limitation also applies to individuals proposed under subcontracts.  It does not apply to fees paid to consultants.  If this is a multiple year contract, it may be subject to unilateral modifications by the Government if an individual's salary rate used to establish contract funding exceeds any salary rate limitation subsequently established in future HHS appropriation acts.

| b. Public Law No. | Fiscal Year | Dollar Amount of Salary Limitation* |
| --- | --- | --- |

[Applicable information to be included at award]

c.	Payment of direct salaries is limited to the Executive Level I rate which was in effect on the date(s) the expense was incurred.

* For the period 10/1/04 - 12/30/04, the Executive Level I rate is $175,700.  Effective January 1, 2005, the Executive Level I rate increased to $180,100 and will remain at that rate until it is revised.  See the web site listed below for the Executive Schedule rates of pay:

FOR FY05 EXECUTIVE LEVEL SALARIES EFFECTIVE JANUARY 1, 2005:

http://www.opm.gov/oca/05tables/html/ex.asp

(NOTE:  This site shows the CY 05 rates.  For previous years, click on “salaries and wages” and then scroll down to the bottom of the page and click on the year to locate the desired Executive Level salary rates).

ARTICLE H.16.  INFORMATION SECURITY

The Statement of Work (SOW) requires the contractor to develop or access Federal automated information systems; therefore, the contractor shall comply with the “DHHS Information Security Program Policy“ (http://www.hhs.gov/read/irmpolicy/FINALHHSInformationSecurityProgramP.doc) as set forth below.  The contractor shall include this provision in any subcontract awarded under this contract.

a.	Information Type

****	(NOTE:  The resultant contract will include the Information Type, however for the purposes of this RFP, the Information Type is specified in SECTION L.2.b. Technical Proposal Instructions of this RFP.) ****

[]	Administrative, Management and Support Information:

[]	Mission Based Information:

b. 	Security Categories and Levels

****	(NOTE:  The resultant contract will include the Security Categories and Levels, however for the purposes of this RFP, the Security Categories and Levels are specified in SECTION L.2.b. Technical Proposal Instructions of this RFP.) ****

Confidentiality		Level:	[ ] Low	[X] Moderate	[ ] High

Integrity 			Level:	[ ] Low	[X] Moderate	[ ] High

Availability			Level:	[ ] Low	[X] Moderate	[ ] High

Overall			Level:	[ ] Low	[X] Moderate	[ ] High

c.	Position Sensitivity Designations

(1)	The following position sensitivity designations and associated clearance and investigation requirements apply under this contract:

****	(NOTE:  The resultant contract will include the Position Sensitivity Designations, however for the purposes of this RFP, the Position Sensitivity Designations applicable to this RFP are specified in SECTION L.2.b. Technical Proposal Instructions of this RFP.) ****

[ ]	Level 6: Public Trust - High Risk (Requires Suitability Determination with a BI).  Contractor employees assigned to a Level 6 position are subject to a Background Investigation (BI).

[X]	Level 5: Public Trust - Moderate Risk (Requires Suitability Determination with NACIC, MBI or LBI). Contractor employees assigned to a Level 5 position with no previous investigation and approval shall undergo a National Agency Check and Inquiry Investigation plus a Credit Check (NACIC), a Minimum Background Investigation (MBI), or a Limited Background Investigation (LBI).

[ ]	Level 1: Non Sensitive (Requires Suitability Determination with an NACI).  Contractor employees assigned to a Level 1 position are subject to a National Agency Check and Inquiry Investigation (NACI).

(2)	The contractor shall submit a roster, by name, position and responsibility, of all IT staff working under the contract. The roster shall be submitted to the Project Officer, with a copy to the Contracting Officer, within 14 days of the effective date of the contract.  Any revisions to the Roster as a result of staffing changes shall be submitted within fifteen (15) calendar days of the change.   The Contracting Officer shall notify the contractor of the appropriate level of suitability investigations to be performed.  An electronic template, “Roster of Employees Requiring Suitability Investigations,”* is available for contractor use at:

http://ais.nci.nih.gov/forms/Suitability-roster.xls

*Note:  The website listed at http://ais.nci.nih.gov provides information about IT Security Policies and the background investigation process.  NCI points of contract do not apply to this contract.  Contact your contract specialist for applicable staff information.

Upon receipt of the Government’s notification of applicable Suitability Investigation required, the contractor shall complete and submit the required forms within 30 days of the notification. Additional submission instructions can be found at the “NCI Information Technology Security Policies, Background Investigation Process” website: http://ais.nci.nih.gov.

Contractor employees who have had a background investigation conducted by the U.S. Office of Personnel Management (OPM) within the last five years may only require an updated or upgraded investigation.

(3)	Contractor employees shall comply with the DHHS criteria for the assigned position sensitivity designations prior to performing any work under this contract.  The following exceptions apply:

Levels 5 and 1: Contractor employees may begin work under the contract after the contractor has submitted the name, position and responsibility of the employee to the Project Officer, as described in paragraph c.(2) above.

Level 6: In special circumstances the Project Officer may request a waiver of the preappointment investigation.  If the waiver is granted, the Project Officer will provide written authorization for the contractor employee to work under the contract.

d.	Systems Security Plan

The contractor shall protect Federal automated information systems that are developed or accessed by the contractor.   System security shall be accomplished in accordance with the contractor’s System Security Plan dated February 1, 2007.   The plan must:

(1)	Include a detailed plan of present and proposed systems security programs commensurate with the size and complexity of the requirements of the Statement of Work. The contractor shall use the NIH Systems Security Plan Template (detailed) at http://irm.cit.nih.gov/security/secplantemp.doc or NIH Systems Security Plan Outline (outline only) at http://irm.cit.nih.gov/nihsecurity/Security_Plan_Outline.doc.

[OR  (To be determined during negotiations)]

(1)	Include a plan of present and proposed systems security programs commensurate with the size and complexity of the requirements of the Statement of Work.  The minimum areas to be addressed include, but are not limited to administrative, technical, and physical security as follows:

(i)	Security Awareness Training

(ii)	Logical Access Control

-Network (ex: firewall)

-System (ex: network OS, tcp wrappers, SSH)

-Application (ex: S-LDAP, SSL)

-Remote Access (ex: VPN)

-Monitoring and support (ex: IDS, pager, NOC)

(iii)	Protection against data loss

-OS security (ex: patch management, configuration)

-Application security (ex: patch management)

-Database security

-Back-up and recovery

-Fault tolerance, high availability

(iv)	Malicious Code Protection (ex: Antivirus, filtering of e-mail attachments, etc)

(v)	Physical Security

-Access control (ex: locks, guards)

-Power conditioning and/or UPS

-Air conditioning

-Fire protection

Include an acknowledgment of its understanding of the security requirements.

Provide similar information for any proposed subcontractor developing or accessing an AIS.

e.	Rules of Behavior

The contractor shall comply with the DHHS Rules of Behavior set forth in DHHS Information Security Program Policy Handbook, Appendix G at:

http://intranet.hhs.gov/infosec/docs/policies_guides/ISPPH/PG_ISHbkv2_11_12_2004.pdf; and

the NIH Information Technology General Rules of Behavior at:

http://irm.cit.nih.gov/security/nihitrob.html.

f.	Information Security Training

Each contractor employee shall complete the NIH Computer Security Awareness Training (http://irtsectraining.nih.gov/) prior to performing any contract work, and on an annual basis thereafter, during the period of performance of this contract.

The contractor shall maintain a listing by name and title of each individual working under this contract that has completed the NIH required training.  Any additional security training completed by contractor staff shall be included on this listing.

Contractor staff shall complete the following additional training prior to performing any work under this contract:

**** [Additional courses will be listed here in the resultant contract, if applicable.] ****

g.	Personnel Security Responsibilities

The contractor shall perform and document the actions identified in the “Employee Separation Checklist”, attached and made a part of this contract, when a contractor employee terminates work under this contract.  All documentation shall be made available to the Project Officer and/or Contracting Officer upon request

h.	Commitment to Protect Departmental Information Systems and Data

(1)	Contractor Agreement

The Contractor shall not release, publish, or disclose sensitive Department information to unauthorized personnel, and shall protect such information in accordance with provisions of the following laws and any other pertinent laws and regulations governing the confidentiality of sensitive information:

-18 U.S.C. 641 (Criminal Code: Public Money, Property or Records)

-18 U.S.C. 1905 (Criminal Code: Disclosure of Confidential Information)

-Public Law 96-511 (Paperwork Reduction Act)

(2)	Contractor-Employee Non-Disclosure Agreements

Each contractor employee who may have access to sensitive Department information under this contract shall complete Commitment To Protect Non-Public Information - Contractor Agreement. A copy of each signed and witnessed Non-Disclosure agreement shall be submitted to the Project Officer prior to performing any work under the contract.

i.	References

  - DHHS Information Security Program Policy:  http://www.hhs.gov/ohr/manual/pssh.pdf

  - DHHS Personnel Security/Suitability Handbook:  http://www.hhs.gov/ohr/manual/pssh.pdf

  - NIST Special Publication 800-16, Information Technology Security Training Requirements:

http://csrc.nist.gov/publications/nistpubs/800-16/800-16.pdf

Appendix A-D:  http://csrc.nist.gov/publications/nistpubs/800-16/AppendixA-D.pdf

  - NIST SP 800-18, Guide for Developing Security Plans for Information Technology Systems:

http://csrc.nist.gov/publications/nistpubs/index.html

  - NIST SP 800-60, Guide for Mapping Types of Information and Information Systems to Security Categories, Volume I:  http://csrc.nist.gov/publications/nistpubs/800-60/SP800-60V1-final.pdf

  - NIST SP 800-60, Guide for Mapping Types of Information and Information Systems to Security Categories, Volume II: http://csrc.nist.gov/publications/nistpubs/800-60/SP800-60V2-final.pdf

  - NIST SP 800-64, Security Considerations in the Information System Development Life Cycle:

http://csrc.nist.gov/publications/nistpubs/800-64/NIST-SP800-64.pdf

  - NIH Computer Security Awareness Training Course:  http://irtsectraining.nih.gov/

  - Roster of Employees Requiring Suitability Investigations:  http://ais.nci.nih.gov/forms/Suitability-roster.xls

  - NCI Information Technology Security Policies, Background Investigation Process:  http://ais.nci.nih.gov/

  - NIH Systems Security Plan Template (detailed): http://irm.cit.nih.gov/security/secplantemp.doc

  - NIH Systems Security Plan Outline (outline only): http://irm.cit.nih.gov/nihsecurity/Security_Plan_Outline.doc

  - NIH Information Technology General Rules of Behavior: http://irm.cit.nih.gov/security/nihitrob.html

  - Commitment To Protect Non-Public Information - Contractor Agreement:

http://irm.cit.nih.gov/security/Nondisclosure.pdf

ARTICLE H.17.  ENERGY STAR REQUIREMENTS

Executive Order 13123, “Greening the Government Through Efficient Energy Management” and FAR 23.203 require that when Federal Agencies acquire energy using products, they select, where life-cycle cost-effective, and available, ENERGY STAR® or other energy efficient products.

Unless the Contracting Officer determines otherwise, all energy-using products acquired under this contract must be either an ENERGY STAR® or other energy efficient product designated by the Department of Energy’s Federal Energy Management Program (FEMP).

For more information about ENERGY STAR® see http://www.energystar.gov/

For more information about FEMP see http://www.eere.energy.gov/

ARTICLE H.18. PUBLICATION AND PUBLICITY

The contractor shall acknowledge the support of the National Institutes of Health whenever publicizing the work under this contract in any media by including an acknowledgment substantially as follows:

"This project has been funded in whole or in part with Federal funds from the National Institute for Allergy and Infectious Diseases, National Institutes of Health, Department of Health and Human Services, under Contract No.               .

ARTICLE H.19.  PRESS RELEASES

a.	Pursuant to Public Law(s) cited in paragraph b., below, the contractor shall clearly state, when issuing statements, press releases, requests for proposals, bid solicitations and other documents describing projects or programs funded in whole or in part with Federal money:  (1) the percentage of the total costs of the program or project which will be financed with Federal money; (2) the dollar amount of Federal funds for the project or program; and (3) the percentage and dollar amount of the total costs of the project or program that will be financed by nongovernmental sources.

| b. Public Law and Section No. | Fiscal Year | Period Covered |
| --- | --- | --- |

[Applicable information to be included at award]

ARTICLE H.20 REPORTING MATTERS INVOLVING FRAUD, WASTE AND ABUSE

Anyone who becomes aware of the existence or apparent existence of fraud, waste and abuse in NIH funded programs is encouraged to report such matters to the HHS Inspector General’s Office in writing or on the Inspector General’s Hotline.  The toll free number is 1-800-HHS-TIPS (1-800-447-8477).   All telephone calls will be handled confidentially.  The e-mail address is Htips@os.dhhs.gov and the mailing address is:

Office of Inspector General

Department of Health and Human Services

TIPS HOTLINE

P.O. Box 23489

Washington, D.C.  20026

ARTICLE H.21.  YEAR 2000 COMPLIANCE

In accordance with FAR 39.106, Information Technology acquired under this contract must be Year 2000 compliant as set forth in the following clause(s):

1.	Service Involving the Use of Information Technology

YEAR 2000 COMPLIANCE--SERVICE INVOLVING THE USE OF INFORMATION TECHNOLOGY

The Contractor agrees that each item of hardware, software, and firmware used under this contract shall be able to accurately process date data (including, but not limited to, calculating, comparing and sequencing) from, into and between the twentieth and twenty-first centuries and the Year 1999 and the Year 2000 and leap year calculations.

(End of Clause)

2.	Noncommercial Supply Items Warranty

YEAR 2000 WARRANTY--NONCOMMERCIAL SUPPLY ITEMS

The contractor warrants that each noncommercial item of hardware, software, and firmware delivered or developed under this contract and listed below shall be able to accurately process date data (including, but not limited to, calculating, comparing and sequencing) from, into and between the twentieth and twenty-first centuries and the Year 1999 and the Year 2000 and leap year calculations, when used in accordance with the item documentation provided by the contractor, provided that all listed or unlisted items (e.g., hardware, software and firmware) used in combination with such listed item properly exchange date data with it.  If the contract requires that specific listed items must perform as a system in accordance with the foregoing warranty, then that warranty shall apply to those listed items as a system.  The duration of this warranty and the remedies available to the Government for breach of this warranty shall be as defined in, and subject to, the terms and limitations of any general warranty provisions of this contract provided that notwithstanding any provision to the contrary in such warranty provision(s), or in the absence of any such warranty provision(s), the remedies available to the Government under this warranty shall include repair or replacement of any listed item whose noncompliance is discovered and made known to the contractor in writing within ninety (90) days after acceptance.  Nothing in this warranty shall be construed to limit any rights or remedies the Government may otherwise have under this contract with respect to defects other than Year 2000 performance.

YEAR 2000 COMPLIANT ITEMS

To be identified at the time of award

(End of Clause)

3.	Commercial Supply Products Warranty

YEAR 2000 WARRANTY--COMMERCIAL SUPPLY ITEMS

The contractor warrants that each hardware, software and firmware product delivered under this contract and listed below shall be able to accurately process date data (including, but not limited to, calculating, comparing, and sequencing) from, into, and between the  twentieth and twenty-first centuries and the Year 1999 and the Year 2000 and leap year calculations, when used in accordance with the product documentation provided by the contractor, provided that all listed or unlisted products (e.g., hardware, software, firmware) used in combination with such listed product properly exchange date data with it.  If the  contract requires that specific listed products must perform as a system in accordance with the foregoing warranty, then that warranty shall apply to those listed products as a system.  The duration of  this warranty and the remedies available to the Government for breach of this warranty shall be as defined in, and subject to, the terms and limitations of the contractor's standard commercial warranty or  warranties contained in this contract, provided that notwithstanding any provision to the contrary in such commercial warranty or warranties, the remedies available to the Government under this warranty shall include repair or replacement of any listed product whose non-compliance is discovered and made known to the contractor in writing within ninety (90) days after acceptance.  Nothing in this warranty shall be construed to limit any rights or remedies the Government may otherwise have under this contract with respect to defects other than Year 2000 performance.

YEAR 2000 COMPLIANT ITEMS

To be identified at the time of contract award

(End of Clause)

ARTICLE H.22.  ANTI -LOBBYING

a.	Pursuant to Public Law(s) cited in paragraph c., below, contract funds shall only be used for normal and recognized executive-legislative relationships.  Contract funds shall not be used, for publicity or propaganda purposes; or for the preparation, distribution, or use of any kit, pamphlet, booklet, publication, radio, television, or video presentation designed to support or defeat legislation pending before the Congress or any State legislature, except in presentation to the Congress or any State legislature itself.

b.	Contract funds shall not be used to pay salary or expenses of the contractor or any agent acting for the contractor, related to any activity designed to influence legislation or appropriations pending before the Congress or any State legislature.

| c. Public Law and Section No. | Fiscal Year | Period Covered |
| --- | --- | --- |

[Applicable information to be included at award]

ARTICLE H. 23.  LIMITATION ON USE OF FUNDS FOR PROMOTION OF LEGALIZATION OF CONTROLLED SUBSTANCES

a.	Pursuant to Public Laws(s) cited in paragraph b., above, contract funds shall not be used to support activities that promote the legalization of any drug or other substance included in schedule I of the schedules of controlled substances established by section 202 of the Controlled Substances Act (21 U.S.C. 812). This limitation shall not apply when the contractor makes known to the contracting officer that there is significant medical evidence of a therapeutic advantage to the use of such drug or other substance or that federally sponsored clinical trials are being conducted to determine therapeutic advantage.

| b. Public Law and Section No. | Fiscal Year | Period Covered |
| --- | --- | --- |

[Applicable information to be included at award]

ARTICLE H.24.  SHARING RESEARCH DATA

[The data sharing plan submitted by the contractor is acceptable/The contractor's data sharing plan, dated                              is hereby incorporated by reference.]  The contractor agrees to adhere to its plan and shall request prior approval of the Contracting Officer for any changes in its plan.

The NIH endorses the sharing of final research data to expedite the translation of research results into knowledge, products, and procedures to improve human health.  This contract is expected to generate research data that must be shared with the public and other researchers.  NIH's data sharing policy may be found at the following Web site:

http://grants.nih.gov/grants/guide/notice-files/NOT-OD-03-032.html

NIH recognizes that data sharing may be complicated or limited, in some cases, by institutional policies, local IRB rules, as well as local, state and Federal laws and regulations, including the Privacy Rule (see HHS-published documentation on the Privacy Rule at http://www.hhs.gov/ocr/).  The rights and privacy of people who participate in NIH-funded research must be protected at all times; thus, data intended for broader use should be free of identifiers that would permit linkages to individual research participants and variables that could lead to deductive disclosure of the identity of individual subjects.

ARTICLE H.25.  POSSESSION USE AND TRANSFER OF SELECT BIOLOGICAL AGENTS OR TOXINS

The contractor shall not conduct work involving select agents or toxins under this contract until it and any associated subcontractor(s) comply with the following:

For prime or subcontract awards to domestic institutions that possess, use, and/or transfer Select Agents under this contract, the institution must comply with the provisions of 42 CFR part 73, 7 CFR part 331, and/or 9 CFR part 121 (http://www.aphis.usda.gov/programs/ag_selectagent/FinalRule3-18-05.pdf), as required, before using NIH funds for research involving Select Agents.   No NIH funds can be used for research involving Select Agents if the final registration certificate is denied.

For prime or subcontract awards to foreign institutions that possess, use, and/or transfer Select Agents under this contract, before using NIH funds for any work directly involving the Select Agents, the foreign institution must provide information satisfactory to the NIAID, NIH that safety, security, and training standards equivalent  to those described in 42 CFR part 73, 7 CFR part 331, and/or 9 CFR part 121  at:

(http://www.aphis.usda.gov/programs/ag_selectagent/FinalRule3-18-05.pdf)

are in place and will be administered on behalf of all Select Agent work sponsored by these funds.  The process for making this determination includes inspection of the foreign laboratory facility by an NIAID representative.  During this inspection, the foreign institution must provide the following information: concise summaries of safety, security, and training plans; names of individuals at the foreign institution who will have access to the Select Agents and procedures for ensuring that only approved and appropriate individuals, in accordance with institution procedures, will have access to the Select Agents under the contract; and copies of or links to any applicable laws, regulations, policies, and procedures applicable to that institution for the safe and secure possession, use, and/or transfer of select agents.  An NIAID-chaired committee of U.S. federal employees (including representatives of NIH grants/contracts and scientific program management, CDC, Department of Justice and other federal intelligence agencies, and Department of State) will ultimately assess the results of the laboratory facility inspection, and the regulations, policies, and procedures of the foreign institution for equivalence to the U.S. requirements described in 42 CFR part 73, 7 CFR part 331, and/or 9 CFR part 121 (http://www.aphis.usda.gov/programs/ag_selectagent/FinalRule3-18-05.pdf). The committee will provide recommendations to the DEA Director, NIAID.  The DEA Director will make the approval decision and notify the Contracting Officer.  The Contracting Officer will inform the prime contractor of the approval status of the foreign institution.  No NIH funds can be used for research involving Select Agents at a foreign institution until NIAID grants this approval.

Listings of HHS select agents and toxins, and overlap select agents or toxins as well as information about the registration process for domestic institutions, are available on the Select Agent Program Web site at http://www.cdc.gov/od/sap/  and http://www.cdc.gov/od/sap/docs/salist.pdf.  Listings of USDA select agents and toxins as well as information about the registration process for domestic institutions are available on the APHIS/USDA website at http://www.aphis.usda.gov/programs/ag_selectagent/index.html and http://www.aphis.usda.gov/programs/ag_selectagent/ag_bioterr_forms.html.  For foreign institutions, see the NIAID Select Agent Award information (http://www.niaid.nih.gov/ncn/clinical/default_biodefense.htm).

ARTICLE H.26.  HOTEL AND MOTEL FIRE SAFETY ACT OF 1990 (P.L. 101-391)

Pursuant to Public Law 101-391, no Federal funds may be used to sponsor or fund in whole or in part a meeting, convention, conference or training seminar that is conducted in, or that otherwise uses the rooms, facilities, or services of a place of public accommodation that do not meet the requirements of the fire prevention and control guidelines as described in the Public Law.  This restriction applies to public accommodations both foreign and domestic.

Public accommodations that meet the requirements can be accessed at:  http://www.usfa.fema.gov/hotel/index.htm

ARTICLE H.27.  PROHIBITION ON CONTRACTOR INVOLVEMENT WITH TERRORIST ACTIVITIES

The contractor acknowledges that U.S. Executive Orders and Laws, including but not limited to E.O. 13224 and P.L. 107-56, prohibit transactions with, and the provision of resources and support to, individuals and organizations associated with terrorism.  It is the legal responsibility of the contractor to ensure compliance with these Executive Orders and Laws.  This clause must be included in all subcontracts issued under this contract.

ARTICLE H.28.  NIH POLICY ON ENHANCING PUBLIC ACCESS TO ARCHIVED PUBLICATIONS RESULTING FROM NIH-FUNDED RESEARCH

The Policy requests that beginning May 2, 2005, NIH-funded investigators submit to the NIH National Library of Medicine’s (NLM) PubMed Central (PMC) an electronic version of the author’s final manuscript, upon acceptance for publication, resulting from research supported in whole or in part with direct costs from NIH.  NIH defines the author’s final manuscript as the final version accepted for journal publication, and includes all modifications from the publishing peer review process.  The PMC archive will preserve permanently these manuscripts for use by the public, health care providers, educators, scientists, and NIH.  The Policy directs electronic submissions to the NIH/NLM/PMC: http://www.pubmedcentral.nih.gov.

Additional information is available at http://grants.nih.gov/grants/guide/notice-files/NOT-OD-05-022.html.

ARTICLE H.29.  CONSTITUTION DAY

Each educational institutional institution that receives Federal funds for a fiscal year shall hold an educational program on the United States Constitution on September 17 of such year for the students serviced by the educational institution in accordance with Public Law 108-447.

ARTICLE H.30.  OBTAINING AND DISSEMINATING BIOMEDICAL RESEARCH RESOURCES

Unique research resources arising from NIH-funded research are to be shared with the scientific research community.  NIH provides guidance, entitled, “Sharing Biomedical Research Resources:  Principles and Guidelines for Recipients of NIH Research Grants and Contracts,” (Federal Register Notice, December 23, 1999 [64 FR 72090]), concerning the appropriate terms for disseminating and acquiring these research resources.  This guidance, found at :  . is intended to help contractors ensure that the conditions they impose and accept on the transfer of research tools will facilitate further biomedical research, consistent with the requirements of the Bayh-Dole Act and NIH funding policy.

Note:  For the purposes of  this Article, the terms, "research tools," "research materials," and "research resources" are used interchangeably and have the same meaning

PART II - CONTRACT CLAUSES

SECTION I - CONTRACT CLAUSES

THE FOLLOWING ARTICLE I.1 GENERAL CLAUSE LISTING(S) WILL BE APPLICABLE TO MOST CONTRACTS RESULTING FROM THIS RFP.  HOWEVER, THE ORGANIZATIONAL STRUCTURE OF THE SUCCESSFUL OFFEROR(S) WILL DETERMINE THE SPECIFIC GENERAL CLAUSE LISTING TO BE CONTAINED IN THE CONTRACT(S) AWARDED FROM THIS RFP:

General Clauses for a Cost-Reimbursement Research and Development Contract

The complete listing of these clauses may be accessed at:

http://rcb.cancer.gov/rcb-internet/appl/general-clauses/clauses.jsp

ARTICLE I.2.  AUTHORIZED SUBSTITUTIONS OF CLAUSES

Any authorized substitutions and/or modifications other than the General Clauses which will be based on the type of contract/Contractor will be determined during negotiations.

It is expected that the following clause(s) will be made part of the resultant contract:

Alternate IV (October 1997) of FAR Clause 52.215-21, Requirements For Cost Or Pricing Data Or Information Other Than Cost Or Pricing Data—Modifications

Alternate II (October 2001) of FAR Clause 52.219-9, Small Business Subcontracting Plan (January 2002) is added.

ARTICLE I.3.  ADDITIONAL CONTRACT CLAUSES

Additional clauses other than those listed below which are based on the type of contract/Contractor shall be determined during negotiations.  Any contract awarded from this solicitation will contain the following:

This contract incorporates the following clauses by reference, (unless otherwise noted), with the same force and effect as if they were given in full text.  Upon request, the Contracting Officer will make their full text available.

a.	FEDERAL ACQUISITION REGULATION (FAR) (48 CFR CHAPTER 1) CLAUSES

(1)		FAR Clause 52.217-8, Option to Extend Services (November 1999)

"....The Contracting Officer may exercise the option by written notice to the Contractor within  30 days”

(2)		FAR Clause 52.219-4, Notice of Price Evaluation Preference for HUBZone Small Business Concerns (July 2005).

"(c)	Waiver of evaluation preference.....

[   ]	Offeror elects to waive the evaluation preference."

(3)		FAR Clause 52.223-12, Refrigeration Equipment and Air Conditioners (May 1995).

(4)		FAR Clause 52.224-1, Privacy Act Notification (April 1984).

(5)		FAR Clause 52.224-2, Privacy Act (April 1984).

    - FAR Clause 52.227-2, Notice & Assistance Regarding Patent &Copyright Infringement

    - FAR Clause 52.227-6, Royalty Information

    - Alternate I (June 1987), FAR Clause 52.227-14, Rights in Data--General (June 1987).

(9)		Alternate III (June 1987), FAR Clause 52.227-14, Rights in Data--General (June 1987).

Additions to, or limitations on, the restricted rights set forth in the Restricted Rights Notice of subparagraph (g)(3) of the clause are expressly stated as follows: NONE.

(10)		FAR Clause 52.227-16, Additional Data Requirements (June 1987).

(11)		FAR Clause 52.239-1, Privacy or Security Safeguards (August 1996)

(12)		FAR Clause 52.242-3, Penalties for Unallowable Costs (May 2001).

(13)		FAR Clause 52.243-2, Changes--Cost Reimbursement (August 1987), Alternate V (April 1984).

(14)		FAR Clause 52.246-23, Limitation of Liability (February 1997).

b.	DEPARTMENT OF HEALTH AND HUMAN SERVICES ACQUISITION REGULATION (HHSAR) (48 CHAPTER 3) CLAUSES:

(1)		HHSAR Clause 352.223-70, Safety and Health (January 2001).

(2)		HHSAR 352.224-70, Confidentiality of Information (APRIL 1984 – including revisions mandated by the 1/3/2005 Register notice which was effective March 2005).

(3)		HHSAR Clause 352.270-1, Accessibility of Meetings, Conferences and Seminars to Persons with Disabilities (January 2001).

(4)		HHSAR Clause 352.270-8, Protection of Human Subjects (March 2005).

  - HHSAR Clause 352.270-9, Care of Live Vertebrate Animals (March 2005).

  - HHSAR Clause 352.333-7001, Choice of Law (Overseas) (March 2005)

c.	NATIONAL INSTITUTES OF HEALTH (NIH) RESEARCH CONTRACTING (RC) CLAUSES:

The following clauses are attached and made a part of this contract:

(1)		NIH (RC)-7, Procurement of Certain Equipment (April 1984)

(2)		NIH(RC)-11, Research Patient Care Costs (4/1/84).

ARTICLE I.4.  ADDITIONAL FAR CONTRACT CLAUSES INCLUDED IN FULL TEXT

Additional clauses other than those listed below which are based on the type of contract/Contractor shall be determined during negotiations.  Any contract awarded from this solicitation will contain the following:

This contract incorporates the following clauses in full text.

FEDERAL ACQUISITION REGULATION (FAR)(48 CFR CHAPTER 1) CLAUSES:

a.	FAR Clause 52.222-39, Notification Of Employee Rights Concerning Payment Of Union Dues Or Fees (December 2004)

(a)	Definition. As used in this clause--

United States means the 50 States, the District of Columbia, Puerto Rico, the Northern Mariana Islands, American Samoa, Guam, the U.S. Virgin Islands, and Wake Island.

(b)	Except as provided in paragraph (e) of this clause, during the term of this contract, the Contractor shall post a notice, in the form of a poster, informing employees of their rights concerning union membership and payment of union dues and fees, in conspicuous places in and about all its plants and offices, including all places where notices to employees are customarily posted.  The notice shall include the following information (except that the information pertaining to National Labor Relations Board shall not be included in notices posted in the plants or offices of carriers subject to the Railway Labor Act, as amended (45 U.S.C. 151-188)).

Notice to Employees

Under Federal law, employees cannot be required to join a union or maintain membership in a union in order to retain their jobs.  Under certain conditions, the law permits a union and an employer to enter into a union-security agreement requiring employees to pay uniform periodic dues and initiation fees. However, employees who are not union members can object to the use of their payments for certain purposes and can only be required to pay their share of union costs relating to collective bargaining, contract administration, and grievance adjustment.

If you do not want to pay that portion of dues or fees used to support activities not related to collective bargaining, contract administration, or grievance adjustment, you are entitled to an appropriate reduction in your payment.  If you believe that you have been required to pay dues or fees used in part to support activities not related to collective bargaining, contract administration, or grievance adjustment, you may be entitled to a refund and to an appropriate reduction in future payments.

For further information concerning your rights, you may wish to contact the National Labor Relations Board (NLRB) either at one of its Regional offices or at the following address or toll free number:

National Labor Relations Board

Division of Information

1099 14th Street, N.W.

Washington, DC 20570

1-866-667-6572

1-866-316-6572 (TTY)

To locate the nearest NLRB office, see NLRB's website at http://www.nlrb.gov.

(c)	The Contractor shall comply with all provisions of Executive Order 13201 of February 17, 2001, and related implementing regulations at 29 CFR part 470, and orders of the Secretary of Labor.

(d)	In the event that the Contractor does not comply with any of the requirements set forth in paragraphs (b), (c), or (g), the Secretary may direct that this contract be cancelled, terminated, or suspended in whole or in part, and declare the Contractor ineligible for further Government contracts in accordance with procedures at 29 CFR part 470, Subpart B--Compliance Evaluations, Complaint Investigations and Enforcement Procedures.  Such other sanctions or remedies may be imposed as are provided by 29 CFR part 470, which implements Executive Order 13201, or as are otherwise provided by law.

(e)	The requirement to post the employee notice in paragraph (b) does not apply to--

(1)	Contractors and subcontractors that employ fewer than 15 persons;

(2)	Contractor establishments or construction work sites where no union has been formally recognized by the Contractor or certified as the exclusive bargaining representative of the Contractor's employees;

(3)	Contractor establishments or construction work sites located in a jurisdiction named in the definition of the United States in which the law of that jurisdiction forbids enforcement of union-security agreements;

(4)	Contractor facilities where upon the written request of the Contractor, the Department of Labor Deputy Assistant Secretary for Labor-Management Programs has waived the posting requirements with respect to any of the Contractor's facilities if the Deputy Assistant Secretary finds that the Contractor has demonstrated that--

(i)	The facility is in all respects separate and distinct from activities of the Contractor related to the performance of a contract; and

(ii)	Such a waiver will not interfere with or impede the effectuation of the Executive order; or

(5)	Work outside the United States that does not involve the recruitment or employment of workers within the United States.

(f)	The Department of Labor publishes the official employee notice in two variations; one for contractors covered by the Railway Labor Act and a second for all other contractors. The Contractor shall--

(1)	Obtain the required employee notice poster from the Division of Interpretations and Standards, Office of Labor-Management Standards, U.S. Department of Labor, 200 Constitution Avenue, NW, Room N-5605, Washington, DC 20210, or from any field office of the Department's Office of Labor-Management Standards or Office of Federal Contract Compliance Programs;

(2)	Download a copy of the poster from the Office of Labor-Management Standards website at http://www.olms.dol.gov; or

(3)	Reproduce and use exact duplicate copies of the Department of Labor's official poster.

(g)	The Contractor shall include the substance of this clause in every subcontract or purchase order that exceeds the simplified acquisition threshold, entered into in connection with this contract, unless exempted by the Department of Labor Deputy Assistant Secretary for Labor-Management Programs on account of special circumstances in the national interest under authority of 29 CFR 470.3(c).  For indefinite quantity subcontracts, the Contractor shall include the substance of this clause if the value of orders in any calendar year of the subcontract is expected to exceed the simplified acquisition threshold.  Pursuant to 29 CFR part 470, Subpart B--Compliance Evaluations, Complaint Investigations and Enforcement Procedures, the Secretary of Labor may direct the Contractor to take such action in the enforcement of these regulations, including the imposition of sanctions for noncompliance with respect to any such subcontract or purchase order.  If the Contractor becomes involved in litigation with a subcontractor or vendor, or is threatened with such involvement, as a result of such direction, the Contractor may request the United States, through the Secretary of Labor, to enter into such litigation to protect the interests of the United States.

PART III - LIST OF DOCUMENTS, EXHIBITS AND OTHER ATTACHMENTS

SECTION J - LIST OF ATTACHMENTS

The following documents are incorporated into this RFP:

SOLICITATION ATTACHMENTS:

| Attachment No. | Title | Location |
| --- | --- | --- |
| Attachment 1: | Packaging and Delivery of Proposal | http://www.niaid.nih.gov/contract/eproposal.htm |
| Attachment 2: | Proposal Intent Response Sheet | See Attachment Section at the end of this RFP |
| Attachment 3: | Statement of Work | See Attachment Section at the end of this RFP |
| Attachment 4: | Information Technology Systems Security - Prospective Offeror Non-Disclosure Agreement | http://rcb.cancer.gov/rcb-internet/forms/IT-security-nondisclosure.pdf |
| Attachment 5: | Appendix A Additional Technical Proposal instructions | See Attachment Section at the end of this RFP |
| Attachment 6: | Appendix B Additional Business Proposal Instructions (Uniform Assumptions) | See Attachment Section at the end of this RFP |

TECHNICAL PROPOSAL ATTACHMENTS:  (The following attachments must be completed, where applicable, and submitted with the Technical Proposal.)

| Attachment No. | Title | Location |
| --- | --- | --- |
| Attachment 7: | Targeted/Planned Enrollment Table | http://rcb.cancer.gov/rcb-internet/forms/enroll-table.pdf |
| Attachment 8: | Annual Technical Progress Report Format for Each Study | http://rcb.cancer.gov/rcb-internet/forms/atpr.pdf |
| Attachment 9: | Technical Proposal Cost Summary | http://www.niaid.nih.gov/contract/forms.htm |
| Attachment 10: | Summary of Related Activities | http://www.niaid.nih.gov/contract/forms.htm |
| Attachment 11: | Government Notice for Handling Proposals | http://www.niaid.nih.gov/contract/forms/form7.pdf |
| Attachment 12: | Protection of Human Subjects Assurance Identification/IRB Certification/Declaration of Exemption, OMB Form No. 0990-0263 (formerly Optional Form 310 | http://rcb.cancer.gov/rcb-internet/forms/of310.pdf |
| Attachment 13: | Project Objectives, NIH 1688-1 | http://rcb.cancer.gov/rcb-internet/forms/nih1688-1.pdf |

BUSINESS PROPOSAL ATTACHMENTS:  (The following attachments must be completed, where applicable, and submitted with the Business Proposal.)

| Attachment No. | Title | Location |
| --- | --- | --- |
| Attachment 14: | Proposal Summary and Data Record, NIH-2043 | http://www.niaid.nih.gov/contract/forms.htm |
| Attachment 15: | Small Business Subcontracting Plan | http://rcb.cancer.gov/rcb-internet/forms/sb-subplan-nci.pdf |
| Attachment 16: | Breakdown of Proposed Estimated Costs (plus Fee) with Excel Spreadsheet | http://www.niaid.nih.gov/contract/forms.htm http://ocm.od.nih.gov/contracts/spsh/spshexcl.xls |
| Attachment 17: | Offeror's Points of Contact | http://www.niaid.nih.gov/contract/forms.htm |
| Attachment 18: | Disclosure of Lobbying Activities, OMB Form SF-LLL | http://rcb.cancer.gov/rcb-internet/forms/sflllin.pdf |

INFORMATIONAL ATTACHMENTS:  (The following Attachments and Reports will become part of any contract resulting from this RFP and will be required during contract performance.)

| Attachment No. | Title | Location |
| --- | --- | --- |
| Attachment 19: | Invoice/Financing Request Instructions--Cost-Reimbursement, NIH(RC)-1 | http://rcb.cancer.gov/rcb-internet/forms/rc1.pdf |
| Attachment 20: | Invoice/Financing Request and Contract Financial Reporting Instructions--Cost Reimbursement, NIH(RC)-4 | http://rcb.cancer.gov/rcb-internet/forms/rc4.pdf |
| Attachment 21: | Financial Report of Individual Project/Contract, NIH 2706 | http://www.niaid.nih.gov/contract/forms/nih-2706.pdf |
| Attachment 22: | Instructions for Completing Form NIH 2706 | http://www.niaid.nih.gov/contract/forms/instructions2706.pdf |
| Attachment 23: | Privacy Act System of Records System of Records No.09-25-0200 is applicable to this RFP. | http://oma.od.nih.gov/ms/privacy/pa-files/read02systems.htm |
| Attachment 24: | Safety and Health, HHSAR Clause 352.223-70 | http://www.niaid.nih.gov/contract/forms/form10.pdf |
| Attachment 25: | Procurement of Certain Equipment, NIH(RC)-7 | http://www.niaid.nih.gov/contract/forms/NIH-RC-7.pdf |
| Attachment 26: | Research Patient Care Costs, NIH(RC)-11 | http://www.niaid.nih.gov/contract/forms/nih-rc-11.pdf |
| Attachment 27: | Inclusion Enrollment Report | http://rcb.cancer.gov/rcb-internet/forms/inclusion-enrollment.pdf |
| Attachment 28: | Employee Separation Checklist | http://rcb.cancer.gov/rcb-internet/forms/Emp-sep-checklist.pdf |
| Attachment 29: | Government Property Schedule | See Attachment Section at the end of this RFP |
| Attachment 30: | Commitment To Protect Non-Public Information Contractor Agreement | http://irm.cit.nih.gov/security/Nondisclosure.pdf |
| Attachment 31: | Roster of Employees Requiring Suitability Investigations | http://ais.nci.nih.gov/forms/Suitability-roster.xls |

Immune Tolerance Network Informational Appendices

| Attachment No. | Title | Location |
| --- | --- | --- |
| Attachment 32: | Appendix C Ongoing ITN Clinical Trials and Tolerance Assay Studies | See Attachment Section at end of this RFP |
| Attachment 33: | Appendix D ITN Core Facilities and Laboratories | See Attachment Section at end of this RFP |
| Attachment 34: | Appendix E NIAID-Funded Clinical Research Support Services | See Attachment Section at end of this RFP |
| Attachment 35: | Appendix F NIH Funded Clinical Research Programs | See Attachment Section at end of this RFP |
| Attachment 36: | Appendix G Internet Sites for ITN and RFP | See Attachment Section at end of this RFP |
| Attachment 37 | Contractor Request to Subcontract Checklist | See Attachment Section at end of this RFP |

PART IV - REPRESENTATIONS AND INSTRUCTIONS

SECTION K - REPRESENTATIONS, CERTIFICATIONS AND OTHER STATEMENTS OF OFFERORS

SECTION K can be accessed electronically from the INTERNET at the following address:

http://rcb.cancer.gov/rcb-internet/wkf/sectionk.pdf

If you are unable to access this document electronically, you may request a copy from the Contracting Officer identified on the cover page of this solicitation.

IF YOU INTEND TO SUBMIT A PROPOSAL, YOU MUST COMPLETE SECTION K AND SUBMIT IT AS PART OF YOUR BUSINESS PROPOSAL.

SECTION L - INSTRUCTIONS, CONDITIONS AND NOTICES TO OFFERORS

1.     GENERAL INFORMATION

- INSTRUCTIONS TO OFFERORS--COMPETITIVE ACQUISITION [FAR Provision 52.215-1 (January 2004)]

(1)	Definitions. As used in this provision--

Discussions are negotiations that occur after establishment of the competitive range that may, at the Contracting Officer's discretion, result in the offeror being allowed to revise its proposal.

"In writing", "writing", or "written" means any worded or numbered expression that can be read, reproduced, and later communicated, and includes electronically transmitted and stored information.

"Proposal modification" is a change made to a proposal before the solicitation's closing date and time, or made in response to an amendment, or made to correct a mistake at any time before award.

"Proposal revision" is a change to a proposal made after the solicitation closing date, at the request of or as allowed by a Contracting Officer as the result of negotiations.

"Time," if stated as a number of days, is calculated using calendar days, unless otherwise specified, and will include Saturdays, Sundays, and legal holidays. However, if the last day falls on a Saturday, Sunday, or legal holiday, then the period shall include the next working day.

(2)	Amendments to solicitations. If this solicitation is amended, all terms and conditions that are not amended remain unchanged. Offerors shall acknowledge receipt of any amendment to this solicitation by the date and time specified in the amendment(s).

(3)	Submission, modification, revision, and withdrawal of proposals. (1) Unless other methods (e.g., electronic commerce or facsimile) are permitted in the solicitation, proposals and modifications to proposals shall be submitted in paper media in sealed envelopes or packages (i) addressed to the office specified in the solicitation, and (ii) showing the time and date specified for receipt, the solicitation number, and the name and address of the offeror. Offerors using commercial carriers should ensure that the proposal is marked on the outermost wrapper with the information in paragraphs (c)(1)(i) and (c)(1)(ii) of this provision.

(a)	The first page of the proposal must show--

1.	The solicitation number;

2.	The name, address, and telephone and facsimile numbers of the offeror (and electronic address if available);

3.	A statement specifying the extent of agreement with all terms, conditions, and provisions included in the solicitation and agreement to furnish any or all items upon which prices are offered at the price set opposite each item;

4.	Names, titles, and telephone and facsimile numbers (and electronic addresses if available) of persons authorized to negotiate on the offeror's behalf with the Government in connection with this solicitation; and

5.	Name, title, and signature of person authorized to sign the proposal. Proposals signed by an agent shall be accompanied by evidence of that agent's authority, unless that evidence has been previously furnished to the issuing office.

(4)	Submission, modification, revision, and withdrawal of proposals.  (i) Offerors are responsible for submitting proposals, and any modifications or revisions, so as to reach the Government office designated in the solicitation by the time specified in the solicitation.  If no time is specified in the solicitation, the time for receipt is 4:30 p.m., local time, for the designated Government office on the date that proposal or revision is due.

(a)	Any proposal, modification, or revision received at the Government office designated in the solicitation after the exact time specified for receipt of offers is "late" and will not be considered unless it is received before award is made, the Contracting Officer determines that accepting the late offer would not unduly delay the acquisition; and--

1.	If it was transmitted through an electronic commerce method authorized by the solicitation, it was received at the initial point of entry to the Government infrastructure not later than 5:00 p.m. one working day prior to the date specified for receipt of proposals; or

2.	There is acceptable evidence to establish that it was received at the Government installation designated for receipt of offers and was under the Government's control prior to the time set for receipt of offers; or

3.	It is the only proposal received.

(b)	However, a late modification of an otherwise successful proposal that makes its terms more favorable to the Government, will be considered at any time it is received and may be accepted.

(c)	Acceptable evidence to establish the time of receipt at the Government installation includes the time/date stamp of that installation on the proposal wrapper, other documentary evidence of receipt maintained by the installation, or oral testimony or statements of Government personnel.

(d)	If an emergency or unanticipated event interrupts normal Government processes so that proposals cannot be received at the office designated for receipt of proposals by the exact time specified in the solicitation, and urgent Government requirements preclude amendment of the solicitation, the time specified for receipt of proposals will be deemed to be extended to the same time of day specified in the solicitation on the first work day on which normal Government processes resume.

(e)	Proposals may be withdrawn by written notice received at any time before award. Oral proposals in response to oral solicitations may be withdrawn orally. If the solicitation authorizes facsimile proposals, proposals may be withdrawn via facsimile received at any time before award, subject to the conditions specified in the provision at 52.215-5, Facsimile Proposals. Proposals may be withdrawn in person by an offeror or an authorized representative, if the identity of the person requesting withdrawal is established and the person signs a receipt for the proposal before award.

(5)	Unless otherwise specified in the solicitation, the offeror may propose to provide any item or combination of items.

(6)	Offerors shall submit proposals in response to this solicitation in English, unless otherwise permitted by the solicitation, and in U.S. dollars, unless the provision at FAR 52.225-17, Evaluation of Foreign Currency Offers, is included in the solicitation.

(7)	Offerors may submit modifications to their proposals at any time before the solicitation closing date and time, and may submit modifications in response to an amendment, or to correct a mistake at any time before award.

(8)	Offerors may submit revised proposals only if requested or allowed by the Contracting Officer.

(9)	Proposals may be withdrawn at any time before award. Withdrawals are effective upon receipt of notice by the Contracting Officer.

(10)	Offer expiration date. Proposals in response to this solicitation will be valid for the number of days specified on the solicitation cover sheet (unless a different period is proposed by the offeror).

(11)	Restriction on disclosure and use of data. (1) The proposal submitted in response to this request

may contain data (trade secrets; business data, e.g., commercial information, financial Information, and cost and pricing data; and technical data) which the offeror, including its prospective subcontractor(s), does not want used or disclosed for any purpose other than for evaluation of the proposal. The use and disclosure of any data may be so restricted; provided, that the Government determines that the data is not required to be disclosed under the Freedom of Information Act, 5 U.S.C. 552, as amended, and the offeror marks the cover sheet of the proposal with the following legend, specifying the particular portions of the proposal which are to be restricted in accordance with the conditions of the legend. The Government's determination to withhold or disclose a record will be based upon the particular circumstances involving the record in question and whether the record may be exempted from disclosure under the Freedom of Information Act. The legend reads:

Unless disclosure is required by the Freedom of Information Act, 5 U.S.C. 552, as amended, (the Act) as determined by Freedom of Information (FOI) officials of the Department of Health and Human Services, data contained in the portions of this proposal which have been specifically identified by page number, paragraph, etc. by the offeror as containing restricted information shall not be used or disclosed except for evaluation purposes.

The offeror acknowledges that the Department may not be able to withhold a record (data, document, etc.) nor deny access to a record requested pursuant to the Act and that the Department's FOI officials must make that determination. The offeror hereby agrees that the Government is not liable for disclosure if the Department has determined that disclosure is required by the Act.

If a contract is awarded to the offeror as a result of, or in connection with, the submission of this proposal, the Government shall have right to use or disclose the data to the extent provided in the contract. Proposals not resulting in a contract remain subject to the Act.

The offeror also agrees that the Government is not liable for disclosure or use of unmarked data and may use or disclose the data for any purpose, including the release of the information pursuant to requests under the Act. The data subject to this restriction are contained in pages (insert page numbers, paragraph designations, etc. or other identification).

In addition, the offeror should mark each page of data it wishes to restrict with the following statement:

“Use or disclosure of data contained on this page is subject to the restriction on the cover sheet of this proposal or quotation.”

Offerors are cautioned that proposals submitted with restrictive legends or statements differing in substance from the above legend may not be considered for award. The Government reserves the right to reject any proposal submitted with a nonconforming legend.

(12)	Contract award.

(a) The Government intends to award a contract or contracts resulting from this solicitation

to the responsible offeror(s) whose proposal(s) represents the best value after evaluation in accordance with the factors and subfactors in the solicitation.

(b)	The Government may reject any or all proposals if such action is in the Government's interest.

(c)	The Government may waive informalities and minor irregularities in proposals received.

(d)	The Government intends to evaluate proposals and award a contract without discussions with offerors (except clarifications as described in FAR 15.306(a)). Therefore, the offeror's initial proposal should contain the offeror's best terms from a cost or price and technical standpoint. The Government reserves the right to conduct discussions if the Contracting Officer later determines them to be necessary. If the Contracting Officer determines that the number of proposals that would otherwise be in the competitive range exceeds the number at which an efficient competition can be conducted, the Contracting Officer may limit the number of proposals in the competitive range to the greatest number that will permit an efficient competition among the most highly rated proposals.

(e)	The Government reserves the right to make an award on any item for a quantity less than the quantity offered, at the unit cost or prices offered, unless the offeror specifies otherwise in the proposal.

(f)	The Government reserves the right to make multiple awards if, after considering the additional administrative costs, it is in the Government's best interest to do so.

(g)	Exchanges with offerors after receipt of a proposal do not constitute a rejection or counteroffer by the Government.

(h)	The Government may determine that a proposal is unacceptable if the prices proposed are materially unbalanced between line items or subline items. Unbalanced pricing exists when, despite an acceptable total evaluated price, the price of one or more contract line items is significantly overstated or understated as indicated by the application of cost or price analysis techniques. A proposal may be rejected if the Contracting Officer determines that the lack of balance poses an unacceptable risk to the Government.

(i)	If a cost realism analysis is performed, cost realism may be considered by the source selection authority in evaluating performance or schedule risk.

(j)	A written award or acceptance of proposal mailed or otherwise furnished to the successful offeror within the time specified in the proposal shall result in a binding contract without further action by either party.

(k)	If a post-award debriefing is given to requesting offerors, the Government shall disclose the following information, if applicable:

1. 	The agency's evaluation of the significant weak or deficient factors in the debriefed offeror's offer.

2.	The overall evaluated cost or price and technical rating of the successful and debriefed offeror and past performance information on the debriefed offeror.

3.	The overall ranking of all offerors, when any ranking was developed by the agency during source selection;

4.	A summary of the rationale for award.

5.	For acquisitions of commercial items, the make and model of the item to be delivered by the successful offeror.

6. 	Reasonable responses to relevant questions posed by the debriefed offeror as to whether source-selection procedures set forth in the solicitation, applicable regulations, and other applicable authorities were followed by the agency.

(End of Provision)

b.	NAICS CODE AND SIZE STANDARD

Note:  The following information is to be used by the offeror in preparing its Representations and Certifications (See Section K of this RFP), specifically in completing the provision entitled, SMALL BUSINESS PROGRAM REPRESENTATION, FAR Clause 52.219-1.

(1)	The North American Industry Classification System (NAICS) code for this acquisition is 541710 .

(2)	The small business size standard is 500 employees.

THIS REQUIREMENT IS NOT SET-ASIDE FOR SMALL BUSINESS.  However, the Federal Acquisition Regulation (FAR) requires in EVERY solicitation, (except for foreign acquisitions) the inclusion of the North American Industry Classification (NAICS) Code and corresponding size standard which best describes the nature of the requirement in the solicitation.

- TYPE OF CONTRACT AND NUMBER OF AWARD(S)

It is anticipated that One Award will be made from this solicitation and that the award will be made on or about February 1, 2007.               .

It is anticipated that the award from this solicitation will be a multiple-year cost reimbursement type completion contract and a term of seven years.  Incremental funding will be used [see Section L.2.c. Business Proposal Instructions].  Multiple options for additional services are anticipated.  These options if exercised will not exceed the seven year period of performance of the basic effort.

- ESTIMATE OF EFFORT

It is expected that a completion type contract will be awarded as a result of this RFP.  To assist you in the preparation of your proposal, the Government considers the basic effort to be approximately 62.8 full time equivalents (FTE’s) per year.  The level of effort for the options, if exercised, will vary but the government estimates a total of 6.5 full time equivalents.  This information is furnished for the offeror's information only and is not to be considered restrictive for proposal purposes.

- COMMITMENT OF PUBLIC FUNDS

The Contracting Officer is the only individual who can legally commit the Government to the expenditure of public funds in connection with the proposed procurement.  Any other commitment, either explicit or implied, is invalid.

- COMMUNICATIONS PRIOR TO CONTRACT AWARD

Offerors shall direct all communications to the attention of the Contract Specialist or Contracting Officer cited on the face page of this RFP.  Communications with other officials may compromise the competitiveness of this acquisition and result in cancellation of the requirement.

- RELEASE OF INFORMATION

Contract selection and award information will be disclosed to offerors in accordance with regulations applicable to negotiated acquisition.  Prompt written notice will be given to unsuccessful offerors as they are eliminated from the competition, and to all offerors following award.

- COMPARATIVE IMPORTANCE OF PROPOSALS

You are advised that paramount consideration shall be given to the evaluation of technical proposals.  All evaluation factors other than cost or price, when combined, are significantly more important than cost or price.  The relative importance of the evaluation factors are specified in SECTION M of this solicitation.  However, the Government reserves the right to make an award to the best advantage of the Government, cost and other factors considered.

- PREPARATION COSTS

This RFP does not commit the Government to pay for the preparation and submission of a proposal.

- SERVICE OF PROTEST (AUGUST 1996) - FAR 52.233-2

(a)	Protests, as defined in section 33.101 of the Federal Acquisition Regulation, that are filed directly with an agency, and copies of any protests that are filed with the General Accounting Office (GAO), shall be served on the Contracting Officer (addressed as follows) by obtaining written and dated acknowledgment of receipt from:

Contracting Officer

Office of Acquisitions

NIH, NIAID

Room 3214

6700-B Rockledge Drive, MSC 7612

BETHESDA MD 20892-7612

(b)	The copy of any protest shall be received in the office designated above within one day of filing a protest with the GAO.

(End of Provision)

- LATE PROPOSALS AND REVISIONS, HHSAR 352.215-70

Notwithstanding the procedures contained in FAR 52.215-1(c)(3) of the provision of this solicitation entitled Instructions to Offerors-Competitive Acquisition, a proposal received after the date specified for receipt may be considered if it offers significant cost or technical advantages to the Government; and it was received before proposals were distributed for evaluation, or within five calendar days after the exact time specified for receipt, whichever is earlier.

(End of provision)

2.    INSTRUCTIONS TO OFFERORS

a.	GENERAL INSTRUCTIONS

INTRODUCTION

The following instructions will establish the acceptable minimum requirements for the format and contents of proposals.  Special attention is directed to the requirements for technical and business proposals to be submitted in accordance with these instructions.

- (1)		Contract Type and General Clauses

It is contemplated that a cost-reimbursement, completion type contract will be awarded.  (See General Information)  Any resultant contract shall include the clauses applicable to the selected offeror's organization and type of contract awarded as required by Public Law, Executive Order, or acquisition regulations in effect at the time of execution of the proposed contract.

- Authorized Official and Submission of Proposal

The proposal must be signed by an official authorized to bind your organization and must stipulate that it is predicated upon all the terms and conditions of this RFP.  Your proposal shall be submitted in the number of copies, to the addresses, and marked as indicated in the Attachment entitled, PACKAGING AND DELIVERY OF PROPOSAL, Part III, Section J hereof. Proposals will be typewritten, paginated, reproduced on letter size paper and will be legible in all required copies. To expedite the proposal evaluation, all documents required for responding to the RFP should be placed in the following order:

I.	COVER PAGE

Include RFP title, number, name of organization, DUNS No., identification of the proposal part, and indicate whether the proposal is an original or a copy.

II.	TECHNICAL PROPOSAL

It is recommended that the technical proposal consist of a cover page, a table of contents, and the information requested in the Technical Proposal Instructions and as specified in SECTION J, List of Attachments.

III.	BUSINESS PROPOSAL

It is recommended that the business proposal consist of a cover page, a table of contents, and the information requested in the Business Proposal Instructions and as specified in SECTION J, List of Attachments.

- Proposal Summary and Data Record (NIH-2043)

The Offeror must complete the Form NIH-2043, attached, with particular attention to the length of time the proposal is firm and the designation of those personnel authorized to conduct negotiations.  (See Section J, Attachment entitled, PROPOSAL SUMMARY AND DATA RECORD.)

- Separation of Technical and Business Proposals

The proposal must be prepared in two parts:  a "Technical Proposal" and a "Business Proposal."  Each of the parts shall be separate and complete in itself so that evaluation of one may be accomplished independently of, and concurrently with, evaluation of the other.  The technical proposal must include direct cost and resources information, such as labor-hours and categories and applicable rates, materials, subcontracts, travel, etc., and associated costs so that the offeror's understanding of the project may be evaluated (See Attachment entitled, TECHNICAL PROPOSAL COST INFORMATION/SUMMARY OF LABOR AND DIRECT COSTS).  However, the technical proposal should not include pricing data relating to individual salary information, indirect cost rates or amounts, fee amounts (if any), and total costs.  The technical proposal should disclose your technical approach in as much detail as possible, including, but not limited to, the requirements of the technical proposal instructions.

- Alternate Proposals

You may, at your discretion, submit alternate proposals, or proposals which deviate from the requirements; provided, that you also submit a proposal for performance of the work as specified in the statement of work.  Such proposals may be considered if overall performance would be improved or not compromised and if they are in the best interests of the Government.  Alternative proposals, or deviations from any requirements of this RFP, shall be clearly identified.

- Evaluation of Proposals

The Government will evaluate technical proposals in accordance with the criteria set forth in Part IV, Section M of this RFP.

- Potential Award Without Discussions

The Government reserves the right to award a contract without discussions if the Contracting Officer determines that the initial prices are fair and reasonable and that discussions are not necessary.

- Use of the Metric System of Measurement

It is the policy of the Department of Health and Human Services to support the Federal transition to the metric system and to use the metric system of measurement in all procurement, grants, and other business related activities unless such use is impracticable or is likely to cause significant inefficiencies.

The offeror is encouraged to prepare their proposal using either "Hard Metric," "Soft Metric," or "Dual Systems" of measurement.  The following definitions are provided for your information:

Hard Metric - The replacement of a standard inch-pound size with an accepted metric size for a particular purpose.  An example of size substitution might be:  selling or packaging liquids by the liter instead of by the pint or quart (as for soft drinks), or instead of by the gallon (as for gasoline).

Soft Metric - The result of a mathematical conversion of inch-pound measurements to metric equivalents for a particular purpose.  The physical characteristics are not changed.

Dual Systems - The use of both inch-pound and metric systems.  For example, an item is designed, produced, and described in inch-pound values with soft metric values also shown for information or comparison purposes.

- Standards for Privacy of Individually Identifiable Health Information

The Department of Health and Human Services (DHHS) issued final modifications to the “Standards for Privacy of Individually Identifiable Health Information,” the “Privacy Rule,” on August 14, 2002.  The Privacy Rule is a federal regulation under the Health Insurance Portability and Accountability Act (HIPAA) of 1996 that governs the protection of individually identifiable health information and is administered and enforced by the DHHS Office for Civil Rights (OCR).  Those who must comply with the Privacy Rule (classified under the Rule as “covered entities” must do so by April 14, 2003 (with the exception of small health plans which have an extra year to comply.

Decisions about the applicability and implementation of the Privacy Rule reside with the contractor and his/her institution.  The OCR Web site (http://www.hhs.gov/ocr/) provides information of the Privacy Rule, including a complete Regulation Text and a set of decision tools on “Am I a covered entity?”  Information on the impact of the HIPAA Privacy Rule on NIH processes involving the review, award, and administration of grants, cooperative agreements and contracts can be found at: http://grants1.nih.gov/grants/guide/notice-files/NOT-OD-03-025.html.

- Care of Live Vertebrate Animals

a. 	The following notice is applicable when contract performance is expected to involve care of live vertebrate animals:

Notice to Offerors of Requirement for Compliance with the Public Health Service Policy on Humane Care and Use of Laboratory Animals (Revised 1986, Reprinted 2000)

The Public Health Service (PHS) Policy on Human Care and Use of Laboratory Animals establishes a number of requirements for research activities involving animals.  Before a PHS award may be made to an applicant organization, the organization shall file, with the Office of Extramural Research (OER), Office of Laboratory Animal Welfare (OLAW), National Institutes of Health (NIH), PHS, a written Animal Welfare Assurance which commits the organization to comply with the provisions of the PHS Policy on Humane Care and Use of Laboratory Animals by Awardee Institutions, the Animal Welfare Act, and the Guide for the Care and Use of Laboratory Animals prepared by the Institute of Laboratory Animal Resources.  In accordance with the PHS Policy on Humane Care and Use of Laboratory Animals by Awardee Institutions, applicant organizations must establish a committee, qualified through the experience and expertise of its members, to oversee the institution's animal program, facilities and procedures.  No PHS award involving the use of animals shall be made unless the Animal Welfare Assurance has been approved by OER, OLAW.  Prior to award, the Contracting Officer will notify Contractor(s) selected for projects that involve live vertebrate animals that an Animal Welfare Assurance is required.  The Contracting Officer will request that OER, OLAW negotiate an acceptable Animal Welfare Assurance with those Contractor(s).  For further information, OER, OLAW, may be contacted at Rockledge Center I - Suite 1050, 6705 Rockledge Drive, Bethesda, MD 20817, (301) 496-7163, ext 234.  FAX copies of the PHS Policy are available at (301) 402-2803.  This policy is also available on the internet at http://www.grants.nih.gov/grants/olaw/olaw.htm.

b.	The following information must be included in the offerors technical proposal:

-	identification of the species and approximate number of animals to be used;

-	rationale for involving animals, and for the appropriateness of the species and numbers used;

-	a complete description of the proposed use of the animals;

-	a description of procedures designed to assure that discomfort and injury to animals will be limited to that which is unavoidable in the conduct of scientifically valuable research, and that analgesic, anesthetic, and tranquilizing drugs will be used where indicated and appropriate to minimize discomfort and pain to animals; and

-	a description of any euthanasia method to be used.

c. 	If an Animal Assurance is already in place, the offeror's proposal shall include:

-The Animal Welfare Assurance number.

-The date last certified by OLAW.  (i.e. assurance letter from OLAW)

-Evidence of recent AAALAC Accreditation.

- Possession, Use and Transfer of Select Biological Agents or Toxins

Notice to Offerors of Requirements of:  42 CFR Part 73, Possession , Use, and  Transfer of Select Agents and Toxins (relating to public health and safety):

(http://www.cdc.gov/od/sap/42_cfr_73_final_rule.pdf);

7 CFR Part 331, Possession, Use, and Transfer of Select Agents and Toxins (relating to plant health or plant products) (http://www.aphis.usda.gov/programs/ag_selectagent/FinalRule3-18-05.pdf); and,

9 CFR Part 121, Possession, Use, and Transfer of Select Agents and Toxins (relating to human and animal health, animal health or animal products)

(http://www.aphis.usda.gov/programs/ag_selectagent/FinalRule3-18-05.pdf) - March 18, 2005.

These regulations implement the Public Health Security and Bioterrorism Preparedness and Response Act of 2002, and the Agricultural Bioterrorism Protection Act of 2002.  They are designed to improve the ability of the United States Government to prevent, prepare for, and respond to bioterrorism and other public health emergencies.  These regulations establish requirements regarding registration, security risk assessments, safety plans, security plans, emergency response plans, training, transfers, record keeping, inspections, and notifications.

Listings of HHS select agents and toxins, and overlap select agents or toxins as well as information about the registration process for domestic institutions, are available on the Select Agent Program Web site at http://www.cdc.gov/od/sap/  and http://www.cdc.gov/od/sap/docs/salist.pdf.  Listings of USDA select agents and toxins as well as information about the registration process for domestic institutions are available on the APHIS/USDA website at http://www.aphis.usda.gov/programs/ag_selectagent/index.html and http://www.aphis.usda.gov/programs/ag_selectagent/ag_bioterr_forms.html.  For foreign institutions, see the NIAID Select Agent Award information (http://www.niaid.nih.gov/ncn/clinical/default_biodefense.htm).

If the proposed contract will not involve Select Agents, the offeror must include a statement in its technical proposal that the work does not now nor will it in the future (i.e. throughout the life of the award) involve Select Agents.

Domestic Institutions

For prime or subcontract awards to domestic institutions that possess, use, and/or transfer Select Agents under this contract, the domestic institution must:

- include details about the select agent in their technical proposal, including the quantity proposed to be used during contract performance.

- comply with 42 CFR part 73, 7 CFR part 331 and/or 9 CFR part 121 at:

http://www.aphis.usda.gov/programs/ag_selectagent/FinalRule3-18-05.pdf, as required, before using NIH funds for research involving Select Agents.  No NIH funds can be used for research involving Select Agents if the final registration certificate is denied.

Foreign Institutions

For prime or subcontract awards to foreign institutions that possess, use, and/or transfer Select Agents under this contract, the foreign institution must:

- include details about the select agent in their technical proposal, including the quantity proposed to be used during contract performance.

- when requested during negotiations, provide information satisfactory to the NIAID/NIH that safety, security, and training standards equivalent to those described in 42 CFR part 73, 7 CFR part 331, and/or 9 CFR part 121 at:  http://www.aphis.usda.gov/programs/ag_selectagent/FinalRule3-18-05.pdf for U.S. institutions are in place and will be administered on behalf of all Select Agent work under the resulting contract.  The process for making this determination includes inspection of the foreign laboratory facility by an NIAID representative.  During this inspection, the foreign institution must provide the following information: concise summaries of safety, security, and training plans; names of all individuals at the foreign institution who will have access to the Select Agents and procedures for ensuring that only approved and appropriate individuals, in accordance with institution procedures, will have access to the Select Agents under the contract; and copies of or links to any applicable laws, regulations, policies, and procedures applicable to that institution for the safe and secure possession, use, and/or transfer of select agents.

An NIAID-chaired committee of U.S. federal employees (including representatives of NIH grants/contracts and scientific program management, CDC , Department of Justice and other federal intelligence agencies, and Department of State) will ultimately assess the results of the facility inspection, the regulations, policies, and procedures of the foreign institution for equivalence  to the U.S. requirements described in 42 CFR part 73, 7 CFR part 331, and/or 9 CFR part 121 at: 	http://www.aphis.usda.gov/programs/ag_selectagent/FinalRule3-18-05.pdf.

The committee will provide recommendations to the DEA Director, NIAID.  The DEA Director will make the approval decision and notify the Contracting Officer.  The Contracting Officer will inform the prime contractor of the approval status of the foreign institution.  No NIH funds can be used for research involving Select Agents at a foreign institution until NIAID grants this approval.

(12)	Obtaining and Disseminating Biomedical Research Resources

As a public sponsor of biomedical research, the National Institutes of Health (NIH) has a dual interest in accelerating scientific discovery and facilitating product development.  Intellectual property restrictions can stifle the broad dissemination of new discoveries and limit future avenues of research and product development.  At the same time, reasonable restrictions on the dissemination of research tools are sometimes necessary to protect legitimate proprietary interests and to preserve incentives for commercial development.  To assist NIH contractors achieve an appropriate balance, the NIH has provided guidance in the form of a two-part document, consisting of Principles setting forth the fundamental concepts and Guidelines that provide specific information to patent and license professionals and sponsored research administrators for implementation.

The purpose of these Principles and Guidelines is to assist NIH funding recipients in determining:  1) Reasonable terms and conditions for making NIH-funded research resources available to scientists in other institutions in the public and private sectors (disseminating research tools); and 2) Restrictions to accept as a condition of receiving access to research tools for use in NIH-funded research (acquiring research tools).  The intent is to help recipients ensure that the conditions they impose and accept on the transfer of research tools will facilitate further biomedical research, consistent with the requirements of the Bayh-Dole Act and NIH funding policy.

This policy, entitled, "Sharing Biomedical Research Resources:  Principles and Guidelines for Recipients of NIH Research Grants and Contracts," (Federal Register Notice, December 23, 1999 [64 FR 72090] will be included in any contract awarded from this solicitation.  It can be found at the following website:  http://ott.od.nih.gov/NewPages/64FR72090.pdf.

(a) 	Sharing Research Data

[Note:  The NIH Guide announcement referenced below states that this policy is applicable to "all investigator-initiated applications with direct costs greater than $500,000 in any single year."  This is an overall grant policy which requires that an applicant must seek agreement by NIH to accept assignment of their application in advance of the submission date.  As such, this policy has no correlation to the contract process, therefore, the threshold is not applicable to contracts.  Thus, this article applies to any contract that may generate research data.]

The NIH endorses the sharing of final research data to expedite the translation of research results into knowledge, products, and procedures to improve human health.  This contract is expected to generate research data.  Therefore, the offeror must submit a plan for data sharing or state why data sharing is not possible.  If data sharing is limited, the offeror should explain such limitations in its data sharing plan.  NIH's data sharing policy may be found at the following Web site:

http://grants.nih.gov/grants/guide/notice-files/NOT-OD-03-032.html

If the resultant contract is part of a collaborative program involving multiple sites, the data sharing will be governed by a dissemination plan to be developed jointly following award.  Offerors must include in their proposals a statement of willingness to work collaboratively after award with the other funded sites to prepare a joint dissemination plan.  Coordinating Center proposals should describe methods to coordinate the dissemination planning and implementation.  The Coordinating Center must include a budget and justification for any additional costs of this collaborative effort.

(b)	Sharing of Model Organisms for Biomedical Research

The  , also referred to as Principles and Guidelines for Recipients of NIH Research Grants and Contracts on Obtaining and Disseminating Biomedical Research Resources: Final Notice,  December 1999, supports the concept of timely sharing and distribution of research resources.  In accordance with NIH Guide Notice , dated May 7, 2004, and the September 10, 2004 extension of this policy , the NIH provides further sharing guidance with particular attention on model organisms for biomedical research.  Such organisms include, but are not limited to: mammalian models such as the mouse and rat, and non-mammalian models, such as budding yeast, social amoebae, round worm, fruit fly, zebra fish, and frog.  Research resources to be shared include genetically modified or mutant organisms, sperm, embryos, protocols for genetic and phenotypic screens, mutagenesis protocols, and genetic and phenotypic data for all mutant strains.

Offerors must include in their proposal a description of a specific plan for sharing and distributing unique model organism research resources generated using NIH funding so that other researchers can benefit from these resources, OR provide appropriate reasons why such sharing is restricted or not possible.  A reasonable time frame for periodic disposition of material and associated data must be specified in the proposal.  In addition, the plan must address if, or how, offerors will exercise their intellectual property rights while making model organisms and research resources available to the broader scientific community.  At a minimum, the plan should address the following:

-	Will material transfers be made with no more restrictive terms than in a Simple Letter Agreement (SLA) ( for the transfer of materials or the Uniform Biological Material Transfer Agreement (UBMTA) ()

-	How will inappropriate “reach-through” requirements (as discussed in the NIH Research Tools Policy) on materials transferred be discussed?

-	How will technologies remain widely available and accessible to the research community, for example, if any intellectual property rights arise for which a patent application may be filed?

Offerors may request funds in their cost proposal to defray reasonable costs associated with sharing materials or data or transfer of model organisms and associated data to appropriate repositories.

(13)  Privacy Act - Treatment of Proposal Information

The Privacy Act of 1974 (P.L. 93-579) requires that a Federal agency advise each individual whom it asks to supply information, the authority which authorizes the solicitation, whether disclosure is voluntary or mandatory, the principal purpose or purposes for which the information is intended to be used, the uses outside the agency which may be made of the information, and the effects on the individual, if any, of not providing all or any part of the requested information.

The NIH is requesting the information called for in this RFP pursuant to the authority provided by Sec. 301(a)(7) of the Public Health Service Act, as amended, and P.L. 92-218, as amended.

Providing the information requested is entirely voluntary. The collection of this information is for the purpose of conducting an accurate, fair, and adequate review prior to a discussion as to whether to award a contract.

Failure to provide any or all of the requested information may result in a less than adequate review.

In addition, the Privacy Act of 1974 (P.L. 93-579, Section 7) requires that the following information be provided when individuals are requested to disclose their social security number.

Provision of the social security number is voluntary.  Social security numbers are requested for the purpose of accurate and efficient identification, referral, review and management of NIH contracting programs.  Authority for requesting this information is provided by Section 301 and Title IV of the PHS Act, as amended.

The information provided by you may be routinely disclosed for the following purposes:

-	to the cognizant audit agency and the General Accounting Office for auditing.

-	to the Department of Justice as required for litigation.

-	to respond to congressional inquiries.

-	to qualified experts, not within the definition of Department employees, for opinions as a part of the review process.

(14)	Selection of Offerors

- The acceptability of the scientific and technical portion of each research contract proposal will be evaluated by a technical review committee.  The committee will evaluate each proposal in strict conformity with the evaluation criteria of the RFP, utilizing point scores and written critiques.  The committee may suggest that the Contracting Officer request clarifying information from an offeror.

- The business portion of each contract proposal will be subjected to a cost and price analysis,

management analysis, etc.

- If award will be made without conducting discussions, offerors may be given the opportunity to clarify certain aspects of their proposal (e.g., the relevance of an offeror's past performance information and adverse past performance information to which the offeror has not previously had an opportunity to respond) or to resolve minor or clerical errors.

- If the Government intends to conduct discussions prior to awarding a contract-

(1)	Communications will be held with offerors whose past performance information is the determining factor preventing them from being placed within the competitive range.  Such communications shall address adverse past performance information to which an offeror has not had a prior opportunity to respond.  Also, communications may be held with any other offerors whose exclusion from, or inclusion in, the competitive range is uncertain.

Such communications shall not be used to cure proposal deficiencies or omissions that alter the technical or cost elements of the proposal, and/or otherwise revise the proposal, but may be considered in rating proposals for the purpose of establishing the competitive range.

(2)	The Contracting Officer will, in concert with program staff, decide which proposals are in the competitive range.  The competitive range will be comprised of all of the most highly rated proposals.  Oral or written discussions will be conducted with all offerors in the competitive range.

While it is NIAID's policy to conduct discussions with all offerors in the competitive range, NIAID reserves the right, in special circumstances, to limit the number of proposals included in the competitive range to the greatest number that will permit an efficient competition.  All aspects of the proposals are subject to discussions, including cost, technical approach, past performance, and contractual terms and conditions.  At the conclusion of discussions, each offeror still in the competitive range shall be given an opportunity to submit a written Final Proposal Revision (FPR) with the reservation of the right to conduct finalization of details with the selected source in accordance with HHSAR 315.370.

e)	The process described in FAR 15.101-1 will be employed, which permits the Government to make tradeoffs among cost or price and non-cost factors and to consider award to other than the lowest price offeror or other than the highest technically rated offeror.  This process will take into consideration the results of the technical evaluation, the past performance evaluation (if applicable) and the cost analysis.

f)	The NIAID reserves the right to make a single award, multiple awards, or no award at all to the RFP.  In addition, the RFP may be amended or canceled as necessary to meet NCI requirements.  Synopses of awards exceeding $25,000 will be published in FedBizOpps.

(15)		Small Business Subcontracting Plan

If the proposed contract exceeds a total estimated cost of $500,000 for the entire period of performance, the apparent successful offeror shall be required to submit an acceptable subcontracting plan in accordance with the terms of the clause entitled "Small Business Subcontracting Plan," FAR Clause No. 52.219-9, incorporated herein by reference in the Solicitation, Attachment    to this RFP is an example of such a plan.

a)	THIS PROVISION DOES NOT APPLY TO SMALL BUSINESS CONCERNS.

b)	The term "subcontract" means any agreement (other than one involving an employer-employee relationship) entered into by a Federal Government prime contractor or subcontractor calling for supplies or services required for the performance of the original contract or subcontract.  This includes, but is not limited to, agreements/purchase orders for supplies and services such as equipment purchase, copying services, and travel services.

c)	The offeror understands that:

(1)	No contract will be awarded unless and until an acceptable plan is negotiated with the Contracting Officer which plan will be incorporated into the contract, as a material part thereof.

(2)	An acceptable plan must, in the determination of the Contracting Officer, provide the maximum practicable opportunity for Small Businesses, Small Disadvantaged Businesses, Women-Owned Small businesses, HubZone Small Businesses, Veteran-Owned Small Businesses, and Service Disabled Veteran-Owned Small Businesses to participate in the performance of the contract.

(3)	If a subcontracting plan acceptable to the Contracting Officer is not negotiated within the time limits prescribed by the contracting activity and such failure arises out of causes within the control and with the fault or negligence of the offeror, the offeror shall be ineligible for an award.   The Contracting Officer shall notify the Contractor in writing of the reasons for determining a subcontracting plan unacceptable early enough in the negotiation process to allow the Contractor to modify the plan within the time limits prescribed.

(4)	Prior compliance of the offeror with other such subcontracting plans under previous contracts will be considered by the Contracting Officer in determining the responsibility of the offeror for award of the contract.

(5)	It is the offeror's responsibility to develop a satisfactory subcontracting plan with respect to Small Business Concerns, Small Disadvantaged Business Concerns, Women-Owned Small Business Concerns, HubZone Small Business Concerns, Veteran-Owned Small Business Concerns, and Service Disabled Veteran-Owned Small Business Concerns that each such aspect of the offeror's plan will be judged independent of the other.

(6)	The offeror will submit, as required by the Contracting Officer, subcontracting reports in accordance with the instructions thereon, and as further directed by the Contracting Officer.  Subcontractors will also submit these reports to the Government's Contracting Officer or as otherwise directed, with a copy to the prime Contractor's designated small and disadvantaged business liaison.

d)	Each plan must contain the following:

(1)	Goals, expressed in terms of percentages of total planned subcontracting dollars, for the use of Small, Small Disadvantaged, Women-Owned, HUBZone, Veteran-Owned, and Service Disabled Veteran-Owned Small Business Concerns as subcontractors.

(2)	A statement of total dollars planned to be subcontracted. A statement of total dollars to be subcontracted to each of the following type of small business concerns:  Small, Small Disadvantaged, Women-Owned, HUBZone, Veteran-Owned, and Service Disabled Veteran-Owned Small Businesses.

(3)	A description of the principal types of supplies and services to be subcontracted with an identification of which supplies and services are expected to be subcontracted to Small, Small Disadvantaged, Women-Owned, HUBZone, Veteran-Owned, and/or  Service Disabled Veteran-Owned Small Business Concerns.

(4)	A description of the method used to develop the subcontracting goals.

(5)	A description of the method used to identify potential sources for solicitation purposes.

(6)	A statement as to whether or not indirect costs were included in establishing subcontracting goals.  If they were, a description of the method used to determine the proportionate share of indirect costs to be incurred with Small, Small Disadvantaged, Women-Owned, HUBZone, Veteran-Owned, and Service Disabled Veteran-Owned Small Businesses.

(7)	The name of the individual employed by the offeror who will administer the offeror's subcontracting program and a description of his/her duties.

(8)	A description of the efforts the offeror will make to assure that Small, Small Disadvantaged, Women-Owned, HUBZone, Veteran-Owned, and Service Disabled Veteran-Owned Small Businesses  have an equitable chance to compete for subcontracts.

(9)	Assurances that the offeror will include in all subcontracts the contract clause "Utilization of Small Business Concerns."  Assure that all subcontractors, other than small businesses, in excess of $500,000 adopt a plan similar to the plan agreed upon by the offeror.

(10)	Assurances that the offeror (and any required subcontractors) will cooperate in studies or surveys as required and submit required reports (SF 294 and SF 295) to the Government.

(11)	List the types of records the offeror will maintain to demonstrate procedures that have been adopted to comply with the requirement and goals in the plan, including establishing source lists.  Also, the offeror shall describe its efforts to locate Small, Small Disadvantaged, Women-Owned, HUBZone, Veteran-Owned, and Service Disabled Veteran-Owned Small Businesses and award subcontracts to them.

For additional information about each of the above elements required to be contained the subcontracting plan, see FAR Clause 52.219-9, Small Business Subcontracting Plan,  and the Sample Subcontracting Plan which is provided as an attachment to this RFP in SECTION J.

HHS expects each procuring activity to establish minimum subcontracting goals for all procurements.  The anticipated minimum goals for this RFP are as follows:

23% for Small Business; 5% for Small Disadvantaged Business; 5% for Women-Owned Small Business; 5% for HUBZone Small Business; and 3% for Veteran-Owned Small Business and Service-Disabled Veteran-Owned Small Business.

(16)		HUBZone Small Business Concerns

Small Business offerors located in underutilized business zones, called "HUBZones," will be evaluated in accordance with FAR Clause 52.219-4, NOTICE OF PRICE EVALUATION PREFERENCE FOR HUBZONE SMALL BUSINESS CONCERNS, which is incorporated by reference in ARTICLE I.3. of this solicitation.  Qualified HUBZone firms are identified in the Small Business Administration website at http://www.sba.gov/hubzone.

(17)		Extent of Small Disadvantaged Business Participation

In accordance with FAR Subpart 15.304(c)(4), the extent of participation of Small Disadvantaged Business (SDB) concerns in performance of the contract in the authorized NAICS Subsectors shall be evaluated in unrestricted competitive acquisitions expected to exceed $500,000 ($1,000,000 for construction) subject to certain limitations (see FAR 19.1202-1 and 19.1202-2(b).  The dollar amounts cited above include any option years/option quantities that may be included in this solicitation.  The definition of a "small disadvantaged business" is cited in FAR 19.001.

The factor entitled “Extent of Small Disadvantaged Business Participation” as set forth under the Evaluation Criteria in Section M shall be used for evaluation purposes.

The Department of Commerce determines, on an annual basis, by Subsectors, as contained in the North American Industry Classification System  (NAICS) code, and region, if any, the authorized SDB procurement mechanisms and applicable factors (percentages).  The NAICS codes can be found at:

http://www.sba.gov/size

The Department of Commerce website for the annual determination for NAICS codes* is:

http://www.arnet.gov/References/sdbadjustments.htm.

*Note:  Public Law 103-355 which authorized the SDB Price Evaluation Adjustment (PEA) and associated percentages/factors expired on December 9, 2004, therefore, the percentages shown at this website are no longer applicable.

Offerors shall include with their offers, SDB targets, expressed as dollars and percentages of total contract value, in each of the applicable, authorized NAICS Subsector(s).  The applicable authorized NAICS Subsector(s) for this project is (are) identified elsewhere in this RFP.   A total target for SDB participation by the prime contractor, that includes any joint ventures and team members, shall be provided as well as a total target for SDB participation by subcontractors.  In addition, offerors must provide information that describes their plans for meeting the targets set forth in their proposal.  This information shall be provided in one clearly marked section of the Business Proposal, which shall describe the extent of participation of SDB concerns in the performance of the contract.

If the evaluation factor in this solicitation includes an SDB evaluation factor or subfactor that considers the extent to which SDB concerns are specifically identified, the SDB concerns considered in the evaluation shall be listed in any resultant contract.   Offerors should note that addressing the extent of small disadvantaged business participation is not in any way intended to be a substitute for submission of the subcontracting plan, if it is required by this solicitation.  An example of the type of information that might be given (in addition to the narrative describing the plan for meeting the targets) follows:

EXAMPLE

Targets for SDB Participation - NAICS Subsector 223

|  | SDB Percentage of Total Contract Value | SDB Dollars |
| --- | --- | --- |
| Total Contract Value- $1,000,000 | 25% | $250,000 |
| SDB Participation by Prime | 10% | $100,000 |
| (Includes joint venture partners and team arrangements)* |  |  |
| SDB Participation by subcontractors | 15% | $150,000 |

*Note:  FAR Subpart 9.6 defines “Contractor team arrangements” to include two or more companies forming a partnership or joint venture to act as a potential prime contractor, or a potential prime contractor who agrees with one or more companies to have them act as its subcontractors on a specific contract or acquisition program.  For purposes of evaluation of the SDB participation factor, FAR 19.1202-4 requires that SDB joint ventures and teaming arrangements at the prime level be presented separately from SDB participation by subcontractors.

- Salary Rate Limitation in Fiscal Year 2005

Offerors are advised that pursuant to P.L. 108-447, no NIH Fiscal Year 2005 (October 1, 2004 - September 30, 2005) funds may be used to pay the direct annual salary of an individual through any contract awarded as a result of this solicitation at a rate in excess of the Executive Schedule, Level I* (direct salary is exclusive of Overhead, Fringe Benefits and General and Administrative expenses, also referred to as "indirect cost" or "facilities and administrative (F&A) costs").  Direct salary has the same meaning as the term "institutional base salary."  An individual's direct salary (or institutional base salary) is the annual compensation that the contractor pays for an individual's appointment whether that individual's time is spent on research, teaching, patient care or other activities.  Direct salary (or institutional base salary) excludes any income that an individual may be permitted to earn outside of duties to the contractor.

This does not preclude the offeror from absorbing that portion of an employee's annual salary (plus the dollar amount for fringe benefits and associated indirect costs) that exceeds a rate of the Executive Schedule, Level I*.  The salary rate limitation set by P.L. 108-447 applies only to Fiscal Year 2005 funds, however, salary rate ceilings for subsequent years may be included in future DHHS appropriation acts.  Multi-year contracts awarded pursuant to this solicitation may be subject to unilateral modifications by the Government if an individual's annual salary exceeds any salary rate ceiling established in future appropriations acts.  The Executive Schedule, Level I* annual salary rate limit also applies to individuals proposed under subcontracts, however it does not apply to consultants.  P.L. 108-447 states in pertinent part:

"None of the funds appropriated in this Act for the National Institutes of Health, the Agency for Healthcare Research and Quality,  and the Substance Abuse, and Mental Health Services Administration shall be used to pay the salary of an individual through a grant or extramural mechanism at a rate in excess of Executive Level I*."

LINK TO EXECUTIVE SCHEDULE SALARIES:  http://www.opm.gov/oca/05tables/html/ex.asp

*Note to Offerors:  The current Fiscal Year Executive Level I Salary Rate should be adhered to in the preparation of your proposal.  All costs associated with any resultant contract award will be required to be in compliance with the current Fiscal Year 2005 Executive Level I Salary rates.

- Institutional Responsibility Regarding Conflicting Interests of Investigators

EACH INSTITUTION MUST:

(a)	Maintain an appropriate written, enforced policy on conflict of interest that complies with 42 CFR Part 50 Subpart F and/or 45 CFR Part 94 as appropriate and inform each investigator of the Institution's policy, the Investigator's reporting responsibilities, and the applicable regulations.  If the Institution carries out the NIH funded research through subgrantees, contractors or collaborators, the Institution must take reasonable steps to ensure that Investigators working for such entities comply with the regulations, either by requiring those investigators to comply with the Institution's policy or by requiring the entities to provide assurances to the Institution that will enable the Institution to comply with the regulations.

(b)	Designate an Institutional official(s) to solicit and review financial disclosure statements from each Investigator who is planning to participate in NIH-funded research.

(c)	Require that by the time an application/proposal is submitted to the NIH each investigator who is planning to participate in the NIH-funded research has submitted to the designated official(s) a listing of his/her known Significant Financial Interests (and those of his/her spouse and dependent children):  (i) that would reasonably appear to be affected by the research for which the NIH funding is sought; and (ii) in entities whose financial interests would reasonably appear to be affected by the research.  All financial disclosures must be updated during the period of the award, either on an annual basis or as new reportable Significant Financial Interests are obtained.

(d)	Provide guidelines consistent with the regulations for the designated official(s) to identify conflicting interests and take such actions as necessary to ensure that such conflicting interests will be managed, reduced, or eliminated.

(e)	Maintain records, identifiable to each award, of all financial disclosures and all actions taken by the institution with respect to each conflicting interest for:  (1) in the case of grants, at least three years from the date of submission of the final expenditures report or, where applicable, from other dates specified in 45 CFR Part 74.53(b) and (2) in the case of contracts, 3 years after final payment or, where applicable, for the other time period specified in 48 CFR Part 4 Subpart 4.7, Contract Records Retention.

(f)	Establish adequate enforcement mechanisms and provide for sanctions where appropriate.

(g)	Certify, in each application/proposal for funding to which the regulations applies, that:

1)	there is in effect at the Institution a written and enforced administrative process to identify and manage, reduce or eliminate conflicting interests with respect to all research projects for which funding is sought from the NIH;

2)	prior to the Institution's expenditure of any funds under the award, the Institution will report to the awarding component the existence of a conflicting interest (but not the nature of the interest or other details) found by the Institution and assure that the interest has been managed, reduced or eliminated in accord with the regulations; and for any interest that the Institution identifies as conflicting subsequent to the expenditure of funds after award, the report will be made and the conflicting interest managed, reduced, or eliminated, at least on a temporary basis within sixty days of that identification;

3)	the Institution agrees to make information available, upon request, to the awarding component regarding all conflicting interests identified by the Institution and how those interested have been managed, reduced, or eliminated to protect the research from bias; and

4)	the Institution will otherwise comply with the regulations.

Institutional Management of Conflicting Interests

(a)	The designated official(s) must:  (1)  review all financial disclosures; and (2)  determine whether conflict of interest exists, and if so, determine what actions should be taken by the Institution to manage, reduce or eliminate such conflict of interest.  A conflict of interest exists when the designated official(s) reasonably determines that a Significant Financial Interest could directly and significantly affect the design, conduct, or reporting of the NIH-funded research.

Examples of conditions or restrictions that might be imposed to manage actual or potential conflicts of interests include, but are not limited to:

(i)	public disclosure of significant financial interests;

(ii)	monitoring of research by independent reviewers;

(iii)	modification of the research plan;

(iv)	disqualification of the Investigator(s) from participation in all or a portion of the research funded by the awarding component;

(v)	divestiture of significant financial interests; or

(vi)	severance of relationships that create actual or potential conflicts of interests.

(b)	An Institution may require the management of other conflicting financial interests in addition to those described in paragraph (a) of this section, as the Institution deems appropriate.

(20)		ROTC Access and Federal Military Recruiting on Campus

Section 514 of the FY 1997 Appropriations Act prohibits NIH from providing contract funds to educational institutions that the Secretary of Defense determines have a policy or practice (regardless of when implemented ) that either prohibits, or in effect prevents (1) the maintaining, establishing, or operation of a unit of the Senior Reserve Officer Training Corps at the covered education entity; or (2) a student at the covered educational entity from enrolling in a unit of the Senior Reserve Officer Training Corps at another institution of higher education.

Further, contract funds may not be provided to educational institutions that have a policy or practice that prohibits or prevents (1) entry to campuses, or access to students (who are 17 years of age or older) on campuses, for purposes of Federal military recruiting; or (2) access by military recruiters for purposes of Federal military recruiting to information pertaining to students (who are 17 years of age or older) enrolled at the covered educational entity.

(21)		Past Performance Information

a)	Offerors shall submit the following information as part of their technical] proposal.

A list of the last five contracts completed during the past three years and the last five contracts  currently in process that are similar in nature to the solicitation workscope.  Contracts listed may include those entered into by the Federal Government, agencies of state and local governments and commercial concerns.  Offerors that are newly formed entities without prior contracts should list contracts and subcontracts as required above for all key personnel.

Include the following information for each contract or subcontract:

1.	Name of Contracting Organization

2.	Contract Number (for subcontracts, provide the prime contract number and the subcontract number)

3.	Contract Type

4.	Total Contract Value

5.	Description of Requirement

6.	Contracting Officer's Name and Telephone Number

7.	Program Manager's Name and Telephone Number

8.	Standard Industrial Code

The offeror shall submit comparable information on all subcontractors that the offeror proposes to perform a major subcontract under this effort.  For the purpose of this solicitation, a "major subcontract" is defined as greater than $500,000 over the seven years of the contract.

The offeror may provide information on problems encountered on the identified contracts and the offeror's corrective actions.

b)	Each offeror will be evaluated on its performance under existing and prior contracts for similar products or services.  The Government is not required to contact all references provided by the offeror.  Also, references other than those identified by the offeror may be contacted by the Government to obtain additional information that will be used in the evaluation of the offeror's past performance.

- Electronic and Information Technology Accessibility

Section 508 of the Rehabilitation Act of 1973 (29 U.S.C. 794d), as amended by P.L.105-220 under Title IV (Rehabilitation Act Amendments of 1998) and the Architectural and Transportation Barriers Compliance Board Electronic and Information Technology (EIT) Accessibility Standards (36 CFR part 1194) require that all EIT acquired must ensure that:

a. 	Federal employees with disabilities have access to and use of information and data that is comparable to the access and use by Federal employees who are not individuals with disabilities; and

b. 	Members of the public with disabilities seeking information or services from an agency have access to and use of information and data that is comparable to the access to and use of information and data by members of the public who are not individuals with disabilities.

This requirement includes the development, maintenance, and/or use of EIT products/services, therefore, any proposal submitted in response to this solicitation must demonstrate compliance with the established EIT Accessibility Standards.

Further information about Section 508 is available via the Internet at http://www.section508.gov .

(23)		Prohibition on Contractor Involvement with Terrorist Activities

The contractor acknowledges that U.S. Executive Orders and Laws, including but not limited to E.O. 13224 and P.L. 107-56, prohibit transactions with, and the provision of resources and support to, individuals and organizations associated with terrorism.  It is the legal responsibility of the contractor to ensure compliance with these Executive Orders and Laws.  This clause must be included in all subcontracts issued under this contract.

- Solicitation Provisions Incorporated by Reference, FAR 52.252-1 (February 1998)

This Solicitation incorporates one or more solicitation provisions by reference, with the same force and effect as if they were given in full text.  Upon request, the Contracting Officer will make their full text available.  The offeror is cautioned that the listed provisions may include blocks that must be completed by the offeror and submitted with its quotation or offer.  In lieu of submitting the full text provisions, the offeror may identify the provision by paragraph identifier and provide the appropriate information with its quotation or offer.  Also, the full text of a solicitation provision may be accessed electronically at this address:  http://www.arnet.gov/far/.

FEDERAL ACQUISITION REGULATION (48 CFR CHAPTER 1):

- Data Universal Numbering System (DUNS) Number, FAR Clause 52.204-6 (October 2003).

- Facilities Capital Cost of Money, FAR Clause 52.215-16, (October 1997).

- Order of Precedence-Uniform Contract Format, FAR Clause 52.215-8, (October 1997).

- Preaward On-Site Equal Opportunity Compliance Evaluation, (Over $10,000,000), FAR Clause

52.222-24, (February 1999).

b.	TECHNICAL PROPOSAL INSTRUCTIONS

A detailed work plan must be submitted indicating how each aspect of the statement of work is to be accomplished.  Your technical approach should be in as much detail as you consider necessary to fully explain your proposed technical approach or method.  The technical proposal should reflect a clear understanding of the nature of the work being undertaken.  The technical proposal must include information on how the project is to be organized, staffed, and managed.  Information should be provided which will demonstrate your understanding and management of important events or tasks.

- Technical Discussions

The technical discussion included in the technical proposal should respond to the items set forth below:

a)	Project Objectives, NIH-1688-1

The offeror shall insert a completed NIH Form 1688-1, Project Objective, as provided in Section J, Attachments, behind the Title Page of each copy of the proposal, along with the “Government Notice for Handling Proposals.”  The NIH Form 1688-1 is to be completed as follows:

- 	For an Institution of Higher Education: The form MUST be completed in its entirety.

- 	For OTHER than an Institution of Higher Education: The starred items (Department, Service, Laboratory or Equivalent, and Major Subdivision) should be left blank.

The information required under the “Summary of Objectives” portion of the form MUST meet the requirements set forth in the section of the form entitled, “INSTRUCTIONS:”

b)	Statement of Work

(1)	Objectives

State the overall objectives and the specific accomplishments you hope to achieve.  Indicate the rationale for your plan, and relation to comparable work in progress elsewhere.  Review pertinent work already published which is relevant to this project and your proposed approach.  This should support the scope of the project as you perceive it.

(2)	Approach

Use as many subparagraphs, appropriately titled, as needed to clearly outline the general plan of work.  Discuss phasing of research and, if appropriate, include experimental design and possible or probable outcome of approaches proposed.

(3)	Methods

Describe in detail the methodologies you will use for the project, indicating your level of experience with each, areas of anticipated difficulties, and any unusual expenses you anticipate.

(4)	Schedule

Provide a schedule for completion of the work and delivery of items specified in the statement of work.  Performance or delivery schedules shall be indicated for phases or segments, as applicable, as well as for the overall program.  Schedules shall be shown in terms of calendar months from the date of authorization to proceed or, where applicable, from the date of a stated event, as for example, receipt of a required approval by the Contracting Officer.  Unless the request for proposal indicates that the stipulated schedules are mandatory, they shall be treated as desired or recommended schedules.  In this event, proposals based upon the offeror's best alternative schedule, involving no overtime, extra shift or other premium, will be accepted for consideration.

c)	Personnel

Describe the experience and qualifications of personnel who will be assigned for direct work on this program.  Information is required which will show the composition of the task or work group, its general qualifications, and recent experience with similar equipment or programs.  Special mention shall be made of direct technical supervisors and key technical personnel, and the approximate percentage of the total time each will be available for this program.

OFFERORS SHOULD ASSURE THAT THE PRINCIPAL INVESTIGATOR, AND ALL OTHER PERSONNEL PROPOSED, SHALL NOT BE COMMITTED ON FEDERAL GRANTS AND CONTRACTS FOR MORE THAN A TOTAL OF 100% OF THEIR TIME.  IF THE SITUATION ARISES WHERE IT IS DETERMINED THAT A PROPOSED EMPLOYEE IS COMMITTED FOR MORE THAN 100% OF HIS OR HER TIME, THE GOVERNMENT WILL REQUIRE ACTION ON THE PART OF THE OFFEROR TO CORRECT THE TIME COMMITMENT.

(1)	Principal Investigator/Project Director

List the name of the Principal Investigator/Project Director responsible for overall implementation of the contract and key contact for technical aspects of the project. Even though there may be co-investigators, identify the Principal Investigator/Project Director who will be responsible for the overall implementation of any awarded contract.  Discuss the qualifications, experience, and accomplishments of the Principal Investigator/Project Director.  State the estimated time to be spent on the project, his/her proposed duties, and the areas or phases for which he/she will be responsible.

(2)	Other Investigators

List all other investigators/professional personnel who will be participating in the project. Discuss the qualifications, experience, and accomplishments. State the estimated time each will spend on the project, proposed duties on the project, and the areas or phases for which each will be responsible.

(3)	Additional Personnel

List names, titles, and proposed duties of additional personnel, if any, who will be required for full-time employment, or on a subcontract or consultant basis.  The technical areas, character, and extent of subcontract or consultant activity will be indicated and the anticipated sources will be specified and qualified.  For all proposed personnel who are not currently members of the offeror's staff, a letter of commitment or other evidence of availability is required.  A resume does not meet this requirement.  Commitment letters for use of consultants and other personnel to be hired must include:

-The specific items or expertise they will provide.

-Their availability to the project and the amount of time anticipated.

-Willingness to act as a consultant.

-How rights to publications and patents will be handled.

(4)	Resumes

Resumes of all key personnel are required.  Each must indicate educational background, recent experience, specific or technical accomplishments, and a listing of relevant publications.

  - The technical proposal should include the information described in Appendix A, Additional Technical Proposal Instructions.

- Technical Evaluation

Proposals will be technically evaluated in accordance with the factors, weights, and order of relative importance as described in the Technical Evaluation Criteria (Section M.5, hereof).

- Additional Technical Proposal Information

a)	Proposals which merely offer to conduct a program in accordance with the requirements of the Government's scope of work will not be eligible for award.  The offeror must submit an explanation of the proposed technical approach in conjunction with the tasks to be performed in achieving the project objectives.

b)	The technical evaluation is conducted in accordance with the weighted technical evaluation criteria by an initial review panel.  This evaluation produces a numerical score (points) which is based upon the information contained in the offeror's proposal only.

- Other Considerations

Record and discuss specific factors not included elsewhere which support your proposal.  Using specifically titled subparagraphs, items may include:

a)	Any agreements and/or arrangements with subcontractor(s).  Provide as much detail as necessary to explain how the statement of work will be accomplished within this working relationship.

b)	Unique arrangements, equipment, etc., which none or very few organizations are likely to have which is advantageous for effective implementation of this project.

c)	Equipment and unusual operating procedures established to protect personnel from hazards associated with this project.

d)	Other factors you feel are important and support your proposed research.

e)	Recommendations for changing reporting requirements if such changes would be more compatible with the offeror's proposed schedules.

IMPORTANT NOTE TO OFFERORS:  The following 12 paragraphs [(5) through (16)] shall be addressed in a SEPARATE SECTION of the Technical Proposal entitled, "HUMAN SUBJECTS."

- Human Subjects

The following notice is applicable when contract performance is expected to involve risk to human subjects:

Notice to Offerors of Requirements of 45 CFR Part 46, Protection of Human Subjects (MARCH 2005)

(a)	Copies of the Department of Health and Human Services (Department) regulations for the protection of human subjects, 45 CFR Part 46, are available from the Office for Human Research Protections (OHRP), Bethesda, Maryland 20892. The regulations provide a systematic means, based on established ethical principles, to safeguard the rights and welfare of individuals who participate as subjects in research activities supported or conducted by the Department.

(b)	The regulations define a human subject as a living individual about whom an investigator (whether professional or student) conducting research obtains data through intervention or interaction with the individual, or identifiable private information. The regulations extend to the use of human organs, tissue, and body fluids from individually identifiable human subjects as well as to graphic, written, or recorded information derived from individually identifiable human subjects. The use of autopsy materials is governed by applicable State and local law and is not directly regulated by 45 CFR Part 46.

(c)	Activities in which the only involvement of human subjects will be in one or more of the categories set forth in 45 CFR 46.101(b)(1-6) are exempt from coverage.

(d)	Inappropriate designations of the noninvolvement of human subjects or of exempt categories of research in a project may result in delays in the review of a proposal. The OpDiv will make a final determination of whether the proposed activities are covered by the regulations or are in an exempt category, based on the information provided in the proposal. In doubtful cases, prior consultation with OHRP, (telephone: 301-496-7005), is recommended.

(e)	In accordance with 45 CFR Part 46, prospective Contractors being considered for award shall be required to file with OHRP an acceptable Assurance of Compliance with the regulations, specifying review procedures and assigning responsibilities for the protection of human subjects. The initial and continuing review of a research project by an institutional review board shall assure that the rights and welfare of the human subjects involved are adequately protected, that the risks to the subjects are reasonable in relation to the potential benefits, if any, to the subjects and the importance of the knowledge to be gained, and that informed consent will be obtained by methods that are adequate and appropriate.  The contracting officer will direct the offeror/contractor to the OHRP IRB Registration and Assurance Filing website, found at http://www.hhs.gov/ohrp/ or to the physical address if the offeror/contractor cannot access the Internet.  HHS regulations for the protection of human subjects may be found at:

http://www.access.gpo.gov/nara/cfr/waisidx_01/45cfr46_01.html

(f)	It is recommended that OHRP be consulted for advice or guidance concerning either regulatory requirements or ethical issues pertaining to research involving human subjects.

(End of provision)

- Instructions to Offerors Regarding Protection of Human Subjects

Offerors must address the following human subjects protections issues if this contract will be for research involving human subjects (note: under each of the following points below, the offeror should indicate whether the information provided relates to the primary research site, or to a collaborating performance site(s), or to all sites:

(a) 	Risks to the subjects

Human Subjects Involvement and Characteristics:

-	Describe the proposed involvement of human subjects in response to the solicitation.

-	Describe the characteristics of the subject population, including their anticipated number, age range, and health status.

-	Identify the criteria for inclusion or exclusion of any subpopulation. Explain the rationale for the involvement of special classes of subjects, such as fetuses, pregnant women, children, prisoners, institutionalized individuals, or others who are likely to be vulnerable populations.

Sources of Materials:

-	Identify the sources of research material obtained from individually identifiable living human subjects in the form of specimens, records, or data. Indicate whether the material or data will be obtained specifically for research purposes or whether use will be made of existing specimens, records, or data.

Potential Risks:

-	Describe the potential risks to subjects (physical, psychological, social, legal, or other) and assess their likelihood and seriousness to the subjects.

-	Describe alternative treatments and procedures, including the risks and benefits of the alternative treatments and procedures, to participants in the proposed research, where appropriate.

(b) 	Adequacy of Protection Against Risks

Recruitment and Informed Consent:

-	Describe plans for the recruitment of subjects and the procedures for obtaining informed consent. Include a description of the circumstances under which consent will be sought and obtained, who will seek it, the nature of the information to be provided to prospective subjects, and the method of documenting consent. The informed consent document for the contractor and any collaborating sites should be submitted only if requested elsewhere in the solicitation.  Be aware that an IRB-approved informed consent document for the contractor and any participating collaborative sites must be provided to the Government prior to patient accrual or participant enrollment.

Protection Against Risk:

-	Describe the procedures for protecting against or minimizing potential risks, including risks to confidentiality, and assess their likely effectiveness.

-	Discuss provisions for ensuring necessary medical or professional intervention in the event of adverse effects to the subjects where appropriate.

-	In studies that involve interventions, describe the provisions for data and safety monitoring of the research to ensure the safety of subjects.

(c) 	Potential Benefits of the Proposed Research to the Subjects and Others

-	Discuss the potential benefits of the research to the subjects and others.

-	Discuss why the risks to subjects are reasonable in relation to the anticipated benefits to subjects and others.

-	Describe treatments and procedures that are alternatives to those provided to the participants by the proposed research, where appropriate.

(d) 	Importance of the Knowledge to be Gained

-	Discuss the importance of the knowledge gained or to be gained as a result of the proposed research.

-	Discuss why the risks to subjects are reasonable in relation to the importance of the knowledge that may reasonably be expected to result.

Note:  If a test article (investigational new drug, device, or biologic) is involved, name the test article and state whether the 30-day interval between submission of offeror’s certification to the Food and Drug Administration (FDA) and its response has elapsed or has been waived and/or whether the FDA has withheld or restricted use of the test article.

Collaborating Site(s)

When research involving human subjects will take place at collaborating site(s) or other performance site(s), the offeror must provide in this section of its proposal a list of the collaborating sites and their assurance numbers. Further, if you are awarded a contract, you must obtain in writing, and keep on file, an assurance from each site that the previous points have been adequately addressed at a level of attention that is at least as high as that documented at your organization. Site(s) added after an award is made must also adhere to the above requirements.

- Required Education in the Protection of Human Research Participants

NIH policy requires education on the protection of human subject participants for all investigators submitting NIH proposals for contracts for research involving human subjects.  This policy announcement is found in the NIH Guide for Grants and Contracts Announcement dated June 5, 2000 at the following website: http://grants.nih.gov/grants/guide/notice-files/NOT-OD-00-039.html.  Offerors should review the policy announcement prior to submission of their offers.  The following is a summary of the Policy Announcement:

For any solicitation for research involving human subjects, the offeror shall provide in its technical proposal the following information:  (1) a list of the names of the principal investigator and any other individuals proposed under the contract who are responsible for the design and/or conduct of the research; (2) the title of the education program completed (or to be completed prior to the award of the contract) for each named personnel; (3) a one sentence description of the program(s) listed in (2) above.  This requirement extends to investigators and all individuals responsible for the design and/or conduct of the research who are working as subcontractors or consultants under the contract.

Curricula that are readily available and meet the educational requirement include the NIH on-line tutorial, titled “Protection of Human Research Subjects: Computer-Based Training for Researchers,” available at http://ohsr.od.nih.gov/cbt/.  You may download the information at this site at no cost and modify it, if desired.  The University of Rochester has made its training program available for individual investigators.  Completion of this program will also satisfy the educational requirement.  The University of Rochester manual can be obtained through Centerwatch, Inc. at

http://www.centerwatch.com/order/pubs_profs_protect.html.

In addition, the NCI sponsors an online training course at:

http://cme.cancer.gov/clinicaltrials/learning/humanparticipant-protections.asp.

If an institution already has developed educational programs on the protection of research participants, completion of these programs also will satisfy the educational requirement.

In addition, prior to the substitution of the principal investigator or any other individuals responsible for the design and/or conduct of the research under the contract, the contractor shall provide the contracting officer with the title of the education program and a one sentence description of the program that the replacement has completed.

- Inclusion of Women and Minorities in Research Involving Human Subjects

It is NIH policy that women and members of minority groups and their sub-populations must be included in all NIH-supported clinical research projects involving human subjects, unless a clear and compelling rationale and justification establishes to the satisfaction of the relevant Institute/Center Director that inclusion is inappropriate with respect to the health of the subjects or the purpose of the research.  The Director, NIH, may determine that exclusion under other circumstances is acceptable, upon the recommendation of an Institute/Center Director, based on a compelling rationale and justification.  Cost is not an acceptable reason for exclusion except when the study would duplicate data from other sources.  Women of childbearing potential should not be routinely excluded from participation in clinical research.  This policy results from the NIH Revitalization Act of 1993 (Section 492B of Public Law 103-43), and applies to research subjects of all ages.

All investigators proposing research involving human subjects should read the UPDATED "NIH Policy and Guidelines on the Inclusion of Women and Minorities as Subjects in Clinical Research, Amended October 2001," published in the NIH Guide for Grants and Contracts on October 9, 2001 at the following web site:

http://grants.nih.gov/grants/funding/women_min/guidelines_amended_10_2001.htm

These guidelines contain a definition of clinical research adopted in June 2001, as:  "(1) Patient-oriented research.  Research conducted with human subjects (or on material of human origin such as tissues, specimens and cognitive phenomena) for which an investigator (or colleague) directly interacts with human subjects.  Excluded from this definition are in vitro studies that utilize human tissues that cannot be linked to a living individual.  Patient-oriented research includes (a) mechanisms of human disease, (b) therapeutic interventions, (c) clinical trials, and (d) development of new technologies; (2) Epidemiologic and behavioral studies; and (3) Outcomes research and health services research,"  at:

(http://www.nih.gov/news/crp/97report/execsum.htm).

Information Required for ALL Clinical Research Proposals

This solicitation contains a review criterion addressing the adequacy of:  (1) the offeror’s plans for inclusion of women and minorities in the research proposed; or (2) the offeror’s justification(s) for exclusion of one or both groups from the research proposed.

Provide information on the composition of the proposed study population in terms of sex/gender and racial/ethnic groups and provide a rationale for selection of such subjects in response to the requirements of the solicitation.  The description may include (but is not limited to) information on the population characteristics of the disease or condition being studied in the planned research, and/or described in the statement of work, national and local demography, knowledge of the racial/ethnic/cultural characteristics of the population, prior experience and collaborations in recruitment and retention of the populations and subpopulations to be studied, and the plans, arrangements and letters of commitment from relevant community groups and organizations for the planned research.

The proposal must include the following information:

-	A description of the subject selection criteria

-	The proposed dates of enrollment (beginning and end)

-	A description of the proposed outreach programs for recruiting women and minorities as subjects

-	A compelling rationale for proposed exclusion of any sex/gender or racial/ethnic group

-	The proposed sample composition using the “Targeted/Planned Enrollment Table”(see Section J, Attachments)

NOTE 1: For all proposals, use the ethnic and racial categories and complete the “Targeted/Planned Enrollment Table in accordance with the Office of Management and Budget (OMB) Directive No. 15, which may be found at: http://www.whitehouse.gov/OMB/fedreg/ombdir15.html.

NOTE 2: If this is an Indefinite Delivery, Indefinite Quantity (IDIQ) or Requirements contract as defined in FAR 16.5, the proposal should describe in general terms how it will comply with each bulleted item above for each task order.  When the Government issues a task order request for proposal, each of the bulleted information items must be fully and specifically addressed in the proposal.

Standards for Collecting Data.  When you, as a contractor, are planning data collection items on race and ethnicity, you shall use, at a minimum, the categories identified in OMB Directive No. 15. The collection of greater detail is encouraged. However, you should design any additional, more detailed items so that they can be aggregated into these required categories. Self-reporting or self-identification using two separate questions is the preferred method for collecting data on race and ethnicity. When you collect race and ethnicity separately, you must collect ethnicity first.  You shall offer respondents the option of selecting one or more racial designations.  When you collect data on race and ethnicity separately, you shall also make provisions to report the number of respondents in each racial category who are Hispanic or Latino.  When you present aggregate data, you shall provide the number of respondents who selected only one category, for each of the five racial categories.  If you collapse data on multiple responses, you shall make available, at a minimum, the total number of respondents reporting “more than one race.” Federal agencies shall not present data on detailed categories if doing so would compromise data quality or confidentiality standards.

In addition to the above requirements, solicitations for NIH defined Phase III clinical trials require that:  a) all proposals and/or protocols provide a description of plans to conduct analyses, as appropriate, to detect significant differences in intervention effect (see NIH Guide:

http://grants.nih.gov/grants/funding/women_min/guidelines_amended_10_2001.htm,

Definitions - Significant Difference), by sex/gender,  racial/ethnic groups, and relevant subpopulations, if applicable; and b) all contractors to report annually cumulative subject accrual, and progress in conducting analyses for sex/gender and race/ethnicity differences.

Offerors may obtain copies of the Updated Guidelines from the sources above or from the contact person listed in the solicitation.

Also, the proposal must include one of the following plans:

-	Plans to conduct valid analysis to detect significant differences in intervention effect among sex/gender and/or racial/ethnic subgroups when prior studies strongly support these significant differences among subgroups, OR

-	Plans to include and analyze sex/gender and/or racial/ethnic subgroups when prior studies strongly support no significant differences in intervention effect between subgroups, OR

-	Plans to conduct valid analyses of the intervention effect in sex/gender and/or racial/ethnic subgroups (without requiring high statistical power for each subgroup) when the prior studies neither support nor negate significant differences in intervention effect between subgroups.

Use the form entitled, "Targeted/Planned Enrollment Table," when preparing your response to the solicitation requirements for inclusion of women and minorities.  (See Section J-List of Documents, Exhibits and Other Attachments of the RFP)

Unless otherwise specified in this solicitation, the Government has determined that the work required by this solicitation does not involve a sex/gender specific study or a single or limited number of minority population groups.  Therefore, the NIH believes that the inclusion of women and minority populations is appropriate for this project.  (See Section M of this RFP for more information about evaluation factors for award.)

Use the form entitled, "Inclusion Enrollment Report," for reporting in the resultant contract.

- Inclusion of Children in Research Involving Human Subjects

It is NIH policy that children (defined below) must be included in all human subjects research, including, but not limited to, clinical trials, conducted under a contract funded by the NIH, unless there are clear and compelling reasons not to include them. (See examples of Justifications for Exclusion of Children below).  For the purposes of this policy, contracts involving human subjects include categories that would otherwise be exempt from the DHHS Policy for Protection of Human Research Subjects (sections 101(b) and 401(b) of 45 CFR 46), such as surveys, evaluation of educational interventions, and studies of existing data or specimens that should include children as participants.   This policy applies to both domestic and foreign research contracts.

For purposes of this policy, a child is defined as an individual under the age of 21 years.

All offerors proposing research involving human subjects should read the "NIH Policy and  Guidelines on the Inclusion of Children as Participants in Research Involving Human Subjects" which was published in the NIH Guide for Grants and Contracts on March 6, 1998 and is available at the following URL address:

http://www.nih.gov/grants/guide/notice-files/not98-024.html

Offerors also may obtain copies from the contact person listed in the RFP.

Inclusion of children as participants in research must be in compliance with all applicable subparts of 45 CFR 46 as well as other pertinent laws and regulations whether or not such research is otherwise exempted from 45 CFR 46.  Therefore, any proposals must include a description of plans for including children, unless the offeror presents clear and convincing justification for an exclusion.  The “Human Subjects” section of your technical proposal should provide either a description of the plans to include children and a rationale for selecting or excluding a specific age range of child, or an explanation of the reason(s) for excluding children as participants in the research.  This solicitation contains a review criterion addressing the adequacy of: (1) the plans for including children as appropriate for the scientific goals of the research; and/or (2) the justification of exclusion of children or exclusion of a specific age range of children.

When children are included, the plan also must include a description of: (1) the expertise of the investigative team for dealing with children at the ages included; (2) the appropriateness of the available facilities to accommodate the children; and, (3) the inclusion of a sufficient number of children to contribute to a meaningful analysis relative to the purpose/objective of the solicitation.

Justifications for Exclusion of Children

It is expected that children will be included in all research involving human subjects unless one or more of the following exclusionary circumstances can be fully justified:

-	The objective of the solicitation is not relevant to children.

-	There are laws or regulations barring the inclusion of children in the research to be conducted under the solicitation.

-	The knowledge being sought in the research is already available for children or will be obtained from another ongoing study, and an additional study will be redundant.  You should provide documentation of other studies justifying the exclusion.

-	A separate, age-specific study in children is warranted and preferable.  Examples include:

-	The relative rarity of the condition in children, as compared with adults (in that extraordinary effort would be needed to include children); or

-	The number of children is limited because the majority are already accessed by a nationwide pediatric disease research network; or

-	Issues of study design preclude direct applicability of hypotheses and/or interventions to both adults and children (including different cognitive, developmental, or disease stages of different age-related metabolic processes); or

-	Insufficient data are available in adults to judge potential risk in children (in which case one of the research objectives could be to obtain sufficient adult data to make this judgment).  While children usually should not be the initial group to be involved in research studies, in some instances, the nature and seriousness of the illness may warrant their participation earlier based on careful risk and benefit analysis; or

-	Study designs aimed at collecting additional data on pre-enrolled adult study subjects (e.g., longitudinal follow-up studies that did not include data on children);

-	Other special cases justified by the offeror and found acceptable to the review group and the Institute Director

Definition of a Child

For the purpose of this solicitation, a child is defined as an individual under the age of 21 years.

The definition of child described above will pertain to this solicitation (notwithstanding the FDA definition of a child as an individual from infancy to 16 years of age, and varying definitions employed by some states). Generally, State laws define what constitutes a “child,” and such definitions dictate whether or not a person can legally consent to participate in a research study. However, State laws vary, and many do not address when a child can consent to participate in research. Federal Regulations (45 CFR 46, subpart D, Sec.401-409) address DHHS protections for children who participate in research, and rely on State definitions of “child” for consent purposes. Consequently, the children included in this policy (persons under the age of 21) may differ in the age at which their own consent is required and sufficient to participate in research under State law. For example, some states consider a person age 18 to be an adult and therefore one who can provide consent without parental permission.

- Data and Safety Monitoring in Clinical Trials

All offerors are directed to the full text of the NIH Policies regarding Data and Safety Monitoring and Reporting of Adverse Events that are found in the NIH Guide for Grants and Contracts Announcements at the following web sites:

http://grants.nih.gov/grants/guide/notice-files/not98-084.html

http://grants.nih.gov/grants/guide/notice-files/not99-107.html

http://grants.nih.gov/grants/guide/notice-files/NOT-OD-00-038.html

All offerors receiving an award under this solicitation must comply with the NIH Policy cited in these NIH Announcements and any other data and safety monitoring requirements found elsewhere in this solicitation.

The following is a brief summary of the Data and Safety Monitoring and Adverse Event Reporting Requirements:

Data and Safety Monitoring is required for every clinical trial.  Monitoring must be performed on a regular basis and the conclusions of the monitoring reported to the Project Officer.

The type of data and safety monitoring required will vary based on the type of clinical trial and the potential risks, complexity and nature of the trial.  A plan for data and safety monitoring is required for all clinical trials.  A general description of a monitoring plan establishes the overall framework for data and safety monitoring.  It should describe the entity that will be responsible for the monitoring, and the policies and procedures for adverse event reporting. Phase III clinical trials generally require the establishment of a Data Safety Monitoring Board (DSMB).  The establishment of a DSMB is optional for Phase I and Phase II clinical trials.

The DSMB/Plan is established at the time the protocol is developed and must be approved by both the Institutional Review Board (IRB) and the Government and in place before the trial begins.  If the protocol will be developed under the contract awarded from this solicitation, a general description of the data and safety monitoring plan must be submitted as part of the proposal and will be reviewed by the scientific review group (Technical Evaluation Panel, (TEP)) convened to evaluate the proposal.  If the protocol is developed and is included as part of the submitted proposal, a complete and specific data and safety monitoring plan must be submitted as part of the proposal.

Monitoring Plans, at a minimum, must include the prompt reporting of adverse events to the IRB, the NIH Office of Biotechnology Activities (OBA), and the Food and Drug Administration (FDA). Also, in the plan you should describe the frequency of reporting of the conclusions of the monitoring activities.  The overall elements of each plan may vary depending on the size and complexity of the trial. The NIH Policy for Data and Safety Monitoring at http://grants.nih.gov/grants/guide/notice-files/not98-084.html describes examples of monitoring activities to be considered.

The frequency of monitoring will depend upon potential risks, complexity, and the nature of the trial; therefore a number of options for monitoring trials are available.  These can include, but are not limited to, monitoring by a:

-	Principal Investigator (required)

-	Independent individual /Safety Officer

-	Designated medical monitor

-	Internal Committee or Board with explicit guidelines

-	Data and Safety Monitoring Board (DSMB - required for multisite trials)

-	Institutional Review Board (IRB - required)

For multi-site Phase I and Phase II trials, a central reporting entity that will be responsible for preparing timely summary reports of adverse events for distribution among sites and IRBs should be considered.

Organizations with a large number of clinical trials may develop standard monitoring plans for Phase I and Phase II trials.  In this case, such organizations may include the IRB-approved monitoring plan as part of the proposal submission.

- Research Involving Human Fetal Tissue

Human Fetal Tissue means tissue or cells obtained from a dead human fetus, including human embryonic stem cells, human pluripotent stem cells and human embryonic germ cells.

The governing federal statute is the Public Health Service Act, 42 U.S.C. 289g-1 and 289g-2.  Implementing regulations and guidance for conducting research on human fetal tissue may be found at 45 CFR 46, Subpart B and http://grants1.nih.gov/grants/guide/notice-files/not93-235.html and any subsequent revisions to this NIH Guide to Grants and Contracts ("Guide") Notice.

By signing the face page of the proposal, the offeror (authorized institutional official) certifies that researchers using human fetal tissue are in compliance with 42 USC 289g-2.  This statute specifically prohibits any person from knowingly acquiring, receiving, or transferring any human fetal tissue for valuable consideration.  "Valuable consideration" is a concept similar to profit, and does not include reasonable payment for costs associated with the collection processing, preservation, storage, quality control or transportation of these tissues.

Research involving the transplantation of human fetal tissue must be conducted in accordance with applicable Federal, State and local law.

- Research Involving Prisoners as Subjects

a. 	HHS Regulations at 45 CFR Part 46, Subpart C provide additional protections pertaining to biomedical and behavioral research involving prisoners or those individuals who, during the period of the contract become prisoners, as subjects.  These regulations also set forth the duties of the Institutional Review Board (IRB) where prisoners are involved in the research.  HHS-funded research involving prisoners as subjects may not proceed until the Office for Human Research Protections (OHRP) issues approval, in writing, as required by 45 CFR 46.306(a)(2).  In addition, OHRP Guidance on the Involvement of Prisoners in Research may be found at:

http://ohrp.osophs.dhhs.gov/humansubjects/guidance/prisoner.htm

b. 	HHS Waiver for Epidemiological Research Involving Prisoners as Subjects

On June 20, 2003 the Secretary of HHS waived the applicability of certain provisions of Subpart C of 45 CFR Part 46, (Additional DHHS Protections Pertaining to Biomedical and Behavioral Research Involving Prisoners as Subjects) to specific types of epidemiological research involving prisoners as subjects.

The applicability of 45 CFR 46.305(a)(1) and 46.306(a)(2) for certain epidemiological research conducted or funded by DHHS is waived when:

1. 	The sole purposes are:

a) 	to describe the prevalence or incidence of a disease by identifying all cases, or

b) 	to study potential risk factor associations for a disease, and

2.	The Institution responsible for the conduct of the research certifies to the OHRP that the Institutional Review Board (IRB) approved the research and fulfilled its duties under 45 CFR 46.305(a)(2-7) and determined and documented that:

a) 	the research presents no more than minimal risk, and

b)	no more than inconvenience to the prisoner-subjects, and

c) 	prisoners are not a particular focus of the research.

For more information about this Waiver see http://www.hhs.gov/ohrp/special/prisoners/Prisoner waiver 6-20-03.pdf

- Research Involving Recombinant DNA Molecules (including Human Gene Transfer Research)

Recombinant DNA Molecules are either 1) molecules that are constructed outside of living cells by joining natural or synthetic DNA segments to DNA molecules that can replicate in a living cell, or 2) DNA molecules that result from the replication of those described in 1).

The NIH Guidelines for Research Involving Recombinant DNA Molecules (http://www4.od.nih.gov/oba/rac/guidelines/guidelines.html and the May 28, 2002 Notice, Compliance with the NIH Guidelines for Research Involving Recombinant DNA Molecules, at:

(http://grants1.nih.gov/grants/guide/notice-files/NOT-OD-02-052.html)

and any subsequent revisions to the Guide Notice) stipulates biosafety and containment measures for recombinant DNA research and delineates critical, ethical principles and key safety reporting requirements for human gene transfer research (See Appendix M of the NIH Guidelines).  These guidelines apply to both basic and clinical research studies.

The Recombinant DNA Advisory Committee (RAC) is charged with the safety of manipulation of genetic material through the use of recombinant DNA techniques.  Prior to beginning any clinical trials involving the transfer of recombinant DNA to humans, the trial must be registered with the RAC.  If this contract involves new protocols that contain unique and//or novel issues, the RAC must discuss them in a public forum and then the Institutional Biosafety Committee (IBC), the Institutional Review Board (IRB), and the project officer and contracting officer must approve the protocol prior to the start of the research.

Failure to comply with these requirements may result in suspension, limitation, or termination of NIH funding for any work related to Recombinant DNA Research or a requirement for the contracting officer’s prior approval of any or all Recombinant DNA projects under any contract awarded from this solicitation.  This includes the requirements of the Standing Institutional Biosafety Committee (IBC) (See http://www4.od.nih.gov/oba/IBC/IBCindexpg.htm).

As specified in Appendix M-1-C-4 of the NIH Guidelines, any serious adverse event must be reported immediately to the IRB, the IBC, the Office for Human Research Protections (if applicable), and the NIH Office for Biotechnology Activities (OBA), followed by the filing of a written report with each office/group and copies to the project officer and contracting officer.

(http://www4.od.nih.gov/oba/rac/guidelines_02/Appendix_M.htm#_Toc7255836)

- Human Embryonic Germ Cell (HEGC) Research

1.	Guidelines.

Research use of human embryonic germ cells derived from fetal tissue with Federal funds requires review of compliance with the NIH Guidelines for Research Using Human Pluripotent Stem Cells (http://stemcells.nih.gov/policy/guidelines.asp) (only the information regarding human embryonic germ cells is relevant).  Embryonic germ cells are pluripotent stem cells derived from human embryos.  See NIH Guide for Grants and Contracts Notice NOT-OD-02-049, requiring that offerors/contractors submit certain documents to the Human Pluripotent Stem Cell Review Group (HPSCRG), which will be reviewed in a public meeting.   Research using human embryonic germ cells may not be performed prior to approval by the HPSCRG.

All offerors should read the "NIH Guidelines"  (http://stemcells.nih.gov/policy/guidelines.asp) if they either:  (1) propose to respond to the Statement of Work requirements by conducting research that uses human embryonic germ cells or, (2) are responding to a Statement of Work that requires the use of  human embryonic germ cells.

Offerors may obtain copies of these Guidelines from the website above or from the contact person listed in this solicitation.

2. 	Procedure for Review by Human Pluripotent Stem Cell Review Group (HPSCRG)

If the offeror intends to fulfill the requirements of the Statement of Work by performing research using human embryonic germ cells, it must so state in its proposal.

If the offeror's proposal includes research using human embryonic germ cells and it receives a contract award, the contractor may not perform any research using these human embryonic germ cells until the Human Pluripotent Stem Cell Review Group (HPSCRG) has reviewed and approved the documentation furnished as prescribed in "Procedures for Submission of Compliance Documents to the Human Pluripotent Stem Cell Review Group (HPSCRG) for the Research Use of Human Embryonic Germ Cells" (http://grants2.nih.gov/grants/guide/notice-files/NOT-OD-02-049.html)  and the contracting officer has notified the contractor of the approval in writing.

The resultant contract will be divided into discrete phases.  During Phase 1 of the contract, the contractor shall submit the original and two copies of the required documentation and assurances that address the areas covered in "Procedures for Submission of Compliance Documents to the Human Pluripotent Stem Cell Review Group (HPSCRG) for the Research Use of Human Embryonic Germ Cells," at:

(http://grants2.nih.gov/grants/guide/notice-files/NOT-OD-02-049.html)

to the contracting officer.  This documentation will be forwarded for review and approval to the HPSCRG.

If the HPSCRG disapproves the documentation presented by the contractor, the Contracting Officer may elect to either terminate the contract in accordance with the Termination for Convenience clause of the contract OR determine not to exercise subsequent option(s) as appropriate based the terms of the specific contract.  Otherwise, when the HPSCRG approves the documentation, the contracting officer will notify the contractor in writing that research using the human embryonic germ cells may commence.

Research involving the use of human embryonic germ cells shall not be conducted under the contract until the HPSCRG review and approval have been obtained, and the contracting officer has provided written notice of such approval to the contractor.

- Human Embryonic Stem Cell (HESC) Research

On August 9, 2001, the President announced the criteria that must be met for Federal funds to be used for research on existing human embryonic stem cell lines.  These criteria were subsequently published by the NIH at:  http://grants1.nih.gov/grants/guide/notice-files/NOT-OD-02-005.html.  The following eligibility criteria must be met:

1. 	The derivation process (which commences with the removal of the inner cell mass from the blastocyst) must have already been initiated prior to August 9, 2001;

2. 	Prior to August 9, 2001, the embryo from which the stem cell line was derived no longer had the possibility of development as a human being;

3.	The stem cells must have been derived from an embryo that was created for reproductive purposes;

4.	The embryo was no longer needed for these purposes;

5.	Informed consent must have been obtained for the donation of the embryo;

6.	No financial inducements were provided for the donation of the embryo.

To facilitate research using human embryonic stem cells, the NIH has established a Human Embryonic Stem Cell Registry ("the NIH Registry”) that lists the human embryonic stem cells that meet the eligibility criteria.  This registry is available at:  http://stemcells.nih.gov/registry/.

Research involving the derivation of new stem cells from human embryos or the use of human embryonic stem cells that are not listed on the NIH Human Embryonic Stem Cell Registry may not be conducted with Federal funding.

If a particular human embryonic stem cell line has not been required by the Statement of Work, an offeror proposing research involving human embryonic stem cells must cite a human embryonic stem cell line that is listed in the NIH Registry in its proposal.

- HIV Antiretroviral Treatment Trials

The NIH is committed to conducting HIV/AIDS research in an effort to improve the health of people living with this disease, particularly people in countries most affected by the epidemic.  It is important that individuals who volunteer to participate in NIH-funded HIV antiretroviral trials be given the option to continue to receive antiretroviral treatment following their completion of the trial.  In order to accomplish this, the contractor must work with the host countries' authorities and other stakeholders to identify sources available, if any, in the country for the provision of such treatment.  It is noted that NIH cannot provide this treatment following the completion of the research.  See NIH Guide Notice, "Guidance for Addressing the Provision of Antiretroviral Treatment for Trial Participants Following Their Completion of NIH-Funded HIV Antiretroviral Treatment Trials in Developing Countries," located at:

http://grants.nih.gov/grants/guide/notice-files/NOT-OD-05-038.html.

The offeror's proposal must address a plan that describes the following:

-	A description of available sources, if any (e.g., name of source, location, contact person of facility/organization) for the provision of antiretroviral treatment and care following the completion of the trial;

-	A summary of the offeror's interaction with the providers;

-	Documents, if any, from available sources/ providers regarding plans for implementation;

-	A description of how this information will be conveyed to the trial participants.

If there are no sources for antiretroviral treatment in or available to the country in which the treatment trials will take place, the offeror must provide:

-	A statement confirming that at the time of the offer, no sources of antiretroviral treatment could be identified;

-	A description of how this information will be conveyed to the trial participants;

-	A commitment to continue to explore potential sources as the trial proceeds.

This plan or the documentation provided regarding the lack of available sources of antiretroviral treatment will be evaluated by the Project Officer as a part of the overall review of the proposal.  While an offeror's documentation of the lack of available sources for antiretroviral treatment will not, of itself, constitute denial of a contract award, priority for contract awards may be given to those offerors who identify sources for the provision of antiretroviral treatment following the completion of the trial.

- (17)		Information Technology Systems Security

IMPORTANT NOTE TO OFFERORS: The following information shall be addressed in a separate section of the Technical Proposal entitled, “Information Security.”

The Statement of Work (SOW) requires the successful offeror to develop or access Federal automated information systems. Pursuant to the DHHS Information Security Program Policy (http://www.hhs.gov/read/irmpolicy/FINALHHSInformationSecurityProgramP.doc), the following requirements apply:

(1)	Information Type

[  ]	Administrative, Management and Support Information:

[  ]	Mission Based Information:

(2)	Security Categories and Levels

Confidentiality		Level:	[ ] Low	[x] Moderate	[ ] High

Integrity 			Level:	[ ] Low	[x] Moderate	[ ] High

Availability			Level:	[ ] Low	[x] Moderate	[ ] High

Overall			Level:	[ ] Low	[x] Moderate	[ ] High

(3)	Position Sensitivity Designations

Prior to award, the Government will determine the position sensitivity designation for each contractor employee that the successful offeror proposes to work under the contract. For proposal preparation purposes, the following designations apply:

[ ]	Level 6: Public Trust - High Risk (Requires Suitability Determination with a BI).  Contractor employees assigned to a Level 6 position are subject to a Background Investigation (BI).

[]	Level 5: Public Trust - Moderate Risk (Requires Suitability Determination with NACIC, MBI or LBI). Contractor employees assigned to a Level 5 position with no previous investigation and approval shall undergo a National Agency Check and Inquiry Investigation plus a Credit Check (NACIC), a Minimum Background Investigation (MBI), or a Limited Background Investigation (LBI).

[x]	Level 1: Non Sensitive (Requires Suitability Determination with an NACI).  Contractor employees assigned to a Level 1 position are subject to a National Agency Check and Inquiry Investigation (NACI).

Upon award, the contractor will be required to submit a roster of all IT staff working under the contract. The Government will determine the appropriate level of suitability investigation required for each staff member.

Contractor employees who have met investigative requirements within the past five years may only require an updated or upgraded investigation.

(4)	Systems Security Plan

The offeror’s proposal must:

(1)	Include a plan commensurate with the size and complexity of the requirements of the Statement of Work.  The minimum areas to be addressed include, but are not limited to administrative, technical, and physical security as follows:

(i)	Security Awareness Training

(ii)	Logical Access Control

-Network (ex: firewall)

-System (ex: network OS, tcp wrappers, SSH)

-Application (ex: S-LDAP, SSL)

-Remote Access (ex: VPN)

-Monitoring and support (ex: IDS, pager, NOC)

(iii)	Protection against data loss

-OS security (ex: patch management, configuration)

-Application security (ex: patch management)

-Database security

-Back-up and recovery

-Fault tolerance, high availability

(iv)	Malicious Code Protection (ex: Antivirus, filtering of e-mail attachments, etc)

(v)	Physical Security

-Access control (ex: locks, guards)

-Power conditioning and/or UPS

-Air conditioning

-Fire protection

Include an acknowledgment of its understanding of the security requirements.

Provide similar information for any proposed subcontractor developing or accessing an AIS.

The SSP that the offeror must submit with its proposal shall be finalized in coordination with the Project Officer no later than 90 calendar days after contract award.

(e) 	Information Systems Security Training

DHHS policy requires contractors receive security training commensurate with their responsibilities for performing work under the terms and conditions of their contractual agreements.

The successful offeror will be responsible for assuring that each contractor employee has completed the NIH Computer Security Awareness Training course(http://irtsectraining.nih.gov/) prior to performing any contract work, and on an annual basis thereafter, during the period of performance of the contract.  The successful offeror shall maintain a listing of all individuals who have completed this training and shall submit this listing to the Project Officer.

Additional security training requirements commensurate with the position may be required as defined in NIST Special Publication 800-16, Information Technology Security Training Requirements (http://csrc.nist.gov/publications/nistpubs/800-16/800-16.pdf).  This document provides information about information security training that may be useful to potential offerors.

(f)	Prospective Offeror Non-Disclosure Agreement

The Government has determined that prospective offerors will not require access to Federal information described below in order to prepare an offer.

Any individual having access to this information must possess a valid and current suitability determination at the following level:

[ ] Level 6:  Public Trust - High Risk

[x Level 5: Public Trust - Moderate Risk

To be considered for access to Federal information, a prospective offeror must:

    - Submit a written request to the Contracting Officer identified in the solicitation;

    - Complete and submit the “Prospective Offeror Non-Disclosure Agreement” provided as an attachment in Section J of this solicitation; and

    - Receive written approval from the Contracting Officer.

Prospective offerors are required to process their requests for access, receive Government approval, and then access the Federal information within the period of time provided in the solicitation for the preparation of offers.

Nothing in this provision shall be construed, in any manner, by a prospective offeror as an extension to the stated date, time, and location in the solicitation for the submission of offers.

(g) 	References

- DHHS Information Security Program Policy:

http://www.hhs.gov/read/irmpolicy/FINALHHSInformationSecurityProgramP.doc

- DHHS Personnel Security/Suitability Handbook:  http://www.hhs.gov/ohr/manual/pssh.pdf

- NIH Systems Security Plan Template:  http://irm.cit.nih.gov/security/secplantemp.doc

- NIH Systems Security Plan Outline: http://irm.cit.nih.gov/nihsecurity/Security_Plan_Outline.doc

- NIH Computer Security Awareness Training Course:  http://irtsectraining.nih.gov/

- NIST Special Publication 800-16, Information Technology Security Training Requirements: http://csrc.nist.gov/publications/nistpubs/800-16/800-16.pdf

- Appendix A-D: http://csrc.nist.gov/publications/nistpubs/800-16/AppendixA-D.pdf

- NIST SP 800-18, Guide for Developing Security Plans for Information Technology Systems: http://csrc.nist.gov/publications/nistpubs/index.html

- NIST SP 800-60, Guide for Mapping Types of Information and Information Systems to Security Categories, Volume I:  http://csrc.nist.gov/publications/nistpubs/800-60/SP800-60V1-final.pdf

- NIST SP 800-60, Guide for Mapping Types of Information and Information Systems to Security Categories, Volume II:  http://csrc.nist.gov/publications/nistpubs/800-60/SP800-60V2-final.pdf

- NIST SP 800-64, Security Considerations in the Information System Development Life Cycle:http://csrc.nist.gov/publications/nistpubs/800-64/NIST-SP800-64.pdf

c.	BUSINESS PROPOSAL INSTRUCTIONS

(1)		Basic Cost/Price Information

The business proposal must contain sufficient information to allow the Government to perform a basic analysis of the proposed cost or price of the work.  This information shall include the amounts of the basic elements of the proposed cost or price.  These elements will include, as applicable, direct labor, fringe benefits, travel, materials, subcontracts, purchased parts, shipping, indirect costs and rate, fee, and profit.

- Proposal Cover Sheet

The following information shall be provided on the first page of your pricing proposal:

1.	Solicitation, contract, and/or modification number;

2.	Name and address of Offeror;

3.	Name and telephone number of point of contact;

4.	Name, address, and telephone number of Contract Administration Office, (if available);

5.	Name, address, and telephone number of Audit Office (if available);

6.	Proposed cost and/or price; profit or fee (as applicable); and total;

7.	The following statement:  By submitting this proposal, the offeror, if selected for discussions, grants the contracting officer or an authorized representative the right to examine, at any time before award, any of those books, records, documents, or other records directly pertinent to the information requested or submitted.

8.	Date of submission; and

9.	Name, title and signature of authorized representative.

This cover sheet information is for use by offerors to submit information to the Government when cost or pricing data are not required but information to help establish price reasonableness or cost realism is necessary.  Such information is not considered cost or pricing data, and shall not be certified in accordance with FAR 15.406-2.

- Information Other than Cost or Pricing Data

a)	The information submitted shall consist of data to permit the Contracting Officer and authorized representatives to determine price reasonableness or cost realism, e.g., information to support an analysis of material costs (when sufficient information  on labor and overhead rates is already available), or information on prices and quantities at which the offeror has previously sold the same or similar items.

Any information submitted must support the price proposed.  Include sufficient detail or cross references to clearly establish the relationship of the information provided to the price proposed.  Support any information provided by explanations or supporting rational as needed to permit the Contracting Officer and authorized representative to evaluate the documentation.

[Unless otherwise stated in this solicitation, the information may be submitted in the offeror's own format.]

b)	The information submitted shall be at the level of detail described below.

1.	Direct Labor

Provide a time-phased (e.g., monthly, quarterly, etc.) breakdown of labor hours, rates, and cost by appropriate category.  Key personnel will be separately estimated as above and identified.  Give the basis for the estimates in each case.

2.	Materials

Provide a consolidated price summary of individual material quantities included in the various tasks, orders, or contract line items being proposed and the basis for pricing (vendor quotes, invoice prices, etc.).

3.	Subcontracted Items

Include parts, components, assemblies, and services that are to be produced or performed by others in accordance with offeror's design, specifications, or direction and that are applicable only to the prime contract.  For each subcontract over $550,000, the support should provide a listing by source, item, quantity, price, type of subcontract, degree of competition, and basis for establishing source and reasonableness of price, as well as the results of review and evaluation of subcontract proposals when required by FAR 15.404-3.

4.	Raw Materials

Consists of material in a form or state that requires further processing.  Provide priced quantities of items required for the proposal.

5.	Purchased Parts

Includes material items not covered above.  Provide priced quantities of items required for the proposal.

6.	Fringe Benefits

Show fringe benefits as a separate line item. Include the rate(s) and/or method of calculating fringe benefits. Provide a copy of your fringe benefit rate or institutional guidelines.

7.	Indirect Costs

Indicate how offeror has computed and applied offeror's indirect costs, including cost breakdowns, and provide a basis for evaluating the reasonableness of proposed rates.  Indicate the rates used and provide an appropriate explanation.  Where a rate agreement exists, provide a copy.

8.	Special Equipment

If direct charge, list any equipment proposed including description, price, quantity, total price, purchase or lease, and the basis for pricing.

9.	Travel

Provide the cost of travel including destination, duration, purpose, per diem, transportation, and the basis for pricing.

10.	Other Costs

List all other costs not otherwise included in the categories described above (e.g., computer services, consultant services) and provide basis for pricing.

- Requirements for Cost or Pricing Data or Information Other than Cost and Pricing Data [FAR Clause 52.215-20 (October 1997)]

(a)	Exceptions from cost or pricing data.

(1)	In lieu of submitting cost or pricing data, offerors may submit a written request for exception by submitting the information described in the following subparagraphs.  The Contracting Officer may require additional supporting information, but only to the extent necessary to determine whether an exception should be granted, and whether the price is fair and reasonable.

(i)	Identification of the law or regulation establishing the price offered.  If the price is controlled under law by periodic rulings, reviews, or similar actions of a governmental body, attach a copy of the controlling document, unless it was previously submitted to the contracting office.

(ii)	Commercial item exception.  For a commercial item exception, the offeror shall submit, at a minimum, information on prices at which the same item or similar items have previously been sold in the commercial market that is adequate for evaluating the reasonableness of the price for this acquisition. Such information may include--

(A)	For catalog items, a copy of or identification of the catalog and its date, or the appropriate pages for the offered items, or a statement that the catalog is on file in the buying office to which the proposal is being submitted. Provide a copy or describe current discount policies and price lists (published or unpublished), e.g., wholesale, original equipment manufacturer, or reseller.  Also explain the basis of each offered price and its relationship to the established catalog price, including how the proposed price relates to the price of recent sales in quantities similar to the proposed quantities;

(B)	For market-priced items, the source and date or period of the market quotation or other basis for market price, the base amount, and applicable discounts.  In addition, describe the nature of the market;

(C)	For items included on an active Federal Supply Service Multiple Award Schedule contract, proof that an exception has been granted for the schedule item.

(2)	The offeror grants the Contracting Officer or an authorized representative the right to examine, at any time before award, books, records, documents, or other directly pertinent records to verify any request for an exception under this provision, and the reasonableness of price.  For items priced using catalog or market prices, or law or regulation, access does not extend to cost or profit information or other data relevant solely to the offeror's determination of the prices to be offered in the catalog or marketplace.

(b)	Requirements for cost or pricing data.  If the offeror is not granted an exception from the requirement to submit cost or pricing data, the following applies:

(1)	The offeror shall prepare and submit cost or pricing data and supporting attachments in accordance with Table 15-2 of FAR 15.408.

(2)	As soon as practicable after agreement on price, but before contract award (except for unpriced actions such as letter contracts), the offeror shall submit a Certificate of Current Cost or Pricing Data, as prescribed by FAR 15.406-2.

(End of provision)

- Qualifications of the Offeror

You are requested to submit a summary of your "General Experience, Organizational Experience Related to this RFP, Performance History and Pertinent Contracts."

a)	General Experience

General experience is defined as general background, experience and qualifications of the offeror.  A discussion of proposed facilities which can be devoted to the project may be appropriate.

b)	Organizational Experience Related to the RFP

Organizational experience is defined as the accomplishment of work, either past or on-going, which is comparable or related to the effort required by this RFP.  This includes overall offeror or corporate experience, but not the experience and/or past performance of individuals who are proposed as personnel involved with the Statement of Work in this RFP.

c)	Performance History

Performance history is defined as meeting contract objectives within delivery and cost schedules on efforts, either past or on-going, which is comparable or related to the effort required by this RFP.

d)	Pertinent Contracts

Pertinent contracts is defined as a listing of each related contract completed within the last three years or currently in process.  The listing should include: 1) the contract number; 2) contracting agency; 3) contract dollar value; 4) dates contract began and ended (or ends); 5) description of contract work; 6) explanation of relevance of work to this RFP; 7) actual delivery and cost performance versus delivery and cost agreed to in the contract(s).  For award fee contracts, separately state in dollars the base fee and award fee available and the award fee actually received.  The same type of organizational experience and past performance data should be submitted.

e)	Pertinent Grants

List grants supported by the Government that involved similar or related work to that called for in this RFP.  Include the grant number, involved agency, names of the grant specialist and the Science Administrator, identification of the work, and when performed.

You are cautioned that omission or an inadequate or inaccurate response to this very important RFP requirement could have a negative effect on the overall selection process.  Experience and past performance are factors which are relevant to the ability of the offerors to perform and are considered in the source selection process.

- Other Administrative Data

a)	Property

(1)	It is DHHS policy that Contractors will provide all equipment and facilities necessary for performance of contracts.  Exception may be granted to furnish Government-owned property, or to authorize purchase with contract funds, only when approved by the Contracting Officer.  If the offeror is proposing that the Government provide any equipment, other than that specified under Government Furnished Property in the RFP, the proposal must include comprehensive justification which includes:

(a)	An explanation that the item is for a special use essential to the direct performance of the contract and the item will be used exclusively for the purpose.  Office equipment such as desks, office machines, etc., will not be provided under a contract except under very exceptional circumstances.

(b)	No practical or economical alternative exists (e.g., rental, capital investment) that can be used to perform the work.

(2)	The offeror shall identify Government-owned property in its possession and/or Contractor titled property acquired from Federal funds, which it proposes to use in the performance of the prospective contract.

(3)	The management and control of any Government property shall be in accordance with DHHS Publication (OS) 686 entitled, "Contractor's Guide for Control of Government Property (1990)," a copy of which will be provided upon request.

c)	Submission of Electronic Funds Transfer Information with Offer, FAR Clause 52.232-38, (May 1999)

The offeror shall provide, with its offer, the following information that is required to make payment by electronic funds transfer (EFT) under any contract that results from this solicitation. This submission satisfies the requirement to provide EFT information under paragraphs (b)(1) and (j) of the clause at 52.232-34, Payment by Electronic Funds Transfer--Other than Central Contractor Registration.

(1)	The solicitation number (or other procurement identification number).

(2)	The offeror's name and remittance address, as stated in the offer.

(3)	The signature (manual or electronic, as appropriate), title, and telephone number of the offeror's official authorized to provide this information.

(4)	The name, address, and 9-digit Routing Transit Number of the offeror's financial agent.

(5)	The offeror's account number and the type of account (checking, savings, or lockbox).

(6)	If applicable, the Fedwire Transfer System telegraphic abbreviation of the offeror's financial agent.

(7)	If applicable, the offeror shall also provide the name, address, telegraphic abbreviation, and 9-digit Routing Transit Number of the correspondent financial institution receiving the wire transfer payment if the offeror's financial agent is not directly on-line to the Fedwire and, therefore, not the receiver of the wire transfer payment.

d)	Financial Capacity

The offeror shall indicate if it has the necessary financial capacity, working capital, and other resources to perform the contract without assistance from any outside source.  If not, indicate the amount required and the anticipated source.

e)	Incremental Funding

An incrementally funded cost-reimbursement contract is a contract in which the total work effort is to be performed over a multiple year period and funds are allotted, as they become available, to cover discernible phases or increments of performance.  The incremental funding technique allows for contracts to be awarded for periods in excess of one year even though the total estimated amount of funds expected to be obligated for the contract are not available at the time of the contract award.  If this requirement is specified elsewhere in this RFP, the offeror shall submit a cost proposal for each year.  In addition, the following provisions are applicable:

HHSAR 352.232-75, Incremental Funding (January 2001)

(a)	It is the Government's intention to negotiate and award a contract using the incremental funding concepts described in the clause entitled Limitation of Funds. Under the clause, which will be included in the resultant contract, initial funds will be obligated under the contract to cover the first year of performance.  Additional funds are intended to be allotted to the contract by contract modification, up to and including the full estimated cost of the contract, to accomplish the entire project. While it is the Government's intention to progressively fund this contract over the entire period of performance up to and including the full estimated cost, the Government will not be obligated to reimburse the Contractor for costs incurred in excess of the periodic allotments, nor will the Contractor be obligated to perform in excess of the amount allotted.

(b)	The Limitation of Funds clause to be included in the resultant contract shall supersede the Limitation of Cost clause found in the General Provisions.

(End of provision)

f)	Facilities Capital Cost of Money,  FAR 52.215-16, (June 2003)

(This is applicable if you are a commercial organization.)

(a)	Facilities capital cost of money will be an allowable cost under the contemplated contract, if the criteria for allowability in FAR 31.205-10(b) are met.  One of the allowability criteria requires the prospective Contractor to propose facilities capital cost of money in its offer.

(b)	If the prospective Contractor does not propose this cost, the resulting contract will include the clause Waiver of Facilities Capital Cost of Money.

(End of Provision)

If the offeror elects to claim this cost, the offeror shall specifically identify or propose it in the cost proposal for the contract by checking the appropriate box below.

[   ]	The prospective Contractor has specifically identified or proposed facilities capital cost of money in its cost proposal and elects to claim this cost as an allowable cost under the contract.  Submit Form CASB-CMF (see FAR 31.205-10).

[   ]	The prospective Contractor has not specifically identified or proposed facilities capital cost of money in its proposal and elects not to claim it as an allowable cost under the contract.

- Subcontractors

If subcontractors are proposed, please include a commitment letter from the subcontractor detailing:

a)	Willingness to perform as a subcontractor for specific duties (list duties).

b)	What priority the work will be given and how it will relate to other work.

c)	The amount of time and facilities available to this project.

d)	Information on their cognizant field audit offices.

e)	How rights to publications and patents are to be handled.

f)	A complete cost proposal in the same format as the offeror's cost proposal.

Note:  Organizations that plan to enter into a subcontract with an educational concern under a contract awarded under this RFP should refer to the following Web Site for a listing of clauses that are required to be incorporated in Research & Development (R&D) subcontracts with educational institutions:

http://ocm.od.nih.gov/contracts/rfps/FDP/FDPclausecover.htm

- Proposer's Annual Financial Report

All offerors included in the competitive range will be required to submit a copy of the organization's most recent annual financial report.

- Representations and Certifications

One copy of the Representations and Certifications attached as Section K shall be completed and be signed by an official authorized to bind your organization.  Additionally, a completed copy of the Representations and Certifications shall be submitted from any proposed subcontractor.

- Travel Costs/Travel Policy

a)	Travel Costs - Commercial

Costs for lodging, meals, and incidental expenses incurred by Contractor personnel shall be considered to be reasonable and allowable to the extent they do not exceed on a daily basis the per diem rates set forth in the Federal Travel Regulations, General Services Administration (GSA).  Therefore, if travel costs are applicable and proposed by offerors, please be advised that they shall be calculated using the per diem rate schedule as established by GSA.  Reimbursement of travel costs under any contract awarded from this RFP shall be in accordance with FAR 31.205-46.

b)	Travel Policy

One copy of the offeror's (and any proposed subcontractor's) written travel policy shall be included in the business proposal (original only). If an offeror (or any proposed subcontractor) does not have a written travel policy, the offeror shall so state.

(12)		Certification of Visas for Non-U.S. Citizens

Proposed personnel under research projects are not required to be citizens of the United States.  However, if non-U.S. citizens are proposed under a contract to be performed in the United States and its outlying areas, then the offeror must indicate in the proposal that these individuals have the required visas.

(13)		Total Compensation Plan - Instructions

a)	Total compensation (salary and fringe benefits) of professional employees under service contracts may, in some cases, be lowered by recompetition of these contracts.  Lowering of compensation can be detrimental in obtaining the necessary quality of professional services needed for adequate performance of service contracts.  It is, therefore, in the best interest of the Government that professional employees, as defined in 29 CFR Part 541, be properly compensated in these contracts.  All offerors as a part of their business proposal will submit a "Total Compensation Plan" (salaries and fringe benefits) for these professional employees for evaluation purposes.

b)	The Government will evaluate the Total Compensation Plan to ensure that this compensation reflects a sound management approach and an understanding of the requirements to be performed.  It will include an assessment of the offeror's ability to provide uninterrupted work of high quality.  The total compensation proposed will be evaluated in terms of enhancing recruitment and retention of personnel and its realism and consistency with a total plan for compensation (both salaries and fringe benefits).

c)	Evaluation for award, therefore, will include an assessment of the Total Compensation Plan submitted by each offeror.

Total Compensation Plan - Evaluation

a)	Total Compensation Plan (Professional Employees)

In establishing compensation levels for professional employees, the total compensation (both salaries and fringe benefits) proposed shall reflect a clear understanding of the requirements of the work to be accomplished and the suitability of the proposed compensation structure to obtain and retain qualified personnel to meet mission objectives.  The salary rates or ranges must recognize the distinct differences in professional skills and the complexity of varied disciplines as well as job difficulty.  Proposals offering total compensation levels less than currently being paid by the predecessor Contractor for the same work will be evaluated, in addition to the above, on the basis of maintaining program continuity, uninterrupted work of high quality, and availability of required competent professional employees.  Offerors are cautioned that instances of lowered compensation for essentially the same professional work may be considered a lack of sound management judgment in addition to indicating a lack of understanding of the requirement.

b)	Cost (Professional Compensation)

Proposals which are unrealistically low or do not reflect a reasonable relationship of compensation to the professional job categories so as to impair the Contractor's ability to recruit and retain competent professional employees, may be viewed as reflecting a failure to comprehend the complexity of the contract requirements.  The Government is concerned with the quality and stability of the work force to be employed on this contract.  The compensation data required will be used in evaluation of the offeror's understanding of the contract requirements.

c)	Other (Labor Relations)

An assessment of the potential for adverse effect upon performance and maintenance of the required number of professional employees with requisite skills resulting from an unrealistically low compensation structure will also be made.

d)	Federal Acquisition Regulation Clauses incorporated by Reference

FAR Clause 52.222-46, Evaluation of Compensation for Professional Employees (FEBRUARY 1993).

SECTION M - EVALUATION FACTORS FOR AWARD

1.	GENERAL

Selection of an offeror for contract award will be based on an evaluation of proposals against four factors.  The factors in order of importance are:  technical, cost, past performance and Small Disadvantaged Business (SDB) participation.  Although technical factors are of paramount consideration in the award of the contract, past performance, cost/price and SDB participation are also important to the overall contract award decision.  All evaluation factors other than cost or price, when combined, are significantly more important than cost or price.    In any event, the Government reserves the right to make an award(s) to that Offeror whose proposal provides the best overall value to the Government.

The evaluation will be based on the demonstrated capabilities of the prospective Contractors in relation to the needs of the project as set forth in the RFP.  The merits of each proposal will be evaluated carefully.  Each proposal must document the feasibility of successful implementation of the requirements of the RFP.  Offerors must submit information sufficient to evaluate their proposals based on the detailed criteria listed below.

2.	HUMAN SUBJECT EVALUATION

This research project involves human subjects.  NIH Policy requires:

(a)	Protection of Human Subjects from Research Risks

The offeror’s proposal must address the involvement of human subjects and protections from research risk relating to their participation in the proposed research plan, or provide sufficient information on the research subjects to allow a determination by NCI that a designated exemption is appropriate.

If you claim that this research should be considered exempt from coverage by the Federal Regulations at 45 CFR 46, the proposal should address why you believe it is exempt, and under which exemption it applies.

The reviewers will evaluate the proposal with regard to four issues: Risks to Human Subjects, Adequacy of Protection Against Risks, Potential Benefits of the Proposed Research to the Subjects and Others, and Importance of the Knowledge to be Gained.  See Section L for a complete discussion of what is required to be addressed for each of these issues. Based on the response to this criterion, this section of the proposal may be rated “unacceptable” (i.e., concerns are identified as to the protections described against risk to human subjects or no discussion is found regarding protections against risk to human subjects) or “acceptable.”  If the reviewers find that this portion of the proposal is "unacceptable" they will provide a narrative supporting their finding.

If the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to address the concerns raised by the reviewers.  You will be able to further discuss and/or clarify your position until submission of your Final Proposal Revision (FPR).  Once discussions are closed with the submission of your FPR, if your proposed plan for the protection of human subjects from research risks is still found to be unacceptable,  then your proposal may not be considered further for award.

(b)	Data and Safety Monitoring

The offeror’s proposal must include a general description of the Data and Safety Monitoring Plan for all clinical trials.  The principles of data and safety monitoring require that all biomedical and behavioral clinical trails be monitored to ensure the safe and effective conduct of human subjects research, and to recommend conclusion of the trial when significant benefits or risks are identified or if it is unlikely that the trial can be concluded successfully.  Risks associated with participation in research must be minimized to the extent practical and the method and degree of monitoring should be commensurate with risk.  Additionally, all plans must include procedures for adverse event reporting.  Finally, generally, for Phase III clinical trials, the establishment of a Data and Safety Monitoring Board (DSMB) is required, whereas for Phase I and II clinical trials, the establishment of a DSMB is optional.  The reviewers will rely on the Statement of Work  and Section L in the solicitation, as well as any further technical evaluation criteria in this Section M, as applicable, for the solicitation's specific requirements for data and safety monitoring.

As a part of the evaluation for proposals, the reviewers will consider the acceptability of the proposed data and safety monitoring plan with respect to the potential risks to human participants, complexity of study design, and methods for data analysis.  Based on the evaluation of the response to this criterion, this section of the proposal may be rated “unacceptable” (i.e., concerns are identified as to the adequacy of the monitoring plan or no discussion can be found regarding the proposed monitoring plans) or “acceptable.”  If the reviewers find that this portion of the proposal is "unacceptable" they will provide a narrative supporting their finding.

If the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to address the concerns raised by the reviewers.  You will be able to further discuss and/or clarify your position until submission of your Final Proposal Revision (FPR).  Once discussions are closed with the submission of your FPR, if your proposed plan for data and safety monitoring is still found to be unacceptable,  then your proposal may not be considered further for award.

(c) 	Women and Minorities

Women and members of minority groups and their subpopulations must be included in the study population of research involving human subjects, unless a clear and compelling rationale and justification are provided indicating that inclusion is inappropriate with respect to the health of the subjects or the purpose of the research.  In addition, for NIH-Defined Phase III clinical trials, all proposals and/or protocols must provide a description of plans to conduct analyses, as appropriate, to detect significant differences in intervention effect (see NIH Guide http://grants.nih.gov/grants/funding/women_min/guidelines_amended_10_2001.htm, Definitions - Significant Difference) by sex/gender, racial/ethnic groups, and relevant subpopulations, if applicable, unless the Government has specified that this solicitation involves a sex/gender specific study or a single or limited number of minority population groups.  The proposal also must include one of the following plans:

-	Plans to conduct valid analysis to detect significant differences in intervention effect among sex/gender and/or racial/ethnic subgroups when prior studies strongly support these significant differences among subgroups, OR

-	Plans to include and analyze sex/gender and/or racial/ethnic subgroups when prior studies strongly support no significant differences in intervention effect between subgroups (representation of sex/gender and/or racial/ethnic groups as subject selection criterion is not required; however, inclusion and analyses are encouraged), OR

-	Plans to conduct valid analyses of the intervention effect in sex/gender and/or racial/ethnic subgroups (without requiring high statistical power for each subgroup) when the prior studies neither support nor negate significant differences in intervention effect between subgroups.

Also, the proposal must address the proposed outreach programs for recruiting women and minorities as participants.

Reviewers will consider the areas covered here and in Section L of the solicitation in narrative form in their evaluation.  Some of the issues they will evaluate include:

-	whether the plan proposed includes minorities and both genders in adequate representation

-	 how the offeror addresses the inclusion of women and members of minority groups and their subpopulations in the development of a proposal that is appropriate to the scientific objectives of the solicitation

-	the description of the proposed study populations in terms of sex/gender and racial/ethnic groups and the rationale for selection of such subjects

-	if exclusion is proposed, that the rationale is appropriate with respect to the health of the subjects and/or to the purpose of the research.

-	In addition, for gender exclusion, the reviewers will examine the rationale to determine if it is because:

-	the purpose of the research constrains the offeror’s selection of study participants by gender (e.g., uniquely valuable stored specimens or existing datasets are single gender; very small numbers of subjects are involved; or

-	overriding factors dictate selection of subjects); or

-	gender representation of specimens or existing datasets cannot be accurately determined, and this does not compromise the scientific objectives of the research.

-	For minority group exclusion, the reviewers will examine the rationale to determine if those minority groups are excluded because:

-	inclusion of those groups would be inappropriate with respect to their health;or

-	inclusion of those groups would be inappropriate with respect to the purpose of the research.

-	For NIH-defined Phase III clinical trials, reviewers will also consider whether there is an adequate description of plans to conduct analyses to detect significant differences of clinical or public health importance in intervention effect(s) by sex/gender and/or racial ethnic subgroups when the intervention effect(s) is expected in the primary analyses, or if there is an adequate description of plans to conduct valid analyses of the intervention effect in subgroups when the intervention effect(s) is not expected in the primary analyses.

If you determine that inclusion of women and minority populations is not feasible, you must submit a detailed rationale and justification for exclusion of one or both groups from the study population with the technical proposal.  The Government will review the rationale to determine if it is appropriate with respect to the health of the subjects and/or the purpose of the research

Based on the evaluation of the response to this criterion, this section of the proposal may be rated “unacceptable” (i.e., no discussion can be found regarding the proposed gender/minority inclusion plans, or concerns are identified as to the gender or minority representation, or the proposal does not adequately address limited representation of one gender or minority; or the plan is not in accordance with NIH policy guidelines) or “acceptable.”  See Section L of the solicitation for the requirements of women/minorities inclusion.  If the reviewers find that this portion of the proposal is "unacceptable" they will provide a narrative supporting their finding.

If the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to address the concerns raised by the reviewers.  You will be able to further discuss and/or clarify your position until submission of your Final Proposal Revision (FPR).  Once discussions are closed with the submission of your FPR, if your proposed plan for the inclusion/exclusion of women and minorities is still found to be unacceptable,  then your proposal may not be considered further for award.

(d)	Children

Children (i.e. individuals under the age of 21) must be included in all human subject research unless there are clear and compelling reasons not to include them.

Your proposal must include a description of plans for including children.  If you plan to exclude children from the required research, your  proposal must present an acceptable justification for the exclusion.  If you determine that exclusion of a specific age range of child is appropriate, your proposal must also address the rationale for such exclusion.  Also, the plan must include a description of the expertise of the investigative team for dealing with children at the ages included, of the appropriateness of the available facilities to accommodate the children, and the inclusion of a sufficient number of children to contribute to a meaningful analysis relative to the purpose/objective of the solicitation.  Also, see Section L of the solicitation for further specific requirements on inclusion of children.

Based on the reviewers’ evaluation of the offeror’s response, this section of the proposal may be rated “unacceptable” (i.e., no discussion can be found regarding the proposed inclusion plans for children; or concerns are identified as to the offeror’s response regarding the inclusion of children; or the plan is not in accordance wit h NIH policy guidelines) or “acceptable.”  If the reviewers find that this portion of the proposal is "unacceptable" they will provide a narrative supporting their finding.

If the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to address the concerns raised by the reviewers.  You will be able to further discuss and/or clarify your position until submission of your Final Proposal Revision (FPR).  Once discussions are closed with the submission of your FPR, if your proposed plan for the inclusion of children is still found to be unacceptable,  then your proposal may not be considered further for award.

If the information provided in your proposal about the inclusion of children is rated “unacceptable” and the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to further discuss, clarify or modify your plan during discussions and in your Final Proposal Revision (FPR).  If your plan for inclusion of children is still considered “unacceptable” by the Government after discussions, your proposal may not be considered further for award.

e.	HIV Antiviral Treatment Trials

The offeror's proposal must address a plan to have host countries authorities and/or other stakeholders identify sources available, if any, to provide antiretroviral treatment to HIV-affected populations that have participated in the contract-funded HIV antiretroviral treatment trial, OR describe why the offeror believes that there are no such sources available.  The information provided must be in accordance with Section L.

The Project Officer will evaluate the documentation provided.  While an offeror's documentation of the lack of available sources for antiretroviral treatment will not, of itself, constitute denial of a contract award, priority for contract awards may be given to those offerors who identify sources for the provision of antiretroviral treatment following the completion of the trial.

3.	EVALUATION OF OPTIONS

It is anticipated that any contract(s) awarded from this solicitation will contain option provisions and periods.

Offerors must propose the options described in the Statement of Work.  Offerors submitting a proposal under this solicitation must prepare a Technical Proposal and Business Proposal for the entire Statement of Work including options.   Proposals for the basic effort alone, or the options alone will not be accepted for review or considered for award.   In accordance with FAR Clause 52.217-5, Evaluation of Options.  (July 1990), the Government will evaluate offers for award purposes by adding the total price for all options to the total price for the basic requirement, except when it is determined in accordance with FAR 17.206(b) not to be in the Government's best interests.  Evaluation of options will not obligate the Government to exercise the option(s).

4.	EVALUATION OF DATA SHARING PLAN

The offeror's plan for the sharing of final research data shall be assessed for appropriateness and adequacy.

If your proposal does not include a plan or if the plan in your proposal is considered “unacceptable,” and the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to further discuss, clarify or modify your data sharing plan during discussions and in your Final Proposal Revision (FPR).  If your data sharing plan is still considered “unacceptable” by the Government after discussions, your proposal may not be considered further for award.

5.	EVALUATION OF PLAN FOR SHARING MODEL ORGANISMS FOR BIOMEDICAL RESEARCH

The offeror’s proposal must address the plans for sharing model organisms, OR state appropriate reasons why such sharing is restricted or not possible.  Offerors must also address as part of the sharing plan if, or how, they will exercise their intellectual property rights while making model organisms and research resources available to the broader scientific community.  The discussion areas regarding intellectual property outlined in Section L should be addressed.

If your proposal does not include a plan, appropriate reasons for restricting sharing, or, if the plan in your proposal is considered “unacceptable,” and the Government includes your proposal in the competitive range (for competitive proposals), or if the Government holds discussions with the selected source (for sole source acquisitions), you will be afforded the opportunity to further discuss, clarify or modify your plan for sharing model organisms during discussions and in your Final Proposal Revision (FPR).  If your plan for sharing model organisms is still considered “unacceptable,” or your justification for restricting sharing is still considered inappropriate by the Government after discussions, your proposal may not be considered further for award.

6.	TECHNICAL EVALUATION CRITERIA

The evaluation criteria are used by the technical evaluation committee when reviewing the technical proposals.  The criteria below are listed in the order of relative importance with weights assigned for evaluation purposes.

CRITERIA										WEIGHT

CRITERION 1:	ORGANIZATIONAL STRUCTURE AND OVERALL

MANAGEMENT AND COORDINATION	30

The strength, appropriateness, adequacy and feasibility of proposed plans in the following areas:

- Plan for Scientific Management and Coordination, including:  (i) priority setting; (ii) development, review and approval of concepts for proposed studies, including ethical issues; (iii) monitoring and evaluating progress and performance; (iv) resource allocation; (v) composition and proposed policies of the Executive Committee; (vi) composition and proposed policies and procedures of the Protocol Review Committee with respect to the solicitation, technical evaluation and development of recommendations on proposed clinical trials, mechanistic studies, tolerance assay studies and nonclinical research and product development; and (vii) the composition and roles of other committees/organizational entities proposed.

- Protocol Development and Implementation, including:  (i) proposed policies and procedures for full protocol development; (ii) procedures and criteria to be used to assess and select non-Network CTUs to participate in clinical trials; and (iii) proposed policies and procedures to ensure timely and accurate completion of clinical trials and reporting on trial results.

- Laboratories, including:  (i) plan for the establishment and management of Network Laboratories, including proposed membership, criteria for selection and capabilities; (ii) policies, procedures and criteria to be used to assess and select non-Network laboratories; and (iii) proposed distribution of responsibilities, lines of reporting authority, and communications.

CRITERION 2: TECHNICAL APPROACH AND PLANS	25

The soundness, appropriateness, adequacy and feasibility of:

      - Strategic Plan and Research Agenda, including: (i) the proposed approaches to the design of clinical trials and mechanistic studies; (ii) immediate and long-range goals, and timelines and milestones for meeting major goals; (iii) proposed approaches to address new scientific or programmatic developments and objectives through periodic review and revision of the Plan; (iv) approaches to identify and capitalize on opportunities for industry partnerships; (v) proposed clinical trials and mechanistic studies and the rationale for their prioritization; and (vi) suitability of the plan to establish a  national and international consortium of experts to design and conduct clinical trials and mechanistic studies for tolerance induction in the areas of transplantation, autoimmune and asthma and allergic diseases.

      - Nonclinical Research and Product Development, including the proposed approach and methods to be used to: (i) conduct feasibility assessments of clinical trials proposals with respect to the need for additional nonclinical studies required prior to study initiation and the availability and quality of the candidate drug; (ii) conduct nonclinical studies (including, proof of principle, toxicology, pharmacodynamics and pharmacokinetics studies, and absorption, distribution, metabolism and excretion studies); (iii) perform cGMP manufacture of candidate drugs; (iv) develop and use qualified assays to measure study product levels and/or immunogenicity; (v) evaluate study data; and (vi) audit and oversee test facilities, personnel and equipment for compliance with cGLP and cGMP requirements.

      - Clinical Trial Units (CTUs):

- CTUs, including:  the number of Network and non-Network CTUs proposed in relation to the feasibility of implementing the Strategic Plan and Research Agenda; (ii) demonstrated availability of a patient pool adequate to ensure the timely screening and enrollment of study participants; (iii) demonstrated experience of the organizations/institutions proposed with respect to: the conduct and management of clinical trials, including patient screening, recruitment, enrollment and retention; informed consent; assessment and reporting of adverse events; collection and laboratory analysis of patient specimens; management of study products; collection, quality control and management of study data; and creation, maintenance and storage of research records; and (iv) clinical and pharmacy facilities as well as facilities and equipment for the collection, testing, storage and shipping of protocol-related patient samples in accordance with protocol specifications and requirements.

      - Assay and Mechanistic Studies and Laboratories:  Proposed approaches, methods and plans to:  (i) evaluate, prioritize and select assays; (ii) design and conduct mechanistic studies and evaluations of potential immune/surrogate markers; (iii) process, ship, track, store and distribute samples and sample collection kits; (iv) establish performance standards and metrics for assays and laboratories; (v) develop standard operating procedures for quality assurance and quality control of assays; and (vi) assess and implement new technologies and transitions from existing to new technologies.  Adequacy of the number of proposed Laboratories in relation to the feasibility of implementing the Strategic Plan and Research Agenda.

      - Bioinformatics, Data Collection and Validation:  Proposed approaches, methods and plans to:  (i) establish a data management system for the collection, storage, archiving and exchange of clinical and mechanistic study data from multiple sources; (ii) develop software for the capture, analysis, query and storage of scientific data; (iii) build a scalable network and computer infrastructure; (iv) establish and implement a sample tracking and inventory system; (v) create an integrated electronic data repository; (vi) disseminate software applications; (vii) develop and disseminate protocols and standard operating procedures; (viii) develop and implement a long-range plan for the long-term maintenance and survival of scientific data and the data system and for monitoring security and system performance; (ix) ensure the interoperability of data systems and/or portability of data; (x) design and implement a reliable system of quality control; and (xi) provide scientific leadership in the design and selection studies and conduct data analyses for mechanistic and combined clinical and mechanistic data.

      - Collaborations with Other Clinical Research Programs and Organizations:  Proposed plans for the development of future collaborations, including the anticipated benefit of such collaborations to furthering progress in immune tolerance research.

      - Initial and final transition plans:  Ability to develop and implement initial and transition plans to execute the orderly transfer of this project to a successor contractor.

CRITERION 3: QUALIFICATIONS OF PROPOSED PERSONNEL    	20

Appropriateness and relevance of the documented training, experience, expertise and availability of proposed scientific, technical staff and administrative in relation to their specific duties and responsibilities, as follows:

- Qualifications of the proposed Principal Investigator to lead and direct the activities to be carried out under this contract either directly or indirectly through subcontracts.  This includes: scientific and technical expertise in scientific disciplines relevant to tolerance induction; the evaluation of tolerance induction therapies in humans for transplantation, autoimmune disorders, and asthma and allergic diseases; the development and conduct of immune/surrogate markers and studies of underlying mechanisms; the solicitation and evaluation of the technical merit of subcontract proposals; and the capacity to monitor progress, assess performance, identify performance problems and implement corrective actions.

- Qualifications of all scientific and technical staff, including subcontractors, with respect to conducting the range of studies and services required, including a proven track record in the design and conduct of clinical trials, mechanistic studies, development of immune/surrogate markers, nonclinical research and product development, and bioinformatics, data management and analysis activities carried out under subcontract.

- Adequacy, thoroughness and feasibility of the detailed technical approaches and plans proposed for soliciting, evaluating, executing and post-award administration of subcontracts, including:

- Qualifications and experience of contract management staff in the acquisition, award and monitoring of subcontracts, including financial monitoring and reporting and adherence to subcontract terms and conditions.

- Understanding of peer review processes and procedures, including principles for avoidance of review conflict of interest with subcontract proposals;

- Plans and procedures for developing solicitations, assembling qualified technical evaluation panels, conducting peer review of proposals received, and negotiating and awarding subcontracts in an objective and efficient manner; and

- Plans for closely monitoring and assessing technical, administrative and operational performance of subcontractors and implementing remedial actions to correct performance problems.

- Appropriateness of the proposed mix and balance of key personnel in relation to their specific responsibilities and time commitments.

CRITERION 4: FACITITIES AND OTHER RESOURCES	25

The adequacy and availability of facilities, equipment and other resources necessary to carry out all contract activities, including, where appropriate, compliance with GLP and cGMP requirements, for the following:

- Laboratories for mechanistic studies and development of immune/surrogate markers;

- Nonclinical research and product development activities, including GLP facilities for the conduct of studies on product safety, toxicology, etc., and for the manufacture of pilot lots under cGMP when necessary; and

- Bioinformatics, data collection and validation functions.

CRITERION 5:  EXPANSION OPTION(S)					20

Demonstrated ability of the Principal Investigator to oversee and manage the expansion; adequacy of the resources and facilities to address expansion needs; adequacy of plans for subcontracting for the necessary expertise and capabilities to conduct work required in the expansion.

TOTAL POSSIBLE POINTS                                                                                         	120

7.	PAST PERFORMANCE FACTOR

An evaluation of offerors' past performance information will be conducted prior to any communications with offerors leading to establishment of the competitive range.  However, this evaluation will not be conducted on any offeror whose proposal will not be admitted to the competitive range on the basis of the results of the evaluation of factors other than past performance.

The evaluation will be based on information obtained from references provided by the offeror, other relevant past performance information obtained from other sources known to the Government, and any information supplied by the offeror concerning problems encountered on the identified contracts and corrective action taken.

The government will assess the relative risks associated with each offeror.  Performance risks are those associated with an offeror's likelihood of success in performing the acquisition requirements as indicated by that offeror's record of past performance.

The assessment of performance risk is not intended to be a product of a mechanical or mathematical analysis of an offeror's performance on a list of contracts but rather the product of subjective judgment by the Government after it considers relevant information.

When assessing performance risks, the Government will focus on the past performance of the offeror as it relates to all acquisition requirements, such as the offeror's record of performing according to specifications, including standards of good workmanship; the offeror's record of controlling and forecasting costs; the offeror's adherence to contract schedules, including the administrative aspects of performance; the offeror's reputation for reasonable and cooperative behavior and commitment to customer satisfaction; and generally, the offeror's business-like concern for the interest of the customer.

The Government will consider the currency and relevance of the information, source of the information, context of the data, and general trends in the offeror's performance.

The lack of a relevant performance record may result in an unknown performance risk assessment, which will neither be used to the advantage nor disadvantage of the offeror.

8.	EXTENT OF SMALL DISADVANTAGED BUSINESS PARTICIPATION

SDB participation will not be scored, but the Government’s conclusions about overall commitment and realism of the offeror’s SDB Participation targets will be used in determining the relative merits of the offeror’s proposal and in selecting the offeror whose proposal is considered to offer the best value to the Government.

The extent of the offeror’s Small Disadvantaged Business Participation Targets will be evaluated before determination of the competitive range.  Evaluation of SDB participation will be assessed based on consideration of the information presented in the offeror’s proposal. The Government is seeking to determine whether the offeror has demonstrated a commitment to use SDB concerns for the work that it intends to perform.

Offers will be evaluated on the following sub-factors:

(a)	Extent of commitment to use SDB concerns

(b)	Realism of the proposal

(c)	Extent of participation of SDB concerns in terms of the value of the total acquisition.

SOLICITATION ATTACHMENTS INCLUDED WITH THE RFP

The following pages include Attachments applicable to this RFP as specified in SECTION J - List of Attachments

PROPOSAL INTENT RESPONSE SHEET

RFP No.: NIH-NIAID-DAIT-07-33

RFP Title: Collaborative Network for Clinical Research on Immune Tolerance

Please review the attached Request for Proposals.  Furnish the information requested below and return this page by April 1, 2006.  Your expression of intent is not binding but will greatly assist us in planning for proposal evaluation.

[ ] DO INTEND TO SUBMIT A PROPOSAL

[ ] DO NOT INTEND TO SUBMIT A PROPOSAL FOR THE FOLLOWING REASONS:

Company/Institution Name (print): ________________________________

Address (print): ________________________________________________

______________________________________________________________

______________________________________________________________

______________________________________________________________

Project Director's Name (print): ___________________________________

Title (print): ____________________________________________________

Signature/Date: _________________________________________________

Telephone Number and E-mail Address (print clearly):

_____________________________________________________________

_____________________________________________________________

*Name of individual to whom electronic proposal instructions should be sent:

Name: __________________________________________________

Title: ___________________________________________________

E-Mail Address: __________________________________________

Telephone Number: _______________________________________

Names of Collaborating Institutions and Investigators (include Subcontractors and Consultants) (print):

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

(Continue list on a separate page if necessary)

RETURN VIA FAX OR E-MAIL TO:

Office of Acquisitions, NIAID, NIH, DHHS

Room 3214

6700-B Rockledge Drive, MSC 7612

Bethesda, MD 20892-7612

Delivery service address:  Bethesda, MD  20817

Attn: Erin M. Goldstein

RFP NIH-NIAID- DAIT-07-33

FAX# (301) 480-0972

Email : eg108r@nih.gov

STATEMENT OF WORK

RFP-NIH-NIAID-DAIT-07-33

INTRODUCTION:  The purpose of this solicitation is to recompete the “Collaborative Network for Clinical Research on Immune Tolerance” (hereinafter referred to as the “Network”) and to expand the requirements to include nonclinical research and product development, bioinformatics, and data collection, validation, and analysis.  For purposes of this solicitation and the resulting contract, immune tolerance is defined as a selective lack of pathogenic immune responses to relevant antigens (e.g., alloantigens, autoantigens or allergens) by any of a variety of approaches, including: deletion, induction of anergy, immune deviation, sequestration, or suppression.  Approaches may target antigen-specific pathways, costimulatory pathways, homing or adhesion molecules, or other relevant molecules, and may use a variety of agents, including antigens, peptides, altered peptide ligands, monoclonal antibody blockade, cytokines, adjuvants, molecularly engineered cells or tissues, DNA vectors or other relevant approaches.  Clinical research protocols that include minimally immunosuppressive drug regimens will be allowable only in the context of efforts to withdraw such agents as a component of an overall plan to achieve a functional state of immune tolerance.

SCOPE:  The scope of work to be performed by the Network includes:

1.	The design and conduct of Phase I-IV clinical trials of  investigational approaches intended to lead to a functional state of immune tolerance in three clinical areas:  autoimmune diseases; asthma and allergic diseases; and graft rejection of transplanted solid organs, tissues and cells;

2.	The design and conduct of mechanistic studies and the development of tolerance assays as integral components of the clinical trials undertaken, including establishing and directing a consortium of laboratories;

3.	Focused product development and nonclinical studies (e.g., toxicology, pharmacology, and pharmacokinetics, etc.) essential for the subsequent evaluation of promising tolerance induction approaches in humans; and

4.	The provision of biostatistics, data collection, validation and analysis resources.

The Network will require strong leadership to provide for the overall scientific direction, coordination and management of complex research studies involving a large number of geographically distributed facilities, subcontractors, and Network personnel.  The Network will also establish collaborations with pharmaceutical and biotechnology companies, other NIH-sponsored clinical research programs, and private research organizations to identify and evaluate tolerance induction therapies, conduct mechanistic studies, and perform assays to assess the induction, maintenance, and loss of tolerance.

TECHNICAL REQUIREMENTS:

Independently and not as an agent of the Government, the Contractor shall furnish all the necessary services, qualified personnel, material, equipment, and facilities, not otherwise provided by the Government under the terms of this contract, as needed to perform the Statement of Work.

The functions to be performed by the Contractor are comprised of ten task areas (Items I-X), and are briefly described below in the Overview section.  The work to be performed for each of these tasks is described in the Detailed Statement of Work section below.

OVERVIEW:

- Strategic Plan and Research Agenda: Develop a Strategic Plan and Research Agenda to advance immune tolerance induction strategies through clinical trials, and to integrate studies of the underlying mechanisms of the induction, maintenance, and loss of tolerance.

- Organizational Structure and Overall director and Coordination of Network Activities: Establish and manage a network of scientific and clinical investigators to include expertise in three areas: (1) transplantation, autoimmune

diseases, and asthma and allergic diseases; (2) assay techniques to measure the induction, maintenance, and loss of tolerance; and (3) nonclinical development and production of candidate drugs.

- Nonclinical Research and Candidate Drug Development:  Design and conduct nonclinical research and product development activities for candidate drugs needed to accomplish the goals and objectives set forth in the Strategic Plan and Research Agenda.  Such activities may include proof-of-principle studies, production, pharmacokinetics and pharmacodynamics studies, and nonclinical toxicity studies in suitable animal models.  Manufacturing and laboratory studies shall be conducted under Good Manufacturing Practices (GMP) or current Good Laboratory Practices (cGLP), as appropriate.

- Clinical Trials:  Implement the Strategic Plan and Research Agenda through the design and conduct of Phase I-IV clinical trials to evaluate the safety and efficacy of promising approaches to achieve immune tolerance in asthma and allergic diseases, autoimmune diseases, and transplantation.

- Mechanistic Studies and Laboratories:  Establish and direct a consortium of laboratories to design and conduct mechanistic studies as an integral part of the Network clinical trials, using a broad range of assays to assess:  (1) stage of disease and likelihood of progression; (2) effect of treatment on immunological status and/or clinical outcome; (3) maintenance of protective immunity; (4) safety of immunosuppressive withdrawal; and (5) identify and evaluate potential immune/surrogate markers of the induction, maintenance, and loss of tolerance.

- Bioinformatics, Data Collection, and Validation:  Establish and maintain a data management and bioinformatics analytical resource with appropriate security and quality control measures.  HHS is responsible for implementing a Department-wide information security program to assure that each information system and associated facility provides a level of security that is commensurate with the risk and magnitude of the harm that could result from the loss, misuse, disclosure, or modification of the information contained in the system. Each system's level of security shall protect the confidentiality, integrity, and availability of the information and comply with all security and privacy-related laws and regulations.  The HHS Information Security Program Policy and Handbook, known as "Secure ONE HHS", provides a baseline of security policies for the Department. These policies apply to the Department, which includes Operating Division (OPDIV) and Staff Division (STAFFDIV) personnel, contractors, and other authorized users.  All information technology related issues such as technical security, information security, personnel security, web management, application management, database management, electronic communications, electronic reporting, etc., defined within this contract is subject to the prescribed methods defined within "Secure ONE HHS".

- Collaboration with Clinical Research Programs and Organizations:  Develop and implement a plan to collaborate with, including information-sharing, other NIH-sponsored clinical research programs, private organizations, and companies involved in research to advance the understanding of immune-mediated diseases.

- Project Management

- Initial and Final Transition:

- Initial Transition: Develop and implement an Initial Transition Plan to ensure the efficient and effective transfer of contract activities and resources.

- Final Transition Plan: Develop and implement a plan to transition studies, data, equipment and other contract resources upon termination of this contract to any successor organization(s) designated by the Government.

X.	Expanded Services through the Exercise of Option(s).

DETAILED STATEMENT OF WORK: Specifically, the Contractor and/or subcontractors shall perform the following tasks:

- STRATEGIC PLAN AND RESEARCH AGENDA

- Two (2) months after contract award, submit a draft Strategic Plan and Research Agenda for review and

approval by the NIAID Project Officer.  The Strategic Plan and Research Agenda shall:

    - Describe the state-of-the-art of efforts to induce tolerance and define the underlying mechanisms in animal models and human studies.  The discussion must include a description of safety concerns, knowledge gaps, and scientific opportunities relevant to the clinical application of tolerance induction strategies in human immune-mediated diseases and transplantation.

    - Delineate approaches to tolerance induction for the prevention or treatment of asthma and allergic diseases, autoimmune diseases, and the prevention of immune-mediated rejection of solid organ, tissue and cell transplants.

    - Delineate mechanisms underlying the induction, maintenance, or loss of immune tolerance.

    - Describe the state-of-the-art of research on the identification, assessment, 
and validation of immune/surrogate markers, biological samples (e.g., blood, tissue, cellular isolates), and new and existing techniques for measuring tolerant states in rodents, non-human primates and humans.

    - Describe the knowledge gaps and opportunities relevant to the further development and improvement of immune/surrogate markers, samples and techniques, including the major sources of variability that may confound clinical applications (biological  and sampling diversity, specimen handling, shipping, storage; and variability of detection procedures); validation against acknowledged disease endpoints; proposed strategies and methods for overcoming and/or reducing variability.

    - Identify immediate and long-range goals of the Network, potential barriers to success, and potential solutions to overcome those barriers.

    - Delineate approaches to identify and capitalize on opportunities for industry partnerships to accomplish the goals of the Network.

    - Establish timelines and milestones to assess adherence to and success in meeting the major aims of the plan.

- Following approval by the NIAID Project Officer, post the Strategic Plan and Research Agenda on the

Network public website and notify the Network members that the document is available.

- At a minimum, conduct annual reviews of the Strategic Plan and Research Agenda to address new scientific, programmatic and fiscal developments; submit a concise report of recommended revisions to the NIAID Project Officer for review and approval.  Following approval, revise the Strategic Plan and Research Agenda as required, post the revised version on the Network public website, and notify the Network members that the revised plan is available.

- Two (2) months after contract award, develop and submit, for review and approval by the NIAID Project Officer, a plan to identify and capitalize on opportunities for industry partnerships to accomplish the goals and objectives described in the Network Strategic Plan and Research Agenda.  Revise and update the plan periodically, but no less than annually, to reflect new collaborative opportunities.

- ORGANIZATIONAL STRUCTURE AND OVERALL DIRECTION AND COORDINATION OF NETWORK ACTIVITIES

The Contractor shall establish and direct the scientific, technical and operational infrastructure of the Network, consisting of a multi-institutional consortium of national and international experts in the areas of: (1) transplantation, autoimmune disorders, and asthma and allergic diseases; (2) assay techniques to measure the induction, maintenance, and loss of tolerance; (3) nonclinical research and product development; and (4) bioinformatics and data collection, validation and analysis.  Specifically, the Contractor shall be responsible for planning, establishing, implementing and directing the organizational entities and activities delineated below.

- Two (2) months after contract award, develop and submit, for NIAID Project Officer review and approval, a plan for the scientific structure, management and coordination of all Network studies.  The plan shall encompass the following:  (1) priority setting procedures and criteria; (2) a process for developing, reviewing and approving concepts for proposed studies; (3) monitoring and evaluating progress and performance, including: augmenting the Network with additional institutions/organizations as may be necessary to capitalize on new scientific opportunities; discontinuing, temporarily or permanently, the services of subcontractors; and terminating or curtailing ongoing and planned research projects; (4) a process for allocating resources; and (5) a plan to determine the need for redirecting the research focus, including reallocation of funds, as needed to achieve the goals of the Strategic Plan and Research Agenda.

- The Network organizational structure must include, at a minimum, the two committees delineated below.  Additional committees and subcommittees may be established to carry out the overall management and coordination functions listed in item C. below.

- Network Executive Committee: Provides scientific leadership and overall governance of the Network and directs the implementation of the Strategic Plan and Research Agenda.  The composition and specific responsibilities of the Network Executive Committee include:

- Chaired by the Network Principal (PI) and consisting of additional Network members, appointed by the PI, to provide leadership in each of the major medical/scientific areas critical to the success of the Network (i.e., nonclinical research and product development, clinical trial design and implementation; autoimmune diseases; asthma and allergic diseases; transplantation; immunological assessment of tolerance; bioinformatics and data analysis).  The Network shall develop and implement a plan for the systematic rotation of membership of Network committees that ensures continuity of deliberations and processes.  The NIAID Project Officer or designee shall be a voting member of the Network Executive Committee.

- Establishes Network priorities and serves as the main decision-making body.  In addition, provides second-level review and approval of recommendations emanating from other Network committees and organizational entities.  The Network Executive Committee shall also be responsible for communicating these decisions to the NIAID Project Officer, Network committees, and Principal Investigators of nonclinical studies, clinical trials, and mechanistic studies.

- Reviews and updates the Strategic Plan and Research Agenda on an annual basis.

- Establishes and maintains communication with the NIAID Project Officer regarding major Network activities, progress, obstacles and proposed approaches to overcome obstacles; submits requests, documents, manuscripts, reports, and other data and information for NIAID Project Officer review and approval.

- Plans and convenes three (3) 1-2-day Network Executive Committee meetings per year, in the Bethesda, MD area (or elsewhere, subject to approval of the NIAID Project Officer), and monthly teleconferences during months in which meetings are not held. The purpose of these meetings and teleconferences is to review governance and fiscal policies and procedures; progress of ongoing clinical trials, mechanistic studies, and nonclinical product development; progress of clinical studies in development; other performance assessments; and future plans.

- Two (2) weeks prior to each Network Executive Committee meeting, prepares an agenda for NIAID Project Officer review and approval; distributes agenda to Committee members and any ad hoc experts.

- Within one (1) week after each Network Executive Committee meeting or teleconference, prepares a list of participants and summary of discussions, action items and recommendations for review and approval by the NIAID Project Officer.

- Designs and implements a performance evaluation plan to include the criteria and measures to be used to assess Network performance.  Conducts performance evaluations on an annual basis and prepares and submits a report on the results of each performance evaluation for NIAID Project Officer review and approval, including recommendations for approaches to improve efficiency, organizational structure, policies and procedures, adherence to established timelines for Network studies, and other factors relevant to the effective performance of Network activities.

- Network Steering Committee: Serves as the primary governing body for Network activities related to: clinical trials; nonclinical research and product development; mechanistic studies and tolerance assays; and bioinformatics/data analysis activities.  Makes recommendations to the Network Executive Committee regarding implementation of new projects and direction of ongoing studies.

- The composition of the Network Steering Committee shall include:

    - The Network Steering Committee Chair, designated by the Network Executive Committee;

    - The directors of the dedicated Network Clinical Trial Units (see Statement of Work Section III), other Network members, and ad-hoc representatives appointed by the Network Steering Committee Chair; and

    - Up to six (6) additional voting members appointed by the NIAID Project Officer.  The NIAID-appointed members may include NIAID staff or ad hoc experts, as deemed necessary by the NIAID Project Officer.

- The responsibilities of the Network Steering Committee shall include:

- Develops and implements a process for the solicitation and review of proposals for clinical trials, nonclinical research and product development, mechanistic studies, and tolerance assays.  The process shall include a standardized form that provides at a minimum:  the Principal Investigator name; study hypothesis, goals, and objectives; patient population(s) and proposed clinical trial sites, including documentation of access to the appropriate patient population(s); a statistical analysis plan; documentation of the availability of study product; and a description of any proposed collaborations, e.g., pharmaceutical companies, NIH-sponsored clinical research programs.

- Conducts reviews to assess the scientific merit and feasibility of all proposed studies; prepares written reports to document the results of all reviews; and communicates the results of reviews to the Network Executive Committee, including recommendations to the Network Executive Committee regarding Network support for clinical trials; nonclinical research and product development; mechanistic studies and tolerance assays; and bioinformatics/data analysis activities.

- Assumes responsibility for the oversight and direction of Network clinical trials; nonclinical research and product development; mechanistic studies and tolerance assays; and bioinformatics/data analysis activities.

- The Network Steering Committee shall convene two (2) to three (3) meetings annually, of one to two (1-2) days in duration, in order to:

- Review study proposals submitted by Network members and non-Network investigators; and

- Monitor progress of, and take remedial actions to address delays or other problems with Network-sponsored clinical trials; nonclinical research and product development activities; mechanistic studies and tolerance assays; and bioinformatics/data analysis activities. Meeting locations must be approved by the NIAID Project Officer. The Network Steering Committee Chair may convene additional teleconferences, videoconferences, or electronic reviews to avoid delays in addressing key issues that cannot be evaluated at the Network Steering Committee’s regularly scheduled meetings.

- One month prior to each Network Steering Committee meeting, teleconference or videoconference, the Network Steering Committee Chair shall prepare an agenda for NIAID Project Officer review and approval, and distribute the approved agenda to members of the Network Steering Committee and the Network Executive Committee.

- Within two weeks of completion of each Network Steering Committee meeting, teleconference or videoconference, the Network Steering Committee Chair shall prepare a list of participants and summary of discussions, action items, and recommendations for review and approval by the Network Steering Committee Chair.

- Prior to implementation, all clinical trial protocols must be reviewed by the NIAID DAIT Clinical Research Committee and approved by the NIAID Project Officer.  The NIAID DAIT Clinical Research Committee is comprised of DAIT Medical Officers, Regulatory Officers, and Project Managers designated by the DAIT Associate Director for Clinical Research.

- The Network shall also be responsible for day-to-day management and coordination with respect to clinical trials, core laboratories and assay studies, bioinformatics and data collection and analysis, ethical aspects of clinical trials and assay studies, conflict of interest, and publications and communications.  The Network may establish subcommittees or project-specific working groups, or assign responsibility to key staff for the following activities:

  - Management of Clinical Trials

    - Oversee protocol development for clinical trials approved for implementation by the Network Executive Committee.

    - Assign Protocol Managers to oversee the implementation and conduct of each clinical trial and to serve as the primary contact to the NIAID medical monitors, NIAID project managers, and NIAID regulatory affairs officers.

    - Identify need for protocol amendments and or remedial actions to ensure adequate patient accrual and retention, adherence to protocol requirements and overall progress of clinical trials in collaboration with the NIAID project officer; make recommendation to the NIAID staff for appropriate actions.

- Tolerance Assays and Laboratory Facilities

- Establish and direct a consortium of institutions necessary to execute the laboratory component of the Network Strategic Plan and Research Agenda.

- Assess requirements for specific tolerance assays and laboratory facilities.

- Develop and disseminate standard operating procedures and operations manuals governing sample collection, shipment, and processing.

- Establish performance metrics for laboratory facilities, assess performance, and recommend and implement improvements and remedial actions when necessary.

- Bioinformatics and Data Collection and Analysis

- Assess requirements for data collection, validation, analysis and security.

- Develop and implement the Network bioinformatics and information management processes.

  - Review and Oversight of Ethical Aspects of Clinical Trials and Tolerance Assays

- Develop and implement a process for the review of the ethical aspects of all clinical trial and tolerance assay proposals to identify potential ethical issues, and recommend modifications to resolve all such issues.

- Develop and implement periodic reviews of ongoing clinical trials for potential ethical issues and recommend modifications for the resolution of all such issues to the Network Executive Committee.

  - Conflict of Interest

  - Develop and implement policies and procedures for identification, disclosure, reporting and management of potential and actual conflicts of interest for members of the Network and subcontractors.  Conflict of Interest information must be reported to the NIAID Project Officer annually, and more frequently as required to address new or changing conflicts.

  - Update and modify Network conflict of interest policies and procedures as needed to remain in compliance with academic standards and other Federal regulations and policies described at http://www.hhs.gov/ohrp/special/conflict.html.

    - Publications and Communications

- Develop and implement policies and procedures for authorship, preparation, review, and final approval of manuscripts resulting from Network studies, and for submission of manuscripts for publication in peer reviewed journals.  The Network must submit manuscripts to the NIAID Project Officer for NIAID approval before submission to journals. The respective role and responsibilities of pharmaceutical companies in the publication review and approval process will be addressed in specific Clinical Trial Agreements (CTA), as appropriate.

- Establish and implement policies and procedures for publicizing Network solicitations, accomplishments, and developments to the scientific and lay communities and other relevant audiences.

- Design and maintain a publicly-accessible, Americans with Disabilities Act Section 508-compliant, internet-based website to provide information regarding Network activities for lay and scientific audiences and Network members.  Information about Section 508 can be found at http://www.section508.gov.

- NONCLINICAL RESEARCH AND PRODUCT DEVELOPMENT

- As directed by the NIAID Project Officer, the Network may manufacture candidate drugs and/or conduct nonclinical safety and efficacy studies (e.g., toxicity, pharmacokinetic and pharmacodynamic) if needed to address priorities in the Network Strategic Plan and Research Agenda.  The NIAID Project Officer or the Network may initiate proposals to manufacture candidate drugs and/or the conduct of nonclinical safety and efficacy studies.  Proposals initiated by the Network must be submitted for NIAID Project Officer approval.  All Network proposals for nonclinical studies and cGMP manufacturing will require consultation with NIAID staff and approval by the NIAID Project Officer.  Approval will be based on well-documented needs (e.g., lack of an industry sponsor and/or need for additional nonclinical studies to meet regulatory requirements) or the high priority of clinical trial proposals based on the Network Strategic Plan and Research Agenda.

- For each clinical trial proposal, the Contractor shall:

- 1.	Assess available data from nonclinical pharmacology and toxicology studies against International Conference on Harmonization (ICH) guidelines (www.fda.gov/cder/guidance/index.htm ).  Determine if the studies, data and information are sufficient to meet Health Authority requirements and allow the proposed clinical trial to proceed.  Identify and determine deficiencies, gaps, data and information that will be required prior to the initiation of a proposed clinical trial.

- 2.	Assess the availability of study products for proposed clinical trials and additional nonclinical studies needed per the above assessments.  Determine amount of product required to perform the proposed studies prior to initiation of the nonclinical studies or clinical trials.

- 3.	If subcontracting is necessary, identify subcontractors to perform the nonclinical studies and identify the source of cGMP-grade study product supply:

    - Pharmaceutical drug manufacturer.

    - Contract manufacturer.

- If a contract manufacturer is necessary, the Network shall subcontract for:

  - The manufacture of drug substance and drug product in accordance with cGMP;

  - Release testing of drug substance and drug product;

  - Stability testing of drug product and drug substance, as necessary;

  - Provision of documentation in formats necessary to meet FDA submission requirements; and

  - Oversight and audit of facilities and studies to ensure personnel, equipment and facilities are compliant with FDA regulatory requirements.

    - Prepare a Nonclinical Product Development Plan that outlines the cGMP manufacturing requirements for all nonclinical studies and clinical trials and the cGLP and non-cGLP nonclinical studies to be conducted. The Nonclinical Product Development Plan must propose a list of potential subcontractors capable of performing the required tasks.  Submit the Nonclinical Product Development Plan to the NIAID Project Officer for review and approval.  The Nonclinical Product Development Plan may include:

- Determination of maximally tolerated dose (MTD);

- Determination of acute and subchronic system toxicity;

- Determination of relevant pharmacokinetic/toxicokinetic parameters;

- Bioavailability studies;

- Absorption distribution, metabolism, and excretion studies;

- Genetic toxicity, reproductive toxicity, and immunotoxicity studies;

- Immunogenicity studies;

- Biotransformation assays;

- Other safety and pharmacology assays and studies, as required;

- Drug concentration, identity, integrity, purity, potency, and contamination required for release for nonclinical or clinical use; and

- Assessment of post-production stability.

  - Solicit and evaluate technical and cost proposals from potential subcontractors and execute and manage subcontracts when necessary to carry out the activities called for in the NIAID-approved Nonclinical Product Development Plan.

  - Develop qualified assays to measure study product levels and/or immunogenicity in appropriate tissues to support nonclinical studies and clinical trials, as necessary.

  - As necessary, evaluate production and laboratory reports, or oversee and/or audit manufacturing and test facilities to ensure that personnel, equipment and facilities are compliant with the requirements of the relevant Health Authorities in the countries in which the proposed clinical trial study sites are located.  All testing must be performed in accordance with cGLP regulations (21 CFR 58) unless otherwise specified by the NIAID Project Officer.

  - Evaluate the data resulting from the conduct of the above studies and draw relevant conclusions about pharmacokinetics, target organ(s) of toxicity, and likely human adverse reactions to the candidate drugs evaluated.  Prepare and submit study reports to the NIAID Project Officer in formats compliant with the International Conference on Harmonization (ICH) guidelines (www.fda.gov).

- CLINICAL TRIALS

Directly, or indirectly through subcontracts, the Contractor shall provide all personnel, resources, and facilities necessary to design and conduct Phase I-IV clinical trials to evaluate the safety and efficacy of immune tolerance strategies as specified in the Network Strategic Plan and Research Agenda.  Specifically, the Contractor shall carry out the following tasks:

- Design and implement a protocol development process:

- For each approved clinical trial, establish a Protocol Development Team to include the protocol Principal Investigator, Network Clinical Trials Management staff, Network investigators with expertise in the design and conduct of clinical trials and mechanistic studies, and NIAID staff to include the Medical Officer, Regulatory Affairs Officer, and Project Manager.

- The Network staff and protocol Principal Investigator shall be responsible for overall protocol development and shall assign responsibilities and establish specific timelines, milestones, and performance guidelines for protocol development.

- For each trial that includes mechanistic studies, the Protocol Development Team shall:

- Define mechanistic study data that may be required for, or contribute to, interim safety, efficacy or utility analyses;

- Prioritize the proposed mechanistic studies for each trial; and

- Establish timelines for generating and reporting mechanistic data from each trial.

  - Data and Safety Monitoring:

    - Data and Safety Monitoring Plan:  For each clinical trial, the Protocol Development Team shall develop a Data and Safety Monitoring Plan to ensure adequate monitoring of human subjects research.  All Data and Safety Monitoring Plans shall be reviewed and approved by the designated ethics experts, committee or subcommittee as established by the Network Executive Committee, and revised as needed to address recommendations of the NIAID Data and Safety Monitoring Boards.

    - NIAID Data and Safety Monitoring Boards (DSMBs):  As directed by the NIAID Project Officer, participate in and prepare materials for review by independent NIAID DSMBs.  The Principal Investigator of each clinical trial shall present the final clinical protocol and the data and safety monitoring plan to the appropriate NIAID DSMB prior to study implementation, and shall also participate in the preparation of materials for and respond to questions and recommendations emanating from DSMB deliberations, including interim and final analyses of clinical study data.

      - Establish Clinical Trial Units (CTUs)

- Dedicated Network CTUs:  A dedicated group of CTUs shall be established from among the institutions participating in the scientific infrastructure of the Network to ensure maximum quality, consistency, timeliness and cost-efficiency in the conduct of Network clinical trials.  Seventy-five percent (75%) of Network clinical trials must include dedicated CTUs and the majority of institutions participating in Network clinical trials must be from among the dedicated Network CTUs, unless otherwise directed by the NIAID Project Officer.

- Non-Network CTUs:  CTUs at institutions outside of the Network scientific infrastructure may participate in the conduct of clinical trials with the approval of the NIAID Project Officer.  Recommendations and procedures for the participation of non-Network CTUs in the conduct of clinical trials will be developed by the Network Executive Committee and submitted to the NIAID Project Officer for approval.

- Requirements for all CTUs: All CTUs participating in Network clinical trials must meet the following requirements:

- Provide clinical investigators, nurse coordinators and other clinical and technical personnel experienced in the conduct and management of clinical trials in accordance with GCP standards and guidelines, including: patient screening, recruitment, enrollment and retention; informed consent; assessment and reporting of adverse events; collection and laboratory testing of protocol-specific patient specimens; receipt, storage, packaging, labeling and management of study products; collection, quality control and management of study data; and creation, maintenance and storage of research records, including participant files, source documents, regulatory files, subject identification information, clinical reports, and case report forms.

- Demonstrate the availability of a patient pool adequate to ensure the timely screening and enrollment of study participants.

  - Management and Oversight of Clinical Trials

- Establish procedures and policies for the management and oversight of Network clinical trials.

- Develop and implement policies and procedures to ensure the timely and accurate completion of all clinical trials in compliance with NIH and other Federal or Health Authority regulations, requirements and policies.

- Provide protocol managers to facilitate study implementation, monitor patient accrual and retention, assess compliance with protocol requirements and adherence to study timelines, and report progress to designated NIAID Project Manager.

- Design and implement policies and procedures to ensure the safe, ethical and timely conduct of clinical research.   Provide documentation of local  Institutional Review Board approval for all clinical research.

- Provide ongoing training to clinical site personnel regarding protocol requirements and compliance with Federal regulations.

- Plan and conduct Investigator Kick-off Meetings at the start of each new clinical trial. The purpose of these meetings is to provide uniform study specific information to investigators and study personnel prior to study start-up.

- Develop and implement procedures for specimen collection, processing and shipping for each clinical trial and mechanistic.  Train and qualify all appropriate laboratory and clinical personnel in these procedures for all approved protocols.

- Ensure that all clinical sites receive the required supply of study products for clinical trial initiation and conduct, and monitor supply throughout the duration of the clinical trial.  Report to the designated NIAID Project Manager any changes in requirements for study products.

- Establish and maintain regular communications about clinical trial progress, report problems and concerns to the designated NIAID Project Manager.

- Prepare and submit, for review and approval by the NIAID Project Officer, “Final Clinical Study Reports” for completed clinical trials within six (6) months of the database freeze.  Formats of these reports must be compliant with ICH Guidelines (see http://www.fda.gov ).

  - MECHANISTIC STUDIES AND LABORATORIES

    - Establish and direct a consortium of institutions and/or companies to:

- Design and conduct studies to identify and evaluate potential immune/surrogate markers of the induction, maintenance, and loss of tolerance in autoimmune disorders, asthma and allergic diseases, and transplantation.

- Develop and submit for Network Executive Committee approval budgetary requirements for specific tolerance assays and laboratories.

- Serve as a central resource for all immune/surrogate marker and mechanistic studies conducted by the Network, including the development of protocol-specific instructions for clinical trial sites for the collection, storage, inventory, packaging and shipping of patient specimens to laboratories and the distribution of sample collection kits.

- In addition to Network-sponsored clinical trials, at the direction of the NIAID Project Officer, develop mechanistic studies for clinical trials conducted by other Federal agencies, private organizations and companies.

- At the request of the NIAID Project Officer, the Contractor shall be responsible for packaging and shipping biological materials collected during the clinical trials and mechanistic studies to other laboratories, Clinical Trials Units, or repositories.  These will include blood and other body fluids and tissue samples.  Specimens shall either be classified as Infectious Substances (the material is known or reasonably expected to contain pathogens that can cause disease in humans or animals) or diagnostic specimens.  No materials on the Center for Disease Control and Prevention‘s (CDC) Select Agent List shall be collected or shipped (http://www2.niaid.nih.gov/Biodefense/bandc_priority.htm).  All material shall be classified, labeled, documented, packaged, shipped, and tracked according to Federal regulations and the International Air Transport Association (IATA) requirements (http://www.iata.org/ps/publications/9065.htm) for dangerous goods shipment.  Samples must be shipped under appropriate cold storage conditions and in a timely fashion as specified in the clinical protocols or other documents.

- Within three (3) months of contract award, develop and implement a process for the selection of laboratories and the development and validation of assays.  This shall include the following:

- Evaluate, prioritize and select assays and participating laboratories.

- Develop performance standards and metrics for assays and laboratories.

- Develop standard operating procedures for mechanistic assays including  quality assurance and quality control.

- Ensure that laboratories meet GLP or equivalent standards or performance and establish appropriate performance standards where none exist (e.g., for emerging technologies).  Within three months of contract award, develop for NIAID Project Officer review and approval, a plan to evaluate laboratories and to identify and remediate problems and deficiencies.

- Assess and implement new technologies and transitions from existing to new technologies.

- Disseminate current versions of assay protocols, standard operating procedures and performance standards to the research community via publications or posting on the Network website.

- Develop and implement standard operating procedures for the conduct of mechanistic studies and reporting of study results, including:

- Adherence to timelines for generating and reporting mechanistic data from each clinical trial as established by the Protocol Development Team.

- Timely reporting of mechanistic data required for interim and final analyses for each clinical trial.

  - BIOINFORMATICS, DATA COLLECTION AND VALIDATION

- Establish a data management system for the collection, storage, archiving, and exchange of clinical and mechanistic data from multiple sources and make these data accessible to Network staff and investigators, and NIAID staff.  Specifically, the Contractor shall:

- Design, implement and maintain a scaleable architecture for a widely distributed, networked system for biomedical and scientific data collection, storage, and exchange.  Data collected will be of many types, including but not limited to, genetic, cellular, molecular, and clinical data.

- Utilize the latest advances in software engineering and computer sciences and translate those advances into practical tools that are easily used by the target users, including Network staff and investigators, and NIAID staff, in this project.  The software development to be conducted under this task shall, whenever possible, integrate rather than displace existing applications.

- Using good software development practices, rapidly develop software for the capture, analysis, query, and storage of scientific data.

- Build a scalable network and computer infrastructure to meet end user needs.

- Create an integrated electronic data repository containing relevant scientific data for each research subject or patient sample, including but not limited to, clinical, diagnostic, and laboratory information.  All such data shall be maintained in integrated electronic databases in a format that permits rapid and efficient production of files for analysis.  Verify and validate all data in the data repository in collaboration with the originating laboratories and the clinical Data Management Contract Research Organization (CRO).

- Develop, implement, and/or disseminate software applications to make data accessible to the scientific community in accordance with the timelines detailed in the NIH Data Sharing Policy http://grants.nih.gov/grants/policy/data_sharing/index.htm ).

- Within six (6) months after contract award, develop standard operating procedures for the collection, storage, archival, and exchange of biomedical data to participating laboratories and the Data Management Contract Research Organization.

- Provide technical assistance in the collection, submission, exchange, and analysis of data to participating laboratories, clinical sites, and Data Management CRO.

- Design and implement a reliable system of quality control applied to all data and media.

- Within six months of contract award, develop and implement a long-range plan for the long-term maintenance and survival of the data and data system. Integrate system updates according to changing technological advances and user needs.

- Fully document systems and software developed.

- Ensure that software applications and standards facilitate the interoperability of the data systems and/or the portability of data.

- Establish a Sample Tracking and Inventory System for the Processing of Laboratory Samples

- Establish an end-to-end automated bar coded system for tracking laboratory samples from the time the sample is obtained from a patient to the time the results from the sample are stored in the final production database.

- Incorporate the ability to generate audit trails and reports from the system at any point in the process to determine the status of a specific sample or batch of samples and to identify problems in the processing pipeline.

- Ensure the quality and integrity of the data generated throughout this process.

  - Provide to participating Principal Investigators for Network clinical trials and mechanistic studies access to data and ongoing bioinformatics analytical support for the primary and secondary analyses of data.  This support shall include:

- Provide scientific leadership in the development and review of cutting edge design and analytic approaches that fully utilize the network of clinical sites, laboratories, and specimen repositories. Specifically, provide input into the development, review, and implementation of concepts and sub-studies by:

- Delineating research questions that can be addressed with study data in areas of high priority for the accomplishment of Network scientific objectives.

- Selecting appropriate study populations and control or comparison groups to address the research questions.

- Selecting and developing alternative study designs and data analysis plans, including approaches for limited sample size, and delineating the compromises that must be made in the face of immutable circumstances (e.g., small sample size due to rarity of disease or procedure).

- Assessing the feasibility of accessing appropriate data for retrospective analyses and for recruiting and retaining adequate numbers of study participants for proposed sub-studies.

- Ensuring that the type, number and volume of participant samples required are available and consulting clinical sites on the appropriate collection, testing, storage, and shipping of participant samples

- Conduct data analyses of mechanistic study data and combined clinical and mechanistic data and participate in the preparation of and manuscripts.  Data analyses for clinical trials alone will be handled by the Data Management Contract Research Organization (CRO).  The Network shall receive clinical data sets from the Data Management CRO for integration with the mechanistic data.  These combined data will be the source for integrated mechanistic and clinical analyses.  Formats and frequency for transfer of the clinical data to the Network will be determined at the time of contract award.

The NIAID has awarded separate contracts to assist the Network with protocol development, implementation, monitoring progress, and data analysis.  Refer to Appendix E for more information regarding support through such contracts in the following areas: (1) design of clinical protocols, including statistical parameters and patient data and patient samples to be collected; (2) preparation of Investigational New Drug Applications (INDs), adherence to regulatory requirements of the Health Authorities or equivalent including reporting of adverse events, clinical site monitoring, ensuring the confidentiality of patient data, documentation of Institutional Review Board approval of protocols, etc; (3) development of procedures for obtaining patient data from clinical sites, establishment and maintenance of a consolidated database for all clinical trials, and data management and quality assurance; (4) analysis of clinical study data; and (5) distribution of investigational agents to clinical sites.

- In addition, the Contractor shall:

  - Provide staff with expertise in the following areas:

- Theoretical statistics

- Epidemiology

- Data modeling, particularly longitudinal data

- Methodologies in controlling for effects of, yet optimizing, repeated measures

- Marginal structural modeling

- Causal inference, including appropriate use of propensity scores and instrumental variables

- Exploratory data analysis and robust methods in determining population and person-level effects

  - Develop a priori data analysis plans as well as plans for secondary analyses.

  - Develop innovative statistical methods to address scientific questions posed by the Network investigators.

  - Identify statistical parameters substantiating the choice of statistical tests employed in the techniques and methodologies used to conduct data analyses.

  - Maintain a tracking system to document the analytic progress and status of Network research proposals.

  - Maintain and distribute to all Network investigators and the NIAID Project Officer, a list of all publications, manuscripts in progress and presentations using data from Network studies.

  - Make drafts of manuscripts available for review (electronically or in hard copy) by the NIAID Project Officer, NIAID Medical Monitors and the NIAID Regulatory Affairs Officers at the time they are circulated to co-authors, and when the final manuscripts are submitted for publication.

- Develop and implement a system for monitoring security and system performance with the aim of maintaining data and system security and integrity, as well as high levels of service to Network staff and investigators and NIAID staff.  Specifically, the Contractor shall:

    - Develop a program for monitoring use of the system.

    - Develop and implement a plan to protect data derived from human subjects in compliance with current Federal regulations.

    - Test the system according to best and standard practices in computer and engineering services to ensure that it is performing according to service levels agreed to at the time of contract award.

    - Report to the NIAID Project Officer or designee and the Network Executive Committee any potential problems with the system; repair problems within seventy-two (72) hours of problem identification. Reports should be made to the NIAID Project Officer or designee and the Network Executive Committee in a timely way.

    - Inform and train designated Network system security staff in the security procedures of the system.

    - Develop, implement, and maintain security requirements, including:

      - An Automated Information System Security Profile, which at a minimum shall include: the System's Security Plan; the Risk Analysis Plan; and the Continuity of Operations Plan (also known as the Contingency Plan).

      - Continuity of Operations Plan testing shall be conducted and the results recorded at least every six months.  Maintain a log or record of the results from testing the Continuity of Operations Plan, any existing plans, and progress reports for implementing additional security safeguards and controls; and the system access authorization list.  The profile shall be kept up-to-date for review and potential inspection upon demand by the U.S. Department of Health and Human Services and/or the NIH.  Upon request, copies of specified profile documents shall be presented to NIH/DHHS for its own system's security reporting purposes.

      - The preparation and submission, for NIAID Project Officer approval, of a Risk Analysis Plan following the guidance given in the NIH Security Plan Template (http://irm.cit.nih.gov/security/secplantemp.doc).  The Risk Analysis Plan is to be maintained and updated every three years, or in advance of implementing major system modifications or enhancements.

      - The preparation and submission of an annual Systems Security Plan, following the instruction in OMB Bulletin 90-08, for review and approval by the NIAID Project Officer and the NIH System Security Officer (http://irm.cit.nih.gov/itmra/omb90-08.html).

      - The development and maintenance of an up-to-date Continuity of Operations Plan following the guidance in the NIH Security Plan Template (http://irm.cit.nih.gov/security/secplantemp.doc).  At a minimum, the Continuity of Operations Plan shall cover emergency operations, backup operations, and recovery plans to ensure continuous operations of the system's facility.

      - Plans, procedures, and a recommended schedule for implementation of security safeguards required to satisfy the anticipated conditions of acquiring data from clinical and basic research study sites.  This includes data integrity and security during electronic transmission or during transit from the sites to the data repository if non-electronic data transmission is used.  All patient identifiable data are subject to the Privacy Act and Health Insurance Portability and Accountability Act of 1996 (“HIPAA”) regulations. Plans, procedures, and schedules must be reviewed and approved by the NIAID Project Officer or designee.

      - Provision for the appropriate labeling, storage, handling, and disposal of sensitive or controlled data, media, and output.

- Collaborate and coordinate activities in conjunction with other NIAID and  bioinformatics groups:

- Deposit all clinical and mechanistic data to the NIAID-supported Bioinformatics Integration Support Contract (BISC) data repository (http://www.niaid.nih.gov/research/bisc.htm). Clinical data will be deposited once the clinical study has been closed and the initial findings have been published.  In accordance with the NIH Data Sharing Policy (http://grants.nih.gov/grants/policy/data_sharing/index.htm), both clinical and mechanistic data will be deposited to BISC no later than sixty (60) days after the initial publication of study results.

- All Network data will have all patient identifiers removed before deposition to BISC.  The BISC system is able to accept most standard file formats that are produced in scientific research.  The BISC is responsible for mapping data coming from the Network studies into the BISC data model. The format of the data files and of the data transfer methods from Network to BISC will be determined at the time of award.

- Work with BISC to develop standards and formats that will lead to ease of interoperability among bioinformatics tools, databases and software developed by the Network, BISC and other NIH-funded programs.

- COLLABORATION WITH NIH-FUNDED CLINICAL RESEARCH PROGRAMS AND OTHER ORGANIZATIONS

- The Contractor shall collaborate with and disseminate research information to other NIH-sponsored networks, private organizations, foundations, and companies involved in research on immune-mediated and infectious diseases.  Within six (6) months of contract award, the Contractor shall:

  - Develop policies and procedures governing collaborations with other clinical research programs and organizations.

  - Develop a written plan that delineates ongoing collaborations with other clinical research programs/organizations and plans for future collaborations with these and other entities.  The plan must specify the role of Network investigators and staff in ongoing and proposed collaborations, and the resources to be shared or provided between the collaborating organizations, including:

- The proposed resources, personnel, and services to be provided to, or shared with, the other research entities and what biological samples, personnel, services or remuneration, if any, the collaborating organizations will provide to the Network;

- The type of  mechanism to be used to formally engage in the collaboration, e.g., Memorandum of Understanding (MOU), subcontract, or Cooperative Research and Development Agreement (CRADA);

- If financial remuneration is planned, a complete description of the estimated charges to this contract and the costs to be charged to the collaborating research entity.

- Management of intellectual property developed through these collaborations;

- Methods to be used for dissemination of the research findings developed through the collaboration.

- Execute, and manage agreement mechanisms and subcontracts needed to implement such collaborations.  The NIAID Project Officer and NIAID Contracting Officer must approve the Network collaboration plan and financial arrangements prior to entering into an agreement or research collaboration.

  - PROJECT MANAGEMENT

    - Overall Project Management.  Provide a technical and administrative infrastructure to ensure the efficient planning, initiation, implementation and management of all projects carried out under this contract and effective communications with the NIAID Project Officer and the NIAID Contracting Officer. This infrastructure shall include a Principal Investigator (PI) with responsibility for overall project management and communications, tracking, monitoring and reporting on project status and progress, and recommending modifications to project requirements and timelines, including projects undertaken by subcontractors.  The PI shall devote not less than 35% effort to this contract.   This infrastructure shall also include Protocol Managers to oversee the implementation and conduct of clinical trials and serve as the primary contact to NIAID staff, as well as administrative staff with responsibility for financial management and financial reporting on all activities conducted by the Contractor and subcontractors.

    - Financial Management. Manage and track the ITN budget and provide updated budget reports, including actual and projected expenditures.  Reported categories shall include,:  total direct labor; accountable personal property; supplies; travel; lease and rental consultants; clinical trials; tolerance assays; subcontracts; service agreements for laboratories and laboratory facilities; vendor agreements; and prime contract and subcontract indirect rates and costs.

    - Subcontract Execution, Management and Reporting. The Contractor shall manage the subcontracting activity and shall ensure that the award and management of subcontracts is in accordance with FAR Clause 52.244-2. Specifically, the Contractor shall carry out the following:

- Execute and manage subcontracts, oversee the technical, administrative and operational activities of subcontractors on a daily basis, including auditing subcontractor facilities, services, financial expenditures, and track deliverables and reporting requirements;

- Assess and provide quarterly technical reports on subcontractor performance and progress toward achievement of defined milestones; and identify and resolve problems with subcontractor performance;

- Ensure that subcontractor personnel, equipment and facilities are compliant with regulatory requirements in effect throughout the contract period;

- Ensure the complete and effective transfer of technology by the subcontractors to the Contractor, the United States Government, or a third party as designated by the NIAID Project Officer; and

- Perform all necessary transition and closeout functions on each subcontract.

- For subcontracts exceeding $500,000, the Contractor shall establish technical review panels for the purpose of evaluating the technical portion of subcontract proposals.  The technical review panel shall provide its recommendations to the Contractor.  The Contractor shall base its selections for subcontractor awards on the panels’ recommendation and forward the subcontract and all required supporting documentation to the NIAID Project Officer and Contracting Officer for final approval.

- INITIAL AND FINAL TRANSITION

A.  Initial Transition. The Contractor shall develop and submit, within six (6) weeks of contract award, a draft Initial Transition Plan for receipt of work in progress by the ITN and describe how all activities, including clinical trials in development, implementation, follow-up, or analysis phases, will be continued and/or completed after contract award.  The Initial Transition Plan must:

- Describe how the Contractor proposes to communicate with and receive from the incumbent contractor information regarding work in progress;

- Propose detailed plans for the continuation and completion of all work in progress and for the movement of other contract-generated resources, including equipment, scientific and clinical data, patient samples, etc.

- Identify the staff assigned to the initial transition and describe their roles, responsibilities, and qualifications; and

- Include a plan to establish subcontracts, consulting agreements, purchase orders/agreements, confidentiality/intellectual property agreements, and leasing agreements in an expedited manner to enable the continuation and/or completion of clinical trials and other research activities without interruptions or delays.

After NIAID Project Officer approval of the draft Initial Transition Plan, the Contractor shall implement the plan to ensure completion of the transition within twelve (12) months of contract award.

B.  Final Transition

- The Contractor shall submit a Final Transition Plan to ensure the orderly transition of the contract data, equipment, animals and other materials to Government designated locations, grantees, or contractors.  The Plan shall be submitted six (6) months prior to contract completion and shall be subject to review and revision by the NIAID Project Officer.

- Develop and execute the Final Transition Plan during the phase-out and transfer of the contract to the Government or to a successor contractor:

    - The Final Transition Plan shall provide for the orderly transfer of all or part of this project to a designated Contractor or the Government at the end of the contract period.  The Final Transition Plan shall include an estimate of transition costs, timeframe to completion, and the staff required to execute a successful and timely transition.  In addition, the Final Transition Plan shall include:

- A description of how all databases, data/information, equipment and other materials identified by NIAID Project Officer will be transferred.

- A schedule for delivery of data, datasets, databases, and/or systems developed under this contract to the NIAID Project Officer.

- A list of open clinical trials and actions needed to ensure their continuation or completion during the transition period.

- A list of incomplete remedial site actions or pending safety issues and plans for their resolution.

- A list of facilities, leases, maintenance contracts, and equipment support provided and any scheduled support to be provided during the transition period.

- A list of subcontracts with a transition plan to either continue through transition to another subcontractor or terminate if the subcontract is at its completion date.  If the subcontract is transitioned to a new organization, all subcontracts must be terminated to coincide with the completion date of the current Network prime contract.  The new contractor must negotiate new subcontract agreements.

    - Should the responsibilities of the Network be transferred to a successor organization or to the Government, the Contractor shall provide the following deliverables not later than the completion date of the contract:

- A cleaned and edited data set, on media and in a format to be determined at the time of delivery by the NIAID Project Officer, and copies of all data management tools, including data documentation, data dictionaries, and data entry software and editing programs to allow reading and analysis of the data.

- All computer programs used for reading, cleaning, manipulating, graphing, and analyzing  data and programs used for generating new datasets.

- An audit trail of all raw data corrections, hard copies of the original data collected from study participants from all studies supported by this contract, and all logs and other records related to data collection, entry, editing, analysis, and transfer.

- Final summaries of analyses performed by the Contractor during the contract period.

- All electronic files in a well-documented format to a location specified by the NIAID Project Officer.

X.	EXPANDED SERVICES THROUGH EXERCISE OF OPTION(S)

- In addition to the tasks outlined in the above Statement of Work to be provided for the basic requirement, Option(s) for additional tasks under the contract may be exercised.  The Government anticipates a potential need for the following additional tasks during the course of the contract’s established seven year period of performance:

  - Nonclinical research and product development

  - Clinical trials

  - Mechanistic studies

  - Bioinformatics support

Such an increase in the Contractor’s activities may be activated, at the discretion of the Government, as an Option.  Under each Option for expansion of services in a task area, the Contractor shall provide the following:

- EXPANSION PLAN:

The Contractor shall develop a plan for the necessary services called for to exercise an option, including all tasks involved in implementing the expansion.  Because the additional tasks fall within items I-IX of the Statement of Work, the Government does not anticipate a substantial increase in Network staff or infrastructure required to implement the expansion.  Accordingly, with the exception of Option 4, above (Bioinformatics Support), the plan should NOT include modifications to the organizational structure, personnel, management procedures or infrastructure of the Network.

- PLAN IMPLEMENTATION:

Based on NIAID Project Officer recommendation to implement the expansion plan, the NIAID Contracting Officer will authorize the exercise of each Option through a Modification to the contract.  Each option may be exercised more than once.  More than one, but not more than ten (10) Options may be exercised in any year.

[END OF STATEMENT OF WORK]

Collaborative Network for Research on Immune Tolerance

RFP-NIH-NIAID-DAIT-07-33

APPENDIX A - ADDITIONAL TECHNICAL PROPOSAL INSTRUCTIONS

FORMAT FOR TECHNICAL PROPOSAL – TABLE OF CONTENTS

It is strongly recommended that offerors use the following template as the Table of Contents for the technical proposal. All information presented in the technical proposal should be presented in the order specified below. The following additional technical proposal instructions reflect the requirements of the RFP and are meant to provide additional instructions as well as a uniform format for technical proposals. The information requested in these instructions should be used as a guide for formatting and preparing the proposal. Offerors are advised to give careful consideration to the statement of work, all reference material, appendices and attachments, the technical evaluation criteria, and, the RFP as a whole, in the development of their proposal. Offerors who propose subcontracts to perform portions of the statement of work should clearly identify the specific tasks for which they plan to utilize subcontractors, as well as the method and level of integration between the prime and subcontractor(s), and the expected advantages of such an approach. Offerors are reminded that the total page limit for the entire technical proposal package is 300 pages, including appendixes providing standard operating procedures, operation manuals, policies and procedures, curriculum vitas, and selected references for publications.

APPENDIX A- ADDITIONAL TECHNICAL PROPOSAL INSTRUCTIONS

TECHNICAL PROPOSAL – TABLE OF CONTENTS

SECTION 1: TECHNICAL PLAN

PART A: STRATEGIC PLAN AND RESEARCH AGENDA

  - The Technical Proposal must include a proposed Strategic Plan and Research Agenda for the Network that address the following:

- Identify the immediate and long-range goals of the proposed Network, potential barriers to success, and solutions to overcome identified barriers.

- A discussion of the state-of-the-art of efforts to induce tolerance and define the underlying mechanisms in animal models and human studies; a description of safety concerns, knowledge gaps, and scientific opportunities relevant to the clinical application of tolerance induction strategies in autoimmune and allergic diseases and transplantation.

- A prioritized list or table of clinical trials and mechanistic studies proposed to be conducted by the Network.  Trials of minimal immunosuppression are acceptable if they involve immunosuppression withdrawal as an approach for achieving clinical tolerance.  Include the rationale for selection and ranking of specific approaches, taking the following into consideration: the strength of preliminary data; the importance of the hypotheses to be tested; the relevance of anticipated findings to more than a single disease or condition; proposed timelines and milestones for proposed clinical trials and mechanistic studies; the feasibility of designing, implementing and completing proposed clinical trials and mechanistic studies; access to adequate numbers of patients; safety and equipoise; availability of study products and other essential reagents; level of industry support; and budgetary and time constraints.  The Government recognizes that the ranking of opportunities and priorities will change with future developments.

- Plans for assessing adherence to the plan and success in meeting the major aims of the plan, and a discussion of how the Network will address new scientific or programmatic developments/objectives through periodic review and revision of the Plan.  Such reviews will be one component of the broader periodic assessment of Network progress in meeting the objectives and milestones outlined in Sections I to VIII of the Statement of Work.

The Government recognizes that proposed clinical trials, mechanistic studies, and assays can be based only on currently available knowledge.  Therefore, the award of this contract does not commit the Government to approve or implement any of the clinical trials and mechanistic/assay studies proposed in the Strategic Plan and Research Agenda.

PART B:	ORGANIZATIONAL STRUCTURE AND OVERALL MANAGEMENT AND COORDINATION

- The Technical Proposal must include a plan for the organizational structure and membership of the Network, including policies and procedures to meet the scientific, technical and functional/operational requirements outlined in item II. of the Detailed Statement of Work.  A broad range of scientific, clinical and program management expertise will be necessary to carry out the requirements of this solicitation.  The Government recognizes that no single institution or organization will have the expertise and facilities necessary to perform all the requirements of the and, therefore, it will be necessary for the Prime Contractor to subcontract portions of the work to be performed. It is also likely that the Network’s leadership will require multiple scientific and clinical investigators in various disease areas.  The Government also recognizes that the specific processes to be used by the Network to manage and coordinate studies, establish priorities, and redirect scientific and fiscal resources will be developed fully after contract award.  All proposed plans, procedures and policies should address the point outlined immediately below in the Technical Proposal and will be subject to review, approval and modification, if necessary by the Government post award.

  - Describe the proposed Network structure and membership and the specific responsibilities, tasks, decision-making processes, and reporting lines of authority for all proposed key organizational entities and key scientific and technical personnel for both the Contractor and any subcontractors.  This includes the Network Executive Committee, the Network Protocol Review Committee, and any other committees or subcommittees proposed, as well as the organizational structure and responsibilities, policies and procedures for the overall management and coordination of clinical trials, tolerance assay studies and Laboratories, bioinformatics and data collection, validation and analysis, review and oversight of ethical aspects of clinical trials and tolerance assay studies, and conflict of interest.  The use of tables, schematics, and flow charts to clarify roles and responsibilities is highly recommended.

  - Propose a plan for the evaluation of the performance of the Network.  The plan must include criteria, measures and methods to objectively evaluate the effectiveness, productivity, and overall performance of the Network and Network subcontractors.

PART C: NONCLINICAL RESEARCH AND PRODUCT DEVELOPMENT

- The government anticipates that to address this requirement, the Network will independently, or through subcontractors, access a range of product development expertise and services (e.g., cGMP manufacture; nonclinical safety and efficacy assessments; pharmacokinetics, absorption, distribution, metabolism and excretion assessments; cGLP nonclinical toxicology studies).  The required product development activities will be identified and delineated in a Nonclinical Product Development Plan tailored to each proposed drug candidate to be evaluated in Network clinical trials.

- Although the study products to be assessed and the type and extent of nonclinical studies or product manufacturing that will be required cannot be defined at this time, the Offerors must provide in the Technical Proposal a detailed discussion of:

  - Methods, techniques and approaches to be utilized to assess the availability and quality of study products;

  - The range of manufacturing activities and nonclinical studies to be performed by the Network or its subcontractors; and

  - The range of product release and stability testing criteria to be used by the Network or its subcontractors.

- The Technical Proposal must document the Network’s capabilities to address the activities outlined in the Nonclinical Product Development Plan, including:

        - Directly, or through subcontractors, manufacturing and/or testing of study products;

        - Overseeing and auditing nonclinical testing and/or cGMP manufacturing facilities to ensure timely, on-budget task completion and compliance with cGLP and/or cGMP requirements; and

        - Meeting regulatory requirements of the relevant Health Authorities;

- Describe the process of identifying, qualifying, auditing, and subcontracting with the necessary nonclinical testing or manufacturing facilities.

PART D: CLINICAL TRIALS

- Protocol review and selection

- Describe proposed policies and procedures for the evaluation, prioritization and approval of concept proposals for further development by the Network.  Such policies and procedures must ensure that Network clinical trials address the priorities outlined in the Network Strategic Plan and Research Agenda and apply to proposals developed internally by the Network investigators and to proposals submitted by non-Network investigators.

- Describe policies and procedures for review and development of full protocols.

- Protocol implementation

  - Describe proposed policies and procedures for the selection of clinical trial sites, including dedicated Network Clinical Trial Units (CTUs) and non-Network CTUs.  Describe proposed policies and procedures for the conduct and monitoring of clinical trials (e.g., adherence to established timelines for study initiation, patient recruitment and enrollment, and study completion, adherence to GCP standards and practices and to protocol-specific requirements, management and quality control of study data, collection and laboratory analysis of patient specimens, etc.).

  - Identify and describe the capabilities of the proposed dedicated Network CTUs (i.e., membership, organization, and lines of authority); delineate the proposed criteria to be used to select dedicated Network CTUs and to propose recommendations for future modification of the CTU membership as may be required to meet performance standards and timelines.

  - Describe criteria, policies, and procedures for determining the need for and recommending to NIAID the expansion, curtailment, or discontinuance of clinical trials, including the participation of individual CTUs, taking into account adherence to milestones, availability of funds, availability of study product, and changing priorities and scientific opportunities.

- Roles and Responsibilities of NIAID Staff and NIAID-Funded Clinical Research Support Services Contractors

The primary role of NIAID staff will be to facilitate, but not to direct, protocol selection, development and implementation activities.  NIAID staff and ongoing NIAID clinical research support contracts will provide a broad range for services to the Contractor for the design, development, implementation and analysis of Network studies.  Specifically,

  - Regulatory Affairs:  NIAID will provide regulatory guidance throughout protocol development and study conduct.  In most instances, and at its discretion, NIAID will serve as the sponsor of Investigational New Drug Applications (INDs) or equivalent clinical trial applications outside the U.S. or delegate this role to industry partners.  As IND sponsor, NIAID will be responsible for tracking and reporting of Adverse Events to appropriate Health Authorities.  NIAID will also monitor the collection of essential documents from individual CTUs.

- cGCP Training: Provide cGCP training directly or through NIAID Contract Research Organizations (CROs) (see Appendix F).

- Biostatistical Support:  NIAID will provide biostatistical support for protocol development and analysis of clinical endpoints through CROs (see Appendix F) or through staff of the NIAID Biostatistics Branch.  Independent of the government, the Network will be responsible for the statistical analyses outlined in Section VI of the Statement of Work: “Bioinformatics, Data Collection, and Validation.”

- Case Report Forms:  NIAID will support development of Case Report Forms CRFs) for the collection of clinical data either directly or through NIAID CROs.

- Medical Monitoring: NIAID staff will serve as medical monitors for all Network clinical trials and as liaisons to the relevant NIAID Data and Safety Monitoring Boards (DSMBs).  DSMB reviews will be held at regular intervals as described in each protocol and/or at the discretion of the primary Medical Officer from NIAID.  The DSMBs are advisory to NIAID and are managed by NIAID.

- Project Management Support:  NIAID will provide the following project management support services:

- Site Management:  Assess individual site competence and direct site training and auditing.

- Timelines and Milestones:  Review study progress timelines to ensure adherence to established timelines.

- Clinical Trial Oversight:  Directly oversee Network activities, or do so through NIAID CROs (see Appendix F), to ensure site compliance with cGCP and safe clinical trial management.

- Study Product Distribution:  Manage all activities related to study product distribution, tracking and retrieval and ensure that such activities are in compliance with cGCP and consistent with relevant Clinical Trial Agreements, where applicable.

PART E: LABORATORIES FOR THE DEVELOPMENT AND VALIDATION OF ASSAYS AND THE CONDUCT OF MECHANISTIC STUDIES

- The Technical Proposal must include a plan for establishment and management of a consortium of institutions and/or companies capable of providing the scientific and technical expertise to design and execute mechanistic studies and to develop and validate new/improved assays to assess the induction, maintenance, or loss of immune tolerance.  This plan must include the following:

- Describe the proposed membership of the consortium, criteria for selection of member laboratories, and the capabilities of each proposed laboratory to include experience in performing laboratory assessments in support of clinical studies and performance in quality management programs.  All work conducted in such laboratories shall use or be directly relevant to the determination of tolerance in human cells and tissues.  Assay development in animal models for ultimate application in humans, other than as described in the Statement of Work, Section 3, Nonclinical Research and Product Development, will not be supported under this contract.

  - Describe laboratory services and assays previously or currently provided by each proposed laboratory.

  - Provide a proposed plan for the management and oversight of the laboratories and for the coordination of studies under taken by these laboratories.  The use of schematics and flow charts to delineate responsibilities, communications, and lines of reporting authority is highly recommended.

  - Describe existing systems or capabilities to design and develop systems for shipping, distribution, storage, and processing of patient samples.   Note that Network capabilities related to sample tracking systems should be addressed separately in the response to Statement of Work, Section 6: “Bioinformatics, Data Collection, and Validation.”

  - Provide examples of standard operating procedures for quality assurance and quality control and document the capabilities of the proposed laboratories to meet cGLP or equivalent performance standards.

  - As required above (Part A, Section 1), the Technical Proposal must include a Strategic Plan and Research Agenda that describes the mechanistic studies to accompany Network clinical trials.  Document the Offeror’s capacity to address the relevant elements of the research agenda and to redirect resources to pursue new opportunities as they arise.

PART F: BIOINFORMATICS, DATA COLLECTION, AND VALIDATION

- Provide a detailed plan for developing and disseminating applications that enable scientists working independently in different studies to generate, normalize, archive, and exchange data of all types easily and without risk of data corruption.

- Provide a detailed plan for establishing a sample tracking and inventory system.  Describe how bar codes will be used throughout the sample processing.

- Provide a detailed plan for ongoing analytical support.

- Briefly describe how the Network will interact with the Bioinformatics Integration Support Contract (BISC) and other support contractors in this area.

- In order to avoid redundancy and maximize efficiency, it is anticipated that the ontology, data models, software and many of the analyses tools developed by the BISC project will have general applicability to Network activities and will be utilized by the Network when appropriate.

PART G:	COLLABORATION WITH OTHER CLINICAL RESEARCH PROGRAMS AND ORGANIZATIONS

To date, the Network has collaborated with the National Institute of Diabetes and Digestive Diseases and Kidney Disorders (NIDDK)-led Type 1 Diabetes TrialNet; the range of collaborative activities includes co-development and implementation of clinical trial protocols, separate conduct of mechanistic studies on behalf of the Type 1 Diabetes TrialNet, and utilization of a common DSMB.  Offerors should include plans for continuation of these activities and future collaborations involving other NIAID-sponsored networks, potentially including: the Autoimmunity Centers of Excellence (ACEs), the Clinical Trials in Organ Transplantation (CTOT), and the Environmental Determinants of Diabetes in the Young (TEDDY).  Brief descriptions of these research programs are provided in Appendix F “NIH- Sponsored Clinical Research Programs.”

The Technical Proposal should briefly describe any proposed collaborations beyond those mentioned immediately above.  In preparing the Technical Proposal, Offerors should assume that collaborations with pharmaceutical and biotechnology industry partners will be governed by Clinical Trial Agreements or Cooperative Research and Development Agreements to be negotiated between the industry partner and the NIAID.  Where appropriate, the Network will be included as a third party to such agreements.

PART H: TRANSITION PLANS

- Initial Transition

Describe the proposed plan for the initial transition of ongoing clinical and mechanistic studies from the incumbent contractor, including the orderly receipt of work in progress from the incumbent contractor.  At a minimum, the initial transition plan must include the proposed timeframe to complete all transition activities and a description of the staff required to execute an orderly and efficient transition.  The transition plan also shall include the items described below and any additional information the Contractor deems necessary for an orderly transition.

- Describe how the Offeror proposes to communicate with and receive from the incumbent contractor information regarding work in progress;

- Propose detailed plans for the continuation and completion of all work in progress and for the movement of other contract-generated resources, including equipment, scientific and clinical data, patient samples, etc.

- Identify the staff assigned to the initial transition and describe their roles, responsibilities, and qualifications; and

- Include a plan to establish subcontracts, consulting agreements, purchase orders/agreements, confidentiality/intellectual property agreements, and leasing agreements in an expedited manner to enable the continuation and/or completion of clinical trials and other research activities without interruptions or delays.

- Final Transition

Describe how activities being carried out under this contract will be transitioned to the Government or to a successor contractor.  Include timelines for the initiation and completion of all transition activities outlined in the Statement of Work and a description of the staffing requirements to execute an orderly and efficient transition.

In the event the contract awarded under this solicitation is recompeted, describe how ongoing activities will be transitioned to a new contractor, including movement of all Government-furnished property to the site of the new contractor by the completion date of this contract.  It is estimated this shall take no longer than 6 calendar months.

PART I: EXPANSION OPTIONS

The Government anticipates a need for additional nonclinical research and product development, clinical trials, mechanistic studies, and bioinformatics support as outlined in this Statement of Work.  Such an increase in the Contractor’s activities may be required, at the discretion of the NIAID, through exercise of an Option for additional tasks under the terms of this contract.  Up to ten (10) options may be exercised in any contract year.

The Offeror shall provide a description of plans to implement the options based on the assumptions below.  The description shall describe the Network capabilities required to implement and direct the expansion and timelines for all tasks required to carry out such an expansion.

- Production of two (2) additional lots of cGMP manufactured study product.  The amount of finished product must be sufficient to complete the nonclinical and clinical studies outlined in (2) and (3) below.

- Two (2) 28-day toxicity studies conducted in two (2) species per study.

- One (1) additional four-year, Phase II clinical trial of eighty (80) subjects.

- Two (2) additional one-year, new mechanistic studies.

- One (1) additional Senior Bioinformatician at 25% effort and one (1) additional Software Engineer at 25% effort.

SECTION 2: PROJECT MANAGEMENT

- Describe how the project will be staffed, organized and managed. Describe in detail the responsibilities and level of effort for all proposed personnel who will be assigned to the contract, and an administrative framework indicating clear lines of authority and responsibility for the personnel. In addition, provide a description of proposed project management controls to keep multiple tasks on time and on budget. Outline how the Principal Investigator will communicate and interact with the NIAID Contracting Officer and the NIAID Project Officer and how the Principal Investigator will communicate, monitor, and manage the project both internally and externally (at subcontractor sites and facilities).

- Subcontract Acquisition and Management:

  - Provide a proposed plan for subcontract acquisition and management, including soliciting, evaluating, negotiating, awarding, and post-award administration in accordance with the requirements established by Federal contracting regulations.

  - Describe proposed plans and methods to assess subcontractor performance, identify performance problems and approaches for their remediation, including noncompliance with subcontract terms and conditions, and implement corrective actions when necessary.

SECTION 3: SCIENTIFIC, TECHNICAL AND ADMINISTRATIVE PERSONNEL

The Technical Proposal should include all information relevant to document organizational and individual experience and management capabilities necessary for the successful completion of all contract requirements.  Proposals should include a Staffing Plan for the conduct of the Statement of Work, including role descriptions and level of effort of key scientific, technical and administrative personnel.  Summarize the experience, expertise, and other relevant qualifications of each CTU Principal Investigator and key staff.

- Principal Investigator (PI):  Describe the PI’s experience, training, expertise, and qualifications, as well as proposed percentage of effort. Describe the PI’s experience in leading and directing projects of similar complexity to this contract either directly or indirectly through subcontracts.  This includes: scientific and technical expertise in scientific disciplines relevant to tolerance induction; the evaluation of tolerance induction therapies in humans for transplantation, autoimmune disorders, and asthma and allergic diseases; the development and conduct of immune/surrogate markers and studies of underlying mechanisms; the solicitation and evaluation of the technical merit of subcontract proposals; and the capacity to monitor progress, assess performance, identify performance problems and implement corrective actions.  Limit the PI’s CV to 2-3 pages and provide selected references for publications relevant to the scope of requirements for the contract.

2.	Other Key Scientific and Technical Personnel: Describe the experience, training, expertise and qualifications, as well as the percentage of effort for all proposed key scientific and technical personnel, including subcontractors.  Include experience in designing and conducting projects of similar complexity.  Limit CVs to 2-3 pages and provide selected references for publications relevant to the scope of requirements for the contract.  Also provide information on ongoing support for training and professional development of key scientific and technical staff to maintain appropriate qualifications.

3.	Other Personnel: Describe the responsibilities and document the relevant experience, training and expertise of other personnel proposed to carry out contract requirements, including all proposed subcontractors.  In particular, Offerors should document their abilities to address the extensive and complex range of subcontracting activities required throughout the duration of the contract, including:

  - The ability to solicit, negotiate, and execute a large number of subcontracts supporting a range of clinical, nonclinical, and mechanistic activities.

  - The ability to oversee and manage the administrative and operational activities of subcontractors on a daily basis, including financial monitoring, tracking of deliverables and reporting requirements, subcontractor performance, and achievement of milestones.

  - Experience with identification and remediation of subcontractor performance deficiencies or noncompliance with subcontract terms and conditions.

  - Ability and availability of key staff to communicate closely with NIAID Project Officer and the NIAID Contracting Officer.

- Confidentiality of Data and Intellectual Property

Describe how the Contractor will safeguard confidentiality and intellectual property rights of the data and materials provided by third parties or the U.S. Government, as well as data generated during the contract.

SECTION 4: FACILITIES AND OTHER RESOURCES

The Technical Proposal should document the availability and adequacy of facilities, equipment, space and other resources necessary to carry out the contract requirements, including:

- Location and features of facilities (lease or ownership information should be provided);

- Identification and description of ALL support resources (including IT systems) which will be required to effectively carry out contract requirements.

SECTION 5: TABLE OF CONTENTS FOR DOCUMENTATION REQUIRED UNDER SECTION L OF THE SOLICITATION

      - Human Subjects

Section L of the RFP specifies the minimum documentation requirements for Human Subjects use.  All related documentation should be included in the proposal in a clearly marked section.  The Technical proposal should document all information necessary to evaluate Human Subject use.  The following information is essential:

- Human Subjects: Include plans for compliance with applicable domestic and international regulations on the use of human subjects (e.g., IRB submission and approval plans, consent procedures, etc.).

- Health Insurance Portability & Accountability Act (HIPAA).  Include plans for compliance with HIPAA.

- Privacy Act

Section L of the RFP specifies the minimum documentation requirements for Privacy Act compliance. All related documentation should be included in the proposal in a clearly marked section.

- Animal Welfare

Section L of the RFP specifies the minimum documentation requirements for Animal Welfare compliance. All related documentation should be included in the proposal in a clearly marked section.  The Technical proposal should document all information necessary to evaluate Animal welfare issues.

- Data Sharing Plan

Section L of the RFP specifies the minimum documentation requirements for Data Sharing.  All related documentation should be included in the proposal in a clearly marked section.  The Technical Proposal should include a plan for Data Sharing as required by the RFP.

- Plan for Sharing Model Organisms

Section L of the RFP specifies the minimum documentation requirements for Model Organism sharing. All related documentation should be included in the proposal in a clearly marked section. The Technical Proposal should include a plan for sharing Model Organisms as required by the RFP.

- Biohazard Safety

The Technical Proposal should include a plan for biohazard security requirements.

- IT Systems Security.

The Technical Proposal should include a plan for IT Systems security.

- Fetal Tissue or DNA Molecule Research

Section L of the RFP specifies the minimum documentation requirements for Fetal Tissue or DNA Molecule research. All related documentation should be included in the proposal in a clearly marked section.

- Project Objectives NIH 1688-1

The offeror shall insert a completed NIH Form 1688-1, Project Objective, as provided in Section J, Attachments, behind the Title Page of each copy of the proposal, along with the “Government Notice for Handling Proposals.”  The NIH Form 1688-1 is to be completed as follows:

For an Institution of Higher Education: The form MUST be completed in its entirety.

For OTHER than an Institution of Higher Education: The starred items (Department, Service, Laboratory or Equivalent, and Major Subdivision) should be left blank.

Collaborative Network for Clinical Research on Immune Tolerance

RFP-NIH-NIAID-DAIT-07-33

APPENDIX B - ADDITIONAL BUSINESS PROPOSAL INSTRUCTIONS

(UNIFORM COST ASSUMPTIONS)

In addition to the format requirements for the business proposal that are contained in Section L of the solicitation, the information provided in this appendix is intended to provide uniform cost assumptions and business clarifications. Offerors are advised to give careful consideration to the statement of work, all reference material provided as appendices and attachments, and the technical evaluation criteria, and, the RFP as a whole, in the development of their proposal. The information requested in these instructions should be used as a guide for the development and formatting of the business proposal. Offerors should consider and include the information requested in this appendix.

APPENDIX B – ADDITIONAL BUSINESS PROPOSAL INSTRUCTIONS

BUSINESS PROPOSAL – TABLE OF CONTENTS

SECTION 1 – PROPOSAL COVERSHEET

SECTION 2 – COST OR PRICE SUPPORT

Section L of the RFP specifies the minimum documentation requirements for cost data and all cost related support. All related documentation should be included in the proposal in a clearly marked section.

SECTION 3 – UNIFORM COST ASSUMPTIONS

- Meetings and Travel

  - Offerors should assume three (3) 2 -day Steering Committee meetings per year, one located on the east coast, one located on the west coast and one in the Midwest for no more than forty-five (45) participants.

  - Offerors should assume three (3) 2-day Network Executive Committee meetings per year, one located on the east coast, one located on the west coast and one located in the Midwest for no more than six (6) participants.

  - Offerors should assume four (4) 2-day clinical trial Investigator Kick-off Meetings per year, two located on the east coast, one located on the west coast and one located in the Midwest for no more than twenty (20) participants.

  - Offerors should assume seven (7) 1-day face-to-face protocol development meetings per year, two on the east coast, two on the west coast and three in the Midwest for no more than twenty (20) participants.

  - Offerors should assume an additional two (2) 2-day meetings per year, conducted on an as needed basis, one on the east coast and one on the west coast for no more than four (4) participants.

  - Offerors should assume thirty (30) 2-day trips for non-local professional development per year.

- Clinical Trials

- Offerors should assume that six (6) clinical trials in autoimmunity, eight (8) clinical trials in transplantation, and three (3) clinical trials in asthma/allergy will be in progress at the time of award and will be transitioned to the successful Offeror.

- Offerors should assume that approximately six (6) new clinical trials at five (5) clinical trial sites will be approved for implementation in each year of the contract.   Assume that three (3) clinical trials will be two-year, Phase II studies with an average of 20 study participants each.  Additionally, assume that three (3) clinical trials will be multi-center, Phase II/III studies with an average of 150 study participants each.

- Offerors should assume that agents, molecules and reagents for the clinical trials conducted by the Network will be provided at no cost to the Contractor through Clinical Trial Agreements or Cooperative Research and Development Agreements (CRADAs) established between NIAID and partners in the pharmaceutical or biotechnology industries.  For certain high priority trials, where no commercial partnership can be formed, the Network may elect to purchase study products.  However, Business Proposals should NOT include any costs associated with the purchase of such investigational agents.

- Offerors should NOT include any costs associated with the purchase of investigational agents.  Note, however, that costs for the manufacture or preclinical evaluation of study products under the Statement of Work, Section III, should be included in the Business Proposal (see specific uniform assumptions in item 3. below).

- Nonclinical Research and Product Development

  - Offerors should assume two (2) single dose toxicity studies (2 species/study- Rodent and Non-rodent species) per year.

  - Offerors should assume two (2) 28-day toxicity studies (2 species/study- Rodent and Non-rodent species) per year.

  - Offerors should assume two (2) pharmacokinetic studies (2 species/study- Rodent and Non-rodent species) per year.

  - Offerors should assume two (2) safety pharmacology studies per year.

  - Offerors should assume they will be responsible for two (2) batches of cGMP manufacture of drug product for Nonclinical and Clinical Studies per year.

- Mechanistic Studies

  - Offerors should assume that there will be six (6) new mechanistic studies sponsored by the Network each year, and four (4) additional mechanistic studies incorporated into non-Network clinical trials.

  - Offerors should assume that there will be two (2) non-Network-sponsored mechanistic studies each year, and that these will be cost-neutral.

- Information Technology Hardware and Software

  - Offerors should assume upgrade of a percentage of existing hardware and software in years three (3) and five (5) of the contract.

SECTION 4 – OPTIONAL ACTIVITIES (If and to the extent exercised)

Offerors submitting a proposal under this solicitation must prepare a Technical Proposal and Business Proposal for the entire Statement of Work including options.   Proposals for the basic effort alone, or the options alone will not be accepted for review or considered for award.

Options will be included in the contract as the government anticipates a need for additional nonclinical research and product development, clinical trials, mechanistic studies, and bioinformatics support.  Exercise of the options shall be solely at the discretion of the Government and will be based on technical merit, need, and the availability of funds during the seven-year period of performance.

The Offeror shall price each option separately based on the following assumptions:

- Production of two (2) additional lots of cGMP manufactured study product.  The amount of finished product must be sufficient to complete the nonclinical and clinical studies outlined in (2) and (3) below.

- Two (2) 28-day toxicity studies conducted in two (2) species per study.

- One (1) additional four-year, Phase II clinical trial of eighty (80) subjects.

- Two (2) additional one-year, new mechanistic studies.

- One (1) additional Senior Bioinformatician at 25% effort and one (1) additional Software Engineer at 25% effort.

SECTION 5 - BUDGET INSTRUCTIONS TO OFFEROR

- Offerors shall provide a one-page budget summary for all years of the contract for:

  - Network scientific, technical and administrative infrastructure alone including all committees, meetings, teleconferences, dedicated CTUs, laboratories, etc. (no costs for studies)

  - Clinical trials in transplantation

  - Clinical trials in asthma and allergic diseases

  - Clinical trials in autoimmune diseases

  - Mechanistic studies and biomarker/surrogate marker development, including laboratories

  - Nonclinical research and product development

  - Bioinformatics and data validation/analysis

- Offerors shall provide individual budget breakdowns for each of the items listed above.

- Offerors shall provide a separate one-page summary for each of the five options.

SECTION 6 - SECURE ONE HHS PERSONNEL REQUIREMENTS

### Background Investigations: All contractor personnel designated with position-sensitivity levels that are commensurate with the responsibilities and risks associated with the position require suitability background investigations to be completed and favorably adjudicated for personnel assigned to these positions prior to allowing access to sensitive Departmental systems and networks.

### Disciplinary Action: Disciplinary or adverse actions against contractors who violate the HHS Information Security Program Policy, HHS Information Security Program Rules of Behavior, and system-specific rules of behavior will be enforced throughout the life of the contract.

### Personnel Separation: Upon contract or contractor employee termination, or other departure, all access and privileges to Departmental systems, networks, and facilities will be immediately revoked.

SECTION 7 – SUBCONTRACTING

1.  Offerors should demonstrate a thorough understanding of the subcontracting process, procedures, rules and regulations as set forth in the Federal Acquisition Regulations, FAR Part 44 and FAR Clause 52.244-2, “subcontracts”;  The Contractor’s Request to Subcontract Checklist is provided as Attachment 37 as a guide.

SECTION 8 - TABLE OF CONTENTS FOR DOCUMENTATION REQUIRED UNDER SECTION L OF THE SOLICITATION

- Small Business Subcontracting Plan

Section L of the RFP specifies the minimum documentation requirements for completing a subcontracting plan.  This plan should be turned in with the original proposal. All related documentation should be included in the proposal in a clearly marked section.

- Extent of Small Disadvantaged Business Participation

Section L of the RFP specifies the minimum documentation requirements for small disadvantaged business utilization.  This information should be turned in with the original proposal. All related documentation should be included in the proposal in a clearly marked section.

- Past Performance Data, including references

Section L of the RFP specifies the minimum documentation requirements for providing past performance information.  This information should be turned in with the original proposal. All related documentation should be included in the proposal in a clearly marked section.

GOVERNMENT PROPERTY - SCHEDULE

| Description | Manufacturer | Item number | Serial Number | Total Cost |
| --- | --- | --- | --- | --- |
| Computer | Dell | L-C610, P3 | TW-06E929- | $ 2,382 |
| Computer | Dell | L-C610, P3 | TW-06E929- | $ 2,493 |
| Laserjet Printer | HP | 4100N | SUSJNF20444 | $ 1,594 |
| Computer | Dell | GX400 | 2J98711 | $ 2,441 |
| Computer | Dell | GX400 | BCDG911 | $ 1,529 |
| Laptop | Sony | R505, P3 | S0131023061 | $ 2,290 |
| Laserjet Printer | HP | 4100TN | USJNF35831 | $ 2,142 |
| Computer | Dell | PC-800 | C8ZNV11 | $ 1,723 |
| Computer | Dell | PC-800 | 2J98711 | $ 1,793 |
| Affymetrix | LIMS | 900253 | 900253 | $ 131,752 |
| Server | Compaq | 142673-B22 | D244JQ31D006 | $ 8,224 |
| Server | Compaq | 33SCSI | 8F2ADDC8Y0HS | $ 1,362 |
| Server | Compaq | Compaq | E84-00125-ZZ | $ 3,078 |
| Server | Compaq | Compaq | M02-000222-ZZ | $ 1,200 |
| Server | Compaq |  | 257913-B21 | $ 3,647 |
| Server | Compaq | DL380 | D246KJN2D006 | $ 17,780 |
| Server | Compaq | COM 36GB | 8H2AFFV6HoTN | $ 3,696 |
| Server | Compaq | HPL HD |  | $ 3,562 |
| Server | Compaq | R3000 | TU433A0023 | $ 1,224 |
| Server | Compaq | COM 36GB | 8H2AFFV6H0K3 | $ 1,584 |
| Desktop computer | Dell | OptiPlex | F5PLG21 | $ 2,194 |
| Desktop computer | Dell | OptiPlex | JCDNL21 | $ 1,856 |
| Desktop computer | Dell | OptiPlex | 2MSZL21 | $ 1,626 |
| Desktop computer | Dell | OptiPlex | FHN8B21 | $ 1,613 |
| Laptop computer | Dell | C640 | BL68K21 | $ 2,536 |
| Laptop computer | Dell | C640 | 32FF521 | $ 2,883 |
| Laptop computer | Dell | C640 | B7YB821 | $ 2,153 |
| Laptop computer | Dell | C640 | JHT6221 | $ 1,731 |
| Desktop | Dell | C640 | GKJGC21 | $ 1,915 |
| Laptop computer | Dell | C640 | F6YTJ21 | $ 2,480 |
| Laptop computer | Dell | C640 | J5YTJ21 | $ 2,659 |
| Laptop Computer | Dell | C640 | 43N1B21 | $ 2,369 |
| Laptop Computer | Dell | C640 | 65X0B21 | $ 2,593 |
| Laptop computer | Dell | C640 | 1M68K21 | $ 2,563 |
| Laptop computer | Dell | C640 | 18BG221 | $ 2,452 |
| Desktop | Dell | 8200 | 5JD811 | $ 1,793 |
| Laptop computer | Dell | C640 | 84M5M21 | $ 2,620 |
| Desktop | Dell | OptiPlex | 64J9R21 | $ 1,546 |
| Desktop | Dell | OptiPlex | J4J9R21 | $ 1,590 |
| Desktop | Dell | OptiPlex | D5J9R21 | $ 1,546 |
| Laptop computer | Dell | C640 | 5SF0V21 | $ 2,600 |
| Laptop computer | Dell | C640 | 5R26Y11 | $ 2,624 |
| Laptop computer | Dell | C640 | FQ26Y11 | $ 2,624 |
| Laptop computer | Dell | PP03L | 2D166A01 | $ 2,421 |
| Laptop computer | Dell | C640 | 5H4H521 | $ 2,883 |
| Laptop computer | Dell | C640 | 63N1B21 | $ 2,306 |
| Laptop Computer | Dell | Latitude D600 | 6FN6M831 | $ 2,684 |
| Description | Manufacturer | Item number | Serial Number | Total Cost |
| DNA Engine | MJ Research | EN 021789 | AL062882 | $ 9,825 |
| Desktop Computer | Dell | Precision | CK45831 | $ 2,540 |
| Laptop Computer | Dell | Latitude | JTFX331 | $ 2,575 |
| Minolta Copier | Minolta | D1351 | 4026311-31009000 | $ 14,054 |
| Desktop Computer | Dell | OptiPlex | 2LQ8831 | $ 1,621 |
| Laptop Computer | Dell | Latitude | 39BCH31 | $ 2,677 |
| Laptop Computer | Dell | Latitude 600 | 2HQHG31 | $ 2,639 |
| Bioanalyzer System | Dell | HP 2100 | DE24802455 | $ 20,253 |
| Dell Powevault | Dell | 221S Tower | 9PJV231 | $ 12,034 |
| Affymetrix | GC 3000 | GC 3000 | FS0779 | $ 154,613 |
| Fisher Scientific | Centrifuge | H2380914 | N/A | $ 5,588 |
| Laptop Computer | Dell | Latitude X300 | 4P77241 | $ 2,718 |
| Desktop Computer | Dell | Precision 360 | FV79441 | $ 2,787 |
| Laptop Computer | Dell | Latitude D600 | 1JFH941 | $ 2,592 |
| Laptop Computer | Dell | Latitude D600 | 4FW7941 | $ 2,694 |
| Laptop Computer | Dell | Latitude D600 | 783Z541 | $ 2,257 |
| Minolta Copier | Minolta | DI 351 | 31729347 | $ 9,025 |
| Minolta Copier | Minolta | DI 351 | 22003226 | $ 10,279 |
| Minolta Copier | Minolta | D1351 | 4026311-31009000 | $ 14,054 |
| Minolta Copier | Minolta | PS3 | 4397311-3001603 | $ 18,110 |
| Laser Jet Printer | Hewlett Packard | 4650 | JPDAC03123 | $ 2,271 |
| Laser Jet Printer | Hewlett Packard | 4650 | JPDAC03124 | $ 2,271 |
| Dell Precision Workstation | Dell | 650 Tower | JMH7Y41 | $ 8,637 |
| Inspirion laptop | Dell | X300 | JSW0X41 | $ 3,895 |
| Dell Laptop | Dell | D600 | 7VB5351 | $ 2,251 |
| Dell Laptop | Dell | D600 | 2QB5351 | $ 2,251 |
| Dell laptop | Dell | D600 | 2TFIJ31 | $ 2,797 |
| Dell laptop | Dell | D600 | HSB5351 | $ 2,251 |
| Dell Laptop | Dell | D600 | 6WB5351 | $ 2,251 |
| Dell laptop | Dell | D600 | 9HKBP41 | $ 3,379 |
| Dell laptop | Dell | D600 | H2Y1G41 | $ 2,780 |
| LCD Projector | Dell | 3200MP | 25B2X21 | $ 1,797 |
| Power Edge | Dell | Dell 6600 | COMY441 | $ 21,086 |
| Dell laptop | Dell | D600 | D6JQB51 | $ 2,692 |
| Dell laptop | Dell | D600 | 8X8FC51 | $ 2,732 |
| Dell laptop | Dell | D600 | G8DGC51 | $ 2,732 |
| Latitude | Dell | D800 | BF7PX41 | $ 3,816 |
| Laptop Computer | Dell | Latitude D600 | B7XGP51 | $ 2,713 |
| Laptop Computer | Dell | Latitude D600 | 11PTF51 | $ 3,155 |
| Laptop Computer | Dell | Latitude D600 | 5WVXM51 | $ 2,763 |
| Laptop Computer | Dell | Latitude X300 | HXVXM51 | $ 2,713 |
| Laptop Computer | Dell | Latitude X300 | 6HLGZ51 | $ 2,555 |
| Laptop Computer | Dell | Latitude X300 | DPNWT51 | $ 2,788 |
| OptiPlex SX270 | Dell | SX270 | 2CP9G41 | $ 1,720 |
| Video Conferencing | Dell | C640 | 510029 | $ 9,487 |
| Laptop Computer | Dell | Latitude D600 | C37Q461 | $ 2,929 |
| Laptop Computer | Dell | Latitude D610 | D508J61 | $ 2,710 |
| Laptop Computer | Dell | Latitude D610 | 9WCVP61 | $ 2,655 |
| Laptop Computer | Dell | Latitude D610 | DHJQV61 | $ 2,941 |
| Description | Manufacturer | Item number | Serial Number | Total Cost |
| Video Conferencing | VSGI |  | 19737 | $ 49,645 |
| Laptop Computer | Dell | Latitude D610 | HQ6JL71 | $ 1,657 |
| Gene Spring Software |  |  |  | $ 84,808 |
| Laptop Computer | Dell | Latitude D610 | J1ZFL71 | $ 1,657 |
| Laptop Computer | Dell | Latitude D610 | FM6JL71 | $ 1,657 |
| Laptop Computer | Dell | Latitude D610 | DFZ2P71 | $ 1,793 |
| Beckman Coulter | BCI |  |  | $ 112,954 |
| Server | Hewlett Packard | HP Proliant | H15896200 | $ 22,337 |
| HP Rack | Hewlett Packard | ML 570G3 | USE533C31L | $ 11,966 |

Collaborative Network for Clinical Research on Immune Tolerance

RFP-NIH-NIAID-DAIT-07-33

APPENDIX C:  Ongoing Immune Tolerance Network Clinical Trials and Tolerance Assay Studies

| Immune Tolerance Network |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AREA of STUDY | Protocol # | Protocol Name | Target Enrollment/ # of sites | Protocol Status (PSD=Projected Start Date) | Study Completion | PROTOCOL CHAIR(S) | Clinical Trials # |
| ITN CLINICAL |  |  |  |  |  |  |  |
| Autoimmune: Allergy | ITN031AD | AIC in Ragweed Induced Asthma | 60/ 3 | Protocol Development PSD: 2005 | ~ 2010 | David Broide |  |
| Autoimmune: Allergy | ITN032AD | A Trial of Oral Tolerance Induction for Prevention of Peanut Allergy | 440/ 2 | Protocol Development PSD: 2006 | ~ 2011 | Gideon Lack, MD |  |
| Autoimmune: Asthma | ITN025AD | Prophylaxis of Atopy and Asthma in Children | 200/ 5 | Protocol Development PSD: 2006 | ~ 2010 | Patrick Holt, DSC |  |
| Autoimmune: Diabetes | ITN027AI | New Phase II Multiple Dose Treatment of Type 1 Diabetes Mellitus with hOKT3γ1 (Ala-Ala) | 81/ 6 | Active Start Date: 2005 | ~ 2009 | Kevan Herold, MD | NCT00129259 |
| Autoimmune: Diabetes | ITN018AI | A Pilot Study to Evaluate the Safety of Interleukin-2 (IL-2) and Sirolimus (Rapamycin) Combination Therapy In Recent-Onset Type 1 Diabetes Mellitus | 10/ 1 | Protocol Development PSD: 2006 | ~ 2009 | Alex Rabinovitch, MD |  |
| Autoimmune: Diabetes | ITN028AI | Thymoglobulin for new onset T1DM | 78/ 6 | Protocol Development PSD: 2005 | ~ 2009 | Stephen Gitelman |  |
| Autoimmune: Rheumatology | ITN002AI | Treatment of Systemic Lupus Erythematosus with CTLA-41g Plus Cyclophosphamide: A Phase II Study | 24/ 4 | Active Start Date: 2004 | ~ 2006; followed by a Phase II trial | Betty Diamond, MD; David Wofsy, MD | NCT00094380 |
| Autoimmune: Rheumatology | ITN021AI | Rituximab Therapy for the Induction of Remission and Tolerance in ANCA-Associated Vasculitis | 200/ 9 | Active Start Date: 2004 | ~ 2009 | John Stone, MD; Ulrich Specks, MD | NCT00104299 |
| Autoimmune: Multiple Sclerosis | ITN020AI | A Randomized, Double-Blind, Placebo-Controlled, Multi-Center Study to Evaluate the Efficacy and Safety of Atorvastatin in Patients with Clinically Isolated Syndrome and High Risk of Conversion to Multiple Sclerosis | 152/ 14 | Active Start Date: 2005 | ~ 2010 | Scott Zamvil, MD | NCT00094172 |
| Transplant: Islet | ITN015CT | Evaluation of the Tolerogenic Efficacy of hOKT3γ1 (Ala-Ala) and Sirolimus Immunotherapy in Type I Diabetic Islet Allograft Recipients | 12/ 1 | On Hold | TBD | Bernhard Hering, MD |  |
| Transplant: Kidney | ITN013ST | The Use of Campath-1H, Tacrolimus, and Sirolimus Followed by Sirolimus Withdrawal in Renal Transplant Patients | 10/ 1 | Active Start Date: 2004 | ~ 2008 | Stuart Knechtle, MD | NCT00078559 |
| Transplant: Kidney | ITN023ST | LEA29Y in an Immunosuppression Withdrawal Regimen in Recipients of Non-HLA Identical Living Donor Renal Transplants | 30/ 2 | Protocol Development PSD: 2005 | ~ 2009 | Flavio Vincenti, MD |  |
| Transplant: Kidney/BMT | ITN008ST | Combined HLA-Matched Bone Marrow and Kidney Transplantation for Multiple Myeloma with Renal Failure | 10/ 1 | Active Start Date: 2001 | ~ 2009 | Megan Sykes, MD; A. Benedict Cosimi, MD | NCT00062621 |
| Transplant: Kidney/BMT | ITN010ST | Renal Allograft Tolerance Through Mixed Chimerism | 10/ 1 | Active Start Date: 2002 | ~ 2010 | David Sachs, MD; A. Benedict Cosimi, MD | NCT00063817 |
| Transplant: Kidney/Stem Cell | ITN022ST | Pilot Study Using Donor Stem Cells And Campath-1H To Induce Renal Transplant Tolerance | 10/ 1 | Active Start Date: 2003 | ~ 2009 | Joshua Miller, MD |  |
| Transplant: Liver | ITN024ST | Immunosuppression Withdrawal in Liver Transplant Recipients | 211/ 14 | Active Start Date: 2004 | ~ 2012 | Richard Thistlethwaite, MD | NCT00105235 |
| Transplant: Liver | ITN030ST | IS Withdrawal in Liver Tx Recipients with HCV Infection. | 157/ 2 | Active Start Date: 2005 | ~ 2011 | Avi Shaked |  |
| Transplant: Liver | ITN029ST | IS Withdrawal in Stable Pediatric LD Liver Tx Recipients | 20/ 2 | Protocol Development PSD: 2005 | ~ 2012 | Sandy Feng |  |

Collaborative Network for Clinical Research on Immune Tolerance

RFP-NIH-NIAID-DAIT-07-33

APPENDIX D - Immune Tolerance Network Core Facilities/Laboratories

DNA-based Assays:

HLA-Typing Core
	Director: Lee Ann Baxter-Lowe, University of California San Francisco

RNA-based Assays (Gene expression profiling):

High Throughput Real Time PCR Core
	Director:  Mimi Roque-Biewer, Applied Biosystems

RNA Preparation Core
Directors:  P. Suzanne Hart & Paul Wood, University of Pittsburgh;

McKesson Bioservices, Rockville, MD

Protein & Cellular Assays:

Enzyme-linked Immunospot (ELISPOT) Assay Core
	Directors: TBD

MHC-Peptide Tetramer Facility

Directors:  Gerald Nepom, Virginia Mason Research Center, Seattle, WA;

Jeffrey A. Bluestone, University of California San Francisco, San Francisco, CA

Type 1 Diabetes Autoantibody Facility
Director:  George Eisenbarth, University of Colorado Health Science Center, Denver, CO

Flow Cytometry Core, United States

Director:  Paul Wallace, Roswell Park Cancer Institute

Flow Cytometry Core, Europe

Director:  Peter Trinder, Thymed GmbH, Mainz, Germany

Alloantibody & Flow Cross-match Core

Director:  Robert Bray, Emory University, Atlanta, GA

IDO Core

Director: David Munn, Medical College of GA, GA

AlloELISPOT Core

Director:  Peter Heeger, Cleveland Clinic Foundation, Cleveland, OH

Luminex Core

Director:  Ger T. Rijkers, Wilhelmina Children’s Hospital, Utrecht, Netherlands

Trans-vivo Delayed Type Hypersensitivity Core

Director:  Will Burlingham, University of Wisconsin, Madison, WI

ELISA Core

Director: Robert Hamilton, Johns Hopkins Allergy and Asthma Center, Baltimore, MD

Tissue & Histochemical Assays:

Liver Tissue Analysis Core
	Director:  Anthony Demetris, University of Pittsburgh

Renal Pathology Core
	Director:  Robert Colvin, Harvard University

Additional Cores:

CMV/EBV Viral Load Core 
Contractors:  ViraCore, Lee's Summit, MO

Specimen Support:

Clinical Specimen Repository 
Contractors:  McKesson Biosciences, Rockville MD

Data Support:

Bioinformatics/Data Analysis Core
Director:  Dave Parrish, Immune Tolerance Network

Collaborative Network for Clinical Research on Immune Tolerance

RFP- NIH-NIAID-DAIT-07-33

APPENDIX E:  NIAID-Funded Clinical Research Support Services Contracts

NIAID/DAIT holds contracts with companies that currently provide and will continue to provide regulatory, clinical site monitoring, data management and analysis, and drug distribution support to the Network.  The contractors with whom the successful Offeror is expected to interact in order to perform functions specified within the Statement of Work are described below.  Notifications will be sent to the successful Offeror of this competition when awards are made for new or recompeted contracts that provide support for these Network functions.

NIAID/DAIT Regulatory Management Center

Social & Scientific Systems, located in Silver Spring, MD, provides regulatory support services.  They will continue to provide support for regulatory and clinical compliance functions and requirements associated with Health Authority Applications such as Investigational New Drug (IND) Applications and Amendments as described below [http://www.niaid.nih.gov/contract/archive/rfp0444.pdf]:

  - Technical assistance for regulatory and current Good Clinical Practice (cGCP) compliance;

  - Electronic tracking of IND safety reports;

  - Electronic clinical site registration system;

  - General administrative support for regulatory affairs and cGCP compliance;

  - Logistical support for all DAIT-sponsored clinical trials; and

  - Services to facilitate an orderly transition.

NIAID/DAIT Clinical Site Monitoring Group

PPD Development, LP located in Wilmington, NC, provides evaluations of good clinical research practices, regulatory compliance, accurate protocol implementation, international quality assurances, and test agent accountability during periodic on-site visits to all DAIT-funded clinical trial sites.  PPD Development specific responsibilities include, but are not limited to, the following [http://www.niaid.nih.gov/contract/archive/rfp0446.pdf]:

- Examine source documents to assess accuracy and completeness of trial data;

- Identify problems with protocol implementation, adherence to GCP and all applicable regulatory requirements;

- Verify proper storage, dispensing and accountability of investigational study products;

- Provide training on general protocol conduct, cGCP, quality management, and DAIT procedures;

- Review internal quality assurance/quality control plans;

- Report progress during the contract and file ending reports that are comprehensive and specific to the description and time tables set forth in the contract; and

- Facilitate an orderly transition.

NIAID/DAIT Drug Distribution Center

EMINENT Services Corporation, located in Frederick, MD, establishes and maintains the Clinical Products Distribution Center for the purpose of purchasing, dispensing and providing quality control of study products for Network clinical trials.  Specific responsibilities of the Contractor include, but are not limited to, the following:[ http://www.emiserv.com].

- Purchasing, receiving, storing, labeling, packaging, shipping and distribution of study products;

- Inventory control and quality assurance of study supplies for each protocol;

- Pharmaceutical services to including to written reviews, reports, transfers, packaging, storage, dosage, labeling, usage and returns of products in conjunction with the NIAID Project Officer’s approval while establishing a secure clinical web site for clinical site pharmacists that supplies protocol-specific information and requirements;

- Security/safety measures and procedures;

- Processing and disposal of returned and unused drug product;

- Record maintenance; and

- Services to facilitate an orderly transfer of all or part of this project to a subsequent contractor or the Federal Government.

NIAID/DAIT Coordinating Center for Biostatistics, Data Management and Pharmaco Vigilance

PPD Development, LP, located in Wilmington, NC, provides a resource to the Network to assure efficient clinical study design, conduct, safety monitoring and data analysis.  Responsibilities of the Contractor include, but are not limited to, the following [http://www.niaid.nih.gov/contract/archive/rfp0459.pdf]:

- Providing statistical leadership and clinical trial design expertise for the development of protocols and analysis of study data;

- Establishing and administering data collection, management, quality assurance and reporting systems;

- Establishing and managing a safety reporting center;

- Detailed record maintenance and timely reporting;

- Collaboration with DAIT and research groups; and

- Completion of the final deliverables.

NIAID/DAIT Bioinformatics Integration Support Contract (BISC)

Northrop Grumman Information Technology, located in Rockville, MD, provides information technology support in the production, analysis, archiving, exchange and integration of genomic, proteomic and related data to NIAID/DAIT-funded research programs via the Immunology and Data Analysis Portal (ImmPort at http://www.immport.org/index.html).  Specific responsibilities of the Contractor include, but are not limited, to the following:

- Accelerate a more collaborative and coordinated research environment

- Create an integrated database that broadens the usefulness of scientific data and advances hypothesis-driven and hypothesis-generating research

- Integrate relevant data sets from participating laboratories, public and government databases, and private data sources

- Provide analysis tools to advance immunological research

Collaborative Network for Clinical Research on Immune Tolerance

RFP-NIH-NIAID-DAIT-06-25

Appendix F - Descriptions of NIH-Funded Clinical Research Programs

The Autoimmune Centers of Excellence (ACEs)

Nine Autoimmunity Centers of Excellence (ACEs) conduct collaborative basic and clinical research on autoimmune diseases, including single-site and multi-site pilot clinical trials of immunomodulatory therapies and mechanism-of-action studies.  The ACEs support close interaction between clinicians and basic researchers, which should facilitate the identification of effective tolerance induction and immune modulation strategies to treat or prevent disease, and accelerate the translation of scientific advances to the clinic.  Examples of ACEs-supported clinical trials include:  anti-CD20 for systemic lupus erythematosus; sirolimus for multiple sclerosis; and a double-masked study of the combination of copaxone and albuterol versus copaxone alone for multiple sclerosis.  The ACEs are co-sponsored by the NIDDK and the NIH Office of Research on Women’s Health.

The Clinical Trials in Organ Transplantation (CTOT)

In FY 2004, NIAID, in collaboration with NIDDK and NHLBI, established a clinical consortium to improve the success of organ transplants.  The goals of the consortium are to identify genetic factors in patients that could help doctors predict transplant outcomes as well as responses to post-transplant therapy; develop diagnostic tests that enable early detection and ongoing monitoring of immune-related processes; and test the safety and effectiveness of new, less toxic immunosuppressive drugs.  The consortium is comprised of three institutions:  Brigham and Women's Hospital, Boston; Cleveland Clinic Lerner College of Medicine of Case Western Reserve University; and the University of Pennsylvania, Philadelphia.

Diabetes TrialNet

TrialNet is an international network of investigators, clinical centers, and core support facilities.  It supports the development and implementation of clinical trials of agents to slow the progression of type 1 diabetes in new onset patients and to prevent the disease in at-risk patients.  The network also supports “natural history studies” that will provide information on risk factors associated with development of type 1 diabetes and that will inform the design of future trials.  TrialNet is supported by the NIDDK, NIAID, NICHD, and JDRF.

The Environmental Determinants of Diabetes in the Young (TEDDY)

TEDDY is an international consortium to recruit genetically-susceptible newborns for studies that test the role of infectious agents, dietary factors, and other environmental conditions that may trigger type 1 diabetes.  Funded by the NIDDK, NIAID, National Institute of Child Health and Human Development (NICHD), National Institute of Environmental Health Sciences (NIEHS), CDC, and Juvenile Diabetes Research Foundation International (JDRF), this long-term project will follow participating individuals through adolescence to ascertain the onset of autoimmunity and/or type 1 diabetes.

Appendix G:  Informational Internet sites for the Immune Tolerance Network and RFP:

Introduction and Background

Immune Tolerance Network website:  http://www.immunetolerance.org

NIAID Plan for Research on Immune Tolerance and the Report of the NIAID Expert Panel on Immune Tolerance: http://www.niaid.nih.gov/research/publications.htm

Recommendations of the NIAID Expert Panel on Ethical Issues in Clinical Trials of Transplant Tolerance:  http://www.niaid.nih.gov/publications/immune/page2.htm

Information about Section 508 [of the Americans With Disabilities Act] can be found at http://www.section508.gov

NIH Data Sharing Policy http://grants2.nih.gov/grants/policy/data_sharing/index.htm).

NIH Security Plan Template http://irm.cit.nih.gov/security/secplantemp.doc

OMB Bulletin 90-08 http://irm.cit.nih.gov/itmra/omb90-08.html

NIH Security Plan Template http://irm.cit.nih.gov/security/secplantemp.doc

Bioinformatics Integration Support Contract (BISC).  Additional information about BISC can be found at http://www.niaid.nih.gov/research/bisc.htm

Contractor’s Request to Subcontract Checklist

Prime Contract Number:______________________

Prime Contractor Name and Point of Contact/Address:

__________________________________________________________________________

__________________________________________________________________________

__________________________________________________________________________

Prime Contract Type:   Cost Reimbursement     Fixed Price    Other ________________

Proposed Subcontractor Name and Address:

__________________________________________________________________________

__________________________________________________________________________

__________________________________________________________________________

Proposed Subcontract Type:  Cost Reimbursement     Fixed Price    Other _____________

Proposed Subcontract cost ceiling or price: $_____________________

Checklist of Documentation

Contractor:  Review the following list and attach the documents needed for your specific circumstances.  Guidance on required documentation can be found in the Federal Acquisition Regulations, Part 44.  This list is not meant to be all inclusive. This document is a tool designed to assist contractors in developing and submitting complete packages for expedited consent to subcontract.   Please refer to the terms and conditions of your contract, NIAID’s Standard Operating Procedure entitled, “Providing Consent to Subcontract SOP,” and FAR Part 44 for all subcontracting requirements.

The following documents are being submitted for subcontract consent:

Signed request for consent to subcontract from an individual authorized to bind the organization.   Submitted with Package

Description of Work to be subcontracted along with a technical justification documenting the scientific necessity in relation to the project.   Submitted with Package

Draft subcontract agreements.  Submitted with Package

A written description of attempts to secure competition, or, the circumstances which prohibit competition.   Submitted with Package

Documentation of a sound basis for selecting the proposed subcontractor.   Submitted with Package

Documentation of the rationale used to determine the responsibility of the proposed subcontractor.  Submitted with Package

Confirmation that the proposed subcontractor has current electronic Representations and Certifications.  Submitted with Package

Confirmation that the proposed subcontractor is not listed on the Excluded Parties List System (FAR Subpart 9.4).  Submitted with Package

Estimates of the cost impact on the prime  budgets.  Submitted with Package

Cost estimates or pricing information for the subcontract.   Submitted with Package

Description of the cost or price analysis or price comparisons made for the subcontract, or a copy of the analysis.

Submitted with Package

Accurate, complete, and current cost or pricing data, including any required certifications.  Submitted with Package

Supporting cost documentation, if required, and the negotiated indirect rate agreement for proposed subcontractors.  Submitted with Package    Not Required

Confirmation that the prime contractor has complied with applicable requirements regarding small business subcontracting.   Submitted with Package    Not Required

Small business subcontracting plans from proposed subcontractors, for subcontracts with an estimated cost of $500,000 or more.  Submitted with Package    Not Required

Three quotations for requested equipment purchases, or, the absence of competition has been documented.  Submitted with Package    Not Required

Human subjects or animal assurance documentation.  Submitted with Package    Not Required

Confirmation of CDC certification or application date for select agent use.  Submitted with Package    Not Required

See NIH Guide http://grants.nih.gov/grants/funding/women_min/guidelines_amended_10_2001.htm, for the Definition of an “NIH-Defined Phase III clinical trial.