## Construction
| PROJECT TITLE | PreAward Notice to FedBizOps | Request for Proposals | Proposal Due Date | Contract Awarded | Amount Obligated | Amount Expensed | Percent Construction Complete
ARTS AND INDUSTRIES BUILDING (AIB) INFRASTRUCTURE
1 | AIB Exterior Masonry Repairs | 2009-04-27
2 | AIB Phase I Demolition and Hazardous Material Removal | 2009-04-15
NATIONAL ZOOLOGICAL PARK
3 | Install Fire Protection for Visitor Center and for Propagation buildings and Boiler Plant | 2009-03-27 | 2009-04-17 | 2009-05-18
4 | Replace Medium Voltage Switches and Transformers | 2009-03-27 | 2009-04-17 | 2009-05-18
5 | Repair Bridges (Road/walkway improvements) | 2009-04-01
5.1 | Repair Bridges (Road/walkway improvements) Contract Management Services | 2009-04-02
6 | Replace Roof and Renovate Exterior at Research Hill Buildings and Lion and Tiger Complex | 2009-03-19 | 2009-04-07 | 2009-05-07
7 | Install Utility Loop (water / fire protection) and Replace Roof and Renovate Slate Hill Barn | 2009-03-23 | 2009-04-22 | 2009-05-26
8 | Replace Waller Barn roof and Renovate Greenhill Barn | 2009-03-25 | 2009-04-13 | 2009-05-13
SMITHSONIAN-WIDE PROJECTS
9 | High Voltage Network Protectors Replacement Note: Award to previously competed contract | 2009-03-16 | See note | See note | 2009-04-10 | 2522937
10 | Install Backflow Preventers and Upgrade Domestic and Fire Pumps | 2009-03-18 | 2009-04-14 | 2009-05-14
11 | Install Emergency Generator Power System Upgrade, Phase 2 Note: Awarded option to previously competed contract | 2009-03-20 | See note | See note | 2009-04-07 | 711562
12 | Install Emergency/Standby Power System Upgrades, Phase 2 and Phase 3 (Construction Administration Services) Note: Mod to existing competed contract | 2009-03-20 | 2009-04-09 | See note | 2009-04-10 | 41448
13 | Install Emergency/Standby Power System Upgrades, Phase 3, plus addendum | 2009-03-20 | 2009-04-01 | 2009-05-01
14 | Repair Elevators/Escalators | 2009-03-20 | 2009-04-28 | 2009-05-21
15 | Project Management Support for Recovery Act Note: Award to previously competed contract | 2009-03-24 | See note | See note | 2009-04-16 | 255271
16 | Personnel Support for Recovery Act | 2009-03-24