Department of Commerce

U.S. Census Bureau

2010 Census Advertising

American Recovery and Reinvestment Act Program Plan

Department of Commerce

U.S. Census Bureau

2010 Census Advertising ARRA Program Plan

Table of Contents

Funding Table

Objectives

Activities

Characteristics

Delivery Schedule

Environmental Review Compliance

Savings or costs

Measures

Monitoring/Evaluation

Transparency

Accountability

Barriers to Effective Implementation

Federal Infrastructure Investments

Funding

The American Recovery and Reinvestment Act provided $1 billion to help the Census Bureau conduct a successful Census in 2010.  This plan focuses on $100 million being added to the advertising contract (a component of the 2010 Census Integrated Communications Campaign), which is used primarily to raise awareness and to educate residents about the 2010 Census and the importance of their response.

Objectives

Funds for the 2010 Census Integrated Communications Campaign will primarily be used to increase our direct paid media purchases to increase the effectiveness of our efforts to reach the hardest to count populations, particularly through the local, specific media outlets they use the most.  The remaining funds will be used to expand other aspects of the campaign that focus on the hard-to-count populations, such as the Census in Schools program.

The funds will also be used for the road tour, which was popular and successful in Census 2000.  The road tour provides support to partners and a forum for generating earned media with a particular focus on hard-to-count populations.    We will also use funds to increase our national and local events to help raise visibility and awareness about the 2010 census.

Activities

The Bureau will use numerous paid media sources such as TV, radio, online,  magazines, and outdoor and commuter media to reach individuals from all clusters and ethnic audiences.

Characteristics

A major focus of the increased advertising and other promotional activities will be in minority communities and other areas that have historically lower-than-average initial response rates. Most of this funding ($258.7 million) will be used to support additional paid media, including local ad buys focused on hard-to-count populations. The remaining funds ($53.4 million) will be directed to partnership support, public relations, and the “Census in Schools” program.

Delivery Schedule

September 2008	Campaign Plan Finalized and Released

May 2009		Enter “upfront” media market (national media)

May 2009		Produce advertisements

June 2009		Census in Schools Print Materials Available (Print/Online)

October 2009		Launch Online Newsroom

December 2009	Final Schedule for Media Purchases

Environmental Review Compliance

N/A

Savings or costs

N/A

Measures

All performance measures will be reported to the Department of Commerce on a quarterly basis and annual results will be published in the Annual Performance and Accountability Report

Measure: Complete key activities for the combined 2010 Census Communications Campaign

2009 Targets Using Base Funding:

- Enter the "Upfront" market by May 2009.

- Begin delivery of promotional items and materials to Partnership Specialists and Assistants at the Regional Offices.

- Mail Principal kits to all schools (K-12) including Puerto Rico and Island Areas (public, charter, and Bureau of Indian Affairs).

2010 Targets Using Base Funding:

- For the Awareness Phase, reach 95% of the population at least 10 times through the paid advertising

- For the Motivation Phase, reach 95% of the population at least 20 times through the paid advertising

- For the Support NRFU Phase, reach lowest responding population at least 3 times through paid advertising

2010 Targets Using Recovery and Reinvestment Act Funding:

- For the Awareness Phase, reach 95% of the population at least 5 more times above base target through the paid advertising

- For the Motivation Phase, reach 95% of the population at least 11 more times above base target through the paid advertising

- For the Support NRFU Phase, reach lowest responding population at least 2 times through paid advertising

Monitoring/Evaluation

The Census Bureau Chief Financial Officer’s organization establishes and operates a comprehensive financial management and internal controls program for the agency.  The robust accounting structure contains detailed coding that allows obligations and expenditures for all activities and operations to be individually tracked and monitored.

The Census Investment Review Board (CIRB) serves as the senior governance body for major investments. The board consists of senior program executives and is chaired by the Deputy Director. The Senior Advisor for Project Management facilitates the review of new initiatives and ongoing programs to identify and manage risks, and to monitor progress in achieving the desired program goals and objectives.  The Census Bureau’s major investments must also be presented to the Department of Commerce Investment Review Board, which conducts periodic reviews of the major programs and projects across all agencies and bureaus within the Department.

The Decennial program offices manage the 2010 Census program requirements, schedule and budget. Program management is centralized within the Decennial Management Division (DMD).  The 2010 Census program is divided into projects, and a program manager is assigned to each of these projects. The program managers oversee the budgets their assigned projects and work closely with the Census offices that participate in the projects to ensure that funds are being used to meet the project’s requirements, and to address any cost or schedule issues.

Monthly briefings are held with senior officials of the Department of Commerce and Office of Management and Budget (OMB) on the status of the 2010 Decennial Census program.  The Monthly Status Report (MSR), which is used as the basis of these briefings, includes information on status and progress of major decennial activities, including all major contracts being managed (including earned value metrics, schedule accomplishments, risks, and issues) as well as obligation and expenditure information.

Decennial management has established comprehensive project and contract management structures for the major Decennial contracts supporting the collection, tabulation, and dissemination of the 2010 Census data. Each contract has a senior Project Manager that leads a Project Management Office (PMO). They work closely with the budget and acquisition staffs in both the Census Bureau and the Department of Commerce to monitor the major contracts. The PMOs monitor the cost, schedule, and technical performance milestones for each system and ensure that financial and contractual controls are in place.. The PMOs conduct regular technical and cost reviews with each contractor that include discussions of actual and projected cost and schedule variances. These reviews enable the Census Bureau to anticipate and address any potential contract cost issues when they first occur. There is also a Program Integration Staff to ensure that all the contractor activities work with each other and with the efforts of government staff.

Transparency

The Census Bureau has established a new Treasury account to track the $1 billion received from the ARRA.  We have also established a financial structure, including unique coding that will allow us to separately track obligations and expenditures for each activity funded through ARRA and to aid in the transparency of these expenditures.  All financial transactions associated with this funding will be captured and retained in the Census Bureau’s Core Financial System.

The Census Bureau’s ARRA spend plan is being made available to the public on the recovery.gov website.  In addition, weekly reports will be completed and posted on the recovery.gov website.

Accountability

The Census Bureau has reporting requirements established by the Department of Commerce in response to guidelines established by OMB to monitor ARRA funding.  The Census Bureau’s Comptroller, according to those established guidelines, will monitor all ARRA funds.

The Acquisitions Program Management staff will also closely monitor work and progress on a daily basis.  In addition, a task manager is assigned to each task under the contract. Budget and program staff conduct detailed monthly reviews of obligations compared to the operating plans, and Census Bureau Executive Staff members, including the Director and Deputy Director are briefed regularly. Budget spending reports are also sent monthly to the Department of Commerce.

Monthly briefings are held with senior officials of the Department of Commerce and Office of Management and Budget (OMB) on the status of the 2010 Decennial Census program.

Barriers to Effective Implementation

The Census Bureau could face challenges with securing optimal slots in the up front media markets, although ARRA funding and base funding are intended to mitigate this challenge.

Federal Infrastructure Investments

N/A