## IGCE
IGCE Report (Example)
Program Name: Functional Area Data Base
Action Officer (Program/Task Manager)/Phone: Col Smith/ 681-1111
Brief Description: Relational Data Base to Support TRICARE ABC Program
Budget Reference: 99AA
Direct Labor
Labor Category | # Labor Hours | Basis of Estimate | Low Rate $ | Low Amt | High Rate $ | High Amt
Task 1: Progect Management
Program Manager (Contractor Site) | 92 | 6 hrs per mo plus 20 hrs start up/close out as per notes on Assumptions TAB. | 101 | 9292 | 107 | 9844
Financial Analyst (Govt site) | 1920 | 1 FTE for 12 months, as per notes on Assumptions TAB. | 65 | 124800 | 69 | 132480
Sr. Computer Programmer (Contractor site) |  |  | 70 | 0 | 71 | 0
Computer Programmer (Contractor site) |  |  | 58 | 0 | 60 | 0
Data Base Manager (Govt site) |  |  | 54 | 0 | 57 | 0
Systems Design Engineer (Mid level, Contractor site) |  |  | 121 | 0 | 140 | 0
Admin/Clerical (Mid level, Govt site) | 160 | 1 FTE for 12 months, as per notes on Assumptions TAB. | 49 | 7840 | 53 | 8480
Computer Systems Analyst (Contractor site) |  |  | 57 | 0 | 61 | 0
Network Analyst (Contractor site) |  |  | 62 | 0 | 67 | 0
Systems Security Analyst (Contractor site) |  |  | 67 | 0 | 71 | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  | TOTALS |  | 141932 |  | 150804
Labor Category | # Labor Hours | Basis of Estimate | Low Rate $ | Low Amt | High Rate $ | High Amt
Task 2: Design Data Base
Program Manager (Contractor Site) |  |  | 101 | 0 | 107 | 0
Financial Analyst (Govt site) |  |  | 65 | 0 | 69 | 0
Sr. Computer Programmer (Contractor site) | 960 | .5 FTE for 12 months, as per notes on Assumptions TAB. | 70 | 67200 | 71 | 68160
Computer Programmer (Contractor site) | 1920 | 1 FTE for 12 months, as per notes on Assumptions TAB. | 58 | 111360 | 60 | 115200
Data Base Manager (Govt site) |  |  | 54 | 0 | 57 | 0
Systems Design Engineer (Mid level, Contractor site) | 768 | .4 FTE for 12 months, as per notes on Assumptions TAB. | 121 | 92928 | 140 | 107520
Admin/Clerical (Mid level, Govt site) |  |  | 49 | 0 | 53 | 0
Computer Systems Analyst (Contractor site) |  |  | 57 | 0 | 61 | 0
Network Analyst (Contractor site) |  |  | 62 | 0 | 67 | 0
Systems Security Analyst (Contractor site) |  |  | 67 | 0 | 71 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  | TOTALS |  | 271488 |  | 290880
Labor Category | # Labor Hours | Basis of Estimate | Low Rate $ | Low Amt | High Rate $ | High Amt
Task 3: Test Data Base
Program Manager (Contractor Site) |  |  | 101 | 0 | 107 | 0
Financial Analyst (Govt site) |  |  | 65 | 0 | 69 | 0
Sr. Computer Programmer (Contractor site) |  |  | 70 | 0 | 71 | 0
Computer Programmer (Contractor site) |  |  | 58 | 0 | 60 | 0
Data Base Manager (Govt site) | 240 | 1 FTE for 3 weeks, as per notes on Assumptions TAB. | 54 | 12960 | 57 | 13680
Systems Design Engineer (Mid level, Contractor site) | 120 | .5 FTE for 3 weeks, as per notes on Assumptions TAB. | 121 | 14520 | 140 | 16800
Admin/Clerical (Mid level, Govt site) |  |  | 49 | 0 | 53 | 0
Computer Systems Analyst (Contractor site) |  |  | 57 | 0 | 61 | 0
Network Analyst (Contractor site) |  |  | 62 | 0 | 67 | 0
Systems Security Analyst (Contractor site) |  |  | 67 | 0 | 71 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  | TOTALS |  | 27480 |  | 30480
Labor Category | # Labor Hours | Basis of Estimate | Low Rate $ | Low Amt | High Rate $ | High Amt
Task 4: Populate Data Base
Program Manager (Contractor Site) |  |  | 101 | 0 | 107 | 0
Financial Analyst (Govt site) |  |  | 65 | 0 | 69 | 0
Sr. Computer Programmer (Contractor site) |  |  | 70 | 0 | 71 | 0
Computer Programmer (Contractor site) |  |  | 58 | 0 | 60 | 0
Data Base Manager (Govt site) | 160 | 1 FTE for one month, as per notes on Assumptions TAB. | 54 | 8640 | 57 | 9120
Systems Design Engineer (Mid level, Contractor site) |  |  | 121 | 0 | 140 | 0
Admin/Clerical (Mid level, Govt site) | 320 | 2 FTE for 1 month, as per notes on Assumptions TAB. | 49 | 15680 | 53 | 16960
Computer Systems Analyst (Contractor site) |  |  | 57 | 0 | 61 | 0
Network Analyst (Contractor site) |  |  | 62 | 0 | 67 | 0
Systems Security Analyst (Contractor site) |  |  | 67 | 0 | 71 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  | TOTALS |  | 24320 |  | 26080
Labor Category | # Labor Hours | Basis of Estimate | Low Rate $ | Low Amt | High Rate $ | High Amt
Task 5: Maintain Data Base
Program Manager (Contractor Site) |  |  | 101 | 0 | 107 | 0
Financial Analyst (Govt site) |  |  | 65 | 0 | 69 | 0
Sr. Computer Programmer (Contractor site) |  |  | 70 | 0 | 71 | 0
Computer Programmer (Contractor site) |  |  | 58 | 0 | 60 | 0
Data Base Manager (Govt site) | 1440 | 1 FTE for 9 months, as per notes on Assumptions TAB. | 54 | 77760 | 57 | 82080
Systems Design Engineer (Mid level, Contractor site) |  |  | 121 | 0 | 140 | 0
Admin/Clerical (Mid level, Govt site) | 1440 | 1 FTE for 9 months, as per notes on Assumptions TAB. | 49 | 70560 | 53 | 76320
Computer Systems Analyst (Contractor site) |  |  | 57 | 0 | 61 | 0
Network Analyst (Contractor site) |  |  | 62 | 0 | 67 | 0
Systems Security Analyst (Contractor site) |  |  | 67 | 0 | 71 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  | TOTALS |  | 148320 |  | 158400
Labor Category | # Labor Hours | Labor Category Totals For All Tasks | Low Rate $ | Low Amt | High Rate $ | High Amt
Program Manager (Contractor Site) | 92 |  | 101 | 9292 | 107 | 9844
Financial Analyst (Govt site) | 1920 |  | 65 | 124800 | 69 | 132480
Sr. Computer Programmer (Contractor site) | 960 |  | 70 | 67200 | 71 | 68160
Computer Programmer (Contractor site) | 1920 |  | 58 | 111360 | 60 | 115200
Data Base Manager (Govt site) | 1840 |  | 54 | 99360 | 57 | 104880
Systems Design Engineer (Mid level, Contractor site) | 888 |  | 121 | 107448 | 140 | 124320
Admin/Clerical (Mid level, Govt site) | 1920 |  | 49 | 94080 | 53 | 101760
Computer Systems Analyst (Contractor site) | 0 |  | 57 | 0 | 61 | 0
Network Analyst (Contractor site) | 0 |  | 62 | 0 | 67 | 0
Systems Security Analyst (Contractor site) | 0 |  | 67 | 0 | 71 | 0
| 0 |  | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 | 0 | 0
|  | TOTALS |  | 613540 |  | 656644
Other Direct Charges
Description | Qty | Reason | Low Cost | Low Amount | High Cost | High Amt
Material/Hardware | [5 empty] | 0
Local Travel | 2760 | two 15 mile round trips per day for 2 months and 2 trips per week for 44 weeks | 0.35 | 966 | 0.35 | 966
Travel - RT from Boston to DC | 4 | four round trips for one person | 255 | 1020 | 260 | 1040
Travel - RT from _______ to _______
Travel - RT from _______ to _______
Travel - RT from _______ to _______
Phone | 5760 | three calls per hour for one year | 1.4 | 8064 | 1.5 | 8640
Postage | 48 | four packages FEDEXed per month for one year | 21 | 1008 | 21 | 1008
Photocopies | 4000 | eight 250 page reports with one draft and one final copy pre report | 0.05 | 200 | 0.05 | 200
|  | TOTALS |  | 11258 |  | 11854
Total "Basic" Labor Plus ODCs |  |  |  | 624798 |  | 668498 | 1325142
OPTIONAL TASK
Labor Category | # Labor Hours | Basis of Estimate | Low Rate $ | Low Amt | High Rate $ | High Amt
Task: Design LAN
Program Manager (Contractor Site) |  |  | 101 | 0 | 107 | 0
Financial Analyst (Govt site) |  |  | 65 | 0 | 69 | 0
Sr. Computer Programmer (Contractor site) |  |  | 70 | 0 | 71 | 0
Computer Programmer (Contractor site) |  |  | 58 | 0 | 60 | 0
Data Base Manager (Govt site) |  |  | 54 | 0 | 57 | 0
Systems Design Engineer (Mid level, Contractor site) |  |  | 121 | 0 | 140 | 0
Admin/Clerical (Mid level, Govt site) |  |  | 49 | 0 | 53 | 0
Computer Systems Analyst (Contractor site) | 160 | .5 FTE for 2 months, as per notes on Assumptions TAB. | 57 | 9120 | 61 | 9760
Network Analyst (Contractor site) | 320 | 2 FTE for 2 months, as per notes on Assumptions TAB. | 62 | 19840 | 67 | 21440
Systems Security Analyst (Contractor site) | 800 | .5 FTE for 1 month, as per notes on Assumptions TAB. | 67 | 53600 | 71 | 56800
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  | TOTALS |  | 82560 |  | 88000
Optional Task(s) Other Direct Charges
Description | Qty | Reason | Low Cost | Low Amount | High Cost | High Amt
Material/Hardware | [5 empty] | 0
Local Travel | 600 | one 15 mile round trip per day for 2 months | 0.35 | 210 | 0.35 | 210
Travel - RT from _______ to _______ |  |  |  | 0 |  | 0
Travel - RT from _______ to _______
Travel - RT from _______ to _______
Travel - RT from _______ to _______
Phone | 120 | 3 calls per day for 2 months | 1.4 | 168 | 1.5 | 180
Postage |  |  |  | 0 |  | 0
Photocopies |  |  |  | 0 |  | 0
|  | TOTALS |  | 378 |  | 390
Option Tasking: Labor Plus ODCs TOTAL |  |  |  | 82938 |  | 88390
Grand Total (Including Optional Tasks) |  |  |  | 707736 |  | 756888
Contracting Agency Surcharge (Memo) |  | Basis of Surcharge: 3% of Contract Cost |  | 18743.94 |  | 20054.94
____________________________________________ |  | ____________________ | ___________
IGCE Preparer |  | Phone | Date
____________________________________________ |  | ____________________ | ___________
Program Office Resource Manager Coordination |  | Phone | Date
____________________________________________ |  | ____________________ | ___________
Program Manager |  | Phone | Date
EXAMPLE
EXAMPLE
EXAMPLE
EXAMPLE

## Assumptions
IGCE Report (Example)
Assumptions and Basis of Estimate Remarks:
1. Period of Performance: One year
2. Where work will be performed: Skyline 1 (Government site) and Contractor sites.
3. Work week = 40 hours
4. Work month = 160 hours
5. Work year = 1920 hours
6. Local Travel Rate = .35 per Mile:
7. Local Telephone Cost = 1.50 per Call:
8. Reproduction Cost = .05 per Copy:
9. Source of Labor Categories and Rates: DISIDDOMS XX, Lot XXX, FYXX.
10. If Cost Plus, Labor Rates Include Burden
11. Administration and management level of effort derrived from SOW and experiences from a similar project (Project Name). Project LOE supporting documentation attached.
12. Data Base and Systems Design hours based on attached engineering estimate.