NOAA Workforce Management Office

Annual Hiring Service Plan

September 2007

Annual Hiring Service Plan

Between

______________________________

(Line Office/Corporate Office)

and

Workforce Management Office

This agreement documents the Annual Strategic Conversation held between the

___________________________________________________ (Line Office/Corporate Office)

and the Workforce Management Office (WFMO) on ___________________ (date).

The conversation included discussion and agreement in the following areas as they affect both organizations:

I.	Strategic Conversation

- Mission:  [any changes to mission]

- Strategic goals:  [changes/additions and their expected impact on human resources]

- Budget:  [anticipated RIF or freeze, contracting out of services, etc.]

- Organizational structure: [anticipated reorganizations, establishment of new positions, etc.]

- Other:

II.	Hiring Cycle Timeframes

The WFMO and the _____________________ (LO/CO) commit to a 70 business-day hiring cycle for every hiring action.  The 70 business-day model begins when the HRA receives a complete hiring package and ends when a job offer is made to the candidate(s). The following identifies the actions to be taken and provides the maximum timeframe for each item required to achieve this hiring model:

| Action Item | Principle Owner * | Contributor* | Time Line (business days) | Target Date | Actual Date |
| --- | --- | --- | --- | --- | --- |
| Strategic Conversation conducted | Hiring official | HRA |  |  |  |
| Complete Recruitment/Hiring Package, (e.g., SF-52 and classified position description, etc) received by HR Advisor. (Beginning of 70 business day hiring cycle). - Discuss and approve staffing timeline. - Conduct Job Analysis – as outlined in Job Analysis SOP - Develop and issue draft vacancy announcement. | Human Resources Advisor (HRA) | Hiring official, Subject Matter Expert (SME), and/or Line Office/Corporate Office (LO/CO) Admin Liaison | 10 |  |  |
| Draft vacancy announcement reviewed and approved | Hiring official | N/A | 5 |  |  |
| Post vacancy announcement on USAJOBS. | HRA | N/A | 2 |  |  |
| Announcement opens/closes |  |  | ************************ 15 |  |  |
| Applications reviewed by HR for referral eligibility and minimum qualifications determination. Certificate of candidates issued. | HRA | SME | 14 |  |  |
| Certificate(s) received by hiring official. - Interviews conducted by hiring official. - Contact references of initial selection - Coordinate Demo Pay Issues if applicable - Certificate with selection returned | Hiring official | Hiring official, SME, and/or Panel | 20 |  |  |
| WFMO reviews selection Job Offer(s) made to candidate(s) by HR. (Close of 70 business day hiring cycle.) | HRA | N/A | 4 |  |  |

*Principle Owner (responsible person to complete task)

*Contributor (responsible for providing supporting information/documentation; includes SME)

NOTE:  70 business-day model begins when HRA receives a complete hiring package and ends when a job offer is made to candidate(s).

Approved:					____      			Date:

Deputy AA, (Line Office/Corporate Office)

Approved:								Date:

(WFMO Client Services Director

For additional information:  WFMO Contact Lists