## Approvals
STAR TD-0.1.A: STAR EPL User's Guide Appendix (v3r0)
Approver | Title | Date
Kenneth Jensen | SEP Lead Engineer | 2009-11-30

## Version History
STAR PG-1.A: STAR EPL Process Guidelines Appendix (v3r0)
Version History Summary
Version | Description | Revised Sheets | Date
1 | No version 1
2 | No version 2
3 | New Document for version 3 by Ken Jensen (Raytheon Mission Operations and Services). Replaces Users Guide Appendix (TD-0.1.A). | N/A | 2009-11-30

## Acronyms
Acronyms
ATBD | Algorithm Theoretical Basis Document
CDD | Critical Design Document
CDR | Critical Design Review
CDRR | Critical Design Review Report
CL | Check List
CM | Configuration Management
CM/DM | Configuration Management/Data Management
COD | Code
CTD | Code Test Document
CTR | Code Test Review
CTRR | Code Test Review Report
DDD | Detailed Design Document
DG | Document Guideline
DPP | Development Project Plan
DPR | Development Project Report
EPG | Enterprise Process Group
EPL | Enterprise Project Lifecycle
EUM | External Users Manual
G1RR | Gate 1 Review Report
G2RR | Gate 2 Review Report
G3RR | Gate 3 Review Report
G4RR | Gate 4 Review Report
G5RR | Gate 5 Review Report
IUM | Internal Users Manual
MDD | Metadata Document
OCD | Operations Concept Document
OPP | Operational Project Plan
OSDPD | Office of Satellite Data Processing and Distribution
PAR | Process Asset Repository
PBR | Project Baseline Report
PDD | Preliminary Design Document
PDR | Preliminary Design Review
PDRR | Preliminary Design Review Report
PG | Process Guideline
PMR | Product Maintenance Report
PP | Project Proposal
PRD | Project Requirements Document
PRG | Peer Review Guideline
PRR | Project Requirements Review
PRRR | Project Requirements Review Report
PSR | Project Status Report
QA | Quality Assurance
R&D | Research and Development
RAD | Requirements Allocation Document
RAS | Requirements Allocation Sheet
RNM | Requirements / Needs Matrix
SEP | Systems Engineering Processes
SG | Stakeholder Guideline
SPSRB | Satellite Products and Services Review Board
SRD | System Readiness Document
SRR | System Readiness Review
SRRR | System Readiness Review Report
STAR | Center for Satellite Applications and Research
STP | System Test Plan
SWA | Software Architecture Document
TD | Training Document
TEST | Test Data
TG | Task Guideline
TRD | Test Readiness Document
TRR | Test Readiness Review
TRRR | Test Readiness Review Report
UTP | Unit Test Plan
UTR | Unit Test Report
VVP | Verification and Validation Plan
VVR | Verification and Validation Report

## README
This document is an Appendix to the Version 3.0 STAR Enterprise Product Lifecycle (EPL) Process Guidelines: "STAR_PG-1_v3r0".
STAR EPL stakeholders should use this Appendix in conjunction with PG-1, to assist in obtaining a high-level understanding of the STAR EPL process.
Stakeholders will also find the material in the following sheets to be a handy reference while reviewing the STAR EPL process assets.
The sheets to follow contain the following:
Sheet Name | Sheet Content
STAR EPL (Version 3.0 Model) | High-Level Stakeholder/Task matrix
Gates and Reviews | High-level description of STAR EPL Reviews
Process Assets | List of STAR EPL process assets
Project Artifacts | List of standard STAR EPL project artifacts
Stakeholders | High-level description of STAR EPL stakeholder roles
STAR EPL (Version 1 Model) | Version 1 matrix, for reference
STAR EPL (Version 2.0 Model) | Version 2.0 matrix, for reference
STAR EPL (Version 2.1 Model) | Version 2.1 matrix, for reference

## STAR EPL (Version 3.0 Model)
STAR Enterprise Product Lifecycle (EPL) - Version 3.0
Primary/Lead Role
Supporting/Review/Approval Role
|  | GATE 1 |  | GATE 2 |  | GATE 3 |  |  | GATE 4 |  |  | GATE 5
Phase | ALL | BASIC | EXPLORATORY |  | PLAN |  | DESIGN |  |  | BUILD
Step | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
| ALL | Basic Research (TG-1) | Focused R&D (TG-2) | Project Proposal (TG-3) | Resource Identification (TG-4) | Development Project Plan (TG-5) | Project Requirements (& PRR) (TG-6) | Preliminary Design (& PDR) (TG-7) | Detailed Design (& CDR) (TG-8) | Code & Test Data Development (& TRR) (TG-9) | Code Test And Refinement (& CTR) (TG-10) | System Integration And Test (& SRR) (TG-11)
STAR EPG (SG-1) | Establishes and maintains STAR EPL set of standard processes. Process Assets: PG-1, PG-1.A, PG-2 Artifacts: All STAR EPL process assets
Research Lead (SG-8) |  | Presents Basic Research algorithm at Gate 1 Review Process Assets: None Artifacts: None |  | Prepares STAR Research Project Proposal. Presents Focused R&D algorithm at Gate 2 Review. Process Assets: TG-3 Artifacts: PP
Research Scientist (SG-9) |  | Develops and tests new/improved algorithms. Supports Gate 1 Review. Process Assets: DG-1.1, DG-1.2, TG-1 Artifacts: ATBD_1.0, SWA_1.0 | Continues algorithm development with operational intent Process Assets: DG-1.1, DG-1.2, TG-2 Artifacts: ATBD_1.1, SWA_1.1 | Prepares STAR Research Project Proposal. Supports presentation at Gate 2 Review. Process Assets: TG-3 Artifacts: PP
Research Tester (SG-10) |  | Supplies test data that meets Basic Research standards. Process Assets: TG-1 Artifacts: RTEST_1.0 | Supplies test data that meets Focused R&D standards. Process Assets: TG-2 Artifacts: RTEST_2.0
Research Programmer (SG-11) |  | Develops "throw-away" prototype code for Basic Researchers Process Assets: TD-11.1, TD-11.1.A, TD-11.2, TG-1 Artifacts: RCOD_1.0 | Develops "research-grade" prototype code Process Assets: TD-11.1, TD-11.1.A, TD-11.2, TG-2 Artifacts: RCOD_2.0
Research Management (SG-12) |  | Conducts a Gate 1 Review. Writes a Gate 1 Review Report (optional). Process Assets: TG-1 Artifacts: G1RR (optional) |  | Supports Gate 2 Review Process Assets: None Artifacts: None
STAR Branch Chief (SG-7) |  |  |  | Leads Gate 2 Review and report. Selects Development Lead. Process Assets: TG-3 Artifacts: G2RR (optional) | Secures supplier agreements for STAR Development Project. Process Assets: TG-4 Artifacts: None | Leads Gate 3 Review and report. Approves Gate 3 Review recommendations. Process Assets: DG-5.5, PRG-5, CL-5, TG-5, TD-7 Artifacts: G3RR |  |  | Leads Gate 4 Review and report. Approves Gate 4 Review recommendations. Process Assets: DG-8.5, PRG-8.2, CL-8.2, TG-8, TD-5, TD-7 Artifacts: G4RR |  |  | Leads Gate 5 Review and report. Approves Gate 5 Review recommendations. Process Assets: DG-11.8, PRG-11.2, CL-11.2, TG-11, TD-5, TD-7 Artifacts: G5RR
STAR Division Chief (SG-7) |  |  |  | Reviews and approves Gate 2 Review recommendations Process Assets: TG-3 Artifacts: None | Secures supplier agreements for STAR Development Project. Process Assets: TG-4 Artifacts: None | Reviews and approves Gate 3 Review recommendations. Process Assets: PRG-5, TG-5, TD-5, TD-7 Artifacts: None |  |  | Reviews and approves Gate 4 Review recommendations. Process Assets: PRG-8.2, TG-8, TD-5, TD-7 Artifacts: None |  |  | Reviews and approves Gate 4 Review recommendations. Process Assets: PRG-8.2, TG-8, TD-5, TD-7 Artifacts: None
STAR CM/DM (SG-4) | [5 empty] | Establishes a project baseline under CM for research code, test data, and documentation. Inserts Baseline Build (BB) 1.0 artifacts into baseline. Writes Project Baseline Report (PBR). Completes BB 1.0 before Gate 3 Review. Completes BB 1.1 after Gate 3 Review. Process Assets: DG-5.4, TD-4, TG-5 Artifacts: PBR_1.0, PBR_1.1 | Adds PRR artifacts to baseline. Updates PBR. Completes BB 2.0 before PRR. Completes BB 2.1 after PRR. Process Assets: DG-5.4, TD-4, TG-6 Artifacts: PBR_2.0, PBR_2.1 | Adds PDR artifacts to baseline. Updates PBR. Completes BB 2.2 before PDR. Completes BB 2.3 after PDR. Process Assets: DG-5.4, TD-4, TG-7 Artifacts: PBR_2.2, PBR_2.3 | Adds CDR artifacts to baseline. Updates PBR. Completes BB 2.4 before CDR. Completes BB 2.5 after CDR. Completes BB 2.6 after Gate 4 Review. Process Assets: DG-5.4, TD-4, TG-8 Artifacts: PBR_2.4, PBR_2.5, PBR_2.6 | Adds TRR artifacts to baseline. Updates PBR. Completes BB 3.0 before TRR. Completes BB 3.1 after TRR. Process Assets: DG-5.4, TD-4, TG-9 Artifacts: PBR_3.0, PBR_3.1 | Adds CTR artifacts to baseline. Updates PBR. Completes BB 3.2 before CTR. Completes BB 3.3 after CTR. Process Assets: DG-5.4, TD-4, TG-10 Artifacts: PBR_3.2, PBR_3.3 | Adds SRR artifacts to baseline. Updates PBR. Completes BB 3.4 before SRR. Completes BB 3.5 after SRR. Completes BB 3.6 after Gate 5 Review. Process Assets: DG-5.4, TD-4, TG-11 Artifacts: PBR_3.4, PBR_3.5, PBR_3.6
Technical Reviewer (SG-18) | [6 empty] | Supports PRR review, approval, and report. Process Assets: DG-6.5, PRG-6, CL-6, TG-6, TD-5 Artifacts: PRRR | Supports PDR review, approval, and report. Process Assets: DG-7.2, PRG-7, CL-7, TG-7, TD-5 Artifacts: PDRR | Supports CDR review, approval, and report. Process Assets: DG-8.3, PRG-8.1, CL-8.1, TG-8, TD-5 Artifacts: CDRR | Supports TRR review, approval, and report. Process Assets: DG-9.3, PRG-9, CL-9, TG-9, TD-5 Artifacts: TRRR | Supports CTR review, approval, and report. Process Assets: DG-10.4, PRG-10, CL-10, TG-10, TD-5, TD-11.1, TD-11.2 Artifacts: CTRR | Supports SRR review, approval, and report. Process Assets: DG-11.6, PRG-11.1, CL-11.1, TG-11, TD-5 Artifacts: SRRR
STAR QA (SG-6) |  |  |  | Verifies that Gate 2 Review meets STAR standards. Process Assets: TG-3, TD-3 Artifacts: None |  | Verifies that Gate 3 Review meets STAR standards. Process Assets: DG-5.5, PRG-5, CL-5, TG-5, TD-3 Artifacts: G3RR Appendix | Verifies that PRR meets STAR standards. Process Assets: DG-6.5, PRG-6, CL-6, TG-6, TD-3 Artifacts: PRRR Appendix | Verifies that PDR meets STAR standards. Process Assets: DG-7.2, PRG-7, CL-7, TG-7, TD-3 Artifacts: PDR Appendix | Verifies that CDR and Gate 4 Review meet STAR standards. Process Assets: DG-8.3, DG-8.5, PRG-8.1, PRG-8.2, CL-8.1, CL-8.2, TG-8, TD-3 Artifacts: CDRR Appendix, G4RR Appendix | Verifies that TRR meets STAR standards. Process Assets: DG-9.3, PRG-9, CL-9, TG-9, TD-3 Artifacts: TRRR Appendix | Verifies that CTR meets STAR standards. Process Assets: DG-10.4, PRG-10, CL-10, TG-10, TD-3 Artifacts: CTRR Appendix | Verifies that SRR and Gate 5 Review meet STAR standards. Process Assets: DG-11.6, DG-11.8, PRG-11.1, PRG-11.2, CL-11.1, CL-11.2, TG-11, TD-3 Artifacts: SRRR Appendix, G5RR Appendix
Development Lead (SG-13) |  |  |  |  | Identifies resources needed for Development Process Assets: TG-4 Artifacts: SPSRB Plan | Prepares STAR Development Project Plan. Documents project status, including risks. Prepares Gate 3 Review presentation. Process Assets: DG-5.1, DG-5.2, DG-5.2.A, DG-5.3, DG-5.3.A, TG-5, TD-8 Artifacts: DPP_1.0, PSR_1.0, G3D | Develops the Operations Concept. Leads the preparation of the project requirements for presentation at PRR, including the Initial Requirements Allocation and the Verification and Validation Plan (VVP). Process Assets: DG-6.1, DG-6.2, DG-6.3, DG-6.4, DG-6.4.A, PRG-6, CL-6, TG-6, TD-5, TD-9 Artifacts: PRD, OCD_1.0, VVP_1.0, RAD_1.0, RNM_1.0, RAS_1.0 | Leads the development of the algorithm. Leads the identification of the external interfaces. Leads the preparation of the Preliminary Design Allocation for presentation at PDR, including the Preliminary Design Allocation. Process Assets: DG-1.1, DG-1.2, DG-6.1, DG-6.2, DG-6.3, DG-7.1, DG-7.1.A, PRG-7, CL-7, TG-7, TD-5, TD-10 Artifacts: ATBD_2.0, SWA_2.0, OCD_1.1, RAD_1.1, RNM_1.1, RAS_1.1, PDD | Supports the detailed design development. Leads the preparation of the detailed design for presentation at CDR, including the Detailed Design Allocation. Updates project plan and project status. Prepares Gate 4 Review presentation. Process Assets: DG-1.1, DG-1.2, DG-5.1, DG-5.2, DG-5.2.A, DG-6.1, DG-6.2, DG-6.3, DG-8.2, DG-8.2.A, DG-8.4, DG-8.4.A, PRG-8.1, CL-8.1, PRG-8.2, CL-8.2, TG-8, TD-5, TD-10 Artifacts: ATBD_2.x, SWA_2.x, DPP_2.x, PSR_2.x, OCD_1.2, VVP_1.2, RAD_1.2, CDD, G4D | Leads the preparation of the pre-operational code, test data, and unit test plan for presentation at TRR. Process Assets: DG-9.2, DG-9.2.A, DG-12.3, PRG-9, CL-9, TG-9 Artifacts: TRD, UTP_1.0 | Leads the preparation of the unit test results and system test plan for presentation at CTR. Process Assets: DG-10.3, DG-10.3.A, PRG-10, CL-10, TG-10 Artifacts: CTD | Leads the preparation of the intergated pre-operational system for presentation at SRR. Updates project plan and project status. Prepares Gate 5 Review presentation. Process Assets: DG-1.1, DG-5.1, DG-5.2, DG-5.2.A, DG-11.1, DG-11.2, DG-11.3, DG-11.5, DG-11.5.A, PRG-11.1, PRG-11.2, CL-11.1, CL-11.2, TG-11, TD-5 Artifacts: ATBD_2.2, MDD_1.0, IUM_1.0, EUM_1.0, SRD, DPP_3.x, PSR_3.x, G5D
Technical Review Lead (SG-17) | [6 empty] | Leads PRR review, approval, and report. Process Assets: DG-6.5, PRG-6, CL-6, TG-6, TD-5 Artifacts: PRRR | Leads PDR review, approval, and report. Process Assets: DG-7.2, PRG-7, CL-7, TG-7, TD-5 Artifacts: PDRR | Leads CDR review, approval, and report. Process Assets: DG-8.3, PRG-8.1, CL-8.1, TG-8, TD-5 Artifacts: CDRR | Leads TRR review, approval, and report. Process Assets: DG-9.3, PRG-9, CL-9, TG-9, TD-5 Artifacts: TRRR | Leads CTR review, approval, and report. Process Assets: DG-10.4, PRG-10, CL-10, TG-10, TD-5, TD-11.1, TD-11.2 Artifacts: CTRR | Leads SRR review, approval, and report. Process Assets: DG-11.6, PRG-11.1, CL-11.1, TG-11, TD-5 Artifacts: SRRR
Development Scientist (SG-14) | [5 empty] | Supports STAR Development Project Plan. Documents project status, including risks. Supports Gate 3 Review presentation. Process Assets: DG-5.1, DG-5.2, DG-5.2.A, DG-5.3, DG-5.3.A, TG-5 Artifacts: DPP_1.0, PSR_1.0, G3D | Develops the Operations Concept. Prepares algorithm requirements for presentation at PRR,, including the Initial Requirements Allocation and the Verification and Validation Plan (VVP). Process Assets: DG-6.1, DG-6.2, DG-6.3, DG-6.4, DG-6.4.A, PRG-6, CL-6, TG-6, TD-5, TD-9 Artifacts: PRD, OCD_1.0, VVP_1.0, RAD_1.0, RNM_1.0, RAS_1.0 | Develops the algorithm, selecting a preferred solution. Identifies external interfaces. Develops preliminary software design to be implemented in "pre-operational" code. Updates ATBD to include preliminary design. Supports preparation of Preliminary Design Allocation for presentation at PDR. Process Assets: DG-1.1, DG-1.2, DG-6.1, DG-6.2, DG-6.3, DG-7.1, DG-7.1.A, PRG-7, CL-7, TG-7, TD-5, TD-10 Artifacts: ATBD_2.0, SWA_2.0, OCD_1.1, RAD_1.1, RNM_1.1, RAS_1.1, PDD | Supports the development of the detailed software design to be implemented in "pre-operational" code. Updates ATBD, SWA, and VVP as needed. Supports preparation of Detailed Design Allocation for presentation at CDR. Supports Gate 4 Review presentation. Process Assets: DG-1.1, DG-1.2, DG-5.1, DG-5.2, DG-5.2.A, DG-6.1, DG-6.2, DG-6.3, DG-8.2, DG-8.2.A, DG-8.4, DG-8.4.A, PRG-8.1, CL-8.1, PRG-8.2, CL-8.2, TG-8, TD-5, TD-10 Artifacts: ATBD_2.x, SWA_2.x, DPP_2.x, PSR_2.x, OCD_1.2, VVP_1.2, RAD_1.2, CDD, G4D | Supports production of test data for testing of "pre-operational" code. Supports the preparation of the unit test plan for presentation at TRR. Process Assets: DG-9.2, DG-9.2.A, DG-12.3, PRG-9, CL-9, TG-9 Artifacts: PTEST-2.0, TRD, UTP_1.0 | Supports unit testing of "pre-operational" code. Suggests code and unit test refinements as necessary. Supports development of system test plan. Supports presentation at CTR. Process Assets: DG-9.1, DG-10.1, DG-10.2, DG-10.3, DG-10.3.A, PRG-10, CL-10, TG-10, TD-6 Artifacts: UTP_1.1, UTR_1.0, STP_1.0, CTD | Supports system test to validate system performance. Develops user documentation. Supports presentation at SRR. Supports Gate 5 Review presentation. Process Assets: DG-1.1, DG-5.2, DG-5.2.A, DG-11.1, DG-11.2, DG-11.4, DG-11.5, DG-11.5.A, DG-11.7, DG-11.7.A, TG-11, TD-5, TD-6 Artifacts: ATBD_2.2, VVR_1.0, IUM_1.0, EUM_1.0, PSR_3.x, SRD, G5D
Development Tester (SG-15) | [6 empty] | Prepares test requirements and their allocation for presentation at PRR. Process Assets: DG-6.2, DG-6.3, DG-6.4.A, DG-6.4, PRG-6, CL-6, TG-6, TD-9 Artifacts: PRD, VVP_1.0, RAD_1.0 | Updates the VVP and RAD as needed. Supports preparation of Preliminary Design Allocation for presentation at PDR. Process Assets: DG-6.2, DG-6.3, DG-7.1, DG-7.1.A, PRG-7, CL-7, TG-7, TD-5, TD-6 Artifacts: RAD_1.1, RAS_1.1, VVP_1.1, PDD | Updates the VVP and RAD as needed. Supports preparation of Detailed Design Allocation for presentation at CDR. Supports Gate 4 Review presentation. Process Assets: DG-6.2, DG-6.3, DG-8.2, DG-8.2.A, PRG-8.1, PRG-8.2, CL-8.1, CL-8.2, TG-8, TD-5, TD-6 Artifacts: RAD_1.2, RAS_1.2, VVP_1.2, CDD, G4D | Produces test data for unit testing of "pre-operational" code. Develops Unit Test Plan (UTP). Supports the preparation of the TRR presentation. Process Assets: DG-9.1, DG-9.2, DG-9.2.A, TG-9, TD-6 Artifacts: PTEST-1, UTP_1.0, TRD | Leads unit tests of "pre-operational" code. Refines unit test data and test plan. Reports unit test results. Develops System Test Plan (STP). Develops system test data. Supports presentation at CTR. Process Assets: DG-9.1, DG-10.1, DG-10.2, DG-10.3, DG-10.3.A, TG-10, TD-6 Artifacts: PTEST-2, UTP_1.x, UTR_1.0, STP_1.0, CTD | Develops system test data. Tests integrated pre-operational system (system test). Refines system test plan and system test data as needed. Supports development of External User Manual (EUM). Reports system test results (VVR). Supports presentation at SRR. Supports Gate 5 Review presentation. Process Assets: DG-5.2, DG-5.2.A, DG-11.2, DG-11.4, DG-11.5, DG-11.5.A, DG-11.7, DG-11.7.A, TG-11, TD-5, TD-6 Artifacts: PTEST_3.x, EUM_1.0, VVR_1.0, PSR_3.x, SRD, G5D
Development Programmer (SG-16) | [7 empty] | Assists in identification of external interfaces. Supports the development of the preliminary software design to be implemented in "pre-operational" code. Supports preparation of Preliminary Design Allocation for presentation at PDR. Process Assets: DG-1.2, DG-7.1, DG-7.1.A, TG-7, TD-5, TD-10 Artifacts: SWA_2.0, PDD | Develops detailed software design to be implemented in "pre-operational" code. Updates VVP and RAD as needed. Supports preparation of Detailed Design Allocation for presentation at CDR. Supports Gate 4 Review presentation. Process Assets: DG-1.2, DG-6.2, DG-6.3, DG-8.1, DG-8.2, DG-8.2.A, PRG-8.1, PRG-8.2, CL-8.1, CL-8.2, TG-8, TD-5, TD-6 Artifacts: SWA_2.1, DDD_1.0, RAD_1.2, RAS_1.2, VVP_1.2, CDD, G4D | Develops "pre-operational" code and Unit Test Plan (UTP) for presentation at TRR. Supports the preparation of the TRR presentation. Process Assets: DG-9.1, DG-9.2, DG-9.2.A, TG-9, TD-6, TD-11.1, TD-11.1.A. TD-11.2 Artifacts: PCOD-1, UTP_1.0, TRD | Supports unit testing of "pre-operational" code. Refines "pre-operational" code and unit test plan as necessary. Contributes to report of unit test results. Develops System Test Plan (STP). Supports presentation at CTR. Process Assets: DG-9.1, DG-10.1, DG-10.2, DG-10.3, DG-10.3.A, TG-10, TD-6, TD-11.1., TD-11.1.A, TD-11.2 Artifacts: PCOD_2, UTP_1.x, UTR_1.0, STP_1.0, CTD | Develops Metadata Document (MDD). Develops Users Manuals (IUM and EUM). Integrates pre-operational code into test environment. Supports system test and refinement of integrated code. Supports report of system test results (VVR). Supports presentation at SRR. Supports Gate 5 Review presentation. Process Assets: DG-5.2, DG-5.2.A, DG-11.1, DG-11.2, DG-11.3, DG-11.4, DG-11.5, DG-11.5.A, DG-11.7, DG-11.7.A, TG-11, TD-5, TD-6 Artifacts: PCOD_3.x, MDD_1.0, IUM_1.0, EUM_1.0, VVR_1.0, PSR_3.x, SRD, G5D
|  | <------- RESEARCH -------> |  |  | <------------------------------------ DEVELOPMENT ----------------------------------->

## Gates & Reviews
STAR EPL Gates & Reviews
GATES are a series of management reviews that review project status to determine whether a project should proceed to the next step in the product life cycle. Gate Review standards are established and maintained under Configuration Management (CM) by an Enterprise Process Group (EPG) under the direction of a Steering Committee (SC). They are contained in a Process Asset Library (PAL) that is accessible to all stakeholders via the STAR EPL Web portal.
TECHNICAL REVIEWS are a series of reviews that review the technical progress of a project with respect to standard criteria. Review standards are established and maintained under Configuration Management (CM) by an Enterprise Process Group (EPG) under the direction of a Steering Committee. They are contained in a Process Asset Library (PAL) that is accessible to all stakeholders via a Web portal.
Gate 1 is an internal review of Basic Research by the research organization. Its purpose is to determine whether organization funds and resources should be expended on Focused R&D of a new/improved algorithm, leading to a Project Proposal to develop an operational product.
Gate 2 is a STAR review of a STAR Research Project Proposal. Its purpose is to determine whether the proposal is compatible with the NESDIS mission and strategic plan, and is technically feasible for development into an operational product. Resource issues are not considered at this time. If a project passes Gate 2, a Development Lead is assigned and the Plan phase commences.
Gate 3 is a STAR review of the project’s readiness for development. Its purpose is to determine whether the development plan is feasible, the identified resources are available, and the identified risks are manageable. If a project passes Gate 3, the project proceeds to the Design phase.
Project Requirements Review (PRR) is a Design Development Phase Technical Review. Its purpose is to establish the requirements to be satisfied by the project and the means to validate them. Upon completion of this review, the preliminary design step of the Design phase commences.
Preliminary Design Review (PDR) is a Design Development Phase Technical Review. Its purpose is to assess the algorithm preliminary design. Upon completion of this review, the detailed design step of the Design phase commences.
Critical Design Review (CDR) is the final Design Development Phase Technical Review. Its purpose is to assess the algorithm detailed design. Upon successful completion of CDR, a Gate 4 Review is held to determine whether the project should proceed to the Build phase.
Gate 4 is a review of the project status follwong the CDR, under the direction of STAR. Its purpose is to determine whether the project is ready to begin development and testing of pre-operational code. If a project passes Gate 4, the project proceeds to the Build phase.
Test Readiness Review (TRR) is a Build Phase Technical Review. Its purpose is to determine whether code and test data development are sufficient to allow definitive testing of the pre-operational algorithm. Upon successful completion of TRR, the code test and refinement step of the Build phase commences.
Code Test Review (CTR) is a Build Phase Technical Review. Its purpose is to determine whether the pre-operational code units meet their requirements. Upon successful completion of CTR, the system integration and test step of the Build phase commences.
System Readiness Review (SRR) is the final Build Phase Technical Review prior to Gate 5. Its purpose is to determine whether the pre-operational product system satisfies its functional and performance requirements, and is ready for installation in the operations environment. Upon successful completion of SRR, preparations are made for a Gate 5 review of readiness for transition to operations.
Gate 5 is the final review of the project status readiness before it is transitioned to operations, under the joint direction of STAR and SPSRB. Its purpose is to determine whether operations is ready to receive the pre-operational system from the developers. If a project passes Gate 5, the pre-operational system and all associated artifacts are delivered to operations.

## Process Assets
STAR EPL Process Assets
PROCESS ASSETS are a set of Process Guidelines, Stakeholder Guidelines, Task Guidelines, Document Guidelines, Peer Review Guidelines, Review Checklists, and Training Documents that define the enterprise standards and best practices. They are established and maintained under Configuration Management (CM) by an Enterprise Process Group (EPG) under the direction of a Steering Committee (SC). They are contained in a STAR Process Asset Library (PAL) that is accessible to all stakeholders via the STAR EPL Web portal.
Legend:
Available in the version 3.0 release of STAR EPL process assets
Planned for a future release of STAR EPL process assets
Deferred: Requires common development with OSDPD
TBD: Possible inclusion in a future version
Process Guidelines (3) |  | Process Guideline documents describe STAR's standard set of practices and guidelines for tailoring them to specific projects
ID | Guideline
PG-1 | STAR EPL Process Guidelines | Description of the STAR Enterprise standard set of practices
PG-1.A | STAR EPL Process Guidelines Appendix | Description of the STAR Enterprise standard set of practices
PG-2 | STAR EPL Tailoring Guidelines | Guidelines for tailoring STAR's standard set of practices for projects
Stakeholder Guidelines (18) |  | Stakeholder Guideline is a description of how to perform all STAR EPL standard tasks assigned to a given type of stakeholder. It should itemize the actions to be taken. It should contain appropriate standards, conventions, and (where appropriate) examples. It should point to the appropriate references and the required artifacts.
ID | Stakeholder
SG-1 | STAR Enterprise Process Group | Guidelines for STAR EPG tasks
SG-2 | STAR Steering Committee | Guidelines for STAR SC tasks
SG-3 | STAR IT | Guidelines for STAR IT EPL tasks
SG-4 | STAR CM/DM | Guidelines for STAR CM/DM EPL tasks
SG-5 | STAR Web Developers | Guidelines for STAR Web Developer EPL tasks
SG-6 | STAR Quality Assurance | Guidelines for STAR QA EPL tasks
SG-7 | STAR Managers | Guidelines for STAR Management EPL tasks
SG-8 | Research Leads | Guidelines for Research Lead EPL tasks
SG-9 | Research Scientists | Guidelines for Research Scientist EPL tasks
SG-10 | Research Testers | Guidelines for Research Tester EPL tasks
SG-11 | Research Programmers | Guidelines for Research Programmer EPL tasks
SG-12 | Research Managers | Guidelines for Research Management EPL tasks
SG-13 | Development Leads | Guidelines for Development Lead EPL tasks
SG-14 | Development Scientists | Guidelines for STAR Scientist EPL tasks
SG-15 | Development Testers | Guidelines for Development Tester EPL tasks
SG-16 | Development Programmers | Guidelines for Development Programmer EPL tasks
SG-17 | Technical Review Leads | Guidelines for Technical Review Lead EPL tasks
SG-18 | Technical Reviewers | Guidelines for STAR Technical Reviewer EPL tasks
SG-19 | Operations Leads | Guidelines for Operations Lead EPL tasks
SG-20 | Operations Management | Guidelines for Operations Management EPL tasks
SG-21 | Integration Programmers | Guidelines for Integration Programmer EPL tasks
SG-22 | Maintenance Programmers | Guidelines for Maintenance Programmer EPL tasks
SG-23 | Operations CM/DM | Guidelines for Operations CM/DM EPL tasks
SG-24 | Operations Quality Assurance | Guidelines for Operations QA EPL tasks
Task Guidelines (11) |  | Task Guideline is a description of how to perform the tasks of a STAR EPL process step. It should itemize the actions to be taken. It should contain appropriate standards, conventions, and (where appropriate) examples. It should point to the appropriate references and the required artifacts. There is one Task Guideline for each step in the STAR EPL.
ID | Guideline
TG-1 | Basic Research Task Guideline | Guidelines for Basic Research step of STAR EPL
TG-2 | Focused R&D Task Guideline | Guidelines for Focused R&D step of STAR EPL
TG-3 | Project Proposal Task Guideline | Guidelines for Project Proposal step of STAR EPL
TG-4 | Resource Identification Task Guideline | Guidelines for Resource Identification step of STAR EPL
TG-5 | Development Project Plan Task Guideline | Guidelines for Development Project Plan step of STAR EPL
TG-6 | Project Requirements Task Guideline | Guidelines for Project Requirements step of STAR EPL
TG-7 | Preliminary Design Task Guideline | Guidelines for Preliminary Design step of STAR EPL
TG-8 | Detailed Design Task Guideline | Guidelines for Detailed Design step of STAR EPL
TG-9 | Code and Test Data Development Task Guideline | Guidelines for Code and Test Data Development step of STAR EPL
TG-10 | Code Test and Refinement Task Guideline | Guidelines for Code Test and Refinement step of STAR EPL
TG-11 | System Integration and Test Task Guideline | Guidelines for System Integration and Test step of STAR EPL
TG-12 | O&M Project Plan Task Guideline | Guidelines for O&M Project Plan step of STAR EPL
TG-13 | Installation & Acceptance Task Guideline | Guidelines for Installation & Acceptance step of STAR EPL
TG-14 | Operations Task Guideline | Guidelines for Operations step of STAR EPL
TG-15 | Reactive Maintenance Task Guideline | Guidelines for Reactive Maintenance step of STAR EPL
TG-16 | Science Maintenance Task Guideline | Guidelines for Science Maintenance step of STAR EPL
TG-17 | Retirement Task Guideline | Guidelines for Retirement step of STAR EPL
Document Guidelines (51) |  | Document Guideline includes a description of the purpose for the document, a standard document outline (table of contents), a brief description of each subsection in the outline, and an Appendix containing an example document.
ID | Document Guideline
DG-0.1 | Document Style Guideline | Style Standards
DG-0.2 | Process Improvement Report (PIR) Guidelines | Guidelines for PIR. | PIR is produced by the EPG, approved by the SC.
DG-0.2.A | Process Improvement Report Appendix Guidelines | Guidelines for PIR Appendix. | PIR Appendix is an Excel workbook that documents the status of process improvement activities
DG-0.3 | Risk Review Report (RRR) Guidelines | Guidelines for RRR. | RRR is produced by the STAR Management, approved by the SC.
DG-0.3.A | Risk Review Report Appendix Guidelines | Guidelines for RRR Appendix. | RRR Appendix is an Excel workbook that maintains the status of organizational-level risks and associated risk mitigation actions
DG-1.1 | Algorithm Theoretical Basis Document (ATBD) | Standards for ATBD
DG-1.2 | Software Architecture Document (SWA) | Standards for SWA
DG-1.3 | Gate 1 Review Report | Standards for G1RR
DG-3.1 | Project Proposal (PP) | Standards for PP
DG-3.2 | Gate 2 Review Report | Standards for G1RR
DG-5.1 | Development Project Plan (DPP) | Standards for DPP
DG-5.2 | Project Status Report (PSR) | Standards for PSR
DG-5.2.A | PSR Appendix | Standards for PSR Appendix
DG-5.3 | Gate 3 Document (G3D) | Standards for G3D
DG-5.3.A | G3D Appendix | Template slides for G3D
DG-5.4 | Project Baseline Report (PBR) | Standards for PBR
DG-5.5 | Gate 3 Review Report (G3RR) | Standards for G3RR
DG-6.1 | Operations Concept Document (OCD) | Standards for OCD
DG-6.2 | Requirements Allocation Document (RAD) | Standards for RAD
DG-6.3 | Verification and Validation Plan (VVP) | Standards for VVP
DG-6.4 | Project Requirements Document (PRD) | Standards for PRD
DG-6.4.A | PRD Appendix | Template slides for PRD
DG-6.5 | Project Requirements Review Report (PRRR) | Standards for PRRR
DG-7.1 | Preliminary Design Document (PDD) | Standards for PDD
DG-7.1.A | PDD Appendix | Template slides for PDD
DG-7.2 | Preliminary Design Review Report (PDRR) | Standards for PDRR
DG-8.1 | Detailed Design Document (DDD) | Standards for DDD
DG-8.2 | Critical Design Document (CDD) | Standards for CDD
DG-8.2.A | CDD Appendix | Template slides for CDD
DG-8.3 | Critical Design Review Report (CDRR) | Standards for CDRR
DG-8.4 | Gate 4 Document (G4D) | Standards for G4D
DG-8.4.A | G4D Appendix | Template slides for G4D
DG-8.5 | Gate 4 Review Report (G4RR) | Standards for G4RR
DG-9.1 | Unit Test Plan (UTP) | Standards for UTP
DG-9.2 | Test Readiness Document (TRD) | Standards for TRD
DG-9.2.A | TRD Appendix | Template slides for TRD
DG-9.3 | Test Readiness Review Report (TRRR) | Standards for TRRR
DG-10.1 | Unit Test Report (UTR) | Standards for UTR
DG-10.2 | System Test Plan (STP) | Standards for STP
DG-10.3 | Code Test Document (CTD) | Standards for CTD
DG-10.3.A | CTD Appendix | Template slides for CTD
DG-10.4 | Code Test Review Report (CTRR) | Standards for CTRR
DG-11.1 | Internal Users Manual (IUM) | Standards for IUM
DG-11.2 | External Users Manual (EUM) | Standards for EUM
DG-11.3 | Metadata Document (MDD) | Standards for MDD
DG-11.4 | Verification and Validation Report (VVR) | Standards for VVR
DG-11.5 | System Readiness Document (SRD) | Standards for SRD
DG-11.5.A | SRD Appendix | Template slides for SRD
DG-11.6 | System Readiness Review Report (SRRR) | Standards for SRRR
DG-11.7 | Gate 5 Document (G5D) | Standards for G5D
DG-11.7.A | G5D Appendix | Template slides for G5D
DG-11.8 | Gate 5 Review Report (G5RR) | Standards for G5RR
DG-11.9 | Development Project Report (DPR) | Standards for DPR
Peer Review Guidelines (15) |  | Peer Review Guideline should describe the objectives of the review, the required artifacts, standards for reviewers, requirements for approval, and options other than approval.
ID | Peer Review Guideline
PRG-0.1 | Process Improvement Review (PIR) Guidelines | Guidelines for PIR | This is a Technical Review.
PRG-0.2 | Risk Review (RR) Guidelines | Guidelines for RR
PRG-1 | Gate 1 Review Guidelines | Guidelines for Gate 1 Review
PRG-3 | Gate 2 Review Guidelines | Guidelines for Gate 2 Review
PRG-5 | Gate 3 Review Guidelines | Guidelines for Gate 3 Review
PRG-6 | Project Requirements Review (PRR) Guidelines | Guidelines for PRR
PRG-7 | Preliminary Design Review (PDR) Guidelines | Guidelines for PDR
PRG-8.1 | Critical Design Review (CDR) Guidelines | Guidelines for CDR
PRG-8.2 | Gate 4 Review Guidelines | Guidelines for Gate 4 Review
PRG-9 | Test Readiness Review (TRR) Guidelines | Guidelines for TRR
PRG-10 | Code Test Review (CTR) Guidelines | Guidelines for CTR
PRG-11.1 | System Readiness Review (SRR) Guidelines | Guidelines for SRR
PRG-11.2 | Gate 5 Review Guidelines | Guidelines for Gate 5 Review
PRG-13 | Gate 6 Review Guidelines | Guidelines for Gate 6 Review
PRG-17 | Gate 7 Review Guidelines | Guidelines for Gate 7 Review
Review Check Lists (15) |  | A form or checklist that includes all the requirements for a review. Each item in the checklist should have a "Disposition" column that contains "Pass", "Conditional Pass", "Defer", "Waive", or "N/A" (Not Applicable). Each item will also have columns for Risk Assessment and for Actions generated.
ID | Review Check List
CL-0.1 | Process Improvement Review Check List | Form and/or checklist for PIR closure. | Risks and actions relating to project compliance with process
CL-0.2 | Risk Review Check List | Form and/or checklist for RR closure.
CL-1 | Gate 1 Review Checklist | Form and/or checklist for Gate 1 approval
CL-3 | Gate 2 Review Checklist | Form and/or checklist for Gate 2 approval
CL-5 | Gate 3 Review Checklist | Form and/or checklist for Gate 3 approval
CL-6 | Project Requirements Review Checklist | Form and/or checklist for PRR approval
CL-7 | Preliminary Design Review Checklist | Form and/or checklist for PDR approval
CL-8.1 | Critical Design Review Checklist | Form and/or checklist for CDR approval
CL-8.2 | Gate 4 Review Checklist | Form and/or checklist for Gate 4 approval
CL-9 | Test Readiness Review Checklist | Form and/or checklist for TRR approval
CL-10 | Code Unit Test Review Checklist | Form and/or checklist for CTR approval
CL-11.1 | System Readiness Review Checklist | Form and/or checklist for SRR approval
CL-11.2 | Gate 5 Review Checklist | Form and/or checklist for Gate 5 approval
CL-13 | Gate 6 Review Checklist | Form and/or checklist for Gate 6 approval
CL-17 | Gate 7 Review Checklist | Form and/or checklist for Gate 7 approval
Training Documents (13) |  | References to assist stakeholders in performing their assigned STAR EPL tasks
ID | Training Document
TD-1 | STAR Training Plan | STAR organizational training tactical plan
TD-2 | Measurement and Decision Analysis | Guidance for measurement and analysis of project work products | Import CMMI MA and DAR process area descriptions
TD-3 | Quality Assurance | Guidance for quality assurance of process and products | Import CMMI PPQA process area descriptions
TD-4 | Configuration Management / Data Management | Description of STAR EPL CM/DM tools and practices. | Import CMMI CM process area descriptions
TD-5 | Risk Management | Techniques and tools for risk management | Import CMMI RSKM process area descriptions - add Quantitative RSKM technique
TD-6 | Verification And Validation | Techniques and tools for verification and validation of project work products | Import CMMI VER and VAL process area descriptions
TD-7 | Project Management | Techniques and tools for project management
TD-8 | Project Planning | Techniques and tools for establishment and maintenance of a project plan | TD-8. Import CMMI PP process area descriptions, also PMC.
TD-9 | Project Requirements | Techniques and tools for requirements development, maintenance, and management | TD-9
TD-10 | System Design | Techniques, tools, and criteria for preliminary design and detailed design
TD-11.1 | FORTRAN Programming Standards and Guidelines | Standards for FORTRAN code | TD-11.1
TD-11.1.A | Transition from Fortran 77 to Fortran 90 | Guidance for Fortran programmers who are upgrading to F90 | TD-11.1.A
TD-11.2 | C Programming Standards and Guidelines | Standards for C code | TD-11.2
Example Documents. Examples of project artifact documents, obtained from project artifact repositories. Ideally, at least one example for each standard document.
ATBD | Algorithm Theoretical Basis Document
SWA | Software Architecture Document
PP | Project Proposal
DPP | Development Project Plan
IMS | Integrated Master Schedule
PSR | Project Status Report
PBR | Project Baseline Report
G3RR | Gate 3 Review Report
OCD | Operations Concept Document
VVP | Verification and Validation Plan
RAD | Requirements Allocation Document
RNM | Requirements / Needs Matrix
RAS | Requirements Allocation Sheet
PRD | Project Requirements Document
PRRR | Project Requirements Review Report
PDD | Preliminary Design Document
PDRR | Preliminary Design Review Report
DDD | Detailed Design Document
MDD | Metadata Document
CDD | Critical Design Document
CDRR | Critical Design Review Report
G4RR | Gate 4 Review Report
UTP | Unit Test Plan
TRD | Test Readiness Document
TRRR | Test Readiness Review Report
UTR | Unit Test Report
STP | System Test Plan
CTD | Code Test Document
CTRR | Code Test Review Report
IUM | Internal Users Manual
EUM | External Users Manual
VVR | Verification and Validation Report
SRD | System Readiness Document
SRRR | System Readiness Review Report
G5RR | Gate 5 Review Report
DPR | Development Project Report
OPP | Operational Project Plan
OEL | Operational Events Log
PMR | Product Maintenance Report
G6RR | Gate 6 Review Report
Example Code. Examples of project code, obtained from project artifact repositories. Ideally, at least one example for each approved language.
RCOD_1 | Basic Research Code
RCOD_2 | R&D Code
PCOD_2 | Pre-Operational Code
OCOD | Operational Code

## Project Artifacts
STAR EPL Project Artifacts
ARTIFACTS are a set of items that must be produced by the appropriate stakeholders during the product life cycle to support the reviews. They are established and maintained under Configuration Management (CM) by an Enterprise Process Group (EPG) under the direction of a Steering Committee (SC). They are contained in a STAR EPL Artifact Repository that is accessible to all stakeholders via the STAR EPL Web portal.
Legend:
Document or Report - Original Version
Document or Report - Planned Revision
Code or Test Data
Step | Phase | Artifact | ID | Item Type | Event | Baseline Build | SG
1 | Basic | Algorithm Theoretical Basis Document v1 | ATBD_1.0 | Document | Gate 1 | None | 9, 10
1 | Basic | Software Architecture Document v1 | SWA_1.0 | Document | Gate 1 | None | 9
1 | Basic | Basic Research Code | RCOD_1.0 | Code | Gate 1 | None | 11
1 | Basic | Basic Research Test Data | RTEST_1.0 | Test Data | Gate 1 | None | 9, 10
1 | Basic | Gate 1 Review Report | G1RR | Report | Gate 2 | None | 8, 12
2 | Exploratory | R&D Code | RCOD_2.0 | Code | Gate 2 | BB 1.0 | 11
2 | Exploratory | R&D Test Data | RTEST_2.0 | Test Data | Gate 2 | BB 1.0 | 9, 10
2 | Exploratory | Algorithm Theoretical Basis Document v1 | ATBD_1.1 | Document | Gate 2 | BB 1.0 | 9, 10
2 | Exploratory | Software Architecture Document v1 | SWA_1.1 | Document | Gate 2 | BB 1.0 | 9
3 | Exploratory | Project Proposal | PP | Document | Gate 2 | BB 1.0 | 8, 9, 10, 11
3 | Exploratory | Gate 2 Review Report | G2RR | Report | Gate 3 | BB 1.0 | 7, 13
4, 5 | Plan | Development Project Plan v1 | DPP_1.0 | Document | Gate 3 | BB 1.0 | 13, 14, 15, 16
5 | Plan | Project Status Report v1 | PSR_1.0 | Report | Gate 3 | BB 1.0 | 13, 14, 15, 16
5 | Plan | Gate 3 Document | G3D | Presentation | Gate 3 | BB 1.0 | 13, 14, 15, 16
5 | Plan | Project Baseline Report v1 | PBR_1.0 | Report | Gate 3 | BB 1.0 | 4
5 | Plan | Gate 3 Review Report | G3RR | Report | Gate 4 | BB 1.1 | 6, 7
5 | Plan | Project Baseline Report v1 | PBR_1.1 | Report | None | BB 1.1 | 4
6 | Design | Development Project Plan v1 | DPP_2.0 | Document | PRR | BB 2.0 | 13, 14, 15, 16
6 | Design | Operations Concept Document v1 | OCD_1.0 | Document | PRR | BB 2.0 | 13, 14
6 | Design | Verification and Validation Plan v1 | VVP_1.0 | Document | PRR | BB 2.0 | 14, 15, 16
6 | Design | Requirements Allocation Document v1 | RAD_1.0 | Document | PRR | BB 2.0 | 13, 14, 15, 16
6 | Design | Project Requirements Document | PRD | Presentation | PRR | BB 2.0 | 13, 14, 15, 16
6 | Design | Project Baseline Report v2 | PBR_2.0 | Report | PRR | BB 2.0 | 4
6 | Design | Project Requirements Review Report | PRRR | Report | PDR | BB 2.1 | 17, 18
6 | Design | Project Baseline Report v2 | PBR_2.1 | Report | None | BB 2.1 | 4
7 | Design | Development Project Plan v1 | DPP_2.x | Document | PDR | BB 2.2 | 13, 14, 15, 16
7 | Design | Algorithm Theoretical Basis Document v2 | ATBD_2.0 | Document | PDR | BB 2.2 | 14, 15
7 | Design | Operations Concept Document v1 | OCD_1.1 | Document | PDR | BB 2.2 | 13, 14
7 | Design | Verification and Validation Plan v1 | VVP_1.1 | Document | PDR | BB 2.2 | 14, 15, 16
7 | Design | Requirements Allocation Document v1 | RAD_1.1 | Document | PDR | BB 2.2 | 13, 14, 15, 16
7 | Design | Software Architecture Document v2 | SWA_2.0 | Document | PDR | BB 2.2 | 14
7 | Design | Preliminary Design Document | PDD | Presentation | PDR | BB 2.2 | 13, 14, 15, 16
7 | Design | Project Baseline Report v2 | PBR_2.2 | Report | PDR | BB 2.2 | 4
7 | Design | Preliminary Design Review Report | PDRR | Report | CDR | BB 2.3 | 17, 18
7 | Design | Project Baseline Report v2 | PBR_2.3 | Report | None | BB 2.3 | 4
8 | Design | Development Project Plan v1 | DPP_2.x | Document | CDR | BB 2.4 | 13, 14, 15, 16
8 | Design | Algorithm Theoretical Basis Document v2 | ATBD_2.1 | Document | CDR | BB 2.4 | 14, 15
8 | Design | Software Architecture Document v2 | SWA_2.1 | Document | CDR | BB 2.4 | 14
8 | Design | Operations Concept Document v1 | OCD_1.2 | Document | CDR, SRR | BB 2.4 | 13, 14
8 | Design | Verification and Validation Plan v1 | VVP_1.2 | Document | CDR | BB 2.4 | 14, 15, 16
8 | Design | Requirements Allocation Document v1 | RAD_1.2 | Document | CDR | BB 2.4 | 13, 14, 15, 16
8 | Design | Detailed Design Document v1 | DDD_1.0 | Document | CDR | BB 2.4 | 16
8 | Design | Critical Design Document | CDD | Presentation | CDR | BB 2.4 | 13, 14, 15, 16
8 | Design | Project Baseline Report v2 | PBR_2.4 | Report | CDR | BB 2.4 | 4
8 | Design | Critical Design Review Report | CDRR | Report | Gate 4, TRR | BB 2.5 | 17, 18
8 | Design | Development Project Plan v2 | DPP_2.0 | Document | Gate 4 | BB 2.5 | 13, 14, 15, 16
8 | Design | Project Status Report v2 | PSR_2.0 | Report | Gate 4 | BB 2.5 | 13, 14, 15, 16
8 | Design | Gate 4 Document | G4D | Presentation | Gate 4 | BB 2.5 | 13, 14, 15, 16
8 | Design | Project Baseline Report v2 | PBR_2.5 | Report | Gate 4 | BB 2.5 | 4
8 | Design | Gate 4 Review Report | G4RR | Report | Gate 4 | BB 2.6 | 6, 7
8 | Design | Project Baseline Report v2 | PBR_2.6 | Report | None | BB 2.6 | 4
9 | Build | Development Project Plan v3 | DPP_3.0 | Document | TRR | BB 3.0 | 13, 14, 15, 16
9 | Build | Pre-Operational Code | PCOD_1.x | Code | TRR | BB 3.0 | 16
9 | Build | Pre-Operational Test Data | PTEST_1.x | Test Data | TRR | BB 3.0 | 14, 15
9 | Build | Verification and Validation Plan v1 | VVP_1.3 | Document | TRR | BB 3.0 | 14, 15, 16
9 | Build | Software Architecture Document v2 | SWA_2.2 | Document | TRR | BB 3.0 | 14
9 | Build | Detailed Design Document v1 | DDD_1.1 | Document | TRR | BB 3.0 | 16
9 | Build | Requirements Allocation Document v1 | RAD_1.3 | Document | TRR | BB 3.0 | 13, 14, 15, 16
9 | Build | Unit Test Plan v1 | UTP_1.0 | Document | TRR | BB 3.0 | 15, 16
9 | Build | Test Readiness Document | TRD | Presentation | TRR | BB 3.0 | 13, 14, 15, 16
9 | Build | Project Baseline Report v3 | PBR_3.0 | Report | TRR | BB 3.0 | 4
9 | Build | Test Readiness Review Report | TRRR | Report | CTR | BB 3.1 | 17, 18
9 | Build | Project Baseline Report v3 | PBR_3.1 | Report | None | BB 3.1 | 4
10 | Build | Development Project Plan v3 | DPP_3.x | Document | CTR | BB 3.2 | 13, 14, 15, 16
10 | Build | Refined Pre-Operational Code | PCOD_2.x | Code | CTR | BB 3.2 | 16
10 | Build | Refined Pre-Operational Test Data | PTEST_2.x | Test Data | CTR | BB 3.2 | 14, 15
10 | Build | Software Architecture Document v2 | SWA_2.3 | Document | CTR, SRR | BB 3.2 | 14
10 | Build | Detailed Design Document v1 | DDD_1.2 | Document | CTR, SRR | BB 3.2 | 16
10 | Build | Requirements Allocation Document v1 | RAD_1.4 | Document | CTR, SRR | BB 3.2 | 13, 14, 15, 16
10 | Build | Unit Test Plan v1 | UTP_1.1 | Document | CTR | BB 3.2 | 15, 16
10 | Build | Unit Test Report v1 | UTR_1.0 | Report | CTR | BB 3.2 | 15, 16
10 | Build | System Test Plan v1 | STP_1.0 | Document | CTR | BB 3.2 | 15, 16
10 | Build | Verification and Validation Plan v1 | VVP_1.4 | Document | CTR, SRR | BB 3.2 | 14, 15, 16
10 | Build | Code Test Document | CTD | Presentation | CTR | BB 3.2 | 13, 14, 15, 16
10 | Build | Project Baseline Report v3 | PBR_3.2 | Report | CTR | BB 3.2 | 4
10 | Build | Code Test Review Report | CTRR | Report | SRR | BB 3.3 | 17, 18
10 | Build | Project Baseline Report v3 | PBR_3.3 | Report | None | BB 3.3 | 4
11 | Build | Development Project Plan v3 | DPP_3.x | Document | SRR | BB 3.4 | 13, 14, 15, 16
11 | Build | Integrated Pre-Op Code | PCOD_3.x | Code | SRR | BB 3.4 | 16
11 | Build | System Test Data | PTEST_3.x | Test Data | SRR | BB 3.4 | 14, 15
11 | Build | Internal Users Manual v1 | IUM_1.0 | Document | SRR | BB 3.4 | 14, 16
11 | Build | External Users Manual v1 | EUM_1.0 | Document | SRR | BB 3.4 | 13, 14, 16
11 | Build | Metadata Document v1 | MDD_1.0 | Document | SRR | BB 3.4 | 16
11 | Build | System Test Plan v1 | STP_1.1 | Document | SRR | BB 3.4 | 15, 16
11 | Build | Verification and Validation Report v1 | VVR_1.0 | Report | SRR | BB 3.4 | 13, 14, 15, 16
11 | Build | Algorithm Theoretical Basis Document v2 | ATBD_2.2 | Document | SRR | BB 3.4 | 14, 15
11 | Build | System Readiness Document | SRD | Presentation | SRR | BB 3.4 | 13, 14, 15, 16
11 | Build | Project Baseline Report v3 | PBR_3.4 | Report | SRR | BB 3.4 | 4
11 | Build | System Readiness Review Report | SRRR | Report | Gate 5 | BB 3.5 | 17, 18
11 | Build | Development Project Plan v3 | DPP_3.x | Document | Gate 5 | BB 3.5 | 13, 14, 15, 16
11 | Build | Project Status Report v3 | PSR_3.0 | Report | Gate 5 | BB 3.5 | 13, 14, 15, 16
11 | Build | Gate 5 Document | G5D | Presentation | Gate 5 | BB 3.5 | 13, 14, 15, 16
11 | Build | Project Baseline Report v3 | PBR_3.5 | Report | Gate 5 | BB 3.5 | 4
11 | Build | Gate 5 Review Report | G5RR | Report | Gate 6 | BB 3.6 | 6, 7
11 | Build | Development Project Report | DPR | Report | EPG | BB 3.6 | All
11 | Build | Project Baseline Report v3 | PBR_3.6 | Report | Operations | BB 3.6 | 4
12 | O&M Planning | Operational Project Plan v1 | OPP_v1r0 | Document | Gate 6 | O&M BUILDS
12 | O&M Planning | System Maintenance Manual v1 | SMM_1.0 | Document | Gate 6 | O&M BUILDS
12 | O&M Planning | Operations Procedures v1 | OP_1.0 | Document | Gate 6 | O&M BUILDS
13 | O&M Planning | Operational Code | COD_4.x | Code | Gate 6 | O&M BUILDS
13 | O&M Planning | External Users Manual v1 | EUM_1.2 | Document | Gate 6 | O&M BUILDS
13 | O&M Planning | Project Status Report v4 | PSR_4.0 | Report | Gate 7 | O&M BUILDS
13 | O&M Planning | Project Baseline Report v4 | PBR_4.0 | Report | Gate 6 | O&M BUILDS
13 | O&M Planning | Gate 6 Review Report | G5RR | Report | Operations | O&M BUILDS
13 | O&M Planning | Project Baseline Report v4 | PBR_4.1 | Report | Operations | O&M BUILDS
14 | O&M | Operational Events Log | OEL | Document | Operations | O&M BUILDS
15, 16 | O&M | Maintenance Code | COD_4.x | Code | Operations | O&M BUILDS
15, 16 | O&M | Product Maintenance Report | PMR | Report | Maintenance | O&M BUILDS
17 | O&M | Project Status Report v5 | PSR_5.0 | Report | Gate 7 | O&M BUILDS
17 | O&M | Gate 7 Review Report | G7RR | Report | Retirement | O&M BUILDS

## Stakeholders
STAR EPL - Stakeholders
Stakeholder | Description and Roles | SG
STAR EPG | Responsible for establishing and maintaining the STAR EPL set of standard processes, the process assets, and the process measures. Responsible for ensuring effective implementation of the process throughout the organization. | 1
Steering Committee | Responsible for management oversight of the STAR EPL. Approval authority for any changes to the set of standard processes. | 2
STAR IT | Responsible for the maintenance of IT systems for STAR projects and personnel. | 3
STAR CM/DM | Responsible for establishing and maintaining project baselines for code, test data, documentation, and reports. Works with each Development Lead to ensure that project artifacts are maintained in accordance with STAR standards. Works with Operations CM/DM on the transition of the project baseline from pre-operational development to operations. | 4
STAR Web Developer | Responsible for maintenance of the STAR web pages. Works with STAR CM/DM to ensure that all project baseline items are posted to the appropriate project artifact repository in a timely fashion. Works with the STAR EPG and STAR CM/DM to ensure that all STAR EPL process assets are posted to the Process Asset Repository, and to ensure that all process measures are posted to the STAR Measurement Repository. | 5
STAR QA | Responsible for ensuring that each project's tailored process meets STAR EPL process standards and ensuring that each project meets its process requirements during its pre-operational development phases. | 6
STAR Management | STAR Division Chiefs and Branch Chiefs. Responsible for management oversight of all STAR projects. | 7
Research Lead | Person located at an organization performing basic research and focused R&D. Responsible for leading a group of scientists, programmers, and testers that is working on preparing an algorithm for a STAR Project Proposal. | 8
Research Scientist | Scientists at an organization performing basic research and focused R&D who have been assigned to one or more of the tasks of developing new or improved algorithms, reviewing algorithm development, and preparing project proposals. | 9
Research Tester | Scientists and programmers at an organization performing basic research and focused R&D who have been assigned to one or more of the tasks of identifying test data appropriate to a research algorithm as it is being developed, acquiring and integrating the test data into the research product processing system, creating test plans, executing tests, and analyzing and reporting test results for review. | 10
Research Programmer | Programmers at an organization performing basic research and focused R&D who have been assigned to one or more of the tasks of designing research code, writing research code, and supporting Research Testers in testing research code. | 11
Research Management | Program managers at an organization performing basic research and focused R&D are responsible for oversight of basic research, focused R&D and project proposals for projects initiated by Research Scientists. | 12
Development Lead | Selected by STAR management with assistance from SPSRB as appropriate, the Development Lead enters the product lifecycle process at the Development Planning phase, after the project proposal has been approved. Works with STAR Management to tailor the STAR EPL process to the project. Guides the project's product development efforts during the Design and Build phases as the lead of an Integrated Product Team (IPT). Works with STAR management to identify and allocate necessary computer and people resources. Represents the project at the Gate Reviews and Technical Reviews. Responsible for all project artifacts that are presented at the reviews. | 13
Development Scientist | Scientists who have been assigned to one or more of the tasks of reviewing the technical content of project proposals, maturing a research algorithm into an operational algorithm, developing project requirements, supporting product design, coding and testing, and providing product validation and science maintenance. | 14
Development Tester | Scientists and software developers on the development IPT who have been assigned to one or more of the tasks of identifying pre-operational test data, acquiring and integrating the test data into the pre-operational product processing system, creating pre-operational unit and system test plans, executing unit and system tests, and analyzing and reporting test results for review. | 15
Development Programmer | Programmers on the development IPT who have been assigned to one or more of the tasks of preliminary design and detailed design of pre-operational code, writing pre-operational code, integrating code into a pre-operational system, and supporting Development Testers in testing pre-operational code. | 16
Technical Review Lead | Responsible for leading a Technical Review team. Works with the Development Lead and the Technical Reviewers to ensure that the review is prepared for, conducted, and closed according to review standards. | 17
Technical Reviewer | Responsible for reviewing and approving project status at Technical Reviews. | 18
Operations Lead | Primary oversight of Operations Staff for the planning and oversight of the installation and acceptance testing of code in the operations environment, routine operational production, monitoring and reactive maintenance. | 19
Operations Management | Primary oversight responsibility for projects that are planned for operational production by OSDPD. SPSRB enters the product lifecycle at the research project assessment step, where it is decided whether a project will be developed for OSDPD operations. SPSRB oversees all subsequent steps for projects planned for OSDPD operations. | 20
Integration Programmer | Responsible for the operational installation and acceptance testing of pre-operational software systems, routine operational production, monitoring and reactive maintenance. | 21
Maintenance Programmer | Responsible for monitoring and reactive maintenance of operational software systems. | 22
Operations CM/DM | Operations personnel who have been assigned the task of maintaining a project baseline for code, test data, documentation, and reports during operations and maintenance. Works with STAR CM/DM on the transition of the project baseline from pre-operational development to operations. | 23
Operations QA | Operations personnel who have been assigned the tasks of ensuring that a project meets its process requirements during operations and maintenance, divestiture or retirement. | 24
PUSH User | Users whose identification of an emerging algorithm technology or a new data source has initiated a product development lifecycle. PUSH users develop new or improved algorithms, prepare project proposals, support STAR management and the SPSRB in planning for product development, perform beta testing of pre-operational code, assist in science maintenance of operational code, and support validation of products they have initiated.
PULL User | End users whose identification of a need for an operational product has initiated a product development lifecycle. PULL Users communicate emerging operational needs to Research Scientists, assist in preparing a project proposal, and support validation and maintenance of products intended for their use.

## STAR EPL (Version 1 Model)
Systems Engineering
Primary/Lead Role
SPSRB Primary/Lead Role |  | STAR Enterprise Product Lifecycle
PULL User Primary/Lead Role
Supporting/Review/Approval Role
Conditional Role (Agency is Lead)
Conditional Role (Agency is Lead) |  | GATE 1 |  |  | GATE 2 |  |  |  | GATE 3 |  |  | GATE 4 |  |  | GATE 5 |  |  | GATE 6 | GATE 7 |  |  |  | GATE 8
Phase | ALL | Basic | Exploratory |  |  | Planning for Development |  |  |  | Design Development |  |  | Code Development and Test |  |  | Planning for Operations |  |  | Transition To Operations | Operations and Maintenance |  |  | Divestiture Or Retirement
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Step | ALL | Basic Research | Focused R&D | STAR Research Project Proposal | STAR Research Project Assessment | Resource Identification | Research Project Plan (RPP) | SPSRB Assessment | Research Project Assessment | Project Requirements (& PRR) | Preliminary Design (& PDR) | Critical Design (& CDR) | Code & Test Data Development (& TRR) | Code Testing And Refinement (& CUTR) | Integration And Test | Resource Refinement | Operational Project Plan | Operational Decision | Operational Installation | Operations | Reactive Maintenance | Science Maintenance | Divestiture or Retirement Decision | Divestiture or Retirement
CI Software Developers |  | Basic 1: Develops "throw-away" prototype code for Basic Researchers Process Assets: TG-1.2, TG-12.1.x Artifacts: COD-1.1; Exploratory 2: Develops "research-grade" prototype code Process Assets: TG-2.2, TG-12.1.x Artifacts: COD-2.1; Design Development 10: Develops preliminary software design to be implemented in operational code Process Assets: DG-1.2, TG-10.1 Artifacts: SwA_v2r0; Design Development 11: Develops detailed software design to be implemented in operational code Process Assets: DG-1.2, DG-11.1, DG-11.4, DG-11.5, TG-11.1, TG-14.3 Artifacts: SwA_v2r1, DDD, MDD, ICD; Code Development and Test 12: Develops "pre-operational" code Process Assets: TG-12.1.x Artifacts: COD-12.1; Code Development and Test 13: Completes "pre-operational code development. Tests code and refines code as necessary. Process Assets: DG-13.1, TG-12.1.x, TG-13.1 Artifacts: COD-13.1, UTD; Code Development and Test 14: Integrates pre-operational code into Ops system test environment. Tests integrated code. Process Assets: DG-14.1, TG-14.1, TG-14.2 Artifacts: COD-14.1, SwA_v2r2, TAR; Transition To Operations 18: Supports installation of project on Ops system Process Assets: TG-18.1 Artifacts: COD-18.1; Operations and Maintenance 20: Modifies operational code as needed to sustain operations. Process Assets: TG-12.1.x Artifacts: COD-20.1
CI Management |  | Basic 1: Holds a Gate 1 Review Process Assets: PRG-1.1, T-1.1, TG-1.3 Artifacts: GRR-1.1; Exploratory 4: Supports Gate 2 Review Process Assets: PRG-4.1, T-4.1, TG-4.2 Artifacts:; Planning for Development 5: Identifies CI resources for STAR Research Project Process Assets: DG-5.1, T-5.1, TG-5.1 Artifacts: RIR_v1; Planning for Development 6: If Project Lead is CI, supports Project Lead in preparing STAR Research Project Plan Process Assets: DG-6.1, TG-6.1 Artifacts:; Planning for Development 7: If Project Lead is CI, supports SPSRB assessment as needed Process Assets: T-7.1, TG-7.1 Artifacts:; Planning for Development 8: If Project Lead is CI, supports Gate 3 review/approval. Process Assets: PRG-8.1, T-8.1, TG-8.1 Artifacts:; Design Development 11: If Project Lead is CI, supports Gate 4 review/approval. Process Assets: PRG-11.2, T-11.2, TG-11.5 Artifacts:; Code Development and Test 14: If Project Lead is CI, supports Gate 5 review/approval. Process Assets: PRG-14.1, T-14.1, TG-14.5 Artifacts:; Planning for Operations 17: If Project Lead is CI, supports Gate 6 review. Process Assets: PRG-17.1, T-17.1, TG-17.2 Artifacts:; Divestiture Or Retirement 22: If Project Lead is CI, supports Gate 8 review. Process Assets: DG-22.2, PRG-22.1, T-22.2, TG-22.3 Artifacts: GRR-22.1; Divestiture Or Retirement 23: Accepts transfer of project. Process Assets: TG-23.1 Artifacts:
CI Test |  | Basic 1: Supplies test data that meets Basic Research standards. Process Assets: TG-1.1 Artifacts: TD-1.1; Exploratory 2: Supplies test data that meets Focused R&D standards. Process Assets: TG-2.1 Artifacts: TD-2.1; Design Development 9: Prepares test data requirements for presentation at Requirements Review Process Assets: DG-9.1, TG-9.1 Artifacts: PRD; Code Development and Test 12: Produces test data for testing of "pre-operational" code Process Assets: TG-12.2 Artifacts: TD-12.1, TDD-12.1; Code Development and Test 14: Tests integrated codes. Process Assets: DG-14.1, TG-14.2 Artifacts: TAR
CI Scientists |  | Basic 1: Develops new/improved algorithms. Supports Gate 1 Review. Process Assets: DG-1.1, DG-1.2, PRG-1.1, T-1.1, TG-1.3 Artifacts: ATBD_v1r0, SwA_v1r0; Exploratory 2: Continues algorithm development with operational intent Process Assets: DG-1.1, DG-1.2, T-1.1, TG-2.3 Artifacts: ATBD_v1r1, SwA_v1r1; Exploratory 3: Prepares STAR Research Project Proposal Process Assets: DG-3.1, TG-3.1 Artifacts: RPPr; Exploratory 4: Supports Gate 2 Review Process Assets: PRG-4.1, T-4.1, TG-4.2 Artifacts:; Design Development 9: Prepares project requirements for presentation at Requirements Review Process Assets: DG-1.1, DG-9.1, TG-9.1 Artifacts: ATBD_v2r0, PRD; Design Development 10: Develops preliminary software design to be implemented in operational code Process Assets: DG-1.2, TG-10.1 Artifacts: SwA_v2r0; Design Development 11: Develops detailed software design to be implemented in operational code Process Assets: DG-1.2, DG-11.1, DG-11.4, DG-11.5, TG-11.1, TG-14.3 Artifacts: SwA_v2r1, DDD, MDD, ICD; Code Development and Test 12: Supports production of test data for testing of "pre-operational" code Process Assets: TG-12.2 Artifacts: TD-12.1, TDD-12.1; Code Development and Test 13: Tests code and suggests code refinements as necessary. Process Assets: DG-13.1, TG-12.2, TG-13.1 Artifacts:; Operations and Maintenance 20: Ongoing validation and reactive maintenance. Identifies problems that may require science maintenance. Process Assets: TG-20.2 Artifacts:; Operations and Maintenance 21: Recommends science maintenance as needed to improve quality and/or recover degraded performance. Supports Project Lead in preparation and update of Project Science Maintenance Report as needed. Process Assets: DG-21.1, TG-21.1 Artifacts: PSMR
Operations Staff |  | Code Development and Test 14: Develops operations documentation. Process Assets: DG-11.6, DG-14.2, DG-14.3, TG-14.3 Artifacts: SDD_v1r1, OM, SMM_v1r0; Planning for Operations 16: Supports Operational Project Plan Process Assets: DG-16.1, TG-16.1 Artifacts: OPP; Planning for Operations 17: Supports Gate 6 review presentation. Process Assets: DG-17.1, PRG-17.1, T-17.1, TG-17.2 Artifacts: GRD-17.1; Transition To Operations 18: Installs project on Ops system. Performs acceptance testing of installed code.Prepares Gate 7 review presentation. Process Assets: DG-18.1, PRG-18.1, T-18.1, TG-18.1, TG-18.2, TG-18.4 Artifacts: SMM_v1r1, COD-18.1, GRD-18.1; Operations and Maintenance 19: Performs normal, routine operational production. Process Assets: DG-19.1, TG-19.1 Artifacts: OEL; Operations and Maintenance 20: Monitors operations for problems. Provides reactive maintenance as needed. Refers problems that may require science maintenance to Project Lead. Process Assets: DG-19.1, TG-20.1 Artifacts: OEL; Divestiture Or Retirement 23: Retires project operational baseline or supports transfer of baseline to another agency under CM. Process Assets: TG-23.1 Artifacts:
Operations QA |  | Transition To Operations 18: Maintains project baseline under CM for transfer of pre-operational code to operations. Process Assets: DG-9.2, TG-9.2 Artifacts: ABR v3r0; Operations and Maintenance 19: Maintains project operational baseline under CM. Process Assets: TG-9.2 Artifacts:; Operations and Maintenance 20: Maintains project operational baseline under CM. Updates baseline report as needed. Process Assets: DG-9.2, TG-9.2 Artifacts: ABR v3rx; Divestiture Or Retirement 23: Oversees retirement or transfer under CM of project operational baseline. Prepares final baseline report. Process Assets: DG-9.2, TG-23.1 Artifacts: ABR v4
Project Lead | [6 empty] | Prepares STAR Research Project Plan Process Assets: DG-6.1, TG-6.1 Artifacts: RPP | Supports SPSRB assessment as needed. Process Assets: T-7.1, TG-7.1 Artifacts: | Supports Gate 3 Review. Process Assets: PRG-8.1, T-8.1, TG-8.1 Artifacts: | Prepares project requirements for presentation at Requirements Review Process Assets: DG-9.1, TG-9.1 Artifacts: PRD | Prepares preliminary design for presentation at PDR Process Assets: DG-10.1, PRG-10.1, T-10.1, TG-10.1, TG-10.3 Artifacts: PDD | Prepares critical design for presentation at CDR. Prepares Gate 4 review presentation. Process Assets: DG-11.2, DG-11.4, DG-11.5, DG-11.6, DG-11.7, PRG-11.1, T-11.1, TG-11.1, TG-11.3, TG-14.3 Artifacts: ICD, MDD, SDD_v1r0, CDD, GRD-11.1 | Prepares test readiness for presentation at TRR Process Assets: DG-12.1, PRG-12.1, T-12.1, TG-12.4 Artifacts: TRD | Oversees preparation for Code Unit Test Review Process Assets: DG-13.1, PRG-13.1, T-13.1, TG-13.1 Artifacts: UTD | Oversees development of operations documentation. Prepares Gate 5 review presentation. Process Assets: DG-1.1, DG-11.6, DG-14.1, DG-14.2, DG-14.3, DG-14.4, DG-14.5, PRG-14.1, T-14.1, TG-14.3, TG-14.5 Artifacts: ATBD_v2r2, SwA_v2r2, SDD_v1r1, TAR, OM, SMM_v1r0, UM, GRD-14.1 |  | Prepares Operational Project Plan Process Assets: DG-16.1, TG-16.1 Artifacts: OPP | Prepares Gate 6 review presentation. Process Assets: DG-17.1, PRG-17.1, T-17.1, TG-17.2 Artifacts: GRD-17.1 | Oversees installation of project on Ops system. Oversees preparation of Gate 7 review presentation. Process Assets: DG-18.1, PRG-18.1, T-18.1, TG-18.1, TG-18.4 Artifacts: GRD-18.1 |  | Oversees reactive maintenance. Process Assets: TG-20.1 Artifacts: | Oversees science maintenance issues. Prepares and updates Project Science Maintenance Report as needed. Process Assets: DG-21.1, TG-21.1 Artifacts: PSMR | Submits retirement/divestiture request. Prepares Gare 8 review document. Process Assets: DG-22.1, T-22.1, TG-22.1, TG-22.3 Artifacts: GRD-22.1
SPSRB * | [7 empty] | Decides whether STAR Research Project should be developed by OSDPD Process Assets: T-7.1, TG-7.1 Artifacts: SAR | Supports Gate 3 review/approval. Process Assets: PRG-8.1, T-8.1, TG-8.1 Artifacts: | Conducts a Requirements Review. Process Assets: DG-9.3, PRG-9.1, T-9.1, TG-9.1 Artifacts: PRRR | Conducts a Preliminary Design Review. Process Assets: DG-10.2, PRG-10.1, T-10.1, TG-10.3 Artifacts: PDRR | Conducts a Critical Design Review. Holds Gate 4 Review. Approves Gate 4 Review recommendations. Process Assets: DG-11.8, PRG-11.1, PRG-11.2, T-11.1, T-11.2, TG-11.3, TG-11.5 Artifacts: CDRR. GRR-11.1 | Conducts a Test Readiness Review. Prepares report. Process Assets: DG-12.2, PRG-12.1, T-12.1, TG-12.4 Artifacts: TRRR | Conducts a Code Unit Test Review. Process Assets: DG-13.2, PRG-13.1, T-13.1, TG-13.1 Artifacts: CUTRR | Holds Gate 5 Review. Approves Gate 5 Review recommendations Process Assets: DG-14.6, PRG-14.1, T-14.1, TG-14.5 Artifacts: GRR-14.1 | Identifies resources for Operations and Maintenance. Process Assets: DG-5.1, T-15.1, TG-15.1 Artifacts: RIR v2 |  | Holds Gate 6 Review. Approves Gate 6 Review recommendations Process Assets: DG-17.2, PRG-17.1, T-17.1, TG-17.2 Artifacts: GRR-17.1 | Holds Gate 7 Review. Approves Gate 7 Review recommendations. Process Assets: DG-18.2, PRG-18.1, T-18.1, TG-18.4 Artifacts: GRR-18.1 | Oversees normal, routine operational production. Process Assets: TG-19.1 Artifacts: |  | Assesses Project Science Maintenance Report as needed. Approves science maintenance actions. Process Assets: TG-21.1 Artifacts: | Receives and processes retirement/divestiture requests. Holds Gate 8 Review. Approves Gate 8 Review recommendations Process Assets: DG-22.2, PRG-22.1, T-22.2, TG-22.1, TG-22.3 Artifacts: GRR-22.1 | Updates product database. Process Assets: TG-23.2 Artifacts:
STAR Branch Lead |  | Basic 1: Holds a Gate 1 Review Process Assets: PRG-1.1, T-1.1, TG-1.3 Artifacts: GRR-1.1; Exploratory 4: Holds Gate 2 Review Process Assets: PRG-4.1, T-4.1, TG-4.2 Artifacts: GRR-4.1; Planning for Development 5: Supports STAR Division Chief in identifying STAR resources for STAR Research Project Process Assets: T-5.1, TG-5.1 Artifacts:; Planning for Development 6: If Project Lead is STAR, supports Project Lead in preparing STAR Research Project Plan Process Assets: TG-6.1 Artifacts:; Planning for Development 7: If Project Lead is STAR, supports SPSRB assessment as needed. Process Assets: TG-7.1 Artifacts:; Planning for Development 8: If Project Lead is STAR, supports Gate 3 review/approval. Process Assets: PRG-8.1, T-8.1, TG-8.1 Artifacts:; Design Development 11: If Project Lead is STAR, supports CDR. Process Assets: PRG-11.1, T-11.1, TG-11.3 Artifacts:; Code Development and Test 14: If Project Lead is STAR, supports Gate 5 Review. Process Assets: PRG-14.1, T-14.1, TG-14.5 Artifacts:; Planning for Operations 15: Supports STAR Division Chief in identifying STAR resources for Operations and Maintenance. Process Assets: T-15.1, TG-15.1 Artifacts:; Planning for Operations 16: If Project Lead is STAR, supports Project Lead in preparing Operational Project Plan Process Assets: DG-16.1, TG-16.1 Artifacts: OPP; Planning for Operations 17: If Project Lead is STAR, supports Gate 6 Review. Process Assets: PRG-17.1, T-17.1, TG-17.2 Artifacts:; Operations and Maintenance 21: Reviews Project Science Maintenance Report as needed. Approves or rejects report recommendations. Forwards final report with recommendations to SPSRB. Process Assets: DG-21.1, TG-21.1 Artifacts:; Divestiture Or Retirement 22: If Project Lead is STAR, supports Gate 8 review. Process Assets: DG-22.2, PRG-22.1, T-22.2, TG-22.3 Artifacts: GRR-22.1
STAR Software Developers |  | Basic 1: Develops "throw-away" prototype code for Basic Researchers Process Assets: TG-1.2, TG-12.1.x Artifacts: COD-1.1; Exploratory 2: Develops "research-grade" prototype code Process Assets: TG-2.2, TG-12.1.x Artifacts: COD-2.1; Design Development 10: Develops preliminary software design to be implemented in operational code Process Assets: DG-1.2, TG-10.1 Artifacts: SwA_v2r0; Design Development 11: Develops detailed software design to be implemented in operational code Process Assets: DG-1.2, DG-11.1, DG-11.4, DG-11.5, TG-11.1, TG-14.3 Artifacts: SwA_v2r1, DDD, MDD, ICD; Code Development and Test 12: Develops "pre-operational" code Process Assets: TG-12.1.x Artifacts: COD-12.1; Code Development and Test 13: Completes "pre-operational code development. Tests code and refines code as necessary. Process Assets: DG-13.1, TG-12.1.x, TG-13.1 Artifacts: COD-13.1, UTD; Code Development and Test 14: Integrates pre-operational code into Ops system test environment. Tests integrated code. Process Assets: DG-14.1, TG-14.1, TG-14.2 Artifacts: COD-14.1, SwA_v2r2, TAR; Transition To Operations 18: Supports installation of project on Ops system Process Assets: TG-18.1 Artifacts: COD-18.1; Operations and Maintenance 20: Modifies operational code as needed to sustain operations. Process Assets: TG-12.1.x, TG-20.1 Artifacts: COD-20.1
STAR Division Chief |  | Exploratory 4: Approves Gate 2 Review recommendations Process Assets: T-4.1, TG-4.2 Artifacts:; Planning for Development 5: Identifies STAR resources for STAR Research Project. Selects Project Lead. Process Assets: DG-5.1, T-5.1, TG-5.1 Artifacts: RIR_v1; Planning for Development 8: Holds Gate 3 Review. Approves Gate 3 Review recommendations. If appropriate, selects operational path. Process Assets: PRG-8.1, T-8.1, TG-8.1 Artifacts: GRR-8.1; Code Development and Test 14: Holds Gate 5 Review. Approves Gate 5 Review recommendations Process Assets: DG-14.6, PRG-14.1, T-14.1, TG-14.5 Artifacts: GRR-14.1; Planning for Operations 15: Identifies STAR resources for Operations and Maintenance. Process Assets: DG-5.1, T-15.1, TG-15.1 Artifacts: RIR v2; Planning for Operations 17: Supports Gate 6 Review. Approves Gate 6 Review recommendations Process Assets: DG-17.2, PRG-17.1, T-17.1, TG-17.2 Artifacts: GRR-17.1; Operations and Maintenance 21: Assesses Project Science Maintenance Report as needed. Approves science maintenance actions. Process Assets: TG-21.1 Artifacts:; Divestiture Or Retirement 22: If Project Lead is STAR, supports Gate 8 review. Process Assets: DG-22.1, PRG-22.1, T-22.1, TG-22.3 Artifacts: GRR-22.1
STAR Test |  | Basic 1: Supplies test data that meets Basic Research standards. Process Assets: TG-1.1 Artifacts: TD-1.1; Exploratory 2: Supplies test data that meets Focused R&D standards. Process Assets: TG-2.1 Artifacts: TD-2.1; Design Development 9: Prepares test data requirements for presentation at Requirements Review Process Assets: DG-9.1, TG-9.1 Artifacts: Project Requirements Document; Code Development and Test 12: Produces test data for testing of "pre-operational" code Process Assets: TG-12.2 Artifacts: TD-12.1, TDD-12.1; Code Development and Test 14: Tests integrated codes. Process Assets: DG-14.1, TG-14.2 Artifacts: TAR; Transition To Operations 18: Supports Gate 7 review presentation. Process Assets: DG-18.1, PRG-18.1, T-18.1, TG-18.4 Artifacts: GRD-18.1
STAR QA |  | Design Development 9: Establishes a project baseline under CM for research-grade code, test data, and documentation Process Assets: DG-9.2, TG-9.2 Artifacts: ABR v1r1; Code Development and Test 12: Maintains project baseline under CM for pre-operations code, test data, and documentation Process Assets: DG-9.2, TG-9.2 Artifacts: ABR v2r0; Code Development and Test 13: Maintains project baseline under CM for pre-operations code, test data, and documentation refinements. Process Assets: DG-9.2, TG-9.2 Artifacts: ABR v2r1; Code Development and Test 14: Maintains project baseline under CM for integrated pre-operational code. Process Assets: DG-9.2, TG-9.2 Artifacts: ABR v2r2; Transition To Operations 18: Maintains project baseline under CM for transfer of pre-operational code to operations. Process Assets: DG-9.2, TG-9.2 Artifacts: ABR v3r0
STAR Scientists |  | Basic 1: Develops new/improved algorithms. Supports Gate 1 Review. Process Assets: DG-1.1, DG-1.2, PRG-1.1, T-1.1, TG-1.3 Artifacts: ATBD_v1r0, SwA_v1r0; Exploratory 2: Continues algorithm development with operational intent Process Assets: DG-1.1, DG-1.2, TG-2.3 Artifacts: ATBD_v1r1, SwA_v1r1; Exploratory 3: Prepares STAR Research Project Proposal Process Assets: DG-3.1, TG-3.1 Artifacts: RPPr; Exploratory 4: Supports Gate 2 Review Process Assets: PRG-4.1, T-4.1, TG-4.2 Artifacts:; Design Development 9: Prepares project requirements for presentation at Requirements Review Process Assets: DG-1.1, DG-9.1, TG-9.1 Artifacts: ATBD_v2r0, PRD; Design Development 10: Develops preliminary software design to be implemented in operational code Process Assets: DG-1.2, TG-10.1 Artifacts: SwA_v2r0; Design Development 11: Develops detailed software design to be implemented in operational code Process Assets: DG-1.2, DG-11.1, DG-11.4, DG-11.5, TG-11.1, TG-14.3 Artifacts: SwA_v2r1, DDD, MDD, ICD; Code Development and Test 12: Supports production of test data for testing of "pre-operational" code Process Assets: TG-12.2 Artifacts: TD-12.1, TDD-12.1; Code Development and Test 13: Tests code and suggests code refinements as necessary. Process Assets: DG-13.1, TG-12.2, TG-13.1 Artifacts:; Operations and Maintenance 20: Ongoing validation and reactive maintenance. Identifies problems that may require science maintenance. Process Assets: TG-20.2 Artifacts:; Operations and Maintenance 21: Recommends science maintenance as needed to improve quality and/or recover degraded performance. Supports Project Lead in preparation and update of Project Science Maintenance Report as needed. Process Assets: DG-21.1, TG-21.1 Artifacts: PSMR
STAR Web Developer |  | Exploratory 4: Posts Gate 2 Review Artifacts Process Assets: TG-4.1 Artifacts:; Planning for Development 6: Posts Gate 3 Review Artifacts Process Assets: TG-6.2 Artifacts:; Planning for Development 8: Posts Gate 3 Review Artifacts Process Assets: TG-6.2 Artifacts:; Design Development 9: Posts PRR artifacts Process Assets: TG-9.3 Artifacts:; Design Development 10: Posts PDR artifacts Process Assets: TG-10.2 Artifacts:; Design Development 11: Posts CDR artifacts. Posts Gate 4 Review artifacts. Process Assets: TG-11.4 Artifacts:; Code Development and Test 12: Posts TRR artifacts Process Assets: TG-12.3 Artifacts:; Code Development and Test 13: Posts CUTR artifacts Process Assets: TG-13.2 Artifacts:; Code Development and Test 14: Posts Gate 5 Review artifacts. Process Assets: TG-14.4 Artifacts:; Planning for Operations 17: Posts Gate 6 Review Artifacts Process Assets: TG-17.1 Artifacts:; Transition To Operations 18: Posts Gate 7 Review Artifacts Process Assets: TG-18.3 Artifacts:; Divestiture Or Retirement 22: Posts Gate 8 Review artifacts. Process Assets: TG-22.2 Artifacts:
STAR Systems Engineering | Establishes and maintains STAR Enterprise System Architecture for all steps. Process Assets: SA-1.0 Artifacts: SESA
User (PULL) ** |  | Basic 1: Identifies emerging needs for Basic Research. Communicates these to Basic Researchers. *** Process Assets: Artifacts:; Planning for Development 8: Supports Gate 3 review/approval. Process Assets: PRG-8.1, T-8.1, TG-8.1 Artifacts:; Design Development 11: Supports CDR. Supports Gate 4 review/approval. Process Assets: PRG-11.1, PRG-11.2, T-11.1, T-11.2, TG-11.3, TG-11.5 Artifacts:; Code Development and Test 14: Limited beta testing of integrated pre-operational code. Supports Gate 5 Review. Process Assets: PRG-14.1, T-14.1, TG-14.2, TG-14.5 Artifacts:; Planning for Operations 15: Identifies PULL User resources for Operations and Maintenance. Process Assets: DG-5.1, T-15.1, TG-15.1 Artifacts: RIR v2; Planning for Operations 16: Supports Project Lead in preparing Operational Project Plan Process Assets: DG-16.1, TG-16.1 Artifacts: OPP; Planning for Operations 17: Supports Gate 6 Review. Process Assets: PRG-17.1, T-17.1, TG-17.2 Artifacts:; Transition To Operations 18: Beta testing of operational code. Supports Gate 7 Review. Process Assets: PRG-18.1, T-18.1, TG-18.2, TG-18.4 Artifacts:; Operations and Maintenance 20: Ongoing validation and reactive maintenance. Identifies problems that may require science maintenance. Process Assets: TG-20.2 Artifacts:; Operations and Maintenance 21: Recommends science maintenance as needed. Supports Project Lead in preparation and update of Project Science Maintenance Report as needed. Process Assets: DG-21.1, TG-21.1 Artifacts: PSMR; Divestiture Or Retirement 23: Accepts transfer of project. Process Assets: TG-23.1 Artifacts:
User (PUSH) |  | Develops new/improved algorithms. Supports Gate 1 Review. Process Assets: DG-1.1, DG-1.2, PRG-1.1, T-1.1, TG-1.3, TG-12.1.x Artifacts: ATBD_v1r0, SwA_v1r0, COD-1.1 | Continues algorithm development with operational intent Process Assets: DG-1.1, DG-1.2, TG-2.3, TG-12.1.x Artifacts: ATBD_v1r1, SwA_v1r1, COD-2.1 | Prepares STAR Research Project Proposal Process Assets: DG-3.1, TG-3.1 Artifacts: RPPr | Supports Gate 2 Review Process Assets: PRG-4.1, T-4.1, TG-4.2 Artifacts: | Identifies PUSH User resources for STAR Research Project Process Assets: DG-5.1, T-5.1, TG-5.1 Artifacts: RIR_v1 | If Project Lead is PUSH User, supports Project Lead in preparing STAR Research Project Plan Process Assets: DG-6.1, TG-6.1 Artifacts: | If Project Lead is PUSH User, supports SPSRB Assessment as needed. Process Assets: TG-7.1 Artifacts: | If Project Lead is PUSH User, supports Gate 3 review/approval. Process Assets: PRG-8.1, T-8.1, TG-8.1 Artifacts: |  |  | If Project Lead is PUSH User, supports Gate 4 review. Process Assets: PRG-11.1, T-11.1, TG-11.5 Artifacts: |  |  | If Project Lead is PUSH User, supports Gate 5 review. Process Assets: PRG-14.1, T-14.1, TG-14.5 Artifacts: |  | If Project Lead is PUSH User, supports Project Lead in preparing Operational Project Plan Process Assets: DG-16.1, TG-16.1 Artifacts: OPP | Supports Gate 6 Review. Process Assets: PRG-17.1, T-17.1, TG-17.2 Artifacts: |  |  | Ongoing validation and reactive maintenance. Identifies problems that may require science maintenance. Process Assets: TG-20.2 Artifacts: | Recommends science maintenance as needed. Supports Project Lead in preparation and update of Project Science Maintenance Report as needed. Process Assets: DG-21.1, TG-21.1 Artifacts: PSMR | If Project Lead is PUSH User, supports Gate 8 review. Process Assets: DG-22.2, PRG-22.1, T-22.2, TG-22.3 Artifacts: GRR-22.1 | Accepts transfer of project. Process Assets: TG-23.1 Artifacts:
* SPSRB involvement when STAR projects identify products for OSDPD.
** PULL User involvement when STAR projects identify products for PULL Users. |  | Basic 1: *** THIS IS AN ALTERNATIVE TO A PULL USER REQUEST DIRECTLY TO SPSRB, WHEREBY SOLUTIONS ANALYSIS STEP IS EFFECTIVELY PERFORMED IN THE EXPLORATORY PHASE
Process Assets for Stakeholders |  | Basic 1: STAR website should have a STAR process link with sub-links for each step in the STAR process. Each step should contain the process assets appropriate for the stakeholder tasks contained in that step.
Documentation Guidelines (DG) |  | Basic 1: Guidelines for each document in the STAR documentation subset appropriate for a step. It should include an outline, a brief description of each subsection in the outline, and an Appendix containing an example document.
Peer Review Guidelines (PRG) |  | Basic 1: Guidelines for each Peer Review that is part of the process step. A Peer Review Guideline should describe the purpose of the review, the required artifacts, standards for reviewers, and requirements for approval.
System Architecture (SA) |  | Basic 1: Shows the STAR process flow, highlighting the process steps relevant to the task.
Template (T) |  | Basic 1: A form or checklist that includes all the requirements for a task.
Work Instruction (WI) |  | Basic 1: A description of how to perform a task. It should itemize the actions to be taken. It should contain appropriate standards, conventions, and (where appropriate) examples. It should point to the appropriate process assets and the required artifacts.

## STAR EPL (Version 2.0 Model)
STAR Enterprise Product Lifecycle (EPL) - Version 2.0
Primary/Lead Role
Supporting/Review/Approval Role
|  | GATE 1 |  |  | GATE 2 |  |  |  | GATE 3 |  |  | GATE 4 |  |  |  |  | GATE 5 |  |  |  |  | GATE 6
Phase | ALL | Basic | Exploratory |  |  | Planning for Development |  |  |  | Design Development |  |  | Code Development and Test |  |  | Planning for Operations |  | Operations and Maintenance |  |  |  | Retirement and Divestiture
Step | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| ALL | Basic Research (TG-1.1) | Focused R&D (TG-2.1) | STAR Research Project Proposal (TG-3.1) | STAR Research Proposal Assessment (TG-4.1) | Resource Identification (TG-5.1) | Research Project Planning (TG-6.1) | SPSRB Assessment (TG-7.1) | Research Project Assessment (TG-8.1) | Project Requirements (& PRR) (TG-9.1) | Preliminary Design (& PDR) (TG-10.1) | Detailed Design (& CDR) (TG-11.1) | Code & Test Data Development (& TRR) (TG-12.1) | Code Test And Refinement (& CUTR) (TG-13.1) | Product Integration And Test (& SRR) (TG-14.1) | Operational Resource Identification (TG-15.1) | Operational Planning (TG-16.1) | Operational Installation (TG-17.1) | Operations (TG-18.1) | Reactive Maintenance (TG-19.1) | Science Maintenance (TG-20.1) | Retirement or Divestiture Decision (TG-21.1) | Retirement or Divestiture (TG-22.1)
STAR EPG (SG-0.1) | Establishes and maintains STAR EPL set of standard processes. Process Assets: PG-0.1, PG-0.2 Artifacts: All STAR EPL process assets
Research Lead (SG-1.1) |  | Presents Basic Research algorithm at Gate 1 Review Process Assets: PRG-1.1, CL-1.1, TG-1.1 Artifacts: None |  | Prepares STAR Research Project Proposal Process Assets: DG-3.1, TG-3.1 Artifacts: RPPr | Presents Focused R&D algorithm at Gate 2 Review. Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None
PUSH User (SG-1.2) |  | Develops new/improved algorithms. Supports Gate 1 Review. Process Assets: DG-1.1, DG-1.2, PRG-1.1, CL-1.1, TG-1.1 Artifacts: ATBD_v1r0, SWA_v1r0 | Supports algorithm development with operational intent Process Assets: DG-1.1, DG-1.2, TG-2.1 Artifacts: ATBD_v1r1, SWA_v1r1 |  | Supports presentation at Gate 2 Review. Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None | Identifies PUSH User resources for STAR Research Project Process Assets: TG-5.1 Artifacts: None | Supports Project Lead in preparing STAR Research Project Plan Process Assets: DG-6.1, TG-6.1 Artifacts: RPP_v1r0 | Supports SPSRB Assessment as needed. Process Assets: TG-7.1 Artifacts: None | [13 empty] | Supports Gate 6 review if organization is involved in accepting transfer of the project. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR | Accepts transfer of project. Process Assets: TG-22.1 Artifacts: None
Research Scientist (SG-1.3) |  | Develops and tests new/improved algorithms. Supports Gate 1 Review. Process Assets: DG-1.1, DG-1.2, PRG-1.1, CL-1.1, TG-1.1 Artifacts: ATBD_v1r0, SWA_v1r0 | Continues algorithm development with operational intent Process Assets: DG-1.1, DG-1.2, TG-2.1 Artifacts: ATBD_v1r1, SWA_v1r1 |  | Supports presentation at Gate 2 Review. Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None | [15 empty] | Recommends science maintenance as needed. Supports Operations Lead in update of PMR as needed. Process Assets: DG-19.1, TG-20.1 Artifacts: PMR_v1rx
Research Tester (SG-1.4) |  | Supplies test data that meets Basic Research standards. Process Assets: TG-1.1 Artifacts: TEST_1.1 | Supplies test data that meets Focused R&D standards. Process Assets: TG-2.1 Artifacts: TEST_2.1
Research Programmer (SG-1.5) |  | Develops "throw-away" prototype code for Basic Researchers Process Assets: TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-1.1 Artifacts: CODE_1.1 | Develops "research-grade" prototype code Process Assets: TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-2.1 Artifacts: CODE_2.1
Research Management (SG-1.6) |  | Holds a Gate 1 Review. Writes a Gate 1 Review Report (optional). Process Assets: PRG-1.1, CL-1.1, TG-1.1 Artifacts: G1RR |  |  | Supports Gate 2 Review Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None | Identifies organization resources for STAR Research Project Process Assets: TG-5.1 Artifacts: None | Supports Project Lead in preparing STAR Research Project Plan Process Assets: DG-6.1, TG-6.1 Artifacts: RPP_v1r0 | Supports SPSRB assessment as needed. Process Assets: TG-7.1 Artifacts: None | Supports Gate 3 review and report. Approves organization development resources. Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: G3RR | [12 empty] | Supports Gate 6 review if organization is involved in accepting transfer of the project. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR | Accepts transfer of project. Process Assets: TG-22.1 Artifacts: None
PULL User (SG-1.2) |  | Identifies emerging needs for Basic Research. Communicates these to Basic Researchers. Process Assets: TG-1.1 Artifacts: None | [6 empty] | Supports Gate 3 review/approval Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: G3RR | [10 empty] | Validation of operational products. Identifies problems that may require reactive maintenance. Supports Operations Lead in initiation of the Product Maintenance Report (PMR). Process Assets: TG-19.1 Artifacts: PMR_v1r0 | Recommends science maintenance as needed. Supports Operations Lead in update of PMR as needed. Process Assets: DG-19.1, TG-20.1 Artifacts: PMR_v1rx |  | Accepts transfer of project. Process Assets: TG-22.1 Artifacts: None
STAR Branch Chief (SG-4.1) |  |  |  |  | Leads Gate 2 Review and report. Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: G2RR | Identifies resources for STAR Research Project. Selects Project Lead. Process Assets: TG-5.1 Artifacts: None |  | Supports SPSRB assessment as needed. Process Assets: TG-7.1 Artifacts: None | Leads Gate 3 Review and report. Approves Gate 3 Review recommendations. Process Assets: DG-8.1, PRG-8.1, CL-8.1, TG-8.1 Artifacts: PSR_v1, G3RR | Leads PRR Review team or selects an alternate Review Lead. Process Assets: PRG-9.1, TG-9.1 Artifacts: None | Leads PDR Review team or selects an alternate Review Lead. Process Assets: PRG-10.1, TG-10.1 Artifacts: None | Leads CDR Review team or selects an alternate Review Lead. Prepares Project Status Report version 2. Process Assets: DG-8.1, PRG-11.1, TG-11.1 Artifacts: PSR_v2 | Leads TRR Review team or selects an alternate Review Lead. Process Assets: PRG-12.1, TG-12.1 Artifacts: None | Leads CUTR Review team or selects an alternate Review Lead.. Process Assets: PRG-13.1, TG-13.1 Artifacts: None | Leads SRR Review team or selects an alternate Review Lead.. Process Assets: PRG-14.1, TG-14.1 Artifacts: None | Identifies STAR resources for Operations and Maintenance. Process Assets: TG-15.1 Artifacts: None | Prepares Project Status Report version 3. Supports Gate 5 Review. Process Assets: DG-8.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: PSR_v3 |  |  |  | Reviews and approves science maintenance tasks as needed. Process Assets: TG-20.1 Artifacts: None | Supports Gate 6 review if organization is involved in accepting transfer of the project. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR
STAR Division Chief (SG-4.1) |  |  |  |  | Reviews and approves Gate 2 Review recommendations Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None |  |  |  | Reviews and approves Gate 3 Review recommendations. Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: None |  |  | Leads Gate 4 Review or selects an alternate Review Lead. Approves Gate 4 Review recommendations. Process Assets: PRG-11.2, CL-11.2, TG-11.1 Artifacts: G4RR | [8 empty] | Reviews and approves science maintenance tasks as needed. Process Assets: TG-20.1 Artifacts: None | Supports Gate 6 review if organization is involved in accepting transfer of the project. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR
STAR Web Developer (SG-4.2) |  |  |  |  | Posts Gate 2 Review Artifacts on STAR EPL web portal Process Assets: TG-4.1 Artifacts: None |  | Posts RPP on STAR EPL web portal. Process Assets: TG-6.1 Artifacts: None |  | Posts Gate 3 Review Artifacts on STAR EPL web portal Process Assets: TG-8.1 Artifacts: None | Posts PRR artifacts on STAR EPL web portal Process Assets: TG-9.1 Artifacts: None | Posts PDR artifacts on STAR EPL web portal Process Assets: TG-10.1 Artifacts: None | Posts CDR artifacts and Gate 4 Review artifacts on STAR EPL web portal Process Assets: TG-11.1 Artifacts: None | Posts TRR artifacts on STAR EPL web portal Process Assets: TG-12.1 Artifacts: None | Posts CUTR artifacts on STAR EPL web portal Process Assets: TG-13.1 Artifacts: None | Posts SRR artifacts on STAR EPL web portal Process Assets: TG-14.1 Artifacts: None |  | Posts Gate 5 Review Artifacts on STAR EPL web portal Process Assets: TG-16.1 Artifacts: None
STAR CM/DM (SG-4.3) | [6 empty] | Establishes a project baseline under CM for research-grade code, test data, and documentation. Inserts RPPr in baseline. Inserts RPP in baseline. Initiates Project Baseline Report (PBR). Process Assets: DG-6.2, TG-6.1 Artifacts: PBR_v1r0 |  | Adds Gate 3 Review document to baseline. Updates PBR. Process Assets: DG-6.2, TG-8.1 Artifacts: PBR_v1r1 | Adds PRR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-9.1 Artifacts: PBR_v1r1 | Adds PDR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-10.1 Artifacts: PBR_v1r2 | Adds CDR and Gate 4 artifacts to baseline. Updates PBR for each review. Process Assets: DG-6.2, TG-11.1 Artifacts: PBR_v1r3, PBR_v1r4 | Adds TRR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-12.1 Artifacts: PBR_v2r0 | Adds CUTR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-13.1 Artifacts: PBR_v2r1 | Adds SRR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-14.1 Artifacts: PBR_v2r2 |  | Adds Gate 5 artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-16.1 Artifacts: PBR_v3r0 | Transfers project baseline to Operations. Process Assets: TG-17.1 Artifacts: None
Technical Reviewer (SG-4.4) | [9 empty] | Supports PRR review, approval, and report. Process Assets: DG-9.2, PRG-9.1, CL-9.1, TG-9.1 Artifacts: PRRR | Supports PDR review, approval, and report. Process Assets: DG-10.2, PRG-10.1, CL-10.1, TG-10.1 Artifacts: PDRR | Supports CDR review, approval, and report. Process Assets: DG-11.3, PRG-11.1, CL-11.1, TG-11.1 Artifacts: CDRR | Supports TRR review, approval, and report. Process Assets: DG-12.2, PRG-12.1, CL-12.1, TG-12.1 Artifacts: TRRR | Supports CUTR review, approval, and report. Process Assets: DG-13.2, PRG-13.1, CL-13.1, TG-13.1 Artifacts: CUTRR | Supports SRR review, approval, and report. Process Assets: DG-14.6, PRG-14.1, CL-14.1, TG-14.1 Artifacts: PDRR
STAR QA (SG-4.5) |  |  |  |  | Verifies that Gate 2 Review meets STAR standards. Process Assets: PRG-4.1, CL-4.1 Artifacts: None |  |  |  | Verifies that Gate 3 Review meets STAR standards. Process Assets: PRG-8.1, CL-8.1 Artifacts: None | Verifies that PRR meets STAR standards. Process Assets: PRG-9.1, CL-9.1, TG-9.1 Artifacts: None | Verifies that PDR meets STAR standards. Process Assets: PRG-10.1, CL-10.1, TG-10.1 Artifacts: None | Verifies that CDR and Gate 4 Review meet STAR standards. Process Assets: PRG-11.1, PRG-11.2, CL-11.1, CL-11.2, TG-11.1 Artifacts: None | Verifies that TRR meets STAR standards. Process Assets: PRG-12.1, CL-12.1, TG-12.1 Artifacts: None | Verifies that CUTR meets STAR standards. Process Assets: PRG-13.1, CL-13.1, TG-13.1 Artifacts: None | Verifies that SRR meets STAR standards. Process Assets: PRG-14.1, CL-14.1, TG-14.1 Artifacts: None
STAR Project Lead (SG-6.1) | [6 empty] | Prepares STAR Research Project Plan. Process Assets: DG-6.1, TG-6.1 Artifacts: RPP_v1r0 | Supports SPSRB assessment as needed. Process Assets: TG-7.1 Artifacts: None | Supports Gate 3 Review. Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: None | Leads the preparation of the project requirements for presentation at PRR Process Assets: DG-6.2, DG-9.1, DG-9.1.A, DG-9.3, DG-9.4, DG-9.5, PRG-9.1, CL-9.1, TD-9.1, TG-9.1 Artifacts: PBR_v1r1, PRD, OCD_v1r0, VVP_v1r0, RAD_v1r0 | Leads the preparation of the preliminary design for presentation at PDR Process Assets: DG-1.1, DG-1.2, DG-6.2, DG-9.3, DG-9.4, DG-9.5, DG-10.1, DG-10.1.A, PRG-10.1, CL-10.1, TG-10.1 Artifacts: ATBD_v2r0, SWA_v2r0, PBR_v1r2, OCD_v1r1, VVP_v1r1, RAD_v1r1, PDD | Leads the preparation of the detailed design for presentation at CDR. Prepares Gate 4 review presentation. Process Assets: DG-1.1, DG-1.2, DG-6.1, DG-6.2, DG-9.3, DG-9.4, DG-9.5, DG-11.1, DG-11.2, DG-11.2.A, DG-11.4, DG-11.5, DG-11.6, PRG-11.1, CL-11.1, PRG-11.2, CL-11.2, TG-11.1 Artifacts: ATBD_v2r1, SWA_v2r1, RPP_v2r0, PBR_v1r3, OCD_v1r2, VVP_v1r2, RAD_v1r2, DDD_v2r0, CDD, MDD_v1r0, ICD_v1r0, SDD_v1r0 | Leads the preparation of the pre-operational code, test data, and unit test plan for presentation at TRR. Process Assets: DG-6.2, DG-12.1, DG-12.1.A, DG-12.3, PRG-12.1, CL-12.1, TG-12.1 Artifacts: CODE_12.1, TEST_12.1, PBR_v2r0, TRD, UTP_v1r0 | Leads the preparation of the unit test results and system test plan for presentation at CUTR. Process Assets: DG-6.2, DG-12.3, DG-13.1, DG-13.1.A, DG-13.3, DG-13.4, PRG-13.1, CL-13.1, TG-13.1 Artifacts: CODE_13.1, TEST_13.1, PBR_v2r1, UTP_v1r1, UTD, UTR_v1r0, STP_v1r0 | Leads the preparation of the intergated pre-operational system for presentation at SRR. Process Assets: DG-1.1, DG-6.2, DG-11.4, DG-11.5, DG-11.6, DG-14.1, DG-14.2, DG-14.3, DG-14.4, DG-14.5, DG-14.5.A, PRG-14.1, CL-14.1, TG-14.1 Artifacts: CODE_14.1, TEST_14.1, ATBD_v2r2, PBR_v2r2, MDD_v2r0, ICD_v2r0, SDD_v2r0, VVR_v1r0, OM_v1r0, SMM_v1r0, UM_v1r0, SRD |  | Prepares Project Status Report version 3. Supports Gate 5 Review. Process Assets: DG-8.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: PSR_v3 | Oversees the transition of the system from the development environment to the operations test environment. Leads the preparation of a Research Project Report. Process Assets: DG-17.1, TG-17.1 Artifacts: RPR_v1r0 |  |  | Supports the review of science maintenance issues as needed. Process Assets: TG-20.1 Artifacts: None
Operations Management (SPSRB) (SG-7.1) | [7 empty] | Decides whether operations should be performed by OSDPD. Process Assets: TG-7.1 Artifacts: None | Supports Gate 3 review/approval. Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: None | Supports the PRR by ensuring that operator needs are addressed. Process Assets: PRG-9.1, CL-9.1, TG-9.1 Artifacts: None |  | Supports Gate 4 Review. Process Assets: PRG-11.2, CL-11.2, TG-11.1 Artifacts: G4RR |  |  |  | Identifies resources for Operations and Maintenance. Selects an Operations Lead. Process Assets: TG-15.1 Artifacts: None | Approves operational project plan. Leads Gate 5 Review. Approves Gate 5 Review recommendations Process Assets: DG-16.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: G5RR |  |  |  |  | Receives and processes retirement/divestiture requests. Leads Gate 6 Review. Approves Gate 6 Review recommendations Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR | Oversees update to product database. Process Assets: TG-22.1 Artifacts: None
Technical Review Lead (SG-9.1) | [9 empty] | Leads PRR review, report, and approvals. Process Assets: DG-9.2, PRG-9.1, CL-9.1, TG-9.1 Artifacts: PRRR | Leads PDR review, report, and approvals. Process Assets: DG-10.2, PRG-10.1, CL-10.1, TG-10.1 Artifacts: PDRR | Leads CDR review, report, and approvals. Process Assets: DG-11.3, PRG-11.1, CL-11.1, TG-11.1 Artifacts: CDRR | Leads TRR review, report, and approvals. Process Assets: DG-12.2, PRG-12.1, CL-12.1, TG-12.1 Artifacts: TRRR | Leads CUTR review, report, and approvals. Process Assets: DG-13.2, PRG-13.1, CL-13.1, TG-13.1 Artifacts: CUTRR | Leads SRR review, report, and approvals. Process Assets: DG-14.6, PRG-14.1, CL-14.1, TG-14.1 Artifacts: SRRR
Development Scientist (SG-9.2) | [9 empty] | Prepares algorithm requirements for presentation at PRR Process Assets: DG-9.1, DG-9.1.A, DG-9.3, DG-9.4, DG-9.5, CL-9.1, TD-9.1, TG-9.1 Artifacts: PRD, OCD_v1r0, VVP_v1r0, RAD_v1r0 | Develops preliminary software design to be implemented in "pre-operational" code. Updates ATBD to include preliminary design. Supports prpearation of preliminary design for presentation at PDR. Process Assets: DG-1.1, DG-1.2, DG-9.3, DG-9.4, DG-9.5, DG-10.1, DG-10.1.A, TG-10.1 Artifacts: ATBD_v2r0, SWA_v2r0, OCD_v1r1, VVP_v1r1, RAD_v1r1, PDD | Supports the development of the detailed software design to be implemented in "pre-operational" code. Updates ATBD, SWA, and VVP as needed. Supports preparation of detailed design for presentation at CDR. Process Assets: DG-1.2, DG-9.4, DG-11.2, DG-11.2.A, TG-11.1 Artifacts: ATBD_v2r1, SWA_v2r1, VVP_v1r2, CDD | Supports production of test data for testing of "pre-operational" code. Supports the preparation of the unit test plan for presentation at TRR. Process Assets: DG-12.1, DG-12.1.A, DG-12.3, TG-12.1 Artifacts: TEST-12.1, TRD, UTP_v1r0 | Supports test of "pre-operational" code. Suggests code and unit test refinements as necessary. Supports development of system test plan. Supports presentation at CUTR. Process Assets: DG-12.3, DG-13.1, DG-13.1.A, DG-13.3, DG-13.4, TG-13.1 Artifacts: UTP_v1r1, UTD, UTR_v1r0, STP_v1r0 | Supports system test. Validates user requirements. Develops user documentation. Supports presentation at SRR. Process Assets: DG-14.1, DG-14.4, DG-14.5, DG-14.5.A, TG-14.1 Artifacts: VVR_v1r0, UM_v1r0, SRD |  |  |  |  | Ongoing validation and reactive maintenance. Identifies problems that may require science maintenance. Supports Operations Lead in initiating the PMR. Process Assets: DG-19.1, TG-19.1 Artifacts: PMR_v1r0 | Recommends science maintenance as needed. Supports Operations Lead in update of PMR as needed. Process Assets: DG-19.1, TG-20.1 Artifacts: PMR_v1rx
Development Tester (SG-9.3) | [9 empty] | Prepares test requirements for presentation at PRR. Process Assets: DG-9.1, DG-9.1.A, DG-9.4, DG-9.5, CL-9.1, TD-9.1, TG-9.1 Artifacts: PRD, VVP_v1r0, RAD_v1r0 | Updates the VVP and RAD as needed. Process Assets: DG-9.4, DG-9.5, TD-9.1, TG-10.1 Artifacts: VVP_v1r1, RAD_v1r1 | Updates the VVP and RAD as needed. Process Assets: DG-9.4, DG-9.5, TD-9.1, TG-11.1 Artifacts: VVP_v1r2, RAD_v1r2 | Produces test data for testing of "pre-operational" code. Supports the preparation of the TRR presentation. Process Assets: DG-12.1, DG-12.1.A, DG-12.3, TG-12.1 Artifacts: TEST-12.1, TRD, UTP_v1r0 | Leads unit tests of "pre-operational" code. Refines unit test data. Develops system test data. Supports presentation at CUTR. Process Assets: DG-12.3, DG-13.1, DG-13.1.A, DG-13.3, DG-13.4, TG-13.1 Artifacts: CODE_13.1, TEST-13.1, UTP_v1r1, UTD, UTR_v1r0, STP_v1r0 | Develops system test data. Tests integrated pre-operational system. Supports presentation at SRR. Process Assets: DG-14.1, DG-14.5, DG-14.5.A, TG-14.1 Artifacts: TEST_14.1, VVR_v1r0, SRD |  |  | Supports installation of project on Ops system Process Assets: TG-17.1 Artifacts: TEST_17.1
Development Programmer (SG-10.1) | [10 empty] | Supports the development of the preliminary software design to be implemented in "pre-operational" code Process Assets: DG-1.2, TG-10.1 Artifacts: SWA_v2r0 | Develops detailed software design to be implemented in "pre-operational" code. Supports preparation of detailed design for presentation at CDR. Process Assets: DG-1.2, DG-11.1, DG-11.2, DG-11.2.A, DG-11.4, DG-11.5, DG-11.6, TG-11.1 Artifacts: SWA_v2r1, DDD_v2r0, CDD, MDD_v1r0, ICD_v1r0, SDD_v1r0 | Develops "pre-operational" code and unit test plan for presentation at TRR. Process Assets: DG-12.1, DG-12.1.A, DG-12.3, TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-12.1 Artifacts: CODE_12.1, TRD, UTP_v1r0 | Supports test of "pre-operational" code. Refines "pre-operational" code and unit test plan as necessary. Supports presentation at CUTR. Process Assets: DG-12.3, DG-13.1, DG-13.1.A, DG-13.3, DG-13.4, TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-13.1 Artifacts: CODE_13.1, UTP_v1r1, UTD, UTR_v1r0, STP_v1r0 | Develops operations documentation. Integrates pre-operational code into test environment. Supports test of integrated code. Supports presentation at SRR. Process Assets: DG-11.4, DG-11.5, DG-11.6, DG-14.1, DG-14.2, DG-14.3, DG-14.5, DG-14.5.A, TG-14.1 Artifacts: CODE_14.1, MDD_v2r0, ICD_v2r0, SDD_v2r0, VVR_v1r0, OM_v1r0, SMM_v1r0, SRD |  |  | Supports installation of project on Ops system Process Assets: TG-17.1 Artifacts: CODE_17.1
Operations (SG-14.1) | [16 empty] | Supports operations planning. Prepares presentation for Gate 5 Review. Process Assets: DG-16.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: OPP_v1r0 | Installs project on Ops system. Performs acceptance testing of installed code. Process Assets: TG-17.1 Artifacts: CODE_17.1, TEST_17.1 | Performs normal, routine operational production. Process Assets: DG-18.1, TG-18.1 Artifacts: OEL | Modifies operational code as needed to sustain operations. Process Assets: TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-19.1 Artifacts: CODE_19.1 |  |  | Retires project operational baseline or supports transfer of baseline to another agency under CM. Process Assets: TG-22.1 Artifacts: None
Operations Lead (SG-16.1) | [16 empty] | Leads operations planning. Leads presentation for Gate 5 Review. Process Assets: DG-16.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: OPP_v1r0 | Oversees installation of project on Ops system. Process Assets: TG-17.1 Artifacts: None | Oversees operations. Process Assets: TG-18.1 Artifacts: None | Oversees reactive maintenance. Initiates PMR Process Assets: DG-19.1, TG-19.1 Artifacts: PMR_v1r0 | Oversees science maintenance issues. Updates PMR as needed. Process Assets: DG-19.1, TG-20.1 Artifacts: PMR_v1rx | Submits retirement/divestiture request. Leads preparation of review artifacts for Gate 6 review. Process Assets: DG-8.1, PRG-21.1, CL-21.1, TG-21.1 Artifacts: PSR_v4 | Oversees retirement or transfer under CM of project operational baseline. Process Assets: TG-22.1 Artifacts: None
Operations QA (SG-16.2) | [16 empty] | Ensures that Gate 5 review is conducted according to the standards of the operational organization. Process Assets: TG-16.1 Artifacts: None |  |  |  |  | Ensures that Gate 6 review is conducted according to the standards of the operational organization. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: None
Operations CM/DM (SG-17.1) | [17 empty] | Accepts project baseline from STAR CM/DM. Updates PBR. Process Assets: DG-6.2, TG-17.1 Artifacts: PBR_v3r0 |  | Adds Step 19 artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-19.1 Artifacts: PBR_v3rx | Adds Step 20 artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-20.1 Artifacts: PBR_v3rx | Adds Step 21 artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-21.1 Artifacts: PBR_v3rx | Oversees retirement or transfer under CM of project operational baseline. Prepares final baseline report. Process Assets: DG-6.2, TG-22.1 Artifacts: PBR_v4r0
| <-------- RESEARCH --------> |  |  |  |  | <------------------------- DEVELOPMENT ------------------------> | [9 empty] | <------------------- OPERATIONS ------------------->

## STAR EPL (Version 2.1 Model)
STAR Enterprise Product Lifecycle (EPL) - Version 2.1
Primary/Lead Role
Supporting/Review/Approval Role
|  | GATE 1 |  |  | GATE 2 |  |  |  | GATE 3 |  |  | GATE 4 |  |  |  |  | GATE 5 |  |  |  |  | GATE 6
Phase | ALL | Basic | Exploratory |  |  | Planning for Development |  |  |  | Design Development |  |  | Code Development and Test |  |  | Planning for Operations |  | Operations and Maintenance |  |  |  | Retirement and Divestiture
Step | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| ALL | Basic Research (TG-1.1) | Focused R&D (TG-2.1) | STAR Research Project Proposal (TG-3.1) | STAR Research Proposal Assessment (TG-4.1) | Resource Identification (TG-5.1) | Research Project Planning (TG-6.1) | SPSRB Assessment (TG-7.1) | Research Project Assessment (TG-8.1) | Project Requirements (& PRR) (TG-9.1) | Preliminary Design (& PDR) (TG-10.1) | Detailed Design (& CDR) (TG-11.1) | Code & Test Data Development (& TRR) (TG-12.1) | Code Test And Refinement (& CUTR) (TG-13.1) | Product Integration And Test (& SRR) (TG-14.1) | Operational Resource Identification (TG-15.1) | Operational Planning (TG-16.1) | Operational Installation (TG-17.1) | Operations (TG-18.1) | Reactive Maintenance (TG-19.1) | Science Maintenance (TG-20.1) | Retirement or Divestiture Decision (TG-21.1) | Retirement or Divestiture (TG-22.1)
STAR EPG (SG-0.1) | Establishes and maintains STAR EPL set of standard processes. Process Assets: PG-0.1, PG-0.2 Artifacts: All STAR EPL process assets
Research Lead (SG-1.1) |  | Presents Basic Research algorithm at Gate 1 Review Process Assets: PRG-1.1, CL-1.1, TG-1.1 Artifacts: None |  | Prepares STAR Research Project Proposal Process Assets: DG-3.1, TG-3.1 Artifacts: RPPr | Presents Focused R&D algorithm at Gate 2 Review. Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None
PUSH User (SG-1.2) |  | Develops new/improved algorithms. Supports Gate 1 Review. Process Assets: DG-1.1, DG-1.2, PRG-1.1, CL-1.1, TG-1.1 Artifacts: ATBD_v1r0, SWA_v1r0 | Supports algorithm development with operational intent Process Assets: DG-1.1, DG-1.2, TG-2.1 Artifacts: ATBD_v1r1, SWA_v1r1 |  | Supports presentation at Gate 2 Review. Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None | Identifies PUSH User resources for STAR Research Project Process Assets: TG-5.1 Artifacts: None | Supports Project Lead in preparing STAR Research Project Plan Process Assets: DG-6.1, TG-6.1 Artifacts: RPP_v1r0 | Supports SPSRB Assessment as needed. Process Assets: TG-7.1 Artifacts: None | [13 empty] | Supports Gate 6 review if organization is involved in accepting transfer of the project. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR | Accepts transfer of project. Process Assets: TG-22.1 Artifacts: None
Research Scientist (SG-1.3) |  | Develops and tests new/improved algorithms. Supports Gate 1 Review. Process Assets: DG-1.1, DG-1.2, PRG-1.1, CL-1.1, TG-1.1 Artifacts: ATBD_v1r0, SWA_v1r0 | Continues algorithm development with operational intent Process Assets: DG-1.1, DG-1.2, TG-2.1 Artifacts: ATBD_v1r1, SWA_v1r1 |  | Supports presentation at Gate 2 Review. Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None | [15 empty] | Recommends science maintenance as needed. Supports Operations Lead in update of PMR as needed. Process Assets: DG-19.1, TG-20.1 Artifacts: PMR_v1rx
Research Tester (SG-1.4) |  | Supplies test data that meets Basic Research standards. Process Assets: TG-1.1 Artifacts: TEST_1.1 | Supplies test data that meets Focused R&D standards. Process Assets: TG-2.1 Artifacts: TEST_2.1
Research Programmer (SG-1.5) |  | Develops "throw-away" prototype code for Basic Researchers Process Assets: TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-1.1 Artifacts: CODE_1.1 | Develops "research-grade" prototype code Process Assets: TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-2.1 Artifacts: CODE_2.1
Research Management (SG-1.6) |  | Holds a Gate 1 Review. Writes a Gate 1 Review Report (optional). Process Assets: PRG-1.1, CL-1.1, TG-1.1 Artifacts: G1RR |  |  | Supports Gate 2 Review Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None | Identifies organization resources for STAR Research Project Process Assets: TG-5.1 Artifacts: None | Supports Project Lead in preparing STAR Research Project Plan Process Assets: DG-6.1, TG-6.1 Artifacts: RPP_v1r0 | Supports SPSRB assessment as needed. Process Assets: TG-7.1 Artifacts: None | Supports Gate 3 review and report. Approves organization development resources. Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: G3RR | [12 empty] | Supports Gate 6 review if organization is involved in accepting transfer of the project. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR | Accepts transfer of project. Process Assets: TG-22.1 Artifacts: None
PULL User (SG-1.2) |  | Identifies emerging needs for Basic Research. Communicates these to Basic Researchers. Process Assets: TG-1.1 Artifacts: None | [6 empty] | Supports Gate 3 review/approval Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: G3RR | [10 empty] | Validation of operational products. Identifies problems that may require reactive maintenance. Supports Operations Lead in initiation of the Product Maintenance Report (PMR). Process Assets: TG-19.1 Artifacts: PMR_v1r0 | Recommends science maintenance as needed. Supports Operations Lead in update of PMR as needed. Process Assets: DG-19.1, TG-20.1 Artifacts: PMR_v1rx |  | Accepts transfer of project. Process Assets: TG-22.1 Artifacts: None
STAR Branch Chief (SG-4.1) |  |  |  |  | Leads Gate 2 Review and report. Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: G2RR | Identifies resources for STAR Research Project. Selects Project Lead. Process Assets: TG-5.1 Artifacts: None |  | Supports SPSRB assessment as needed. Process Assets: TG-7.1 Artifacts: None | Leads Gate 3 Review and report. Approves Gate 3 Review recommendations. Process Assets: DG-8.1, PRG-8.1, CL-8.1, TG-8.1 Artifacts: PSR_v1, G3RR | Leads PRR Review team or selects an alternate Review Lead. Process Assets: PRG-9.1, TG-9.1 Artifacts: None | Leads PDR Review team or selects an alternate Review Lead. Process Assets: PRG-10.1, TG-10.1 Artifacts: None | Leads CDR Review team or selects an alternate Review Lead. Prepares Project Status Report version 2. Process Assets: DG-8.1, PRG-11.1, TG-11.1 Artifacts: PSR_v2 | Leads TRR Review team or selects an alternate Review Lead. Process Assets: PRG-12.1, TG-12.1 Artifacts: None | Leads CUTR Review team or selects an alternate Review Lead.. Process Assets: PRG-13.1, TG-13.1 Artifacts: None | Leads SRR Review team or selects an alternate Review Lead.. Process Assets: PRG-14.1, TG-14.1 Artifacts: None | Identifies STAR resources for Operations and Maintenance. Process Assets: TG-15.1 Artifacts: None | Prepares Project Status Report version 3. Supports Gate 5 Review. Process Assets: DG-8.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: PSR_v3 |  |  |  | Reviews and approves science maintenance tasks as needed. Process Assets: TG-20.1 Artifacts: None | Supports Gate 6 review if organization is involved in accepting transfer of the project. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR
STAR Division Chief (SG-4.1) |  |  |  |  | Reviews and approves Gate 2 Review recommendations Process Assets: PRG-4.1, CL-4.1, TG-4.1 Artifacts: None |  |  |  | Reviews and approves Gate 3 Review recommendations. Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: None |  |  | Leads Gate 4 Review or selects an alternate Review Lead. Approves Gate 4 Review recommendations. Process Assets: PRG-11.2, CL-11.2, TG-11.1 Artifacts: G4RR | [8 empty] | Reviews and approves science maintenance tasks as needed. Process Assets: TG-20.1 Artifacts: None | Supports Gate 6 review if organization is involved in accepting transfer of the project. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR
STAR Web Developer (SG-4.2) |  |  |  |  | Posts Gate 2 Review Artifacts on STAR EPL web portal Process Assets: TG-4.1 Artifacts: None |  | Posts RPP on STAR EPL web portal. Process Assets: TG-6.1 Artifacts: None |  | Posts Gate 3 Review Artifacts on STAR EPL web portal Process Assets: TG-8.1 Artifacts: None | Posts PRR artifacts on STAR EPL web portal Process Assets: TG-9.1 Artifacts: None | Posts PDR artifacts on STAR EPL web portal Process Assets: TG-10.1 Artifacts: None | Posts CDR artifacts and Gate 4 Review artifacts on STAR EPL web portal Process Assets: TG-11.1 Artifacts: None | Posts TRR artifacts on STAR EPL web portal Process Assets: TG-12.1 Artifacts: None | Posts CUTR artifacts on STAR EPL web portal Process Assets: TG-13.1 Artifacts: None | Posts SRR artifacts on STAR EPL web portal Process Assets: TG-14.1 Artifacts: None |  | Posts Gate 5 Review Artifacts on STAR EPL web portal Process Assets: TG-16.1 Artifacts: None
STAR CM/DM (SG-4.3) | [6 empty] | Establishes a project baseline under CM for research-grade code, test data, and documentation. Inserts RPPr in baseline. Inserts RPP in baseline. Initiates Project Baseline Report (PBR). Process Assets: DG-6.2, TG-6.1 Artifacts: PBR_v1r0 |  | Adds Gate 3 Review document to baseline. Updates PBR. Process Assets: DG-6.2, TG-8.1 Artifacts: PBR_v1r1 | Adds PRR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-9.1 Artifacts: PBR_v1r1 | Adds PDR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-10.1 Artifacts: PBR_v1r2 | Adds CDR and Gate 4 artifacts to baseline. Updates PBR for each review. Process Assets: DG-6.2, TG-11.1 Artifacts: PBR_v1r3, PBR_v1r4 | Adds TRR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-12.1 Artifacts: PBR_v2r0 | Adds CUTR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-13.1 Artifacts: PBR_v2r1 | Adds SRR artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-14.1 Artifacts: PBR_v2r2 |  | Adds Gate 5 artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-16.1 Artifacts: PBR_v3r0 | Transfers project baseline to Operations. Process Assets: TG-17.1 Artifacts: None
Technical Reviewer (SG-4.4) | [9 empty] | Supports PRR review, approval, and report. Process Assets: DG-9.2, PRG-9.1, CL-9.1, TG-9.1 Artifacts: PRRR | Supports PDR review, approval, and report. Process Assets: DG-10.2, PRG-10.1, CL-10.1, TG-10.1 Artifacts: PDRR | Supports CDR review, approval, and report. Process Assets: DG-11.3, PRG-11.1, CL-11.1, TG-11.1 Artifacts: CDRR | Supports TRR review, approval, and report. Process Assets: DG-12.2, PRG-12.1, CL-12.1, TG-12.1 Artifacts: TRRR | Supports CUTR review, approval, and report. Process Assets: DG-13.2, PRG-13.1, CL-13.1, TG-13.1 Artifacts: CUTRR | Supports SRR review, approval, and report. Process Assets: DG-14.6, PRG-14.1, CL-14.1, TG-14.1 Artifacts: PDRR
STAR QA (SG-4.5) |  |  |  |  | Verifies that Gate 2 Review meets STAR standards. Process Assets: PRG-4.1, CL-4.1 Artifacts: None |  |  |  | Verifies that Gate 3 Review meets STAR standards. Process Assets: PRG-8.1, CL-8.1 Artifacts: None | Verifies that PRR meets STAR standards. Process Assets: PRG-9.1, CL-9.1, TG-9.1 Artifacts: None | Verifies that PDR meets STAR standards. Process Assets: PRG-10.1, CL-10.1, TG-10.1 Artifacts: None | Verifies that CDR and Gate 4 Review meet STAR standards. Process Assets: PRG-11.1, PRG-11.2, CL-11.1, CL-11.2, TG-11.1 Artifacts: None | Verifies that TRR meets STAR standards. Process Assets: PRG-12.1, CL-12.1, TG-12.1 Artifacts: None | Verifies that CUTR meets STAR standards. Process Assets: PRG-13.1, CL-13.1, TG-13.1 Artifacts: None | Verifies that SRR meets STAR standards. Process Assets: PRG-14.1, CL-14.1, TG-14.1 Artifacts: None
STAR Project Lead (SG-6.1) | [6 empty] | Prepares STAR Research Project Plan. Process Assets: DG-6.1, TG-6.1 Artifacts: RPP_v1r0 | Supports SPSRB assessment as needed. Process Assets: TG-7.1 Artifacts: None | Supports Gate 3 Review. Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: None | Leads the preparation of the project requirements for presentation at PRR Process Assets: DG-6.2, DG-9.1, DG-9.1.A, DG-9.3, DG-9.4, DG-9.5, PRG-9.1, CL-9.1, TD-9.1, TG-9.1 Artifacts: PBR_v1r1, PRD, OCD_v1r0, VVP_v1r0, RAD_v1r0 | Leads the preparation of the preliminary design for presentation at PDR Process Assets: DG-1.1, DG-1.2, DG-6.2, DG-9.3, DG-9.4, DG-9.5, DG-10.1, DG-10.1.A, PRG-10.1, CL-10.1, TG-10.1 Artifacts: ATBD_v2r0, SWA_v2r0, PBR_v1r2, OCD_v1r1, VVP_v1r1, RAD_v1r1, PDD | Leads the preparation of the detailed design for presentation at CDR. Prepares Gate 4 review presentation. Process Assets: DG-1.1, DG-1.2, DG-6.1, DG-6.2, DG-9.3, DG-9.4, DG-9.5, DG-11.1, DG-11.2, DG-11.2.A, DG-11.4, DG-11.5, DG-11.6, PRG-11.1, CL-11.1, PRG-11.2, CL-11.2, TG-11.1 Artifacts: ATBD_v2r1, SWA_v2r1, RPP_v2r0, PBR_v1r3, OCD_v1r2, VVP_v1r2, RAD_v1r2, DDD_v2r0, CDD, MDD_v1r0, ICD_v1r0, SDD_v1r0 | Leads the preparation of the pre-operational code, test data, and unit test plan for presentation at TRR. Process Assets: DG-6.2, DG-12.1, DG-12.1.A, DG-12.3, PRG-12.1, CL-12.1, TG-12.1 Artifacts: CODE_12.1, TEST_12.1, PBR_v2r0, TRD, UTP_v1r0 | Leads the preparation of the unit test results and system test plan for presentation at CUTR. Process Assets: DG-6.2, DG-12.3, DG-13.1, DG-13.1.A, DG-13.3, DG-13.4, PRG-13.1, CL-13.1, TG-13.1 Artifacts: CODE_13.1, TEST_13.1, PBR_v2r1, UTP_v1r1, UTD, UTR_v1r0, STP_v1r0 | Leads the preparation of the intergated pre-operational system for presentation at SRR. Process Assets: DG-1.1, DG-6.2, DG-11.4, DG-11.5, DG-11.6, DG-14.1, DG-14.2, DG-14.3, DG-14.4, DG-14.5, DG-14.5.A, PRG-14.1, CL-14.1, TG-14.1 Artifacts: CODE_14.1, TEST_14.1, ATBD_v2r2, PBR_v2r2, MDD_v2r0, ICD_v2r0, SDD_v2r0, VVR_v1r0, OM_v1r0, SMM_v1r0, UM_v1r0, SRD |  | Prepares Project Status Report version 3. Supports Gate 5 Review. Process Assets: DG-8.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: PSR_v3 | Oversees the transition of the system from the development environment to the operations test environment. Leads the preparation of a Research Project Report. Process Assets: DG-17.1, TG-17.1 Artifacts: RPR_v1r0 |  |  | Supports the review of science maintenance issues as needed. Process Assets: TG-20.1 Artifacts: None
Operations Management (SPSRB) (SG-7.1) | [7 empty] | Decides whether operations should be performed by OSDPD. Process Assets: TG-7.1 Artifacts: None | Supports Gate 3 review/approval. Process Assets: PRG-8.1, CL-8.1, TG-8.1 Artifacts: None | Supports the PRR by ensuring that operator needs are addressed. Process Assets: PRG-9.1, CL-9.1, TG-9.1 Artifacts: None |  | Supports Gate 4 Review. Process Assets: PRG-11.2, CL-11.2, TG-11.1 Artifacts: G4RR |  |  |  | Identifies resources for Operations and Maintenance. Selects an Operations Lead. Process Assets: TG-15.1 Artifacts: None | Approves operational project plan. Leads Gate 5 Review. Approves Gate 5 Review recommendations Process Assets: DG-16.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: G5RR |  |  |  |  | Receives and processes retirement/divestiture requests. Leads Gate 6 Review. Approves Gate 6 Review recommendations Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: G6RR | Oversees update to product database. Process Assets: TG-22.1 Artifacts: None
Technical Review Lead (SG-9.1) | [9 empty] | Leads PRR review, report, and approvals. Process Assets: DG-9.2, PRG-9.1, CL-9.1, TG-9.1 Artifacts: PRRR | Leads PDR review, report, and approvals. Process Assets: DG-10.2, PRG-10.1, CL-10.1, TG-10.1 Artifacts: PDRR | Leads CDR review, report, and approvals. Process Assets: DG-11.3, PRG-11.1, CL-11.1, TG-11.1 Artifacts: CDRR | Leads TRR review, report, and approvals. Process Assets: DG-12.2, PRG-12.1, CL-12.1, TG-12.1 Artifacts: TRRR | Leads CUTR review, report, and approvals. Process Assets: DG-13.2, PRG-13.1, CL-13.1, TG-13.1 Artifacts: CUTRR | Leads SRR review, report, and approvals. Process Assets: DG-14.6, PRG-14.1, CL-14.1, TG-14.1 Artifacts: SRRR
Development Scientist (SG-9.2) | [9 empty] | Prepares algorithm requirements for presentation at PRR Process Assets: DG-9.1, DG-9.1.A, DG-9.3, DG-9.4, DG-9.5, CL-9.1, TD-9.1, TG-9.1 Artifacts: PRD, OCD_v1r0, VVP_v1r0, RAD_v1r0 | Develops preliminary software design to be implemented in "pre-operational" code. Updates ATBD to include preliminary design. Supports prpearation of preliminary design for presentation at PDR. Process Assets: DG-1.1, DG-1.2, DG-9.3, DG-9.4, DG-9.5, DG-10.1, DG-10.1.A, TG-10.1 Artifacts: ATBD_v2r0, SWA_v2r0, OCD_v1r1, VVP_v1r1, RAD_v1r1, PDD | Supports the development of the detailed software design to be implemented in "pre-operational" code. Updates ATBD, SWA, and VVP as needed. Supports preparation of detailed design for presentation at CDR. Process Assets: DG-1.2, DG-9.4, DG-11.2, DG-11.2.A, TG-11.1 Artifacts: ATBD_v2r1, SWA_v2r1, VVP_v1r2, CDD | Supports production of test data for testing of "pre-operational" code. Supports the preparation of the unit test plan for presentation at TRR. Process Assets: DG-12.1, DG-12.1.A, DG-12.3, TG-12.1 Artifacts: TEST-12.1, TRD, UTP_v1r0 | Supports test of "pre-operational" code. Suggests code and unit test refinements as necessary. Supports development of system test plan. Supports presentation at CUTR. Process Assets: DG-12.3, DG-13.1, DG-13.1.A, DG-13.3, DG-13.4, TG-13.1 Artifacts: UTP_v1r1, UTD, UTR_v1r0, STP_v1r0 | Supports system test. Validates user requirements. Develops user documentation. Supports presentation at SRR. Process Assets: DG-14.1, DG-14.4, DG-14.5, DG-14.5.A, TG-14.1 Artifacts: VVR_v1r0, UM_v1r0, SRD |  |  |  |  | Ongoing validation and reactive maintenance. Identifies problems that may require science maintenance. Supports Operations Lead in initiating the PMR. Process Assets: DG-19.1, TG-19.1 Artifacts: PMR_v1r0 | Recommends science maintenance as needed. Supports Operations Lead in update of PMR as needed. Process Assets: DG-19.1, TG-20.1 Artifacts: PMR_v1rx
Development Tester (SG-9.3) | [9 empty] | Prepares test requirements for presentation at PRR. Process Assets: DG-9.1, DG-9.1.A, DG-9.4, DG-9.5, CL-9.1, TD-9.1, TG-9.1 Artifacts: PRD, VVP_v1r0, RAD_v1r0 | Updates the VVP and RAD as needed. Process Assets: DG-9.4, DG-9.5, TD-9.1, TG-10.1 Artifacts: VVP_v1r1, RAD_v1r1 | Updates the VVP and RAD as needed. Process Assets: DG-9.4, DG-9.5, TD-9.1, TG-11.1 Artifacts: VVP_v1r2, RAD_v1r2 | Produces test data for testing of "pre-operational" code. Supports the preparation of the TRR presentation. Process Assets: DG-12.1, DG-12.1.A, DG-12.3, TG-12.1 Artifacts: TEST-12.1, TRD, UTP_v1r0 | Leads unit tests of "pre-operational" code. Refines unit test data. Develops system test data. Supports presentation at CUTR. Process Assets: DG-12.3, DG-13.1, DG-13.1.A, DG-13.3, DG-13.4, TG-13.1 Artifacts: CODE_13.1, TEST-13.1, UTP_v1r1, UTD, UTR_v1r0, STP_v1r0 | Develops system test data. Tests integrated pre-operational system. Supports presentation at SRR. Process Assets: DG-14.1, DG-14.5, DG-14.5.A, TG-14.1 Artifacts: TEST_14.1, VVR_v1r0, SRD |  |  | Supports installation of project on Ops system Process Assets: TG-17.1 Artifacts: TEST_17.1
Development Programmer (SG-10.1) | [10 empty] | Supports the development of the preliminary software design to be implemented in "pre-operational" code Process Assets: DG-1.2, TG-10.1 Artifacts: SWA_v2r0 | Develops detailed software design to be implemented in "pre-operational" code. Supports preparation of detailed design for presentation at CDR. Process Assets: DG-1.2, DG-11.1, DG-11.2, DG-11.2.A, DG-11.4, DG-11.5, DG-11.6, TG-11.1 Artifacts: SWA_v2r1, DDD_v2r0, CDD, MDD_v1r0, ICD_v1r0, SDD_v1r0 | Develops "pre-operational" code and unit test plan for presentation at TRR. Process Assets: DG-12.1, DG-12.1.A, DG-12.3, TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-12.1 Artifacts: CODE_12.1, TRD, UTP_v1r0 | Supports test of "pre-operational" code. Refines "pre-operational" code and unit test plan as necessary. Supports presentation at CUTR. Process Assets: DG-12.3, DG-13.1, DG-13.1.A, DG-13.3, DG-13.4, TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-13.1 Artifacts: CODE_13.1, UTP_v1r1, UTD, UTR_v1r0, STP_v1r0 | Develops operations documentation. Integrates pre-operational code into test environment. Supports test of integrated code. Supports presentation at SRR. Process Assets: DG-11.4, DG-11.5, DG-11.6, DG-14.1, DG-14.2, DG-14.3, DG-14.5, DG-14.5.A, TG-14.1 Artifacts: CODE_14.1, MDD_v2r0, ICD_v2r0, SDD_v2r0, VVR_v1r0, OM_v1r0, SMM_v1r0, SRD |  |  | Supports installation of project on Ops system Process Assets: TG-17.1 Artifacts: CODE_17.1
Operations (SG-14.1) | [16 empty] | Supports operations planning. Prepares presentation for Gate 5 Review. Process Assets: DG-16.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: OPP_v1r0 | Installs project on Ops system. Performs acceptance testing of installed code. Process Assets: TG-17.1 Artifacts: CODE_17.1, TEST_17.1 | Performs normal, routine operational production. Process Assets: DG-18.1, TG-18.1 Artifacts: OEL | Modifies operational code as needed to sustain operations. Process Assets: TD-12.1.1, TD-12.1.2, TD-12.1.3, TG-19.1 Artifacts: CODE_19.1 |  |  | Retires project operational baseline or supports transfer of baseline to another agency under CM. Process Assets: TG-22.1 Artifacts: None
Operations Lead (SG-16.1) | [16 empty] | Leads operations planning. Leads presentation for Gate 5 Review. Process Assets: DG-16.1, PRG-16.1, CL-16.1, TG-16.1 Artifacts: OPP_v1r0 | Oversees installation of project on Ops system. Process Assets: TG-17.1 Artifacts: None | Oversees operations. Process Assets: TG-18.1 Artifacts: None | Oversees reactive maintenance. Initiates PMR Process Assets: DG-19.1, TG-19.1 Artifacts: PMR_v1r0 | Oversees science maintenance issues. Updates PMR as needed. Process Assets: DG-19.1, TG-20.1 Artifacts: PMR_v1rx | Submits retirement/divestiture request. Leads preparation of review artifacts for Gate 6 review. Process Assets: DG-8.1, PRG-21.1, CL-21.1, TG-21.1 Artifacts: PSR_v4 | Oversees retirement or transfer under CM of project operational baseline. Process Assets: TG-22.1 Artifacts: None
Operations QA (SG-16.2) | [16 empty] | Ensures that Gate 5 review is conducted according to the standards of the operational organization. Process Assets: TG-16.1 Artifacts: None |  |  |  |  | Ensures that Gate 6 review is conducted according to the standards of the operational organization. Process Assets: PRG-21.1, CL-21.1, TG-21.1 Artifacts: None
Operations CM/DM (SG-17.1) | [17 empty] | Accepts project baseline from STAR CM/DM. Updates PBR. Process Assets: DG-6.2, TG-17.1 Artifacts: PBR_v3r0 |  | Adds Step 19 artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-19.1 Artifacts: PBR_v3rx | Adds Step 20 artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-20.1 Artifacts: PBR_v3rx | Adds Step 21 artifacts to baseline. Updates PBR. Process Assets: DG-6.2, TG-21.1 Artifacts: PBR_v3rx | Oversees retirement or transfer under CM of project operational baseline. Prepares final baseline report. Process Assets: DG-6.2, TG-22.1 Artifacts: PBR_v4r0
| <-------- RESEARCH --------> |  |  |  |  | <------------------------- DEVELOPMENT ------------------------> | [9 empty] | <------------------- OPERATIONS ------------------->