## Chapter 9
Specially Adapted Housing (SAH) Vacant Land and Existing Home Inspections and Construction Plan Reviews

#### Overview

| Introduction | This chapter contains information about Specially Adapted Housing (SAH) vacant land and existing home inspections and construction plan reviews, including: the process for inspection and design Specially Adapted Housing (SAH) vacant land inspections SAH existing home inspections interviews with the architect and/or contractor the cost analysis SAH construction plans the inspection schedule and assignment of a Department of Veterans Affairs (VA) Compliance Inspector, and bid reviews and contract acceptance for SAH cases. |
| --- | --- |

| In this Chapter | This chapter includes the following sections: |
| --- | --- |

| Section | Section Name | See Page |
| --- | --- | --- |
| A | Inspection and Design Process | 9-A-1 |
| B | Specially Adapted Housing (SAH) Vacant Land Inspections | 9-B-1 |
| C | Specially Adapted Housing (SAH) Existing Home Inspections | 9-C-1 |
| D | Interviews with the Architect and/or Contractor | 9-D-1 |
| E | The Cost Analysis | 9-E-1 |
| F | Specially Adapted Housing (SAH) Construction Plans | 9-F-1 |
| G | Specially Adapted Housing (SAH) Inspection Schedule and Assignment of a Department of Veterans Affairs (VA) Compliance Inspector | 9-G-1 |
| H | Bid (Proposal) Reviews and Contract Acceptance for Specially Adapted Housing (SAH) Cases | 9-H-1 |

## Section A
Inspection and Design Process

#### Overview

| Introduction | This section contains information about the inspection and design process. |
| --- | --- |

| In this Section | This section includes the topic “Process for Inspection and Design.” |
| --- | --- |

#### Process for Inspection and Design

| Introduction | This topic contains information about the process for inspection and design. |
| --- | --- |

| Stages of the Inspection and Design Process | This table describes the stages of the inspection and design process. |
| --- | --- |

| Stage | Description |
| --- | --- |
| 1 | The home or site is inspected and feasibility is determined. |
| 2 | The architect and/or contractor are interviewed, and the Department of Veterans Affairs (VA) Builder ID number is assigned. |
| 3 | The construction plans are reviewed with the veteran and contractor. |
| 4 | The bids are reviewed, with the veteran, and a contract is accepted. |
| 5 | The cost analysis is performed. |
| 6 | The inspection schedule is created. |
| 7 | The VA Compliance Inspector (CI) is assigned. |
| 8 | The payment voucher for the CI is prepared. |

## Section B
Specially Adapted Housing (SAH) Vacant Land Inspections

#### Overview

| Introduction | This section contains information about Specially Adapted Housing (SAH) vacant land inspections, including the procedure for inspecting the vacant land. |
| --- | --- |

| In this Section | This section includes the topic “Inspecting the Vacant Land.” |
| --- | --- |

#### Inspecting the Vacant Land

| Introduction | This topic contains information about inspecting vacant land for the Specially Adapted Housing (SAH) Grant, including: the purpose when to perform documenting the findings how to inspect the vacant land, and how to handle the feasibility of the lot. |
| --- | --- |

| Purpose | A SAH vacant land inspection is conducted to determine the feasibility of the land for building a new home. |
| --- | --- |

| When to Perform | Perform the inspection of the vacant land: upon the veteran’s request, or at the time of the initial interview with the veteran. Note: The site inspection must occur prior to grant approval. |
| --- | --- |

| Documenting the Findings | Document all findings from the vacant land inspection. Findings can be documented on VA Form 26-1858, Field Review, or a similar document. |
| --- | --- |

Continued on next page

Inspecting the Vacant Land, Continued

| How to Inspect the Vacant Land | Complete the tasks in the table below to inspect the vacant land. IMPORTANT: Clearly explain all observations and recommendations to the veteran, so that he/she has a clear understanding of the feasibility of the land. |
| --- | --- |

| Task | Description | Rationale |
| --- | --- | --- |
| 1 | Inspect the size and slope of the lot. | The size of the lot must accommodate the necessary improvements. Although the home may sit on a level area, the driveways and walkways should not exceed a slope of 8%. |
| 2 | Determine if the area is in a flood zone, and confirm that the home will not be located in a hazard area by researching available Federal Emergency Management Agency (FEMA) Special Flood Area maps or via the Internet at http://www.fema.gov/ | VA will approve grants for homes built in flood zones. If the new or existing home is in a flood plain, adaptations may be considered. The veteran will provide evidence that he/she purchased flood insurance if the home is in the 100-year flood plain. |
| 3 | Obtain information from local authorities regarding the zoning restrictions for the site or property. | Zoning may affect the type of design of construction, use, or if a residential property can be constructed. |
| 4 | Obtain information about whether or not the property has any homeowner association restrictions. | Some associations may restrict exterior styles of the home if the style is different from the other homes in the area. However, these restrictions are not enforceable under Federal Statute (i.e. Fair Housing Act – 1988) Example: Ramps/carports may not be allowed. |

Continued on next page

Inspecting the Vacant Land, Continued

How to Inspect the Vacant Land (continued)

| Task | Description | Rationale |
| --- | --- | --- |
| 5 | Inspect the vegetation of the site, including any trees on the property. | Lush vegetation can be a sign of high water table. A high water table could restrict: the type of construction, and whether or not a septic system can be installed because a high water table may indicate a potential drainage problem. A dense tree population on the property could cause problems for construction of the foundation and driveway/walkway. Tree removal can also add additional cost to the project. |
| 6 | Consider the area’s amenities, including: emergency (police, fire, etc.) medical facilities transportation (cabs, buses, etc.), and other services. | The area’s amenities increase the veteran’s security and quality of life. It is important that the veteran have unrestricted access to his/her property. Undeveloped roads, unstable surfaces, high water crossings, bridges, etc. can restrict access not only to the veteran, but also to emergency vehicles. |
| 7 | Consider any negative physical and economic conditions of the area. | Excessive deterioration of surrounding properties, streets, and other amenities can indicate: unsafe areas higher crime reduced services, and changing economic conditions. |

Continued on next page

Inspecting the Vacant Land, Continued

| How to Handle the Feasibility of the Lot | To handle the feasibility of the lot: document that the land is or is not feasible on VA Form 26-1858, Field Review, or similar document notify the veteran (by phone or letter) as to whether or not the land is feasible for construction of the SAH home, and document the file by making a copy of the letter, or including a report of the telephone conversation with the veteran, and including pictures of the site. |
| --- | --- |

## Section C
Specially Adapted Housing (SAH) Existing Home Inspections

#### Overview

| Introduction | This section contains information about Specially Adapted Housing (SAH) existing home inspections, including the procedure for performing the inspection. |
| --- | --- |

| In this Section | This section includes the following topics: |
| --- | --- |

| Topic | Topic Name | See Page |
| --- | --- | --- |
| 1 | General Information About Existing Home Inspections | 9-C-2 |
| 2 | Inspecting the Existing Home | 9-C-4 |

#### General Information About Existing Home Inspections

| Introduction | This topic contains information about existing home inspections, including: the purpose considerations for the veteran and the veteran’s family, and veteran’s future needs exterior items to inspect, and interior items to inspect. |
| --- | --- |

| Purpose | An existing home is inspected to verify that all Specially Adapted Housing (SAH) Minimum Property Requirements (MPRs) are present or can feasibly be installed, including additions. |
| --- | --- |

| Considerations for the Veteran and Veteran’s Family | When conducting an inspection of an existing home, be aware of the needs of the veteran and other family members. Common rooms, such as living room, kitchen, and bathrooms, should be designed to accommodate the entire family. |
| --- | --- |

| Considerations for the Future | When conducting an inspection of an existing home, consider whether or not the modifications determined for the house will meet the veteran’s future needs and abilities. Some thought should be given to how the home will accommodate the veteran should his/her condition deteriorate. |
| --- | --- |

| Exterior Items to Inspect | When performing an inspection of the existing home’s exterior, check for acceptability or the feasibility of the installation of the following items: topography of the housing site ramps and handrails doors walkways, and a garage or carport. |
| --- | --- |

Continued on next page

General Information About Existing Home Inspections, Continued

| Interior Items to Inspect | When performing an inspection of the existing home’s interior, the following items are inspected: bathroom(s) doors and windows bedroom(s) hallways flooring kitchen electrical service, heating, and air conditioning, and overall accessibility of the home, especially ingress/egress. Note: The SAH agent should pay particular attention to thresholds throughout the home. |
| --- | --- |

#### Inspecting the Existing Home

| Introduction | This topic contains information about inspecting the existing home for the Specially Adapted Housing (SAH) Grant, including: when to perform documenting the findings how to inspect the exterior of the home, and interior of the home, and how to handle the feasibility of the existing home. |
| --- | --- |

| When to Perform | Perform the inspection of the existing home: on the veteran’s request, or at the time of the initial interview with the veteran. Note: The existing home inspection must occur prior to grant approval. |
| --- | --- |

| Documenting the Findings | Document all findings from the existing home inspection on Department of Veterans Affairs (VA) Form 26-1858, Field Review, or a similar document and include pictures for the grant file. |
| --- | --- |

Continued on next page

Inspecting the Existing Home, Continued

| How to Inspect the Exterior of the Home | Complete the tasks in the table below to inspect the exterior of the existing home. Consideration must be given to the overall physical condition of the home. Extensive deferred maintenance may cause the adaptation of the home to be non-feasible. IMPORTANT: Clearly explain all observations and recommendations to the veteran, so that he/she has a clear understanding of the feasibility of the home. Reference: For more information about inspecting the exterior of the home, see Chapter 7, “Specially Adapted Housing (SAH) Minimum Property Requirements (MPRs).” |
| --- | --- |

| Task | Description | Rationale |
| --- | --- | --- |
| 1 | Inspect the exterior topography of the home site. | Consider if items such as special walkways and additional ramps are: necessary, or feasible to install. The topography should not allow a ramp or driveway to exceed a slope of 8%. |
| 2 | Inspect existing ramps and handrails. | Existing ramps and handrails must comply with SAH Minimum Property Requirements (MPRs). If these items do not comply, they must be corrected to meet the requirements. Restrictions for these improvements may exist. Verify deed, homeowners association restrictions, and local building code requirements to determine if improvements can be made. |
| 3 | Review the means of ingress and egress through exterior doors. | All exterior doorways must be a minimum of 36 inches wide with a maximum threshold height of ½ inch. |
| 4 | Inspect existing walkways. | All existing walkways must be a minimum of 42 inches wide. Note: It is recommended that all sidewalks be widened to 48 inches with no 90° turns without a 5-foot turn radius. |

Continued on next page

Inspecting the Existing Home, Continued

How to Inspect the Exterior of the Home (continued)

| Task | Description | Rationale |
| --- | --- | --- |
| 5 | Inspect the existing garage or carport. | Veterans should have enough free area in the garage or carport to: include a minimum of 5 feet unrestricted, wheelchair maneuverability on at least 1 side of the vehicle(s) accommodate the veteran’s specially equipped vehicle (for example, an 8-foot overhead door height instead of a 7-foot overhead door height, or sufficient room for a wheelchair lift dropdown platform), and accommodate the need for a ramp. |

| How to Inspect the Interior of the Home | Complete the tasks in the table below to inspect the interior of the existing home. IMPORTANT: Clearly explain all observations and recommendations to the veteran, so that he/she has a clear understanding of the feasibility of the home. Reference: For more information about inspecting the interior of the home, see Chapter 7, “Specially Adapted Housing (SAH) Minimum Property Requirements (MPRs).” |
| --- | --- |

| Task | Description | Rationale |
| --- | --- | --- |
| 1 | Inspect the bathroom. | The bathroom must have adequate space to maneuver a wheelchair with placement of all fixtures permitting the veteran unimpeded access. |

Continued on next page

Inspecting the Existing Home, Continued

How to Inspect the Interior of the Home (continued)

| Task | Description | Rationale |
| --- | --- | --- |
| 2 | Inspect all: interior passageway doors, and windows. | Interior doors for homes must be a minimum width of 32 inches. Windows must be accessible from the wheelchair. However, there are instances when a window will not need to be accessible to the veteran. Example: A window above a tub or sink does not need to be accessible to the veteran. |
| 3 | Inspect the bedroom, and consider any items that can accommodate the veteran, such as items that: have been added to the rooms, or need to be added to the room (such as handrails). | The veteran must have complete access to the room, closets, doors, and windows, as well as other items contained in the room. |
| 4 | Inspect all hallways. | Hallways must be a minimum width of 42 inches. |
| 5 | Inspect the type and condition of flooring (tile, vinyl, carpet, and wood). | Thought must be given to the best flooring to allow the veteran mobility throughout the home. No flooring can impede the maneuverability of the veteran in the wheelchair. If carpet is used, it must be low pile and closely woven. The carpet pad must have the ability to withstand constant wheelchair use. |

Continued on next page

Inspecting the Existing Home, Continued

How to Inspect the Interior of the Home (continued)

| Task | Description | Rationale |
| --- | --- | --- |
| 6 | Inspect the kitchen for its working condition and utility to the veteran; Look for opportunities to make the kitchen user-friendly for the veteran; and Identify the remodeling that may be necessary. | The kitchen must have adequate space to maneuver a wheelchair with placement of all fixtures permitting the veteran unimpeded access. |
| 7 | Inspect the home for electrical service, heat, and/or air conditioning. | Electrical service must be adequate for current and future usage. Heat and/or air conditioning must be adequate to meet the veteran’s needs. |
| 8 | Inspect the home to identify any obstacles or obstructions that keep the veteran from accessing rooms. | The veteran must be provided with unimpeded access to the entire home, especially common rooms, including the: family room living room, and kitchen. In some cases, doorways may need to be widened to accommodate the veteran’s wheelchair. |
| 9 | Provide interior sketch of the veteran’s home. | In all cases, interior sketch (including dimensions) must include: interior walls hallway widths door locations doorway widths room identification, and plumbing fixture locations. |

Continued on next page

Inspecting the Existing Home, Continued

| How to Handle the Feasibility of the Existing Home | To handle the feasibility of the existing home: document that the site is or is not feasible on VA Form 26-1858, Field Review, or a similar document notify the veteran (by phone or letter) as to whether or not the existing home is feasible, and document the file by making a copy of the letter, or including a report of the telephone conversation with the veteran. |
| --- | --- |

## Section D
Interviews with the Architect and/or Contractor

#### Overview

| Introduction | This section contains information about interviews with the architect and/or contractor, including: interviewing the architect and/or contractor, and confirming the assignment of the Builder Identification (ID) number. |
| --- | --- |

| In this Section | This section includes the following topics: |
| --- | --- |

| Topic | Topic Name | See Page |
| --- | --- | --- |
| 1 | Interviewing the Architect and/or Contractor | 9-D-2 |
| 2 | Confirming the Assignment of the Department of Veterans Affairs (VA) Builder Identification (ID) Number | 9-D-6 |

#### Interviewing the Architect and/or Contractor

| Introduction | This topic contains information about interviewing the architect and/or contractor, including: the purpose when to perform method of the interview subjects to discuss, and how to interview the architect and/or contractor. |
| --- | --- |

| Purpose | The purpose of conducting a personal interview with the architect and/or contractor selected for the project is to: clarify the role of the Department of Veterans Affairs (VA) in the project clarify the needs of the veteran and how those needs apply to the project establish a relationship with the architect and/or contractor establish requirements and expectations for the project provide a complete understanding of the Grant Program, requirements, adaptations, and procedures allow the architect and/or contractor to ask questions about the Specially Adapted Housing (SAH) Grant Program, and establish a team approach to the adaptive design of the veteran’s home. |
| --- | --- |

| When to Perform | Perform the interview with the architect and/or contractor prior to execution of the construction contract. Reference: For more information about the construction contract, see Chapter 9, Section H, “Bid (Proposal) Reviews and Contract Acceptance for Specially Adapted Housing (SAH) Cases.” |
| --- | --- |

Continued on next page

Interviewing the Architect and/or Contractor, Continued

| Method of the Interview | When meeting with the architect and/or contractor, it is best to conduct a face-to-face interview. A phone interview is acceptable, but must be documented in the grant file. |
| --- | --- |

| Subjects to Discuss | The table below describes the subjects to discuss during the interview with the architect and/or contractor. |
| --- | --- |

| Subject | Reference |
| --- | --- |
| VA’s participation in the project | --- |
| Veteran’s needs, and physical and mental abilities. | See Chapter 8, Section A, “Conducting Veteran Interviews.” |
| Inclusion of Minimum Property Requirements (MPRs) and other planning considerations. | See Chapter 7, “Specially Adapted Housing (SAH) Minimum Property Requirements (MPRs).” |
| Items required on the design or construction plans. | See Chapter 9, Section G, “The Inspection Schedule and Assignment of a Department of Veterans Affairs (VA) Compliance Inspector.” |
| Number of plan sets and exhibits (description of materials, certifications, etc.) to produce. | See Chapter 9, Section F, “General Information About Specially Adapted Housing (SAH) Construction Plans.” |
| Procedure for changes and omissions to plans. | See Chapter 9, Section F, “Handling Changes after Plan Approval.” |
| VA compliance inspections. | See Chapter 13, “Escrows, Escrow Agents, Compliance Inspection Reports and the Authorization of Funds.” |
| Escrow agreement and disbursement schedule. | See Chapter 13, “Escrows, Escrow Agents, Compliance Inspection Reports, and the Authorization of Funds.” |

Continued on next page

Interviewing the Architect and/or Contractor, Continued

Subjects to Discuss (continued)

| Subject | Reference: |
| --- | --- |
| Warranties. | See: local and State warranty requirements VA Form 26-1859, and HUD approved 10-year warranty programs. Note: 3 VA compliance inspections are required regardless of the type of warranty. |

| How to Interview the Architect and/or Contractor | Follow the steps in the table below to conduct the interview with the architect and/or contractor. IMPORTANT: During the initial interview with the architect and/or contractor, take thorough notes, including descriptions of: dimensions materials to be used, and products to be installed. |
| --- | --- |

| Step | Action |
| --- | --- |
| 1 | Conduct preliminary introductions, and provide a brief explanation of the SAH Grant Program and program requirements. |
| 2 | Ask the contractor if he/she has a VA Builder ID number, professional and state license, and if necessary, provide the Builder Participation Forms. |
| 3 | Ask the architect and/or contractor if he/she has questions. |

Continued on next page

Interviewing the Architect and/or Contractor, Continued

How to Interview the Architect and/or Contractor (continued)

| Step | Action |
| --- | --- |
| 4 | Provide the architect and/or contractor with: VA Pamphlet 26-13, The SAH Handbook for Design, to familiarize him/her with the needs required by most disabled veterans, and a list of MPRs. |
| 5 | If the project is a: remodeling project, walk around the home, room-by-room, and discuss the MPRs for each room, or proposed construction project, discuss the MPRs for each room in the home. |
| 6 | Advise the architect and/or contractor that the MPRs must be illustrated on the plans and described in the specification sheet. |
| 7 | Discuss the remaining items in “Subjects to Discuss” earlier in this topic. |
| 8 | Document the interview in the grant file. |

#### Confirming the Assignment of the Department of Veterans Affairs (VA) Builder Identification (ID) Number

| Introduction | This topic contains information about confirming the assignment of the Department of Veterans Affairs (VA) Builder ID number, including: a description the purpose, and how to confirm the assignment of the VA Builder ID number. |
| --- | --- |

| Description | The VA Builder ID number is a 4-digit numeric code which: is assigned by the Regional Loan Center (RLC) is entered into Specially Adapted Housing (SAH)/The Appraisal System (TAS) identifies the contractor, and provides the contractor’s company information. |
| --- | --- |

| Purpose | The VA Builder ID number indicates that the required documents from the contractor have been presented and accepted by the VA office having jurisdiction over the State where the contractor works. |
| --- | --- |

| How to Confirm Assignment of the VA Builder ID Number | Use SAH/TAS to determine if the contractor has a VA Builder ID number. Reference: For more information about determining if the contractor has a VA Builder ID number, see the SAH/TAS Help link in SAH/TAS. |
| --- | --- |

## Section E
The Cost Analysis

#### Overview

| Introduction | This section contains information about the cost analysis, including: general information about the cost analysis, and performing the cost analysis. |
| --- | --- |

| In this Section | This section includes the following topics: |
| --- | --- |

| Topic | Topic Name | See Page |
| --- | --- | --- |
| 1 | General Information About the Cost Analysis | 9-E-2 |
| 2 | Performing the Cost Analysis | 9-E-5 |

#### General Information About the Cost Analysis

| Introduction | This topic contains information about the cost analysis, including: purpose types of costs cost-estimating tools and guides Department of Veterans Affairs (VA) acceptable nationwide resources for cost-estimating resources for product and cost-estimates, and challenges with cost-estimation. |
| --- | --- |

| Purpose | A cost analysis helps to determine if the construction contract is appropriate for the type of project. |
| --- | --- |

| Types of Costs | The types of costs to consider include: material labor overhead job conditions remodeling work, and subcontractors. |
| --- | --- |

| Cost-Estimating Tools and Guides | On-the-job experience provides the best cost-estimating knowledge. However, many cost-estimating tools and guides are available for assistance. However, contractors, architects, and estimators in the construction industry use cost-estimating tools (Marshall & Swift, Boeck’s, etc.) and guides because they provide an accurate means of estimating project costs. |
| --- | --- |

Continued on next page

General Information About the Cost Analysis, Continued

| Acceptable Nationwide Software Application Resource for Cost Estimating | The Marshall & Swift Cost Estimator, a software application, is a cost-estimating tool that can be used by Specially Adapted Housing (SAH) agents in the field. It is available nationwide at http://www.swiftestimator.com/. This resource provides a cost breakdown by: square foot quality, and location. |
| --- | --- |

| Resources for Product and Cost-Estimates | Resources for product and cost-estimates include: builders associations seminars suppliers (retail and wholesale) manufacturers tradesmen contractors, and the Internet. Note: The Internet serves as an excellent source of comparative cost and product information. |
| --- | --- |

Continued on next page

General Information About the Cost Analysis, Continued

| Challenges with Cost-Estimation | Cost-estimating is one of the most difficult parts of the grant process because: every project is different the needs of each veteran are unique conditions under which jobs are performed in the building trades are variable there is a lot of room for interpretation between contractors regarding costs for particular work cost changes occur frequently and are not always consistent with general economic conditions in an area, despite the fact that building costs throughout the United States and Canada are monitored, and remodeling work may involve hidden problems (termite or water damage, structural damage, foundation defects, etc.), resulting in additional costs, and inherent structural and site limitations, providing less flexibility in design and use of materials. IMPORTANT: Regardless of the variables, every effort should be made to provide the veteran with the most accurate cost information. |
| --- | --- |

#### Performing the Cost Analysis

| Introduction | This topic contains information about performing the cost analysis, including: the purpose when to perform contractor’s cost breakdown appraiser’s cost analysis documenting the findings how to perform the cost analysis, and when the cost analysis shows overcharging by a contractor. |
| --- | --- |

| Purpose | The cost analysis assures that the contractor is not overcharging on the project. |
| --- | --- |

| When to Perform | Perform the cost analysis after receiving the: construction contract plans, and specifications. |
| --- | --- |

| Contractor’s Cost Breakdown | The contractor can provide an itemized cost breakdown, in lieu of the cost analysis by the Specially Adapted Housing (SAH) agent, but the cost breakdown must be reviewed and accepted by the Valuation Officer or designee as a justified cost for the project. The itemized cost breakdown must be provided for all remodeling cases. |
| --- | --- |

| Appraiser’s Cost Analysis | The appraiser’s cost analysis is accepted if it is completed by an acceptable cost estimating resource. IMPORTANT: The cost analysis of the Uniform Residential Appraisal Report (URAR) is not acceptable without supporting documentation from a Department of Veterans Affairs (VA) acceptable cost-estimating resource. |
| --- | --- |

Continued on next page

Performing the Cost Analysis, Continued

| Where to Document the Findings | Document the costs on the appropriate form that accompanies the resource used to perform the cost analysis. |
| --- | --- |

| How to Perform the Cost Analysis | Follow the steps in the table below to perform the cost analysis. |
| --- | --- |

| Step | Action |
| --- | --- |
| 1 | Review the plans and specifications for: size quality, and materials. |
| 2 | Use the project specifications to check the cost-estimating resources. |
| 3 | Obtain verification of cost from a specialty supplier for any special equipment. |
| 4 | Document the grant file by including a completed cost estimate. |

| When the Cost Analysis Shows Overcharging by a Contractor | When the cost analysis shows significant overcharging by a contractor: notify the veteran by letter file a copy of the letter to the grant file, and obtain a written statement from the veteran acknowledging the disparity acknowledging if he/she wants to continue with the project, and verifying the source of funds (loan, savings, etc.) beyond the maximum grant amount. |
| --- | --- |

## Section F
Specially Adapted Housing (SAH) Construction Plans

#### Overview

| Introduction | This section contains information about Specially Adapted Housing (SAH) construction plans, including: general information about SAH construction plans building code requirements obtaining the SAH construction plans and required certifications VA Form 26-1852, Description of Materials plot and foundation plans floor and wall plans exterior and interior elevation plans other required SAH exhibits and certifications reviewing the SAH construction plans for new construction cases reviewing the SAH construction plans for remodeling cases, and handling plan inaccuracies, changes, and omissions. |
| --- | --- |

| In this Section | This section includes the following topics: |
| --- | --- |

| Topic | Topic Name | See Page |
| --- | --- | --- |
| 1 | General Information About Specially Adapted Housing (SAH) Construction Plans | 9-F-2 |
| 2 | Building Code Requirements | 9-F-5 |
| 3 | Obtaining the SAH Construction Plans and Required Certifications | 9-F-6 |
| 4 | VA Form 26-1852, Description of Materials | 9-F-7 |
| 5 | Plot and Foundation Plans | 9-F-8 |
| 6 | Floor and Wall Plans | 9-F-10 |
| 7 | Exterior and Interior Elevation Plans | 9-F-11 |
| 8 | Other Required SAH Exhibits and Certifications | 9-F-13 |
| 9 | Reviewing the SAH Construction Plans for Proposed Construction and Remodeling | 9-F-15 |
| 10 | Handling Changes After Plan Approval | 9-F-17 |

#### General Information About Specially Adapted Housing (SAH) Construction Plans

| Introduction | This topic contains information about Specially Adapted Housing (SAH) construction plan requirements, including: an important note when plans are drawn number of copies recipients, and components of the plans. |
| --- | --- |

| IMPORTANT | Never assume that all parties know what is to be built and included, regardless of any verbal assurances. Unless specified in writing, work is not required to be completed or installed; therefore, documentation is critical. |
| --- | --- |

| When Plans Are Drawn | The architect and/or contractor draws up a set of construction plans after: reviewing VA Pamphlet 26-13 Handbook for Design SAH agent and the architect and/or contractor have discussed how the Minimum Property Requirements (MPRs) will be met, and other planning considerations, and architect and/or contractor have gathered all the needed information. |
| --- | --- |

| Number of Copies | For cases that involve proposed construction or room additions, four plan sets are required. If the veteran has a Department of Veterans Affairs (VA) home loan, a fifth set is required for VA. Exception: The fifth set of plans is not required for veterans with conventional home loans. |
| --- | --- |

Continued on next page

General Information About Specially Adapted Housing (SAH) Construction Plans, Continued

| Recipients | The following individuals should receive a copy of the plans: SAH agent contractor veteran, and VA-assigned Compliance Inspector (CI). Note: The SAH agent’s set of the approved plans is filed in the grant file. Reference: For more information about the requirement for filing one set of plans in the grant file, see M26-9: “Quality Control Procedures, Loan Guaranty Operations.” |
| --- | --- |

| Components of the Plans | The table below lists the components that need to be included when the architect and/or contractor draws up a set of construction plans. |
| --- | --- |

| Component | Reference |
| --- | --- |
| VA Form 26-1852, Description of Materials | See “VA Form 26-1852, Description of Materials” later in this section. |
| Plot and Foundation plans | See “Plot and Foundation Plans” later in this section. |
| Floor levels/floor plans | See “Floor and Wall Plans” later in this section. |
| Wall detail | See “Floor and Wall Plans” later in this section. |
| Interior/exterior elevations | See “Exterior and Interior Elevation Plans” later in this section. |
| Other required exhibits and certifications | See “Other Required SAH Exhibits and Certifications” later in this section. |

Notes: For remodeling cases, with a proposed addition, all items above are required. If only remodeling is involved, then the floor plan where the veteran will reside, must be submitted. The layout and dimensions of all rooms of the existing floor plan must be submitted, along with another set showing the adaptations that are to be completed.

Continued on next page

General Information About Specially Adapted Housing (SAH) Construction Plans, Continued

| Changes to Plans and Specifications | The SAH agent must inform the veteran and contractor that changes to plans and specifications cannot be made without prior approval of the SAH agent. Reference: For information on handling changes after plan approval, see “Handling Changes after Plan Approval” later in this section. |
| --- | --- |

#### Building Code Requirements

| Introduction | This topic contains information about building code requirements. |
| --- | --- |

| Building Code Requirements | If the property is located in a jurisdiction which enforces a State, county or local building code, then Department of Veterans Affairs (VA) Minimum Property Requirements (MPRs) require that the construction comply with: the applicable State, county or local building codes 24 Code of Federal Regulations (CFR) 200.926d, Construction Requirements 1992 Council of American Building Officials (CABO) Model Energy Code (MEC), and HUD engineering bulletins and materials. If the property is located in a jurisdiction which does not enforce a State, county, or local building code, then VA MPRs require that the construction comply with: applicable provisions of the current 1995 CABO, 1998 International, One and Two Family Dwelling Code, and any mandatory codes or standards incorporated by reference 24 CFR 200.926d, Construction Requirements 24 CFR 200.926e, Supplemental Information for Use with 1995 CABO One and Two Family Dwelling Code 1992 CABO Model Energy Code (MEC), and HUD engineering bulletins and materials. |
| --- | --- |

#### Obtaining the SAH Construction Plans and Required Certifications

| Introduction | This topic contains information about obtaining the construction plans and required certifications, including: the purpose when to perform, and how to obtain construction plans and required certifications. |
| --- | --- |

| Purpose | The purpose of obtaining the construction plans and required certifications is to define the project. |
| --- | --- |

| When to Perform | Review the construction plans and required certifications upon receipt. |
| --- | --- |

| How to Obtain Construction Plans and Required Certifications | The table below lists the plans and certifications that need to be requested from the contractor for both proposed construction and remodeling cases as applicable. |
| --- | --- |

| Plan/Certifications | Reference |
| --- | --- |
| VA Form 26-1852 | See “VA Form 26-1852, Description of Materials” later in this section. |
| Plot and Foundation plans | See “Plot and Foundation Plans” later in this section. |
| Floor levels/floor plans | See “Floor and Wall Plans” later in this section. |
| Wall detail | See “Floor and Wall Plans” later in this section. |
| Exterior/interior elevations | See “Exterior and Interior Elevation Plans” later in this section. |
| Other required exhibits and certifications | See “Other Required SAH Exhibits and Certifications” later in this section. |

#### VA Form 26-1852, Description of Materials

| Introduction | This topic contains information about VA Form 26-1852, Description of Materials, including: formats. |
| --- | --- |

| Formats | Specially Adapted Housing (SAH) agents use VA Form 26-1852 (HUD Form 920005) to document the description of materials. VA Form 26-1852 must be fully completed and have the original signatures of the veteran and the contractor on the form filed in the grant folder. Other specification formats are acceptable, provided that they are signed and dated by the contractor and veteran as described above, and are specifically detailed for SAH, appraisal, and compliance inspection purposes. |
| --- | --- |

#### Plot and Foundation Plans

| Introduction | This topic contains information about the plot and foundation plans, including: plot plan requirements sea level heights foundation plan requirements, and a reference. |
| --- | --- |

| Plot Plan Requirements | A plot plan should illustrate where the following items will be located: the proposed house or addition sidewalks driveways outbuildings drainage other improvements, and well and/or septic systems, if applicable. |
| --- | --- |

| Sea Level Heights | It is preferable that the plot plan show the grade elevations of finished grade at the: foundation proposed finished floor height, and four corners of the site. Note: If the site is large, grade elevations of the site should be identified 30 feet from the four corners of the foundation. |
| --- | --- |

Continued on next page

Plot and Foundation Plans, Continued

| Foundation Plan Requirements | Foundation plans should include the dimensions and materials used for: footings walls slab, and support piers. |
| --- | --- |

| Reference | For more information about plot plans and foundation plans, see Chapter 7, “Specially Adapted Housing (SAH) Minimum Property Requirements (MPRs).” |
| --- | --- |

#### Floor and Wall Plans

| Introduction | This topic contains information about floor and wall plans, including: wall plan requirements floor plan requirements, and a reference. |
| --- | --- |

| Wall Plan Requirements | The wall plan should illustrate the sectional wall cross detail, including the: window sill and window hardware heights electrical outlet and switch heights, and design of the proposed construction from the foundation footing upward to the roof ridge. |
| --- | --- |

| Floor Plan Requirements | Floor plans should illustrate the design and layout of: all levels, including dimensions of the home garage or carport dimensions heating and cooling layout electrical layout size and location of doors and windows, and room and hallway dimensions. IMPORTANT: In most cases, the flooring samples will not be available at the time of the plan approval, but make a notation on the plan indicating that flooring should not be installed until samples or acceptable descriptions of materials are submitted and approved by the Department of Veterans Affairs (VA). |
| --- | --- |

| Reference | For more information about floor and wall plans, see Chapter 7, “Specially Adapted Housing (SAH) Minimum Property Requirements (MPRs).” |
| --- | --- |

#### Exterior and Interior Elevation Plans

| Introduction | This topic contains information about exterior and interior elevation plans, including: exterior elevation requirements interior elevation requirements bathroom requirements kitchen requirements, and a reference. |
| --- | --- |

| Exterior Elevation Requirements | Exterior elevations on all four sides of the house should be shown, including: front back right, and left. |
| --- | --- |

| Interior Elevation Requirements | Interior elevations of cabinets and fixtures for every room in the house should be shown, paying particular attention to: bathrooms the kitchen, and closet and storage areas, including the location and height of closet rods and shelving. |
| --- | --- |

Continued on next page

Exterior and Interior Elevation Plans, Continued

| Bathroom Requirements | Interior elevation details for the bathroom should be shown, including details for the: shower, including grab bar mounting locations water control locations bathtubs, including transfer platform grab bar mounting locations, and water control locations toilet, including grab bar mounting locations mirrors (tilted or lowered), and cabinet details for sink/vanity, including knee spaces, and plumbing. |
| --- | --- |

| Kitchen Requirements | Interior elevations for the kitchen should be shown, including details for the: cabinet and counter heights sink basin workspaces, and appliance locations. Note: Free standing stove/oven combinations must be located at the end of the counter space for easy and safe access to a person using a wheelchair. |
| --- | --- |

| Reference | For more information about exterior and interior elevation plans, see Chapter 7, “Specially Adapted Housing (SAH) Minimum Property Requirements (MPRs).” |
| --- | --- |

#### Other Required SAH Exhibits and Certifications

| Introduction | This topic contains information about other required Specially Adapted Housing (SAH) exhibits and certifications, including: electrical specifications heating and air conditioning specifications floor samples special equipment specifications, and the VA Builder Certification. |
| --- | --- |

| Electrical Specifications | Plans should illustrate the electrical layout and detail. The following items should be located so they are easily accessed by a person using a wheelchair: electrical service panel switches outlets, and thermostats. |
| --- | --- |

| Heating and Air Conditioning Specifications | Plans should illustrate the heating and air conditioning layout and detail. |
| --- | --- |

| Floor Samples | Include floor samples of carpet, carpet pad, ceramic, vinyl, and wood, or acceptable descriptions of the materials. |
| --- | --- |

| Special Equipment Specifications | Plans should illustrate details for the installation of any special equipment (automatic door openers, fold-down benches, trapeze, etc.). |
| --- | --- |

Continued on next page

Other Required SAH Exhibits and Certifications, Continued

| VA Builder Certification | The VA Builder Certification should be: signed and dated by a technically qualified and properly identified individual (such as the contractor, architect, engineer, etc.), and contain the following language, indicating that the home meets code requirements and is free of hazardous material: “I certify that the construction exhibits for (identification of the property by house type, lot, lock, subdivision name, and so on) meet all local code requirements and are in substantial conformity with both SAH and VA Minimum Property Requirements, and all building standards as required by VA.” Note: The Department of Veterans Affairs (VA) accepts HUD Form 92541, Builder’s Certification of Plans, Specification, and Site, in lieu of the certification. |
| --- | --- |

#### Reviewing the SAH Construction Plans for Proposed Construction and Remodeling

| Introduction | This topic contains information about reviewing the plans for proposed construction and remodeling cases, including: the purpose when to perform, and how to review the plans. |
| --- | --- |

| Purpose | The purpose of reviewing the plans for proposed construction and remodeling is to assure the house meets Minimum Property Requirements (MPRs). |
| --- | --- |

| When to Perform | Review the construction plans upon receipt. |
| --- | --- |

| How to Review Plans for Remodeling | Review the floor plan of the existing house, layout, and dimensions of all rooms, and compare with the floor plan showing the proposed adaptive changes that are to be completed. Note: For new additions, review the plans in the manner required for proposed construction. |
| --- | --- |

Continued on next page

Reviewing the SAH Construction Plans for Proposed Construction and Remodeling, Continued

| How to Review the Plans for Proposed Construction | Follow the steps in the table below to review the plans for proposed construction cases. |
| --- | --- |

| Step | Action |
| --- | --- |
| 1 | Verify that the plans contain the exhibits and certifications necessary for the proposed construction. |
| 2 | Verify that the plans, specifications, and associated exhibits adhere to the MPRs, and that the work contained in the contract matches the plans and specifications. Note: If plans are: acceptable continue processing for grant approval, and file a copy of the approved plans, specifications, and associated exhibits in the grant file. not acceptable, write a letter to the contractor and veteran specifying the necessary revisions. |

#### Handling Changes after Plan Approval

| Introduction | This topic contains information about handling changes after plan approval, including: the purpose when to perform requirements to authorize changes, and how to handle changes after plan approval. |
| --- | --- |

| Purpose | The purpose of this procedure is to ensure that: the changes are acceptable, and no Minimum Property Requirement (MPR) item is removed. |
| --- | --- |

| When to Perform | Perform this procedure upon notification of changes to the plans and specifications. |
| --- | --- |

| Requirements to Authorize Changes | Changes can only be authorized: upon receipt of VA Form 26-1844, Request for Acceptance of Changes in Approved Drawings and Specifications, which specifically itemizes the changes, cost of changes, and signed by the veteran, contractor, and lender (if applicable), or written notification specifically itemizing the changes, costs of changes, and signed by the veteran, contractor, and lender (if applicable), and if no MPRs are changed. Note: Copies of the changes, whether approved or denied, must be retained in the grant file. |
| --- | --- |

Continued on next page

Handling Changes after Plan Approval, Continued

| How to Handle Changes after Plan Approval | To handle changes after plan approval: accept or deny the changes by signing: VA Form 26-1844 indicating the decision, or the change order request, indicating acceptance or denial, and notify the following individuals of the findings: contractor veteran lender (if applicable), and Department of Veterans Affairs (VA)-assigned Compliance Inspector (CI). IMPORTANT: Any adjustment in costs of 5percent or more must be approved by the Valuation Officer, or designee. |
| --- | --- |

## Section G
Specially Adapted Housing (SAH) Inspection Schedule and Assignment of a Department of Veterans Affairs (VA) Compliance Inspector

#### Overview

| Introduction | This section contains information about Specially Adapted Housing (SAH) inspection schedules and assignment of a Department of Veterans Affairs (VA) Compliance Inspector (CI), including: general information about inspection schedules assigning the VA CI, and final field review. |
| --- | --- |

| In this Section | This section includes the following topics: |
| --- | --- |

| Topic | Topic Name | See Page |
| --- | --- | --- |
| 1 | General Information About Inspection Schedules | 9-G-2 |
| 2 | Assigning the Department of Veterans Affairs (VA) Compliance Inspector | 9-G-4 |
| 3 | Final Field Review | 9-G-6 |

#### General Information About Inspection Schedules

| Introduction | This topic contains information about creating the inspection schedule, including: the purpose when to perform a description of standard number of inspections, and how to determine the number of required inspections. |
| --- | --- |

| Purpose | The purpose of creating the inspection schedule is to notify the Department of Veterans Affairs (VA) Compliance Inspector (CI) of the number of inspections required for a project. |
| --- | --- |

| When to Perform | Create the inspection schedule before construction starts. |
| --- | --- |

| Description of the Minimum Number of Inspections | The minimum number of inspections for proposed construction is three. The three inspections include the: first inspection when the foundations walls are complete and ready for backfill second inspection when the building is enclosed, including rough-ins (electrical, heating, and plumbing) third inspection when the building and landscape is complete. Note: The number of inspections may increase depending on the project. |
| --- | --- |

Continued on next page

General Information About Inspection Schedules, Continued

| How to Determine the Number of Required Inspections | Use the table below to determine the number of required VA compliance inspections. |
| --- | --- |

| If the case involves … | Then the number of required VA compliance inspections is … |
| --- | --- |
| proposed construction | a minimum of 3. |
| remodeling job that includes an addition | a minimum of 3. |
| remodeling job that does not include an addition | 3 or less depending on the complexity of the project. |

#### Assigning the Department of Veterans Affairs (VA) Compliance Inspector

| Introduction | This topic contains information about assigning the Department of Veterans Affairs (VA) Compliance Inspector (CI), including: the selection of the VA CI SAH/TAS Letter #16 (FL 26-638), Inspector Assignment Letter documents sent with the SAH/TAS Letter #16 (FL 26-638) when the assigned VA CI is unavailable areas without a VA CI, and payment vouchers. |
| --- | --- |

| Selection of the VA Compliance Inspector | Select the VA CI from Specially Adapted Housing (SAH)/The Appraisal System (TAS). |
| --- | --- |

| The SAH/TAS Letter #16 (FL 26-638), Inspector Assignment Letter | The SAH/TAS Letter #16 (FL 26-638), Inspector Assignment Letter: is used to assign the VA CI, and includes important information, such as the amount to be paid for the inspections number of inspections name of the veteran location of the project, and voucher with an obligation number. Note: The obligation number is assigned in accordance with Regional Loan Center (RLC) procedures. |
| --- | --- |

| Documents Sent with SAH/TAS Letter #16 (FL 26-638) | The following documents are sent with SAH/TAS Letter #16 (FL 26-638): the approved plans, and the specifications. |
| --- | --- |

Continued on next page

Assigning the Department of Veterans Affairs (VA) Compliance Inspector, Continued

| When the Assigned VA-Approved Compliance Inspector Is Unavailable | If a VA CI has been assigned, but is unavailable at the time of request for the inspection, the following individuals may conduct the inspection: another VA CI SAH agent, or other qualified VA staff personnel. IMPORTANT: Compliance inspections must be performed by a designated fee compliance inspector. Compliance inspections may be made by qualified salaried personnel only when designated fee compliance inspectors are not immediately available. The Loan Guaranty Officer must notify the Chief of Specially Adapted Housing, Central Office, prior to the use of an individual other than a designated fee compliance inspector. |
| --- | --- |

| Areas without VA Compliance Inspectors | In areas without VA CIs, qualified, salaried personnel may perform compliance inspections. Requirements: The Loan Guaranty Officer (LGO) must approve the use of a contracted inspector for a project. The SAH agent must document the grant file or obtain evidence documenting the need for assignment of the inspector on the project. |
| --- | --- |

| Payment Vouchers | Upon receipt of a completed voucher from the CI, the voucher is: certified by an LGO-designated individual, and processed for payment through finance activity. |
| --- | --- |
| SAH Agent Responsibilities | IMPORTANT: SAH agent should conduct follow-up reviews for both quality of construction and performance of the inspector. |

#### Final Field Review

| Introduction | This topic contains information about the Final Field Review, including: the purpose who can perform when to perform, and requirements. |
| --- | --- |

| Purpose | The purpose of the Final Field Review is to ensure that the Specially Adapted Housing (SAH) Minimum Property Requirements (MPRs) are met prior to the release of the holdback funds. |
| --- | --- |

| Who Can Perform | The Final Field Review must be conducted by: the SAH agent Regional Loan Center (RLC) management staff, or any other qualified Department of Veterans Affairs (VA) personnel, as determined by the Loan Guaranty Officer (LGO). |
| --- | --- |

| When to Perform | The Final Field Review must be completed within 15 work days of the receipt of the VA Form 26-1839, Compliance Inspection Report, from the Compliance Inspector (CI). |
| --- | --- |

| Requirements | The Final Field Review must: be completed using VA Form 26-1858 format, found in SAH/The Appraisal System (TAS) under SAH/Letters, or other locally developed narrative report format evidence that all work is in conformity with SAH MPRs and VA approved plans and specifications, and includes all special adaptive features, as required include digital photographs of the subject property (including a minimum of front, rear, and interior of veteran’s bedroom, bathroom, and all other design adaptations) be reviewed and approved by RLC management prior to the final release of grant funds, and be included in the Final Accounting package sent to Central Office (CO). |
| --- | --- |

## Section H
Bid (Proposal) Reviews and Contract Acceptance for
Specially Adapted Housing (SAH) Cases

#### Overview

| Introduction | This section contains information about bids (proposals) reviews and contract acceptance for Specially Adapted Housing (SAH) cases, including: construction/remodeling bids (proposals) for SAH cases construction contracts, and components of the construction contract. |
| --- | --- |

| In this Section | This section includes the following topics: |
| --- | --- |

| Topic | Topic Name | See Page |
| --- | --- | --- |
| 1 | General Information About Construction/ Remodeling Bids (Proposals) and Lien and Performance Bonds for Specially Adapted Housing (SAH) Cases | 9-H-2 |
| 2 | General Information About the Construction Contract | 9-H-4 |
| 3 | Components of the Construction Contract | 9-H-6 |

#### General Information About Construction/Remodeling Bids (Proposals) and Lien and Performance Bonds for Specially Adapted Housing (SAH) Cases

| Introduction | This topic contains information about construction/remodeling bids (proposals) for Specially Adapted Housing (SAH) cases, including: a description the purpose three-bid (proposal) requirement lien and performance bond requirement waivers, and updating SAH/The Appraisal System (TAS). |
| --- | --- |

| Description | The construction/remodeling bid is a proposal specifying the project and cost. |
| --- | --- |

| Purpose | The construction/remodeling bid (proposal) provides the veteran with an estimate for the cost of the project. |
| --- | --- |

| Bid (Proposal) Requirement | A veteran must obtain three competitive bids (proposals) for SAH cases that: include fixed, maximum prices are from contractors of the veteran’s choice, and specifically relate to the proposed construction or remodeling. |
| --- | --- |
| Lien and Performance Bond Requirement | A veteran must obtain a lien and performance bond from the contractor for all SAH cases to: provide insurance coverage in the event the builder is unable to complete the project or places liens against the property provide the necessary funds to allow completion of the project, and give the veteran protection against any loss that could occur. |

Continued on next page

General Information About Construction/Remodeling Bids (Proposals) and Lien and Performance Bonds for Specially Adapted Housing (SAH) Cases, Continued

| Waivers | Waivers apply when: a veteran feels it is a burden to obtain 3 bids (proposals) it is impractical to require additional bids (proposals), or a lien and performance bond may be economically burdensome. Reference: For more information about waivers, see Chapter 11, Section B, “Processing Medical and Non-Medical Waiver Requests.” |
| --- | --- |

| Who Waives the Requirement | The Loan Guaranty Officer (LGO), or designee, may waive the requirement on a case-by-case basis upon submission of a written request by the veteran. IMPORTANT: SAH agents are not allowed to waive requests. |
| --- | --- |

| Updating SAH/The Appraisal System (TAS) | The SAH/TAS must be updated to show the receipt of the: three bids (proposals), or waivers. |
| --- | --- |

#### General Information About the Construction Contract

| Introduction | This topic contains information about the construction contract, including: the purpose required components of the contract land contracts amendments to the signed contract, and filing the contract. |
| --- | --- |

| Purpose | The purpose of a fixed contract is to: clearly state the scope of the work and the total cost protect the veteran against increases in labor and material and other influences require the contractor to complete the project in a timely manner, and protect the veteran from incurring additional costs above and beyond the original contract. |
| --- | --- |

| Required Components of the Contract | The fixed contract should include the following components: parties to the contract a legal description of the property a reference to a specific plan and specifications terms and cost of the project a Department of Veterans Affairs (VA) Central Office (CO)-approved escape clause completion date, and signatures and signature dates from all parties. Reference: For more information about the required components of the contract, see “Components of the Construction Contract” later in this section. |
| --- | --- |

Continued on next page

General Information About the Construction Contract, Continued

| Land Contracts | Land contracts have the same components as the construction contract listed previously. However, the completion date is replaced with a settlement date. |
| --- | --- |

| Amendments to the Signed Contract | The VA must review any amendments to the signed contract. IMPORTANT: If the amendments exceed the contract price, it must be determined that the veteran has the ability to pay the difference prior to approval of the changes. |
| --- | --- |

| Filing the Contract | A copy of the contract, signed by all parties, must be retained in the grant file. |
| --- | --- |

#### Components of the Construction Contract

| Introduction | This topic contains information about the components of the construction contract, including: parties to the contract legal description of the property a reference to a specific plan and specifications terms and cost of the contract escape clause the completion date, and signatures and signature dates from all parties. |
| --- | --- |

| Legal Description of the Property | The contract must include the legal description of the property identifying the location of the property. |
| --- | --- |

| Reference to a Specific Plan and Specifications | The contract must include a reference to a specific plan and specifications identifying the project for construction or remodeling. |
| --- | --- |

| Terms and Cost | The contract must include the terms and the total amount of the project so that the terms and the cost of the project are defined and cannot be changed without amendments signed by all parties. |
| --- | --- |

| Escape clause | The contract must include an escape clause with the following statement, exactly as shown below: “This contract is conditioned in its entirety upon the veteran receiving a grant under Title 38 U.S.C. Chapter 21 and if this veteran does not receive this grant, this contract is null and void and any and all monies will be returned without exception.” |
| --- | --- |

| Completion Date | The contract must provide the completion date of the project. Note: The completion date may change due to conditions beyond control of the parties. |
| --- | --- |