U.S. Department of Transportation

Federal Highway Administration

January 2001

Office of Freight Management and Operations

# EXECUTIVE SUMMARY

The Federal Highway Administration's (FHWA) Office of Freight Management and Operations initiated this study to examine the relationship between freight facilities and the environment. More specifically, the focus of the study is how the environmental review process affects the development or expansion of intermodal freight facilities. Law mandates consideration of both human and natural environmental resources where there is federal involvement in transportation improvements. This involvement can include permitting, loan guarantees, direct federal aid and other activities requiring a "federal action" and apply to public as well as private sector sponsors. The degree that environmental laws are understood, acknowledged, and complied with can affect project schedules, design, and costs.

FHWA employed a case study methodology. Projects were reviewed across the nation for all modes of transportation. FHWA’s interests included both projects that had encountered delays as well as those that had successfully completed the environmental review process in a timely manner. The eight selected projects included: one rail/highway facility in Waterville, Maine; four rail/highway/port facilities in Oakland, California, Sears Island/Mack Point, Maine, West Hayden Island, Portland, Oregon, and the FAST Corridor in the Seattle/Tacoma area; and two port/rail facilities in the Long Beach Naval Yard, Long Beach, California and the Alameda Corridor, Los Angeles, California.

The types of intermodal projects captured in this sample were determined largely by whether a federal agency had a funding, approval, or permitting role. The water side of port improvement projects most frequently requires National Environmental Policy Act (NEP A) reviews in the form of Environmental Impact Statements and Environmental Assessment due to the Army Corps of Engineers (COE) permitting requirements and expenditures of the Harbor Maintenance Tax for capital improvements, such as dredging. FHW A becomes involved with port improvements through land side access projects including: new access into and out of ports for federal-aid highways, rail/highway grade separations at ports, and installation of Intelligent Transportation System (ITS) technology to improve the efficiency of port-highway interfaces. Inland rail/highway intermodal facilities are mostly owned by railroads and are not as likely to require federal permits and funding, and therefore tend not to trigger NEP A reviews (in the past).

The FHWA evaluated the environmental issues associated with the selected projects and the project's level of success in the environmental review process. The findings are based on data that is restricted to what could be obtained through interviews with a variety of participants on the different projects. The total number of intermodal freight transportation projects currently underway in the United States is unknown. Therefore, this is not a statistical sample of all port, rail, highway, and airport facilities. The information represents a first look at environmental issues affecting development of intermodal freight transportation facilities. Environmental factors identified from the case studies as issues associated with intermodal facility development include, but may not be limited to:

- Air quality,

- Cultural resources,

- Land use compatibility,

- Local transportation,

- Natural resources,

- Noise/vibration,

- Hazardous waste,

- Socioeconomics,

  - Environmental Justice

- Water quality

Initial observations that can be drawn from the information reviewed include, but are not limited to the following:

- Intermodal freight transportation projects, depending on federal funds or permits, frequently involve a variety of federal agencies as reviewers or that could that could be directly affected (port improvements and landside access issues).

- Clear communications and early involvement of federal and state agencies are critical to the successful completion of environmental analysis for projects (time, money spent, design of project, etc.)

- Conflicts between state and federal environmental requirements can cause delays on projects but can be overcome with early recognition of issues and agreements among agencies on how to proceed.

- Consideration of environmental resources (including avoidance and minimization of impacts through site selection and design) early in the planning and project design phases can result in simplified environmental review and avoidance of costly delays in project schedules.

- Early coordination with public interests on intermodal freight projects can lead to resolving concerns before they become a problem.

- NEPA streamlining through improved agency consultation may be difficult to achieve on many projects if the regulatory agencies do not have adequate resources to engage in early consultation.

- When questions or disagreements arise over the assumptions behind a project's purpose and need, and alternatives, regulatory agencies do not always have the resources to independently verify cargo projections, market analyses, and facility land use needs.

- Port dredging, land side development, and land side access projects are sometimes covered by separate NEP A documents because funding is not always available to cover all three types of activity simultaneously and because different agencies take the lead on these projects. On a related note, there does not appear to be any regional or national guidance or policies for project sponsor agencies and regulatory agencies to follow when considering the funding, permitting, and environmental review of projects in separate political or planning jurisdictions that compete in the same freight markets.

Additional efforts in this area of environmental review might include the following next steps:

- Further research including more case studies and a better understanding of the numbers of projects that exist to confirm the preliminary conclusions discussed above.

- Further research into how FHW A Division staff considers a project's purpose and need, and alternatives when it is a cooperating or review agency.

- Further research into how other reviewing agencies (e.g., Environmental Protection Agency, U.S Fish and Wildlife Service, National Marine Fisheries Service, and State Historic Preservation Officers) consider a project's purpose and need and develop alternatives.

- Exploring opportunities for multi-agency project sponsorship and agreements among agencies regarding cooperation on intermodal projects (e.g., COE and FHW A on port improvements and landside access as well as Federal Railroad Administration and U.S. Coast Guard when appropriate}.

Table of Contents

Page

SECTION 1.0	INTRODUCTION	1-1

Definitions	1-2

Environmental Considerations in Planning Intermodal Facilities	1-2

Environmental Issues as an Opportunity to Advance Intermodal Projects	1-2

Environmental Impacts as a Potential Source of Delay and/or an Obstacle	1-2

Structure of the report	1-3

SECTION 2.0	METHODOLOGY	2-1

Project Selection	2-1

Initial Project Evaluation and Investigation	2-2

Implementation of Case Studies	2-3

Preparation of Case Study Summaries	2-3

SECTION 3.0	EVALUATION	3-1

Overview	3-1

Summary of Selected Projects	3-1

Environmental Issues	3-5

Level of Success in the Environmental Review Process	3-7

SECTION 4	CONCLUSIONS AND RECOMMENDATIONS	4-1

Conclusions	4-1

Recommendations	4-2

APPENDIX A - INTERMODAL PROJECTS CONSIDERED FOR DEVELOPMENT AS CASE STUDIES	A-1

Part I – Projects advanced as case studies	A-1

Part II – Projects strongly considered but not advanced as case studies	A-3

Part III – Projects initially considered, but not advanced as worthy of consideration as case studies	A-5

APPENDIX B -- INTERMODAL FACILITY DESCRIPTIVE MATRIX	B-1

APPENDIX C -- SELECTION AND EVALUATION CRITERIA	C-1

Phase One Selection Criteria	C-1

Initial Screening Questions for Projects	C-1

APPENDIX D  -- INTERVIEW QUESTIONS FOR SELECTED PROJECTS	D-1

APPENDIX E	-- SELECTED INTERMODAL PROJECTS	E-1

List of Acronyms

ACHP		Advisory Council on Historic Preservation

COE		Army Corps of Engineers

EA		Environmental Assessment

EIS		Environmental Impact Statement

FHWA		Federal Highway Administration

NEPA		National Environmental Policy Act

NHS		National Highway System

NMFS		National Marine Fisheries

SHPO		State Historic Preservation Office

FWS		U.S. Fish and Wildlife Service

# SECTION 1.0	INTRODUCTION

The Office of Freight Management and Operations within the Operations Core Business Unit (CBU) of the Federal Highway Administration (FHWA) was created in January 1999.  The Office focuses on freight issues within FHWA to fulfill both the U.S. DOT and FHWA strategic plans to “…advance America’s economic growth and competitiveness…”. The Operations CBU is charged with “optimizing performance” of the transportation network.  A “roadmap” was designed for the Freight Office to provide a structure for achieving the goals and objectives of the agency regarding freight transportation.  The “roadmap outlines six cross cutting issues in freight transportation which are:  environment, planning, finance, economic benefits, freight performance measures, and intermodal freight analysis/decision framework.  Each of the six items is important to understanding and developing a freight transportation system.

Environmental issues, relating to intermodal freight transportation facilities are the focus of this study.  The purpose is three fold: 1) to develop an understanding of how these facilities affect environmental resources, 2) how, and what, environmental resources affect the development of intermodal freight facilities, and 3) understanding how projects are implemented given the environmental regulations and agency review process.

Consideration of environmental resources, both human and natural, is mandated by law where there is federal involvement in transportation improvements.  This involvement can include permitting, loan guarantees, direct federal aid and other activities requiring a “federal action” and apply to public as well as private sector sponsors.  State and local laws may also require the consideration of a variety of environmental resources before a transportation project can advance regardless of the sponsoring entity involved.  The degree that environmental laws are understood, acknowledged, and complied with can affect project schedules, design, and costs.

This report identifies a number of environmental constraints affecting the development and expansion of intermodal freight facilities.  These constraints include:  facilities that enhance the movement of freight between modes, including rail yards with highway connections, ports with rail and highway connections, and airports with highway and rail connections.  The report is one of several ongoing studies by the FHWA related to intermodal freight transportation.  Selected intermodal projects are presented in this report that reflect environmental issues raised during project planning and advancement, and highlights where environmental issues:

- Provided a rationale for particular solutions;

- Affected Schedules;

- Affected costs (positively or negatively); or

- Affected the viability of a proposed action.

The sample of intermodal projects illustrates the environmental issues facing agencies, authorities, and private sector entities engaged in advancing freight transportation improvements.

The report includes evaluations of some of the causes of delays and cost increases (e.g., the agency review process, presence or absence of a structured approach to environmental analysis, and public involvement).

## Definitions

An intermodal facility is a site where freight is conveyed from one mode of freight transportation to another.  Examples include water/port to rail or highway movements, and truck/rail interfaces.

Intermodalism received national attention with the 1991 Intermodal Surface Transportation Efficiency Act (ISTEA). With new language under the Transportation Equity Act for the 21st Century (TEA-21), expenditures from federal sources for the development or improvement of intermodal freight facilities are likely to increase.  A number of state initiatives have been undertaken, including legislation in California and Virginia, to facilitate private development of what had previously been thought of as public infrastructure. These federal, state, and private sector initiatives also hold the potential for raising environmental concerns related to freight transport.

## Environmental Considerations in Planning Intermodal Facilities

Planning new or expanded intermodal facilities can require evaluating a broad range of potential environmental and related social impacts.  Planning for federally aided facilities requires funding applications, and coordination and review among local, state, and federal transportation agencies as well as environmental review agencies.  Under the implementing regulations for the National Environmental Policy Act (NEPA), a federal agency must prepare or oversee the preparation of an environmental impact statement (EIS) if the proposed action could result in a significant environmental impact.  Federal agencies prepare or oversee the preparation of an environmental assessment (EA) to determine whether to prepare an EIS or a Finding of No Significant Impact (FONSI).  NEPA requires sponsoring agencies to consult with other agencies, involve the public, and have a review period for EISs and some EAs.  The environmental review process encompasses other federal regulations as well, including the National Historic Preservation Act, the Endangered Species Act, the Clean Water Act, Title VI of the Civil Rights Act, the Executive Order on Environmental Justice, and the Uniform Relocation and Assistance Act.

The attention paid to the environmental impacts of potential intermodal facilities is both an opportunity to advance many projects, and a potential source of delay and/or an obstacle to construction.

## Environmental Issues as an Opportunity to Advance Intermodal Projects

The transportation industry has embraced intermodalism because it is efficient. That efficiency can produce substantial environmental benefits, and thus, can aid intermodal facility development.  For example, facilities that help decrease congestion can reduce emissions of concern locally, regionally, nationally, and internationally.  That emissions reduction qualifies such facilities for funding from the Congestion Mitigation and Air Quality (CMAQ) program of the U.S. Department of Transportation.  Several intermodal facilities have taken advantage of that eligibility, and we profile one, in Waterville, Maine.

## Environmental Impacts as a Potential Source of Delay and/or an Obstacle

The Process of identifying environmental resources and assessing the impacts of freight transportation facility projects on those resources can be a source of delay or an obstacle to a project in two ways.  First, procedurally.  Both federally and non-federally aided projects must comply with environmental regulations pertaining to wetlands, endangered species, local zoning processes, and construction permits.  Agencies may encounter delays in the preparation of an EIS or EA when they cannot achieve internal agreement on the proposed action or on methodologies for characterizing specific resources and impacts.  Such delays may occur even in the absence of substantial environmental concerns, although concerns clearly make a delay more likely.  Because agency consultation requires time, promptly initiating consultation is important and can minimize adverse impacts to a project schedule.  Although proper integration of environmental considerations into the planning process cannot ensure a smooth agency consultation and public involvement process, it greatly increases the likelihood.  This approach can also produce benefits to the environment as well.  Second, substantively.  Environmental review may discover, quantify, or otherwise raise environmental impacts that are of serious concern.  Issues, especially with noise and land use compatibility, may arise apart from any formal evaluation process.

Many environmental concerns can be addressed through avoidance of resources during planning and design, and in some cases project redesign can not only reduce impacts, but also add benefits. Whether a concern is raised and addressed early in the planning process often determines whether or not the concern delays (or ultimately prevents) the project and affects the cost.  Not anticipating a concern and planning for it early in the planning stages can add months to a project schedule and possibly result in project cancellation.  Effective planning includes early consideration of potential environmental issues while the project proponent is still in a position to alter the project design if necessary, and early consultation with the public and agencies having regulatory jurisdiction.  Early consideration of potential environmental impacts improves the likelihood that impacts can be avoided, minimized, or mitigated and in the best case, environmental benefits can be produced.

## Structure of the report

Section 2 of this report addresses the methodology; Section 3 describes the results of the analysis; and Section 4 presents summary and observations.  The appendices contain a list of intermodal projects considered for development as case studies, an intermodal facility descriptive matrix, selection and evaluation criteria, interview questions for selected projects, and further information on each of the selected intermodal projects.

# SECTION 2.0	METHODOLOGY

FHWA employed a case study methodology to examine the ways that the environmental review process and environmental factors can affect the development and expansion of intermodal facilities.  Projects were reviewed across the nation for all modes of transportation.  FHWA’s interests include both projects that had encountered delays as well as those that had succeed in getting through the environmental review process in a timely or expeditious manner.  An attempt was also made to identify additional success stories where the environmental review process or environmental factors worked to the advantage of the project’s funding, timing, or scope.

## Project Selection

The project team began by reviewing available intermodal project lists and conducting a brainstorming session to generate an initial list of projects for consideration.  A table and listing indicating the universe of projects that were considered is included in Appendix A.  To narrow the list of projects for further study, FHWA applied two screening phases.  The first phase involved a set of minimum requirements, including:

- Needing either federal funding or a federal permit;

- Having a clear relationship to intermodal freight terminals and/or operations;

- Being far enough into the planning and development process that the project proponents and reviewing agencies were able to discuss the potential or actual impacts, the level of public concern, and any issues associated with agency consultation/permitting; and

- Having the potential to affect (either negatively or positively) environmental resources across one or more (natural and/or human) environment dimensions.  The project could be included if it lacked these impacts but had substantial public opposition.

The second screening phase was applied to projects passing the initial screening criteria and was based on information availability.  A series of initial inquiries were made to identify projects for which appropriate individuals could be found who were knowledgeable and willing to speak about the project.  Individuals who understood the perspectives of the agencies and stakeholders were sought.  Study constraints did limit time in finding individuals.  Table 1 presents the case studies and Figure 1 shows their locations.

TABLE 1

COMPLETED CASE STUDIES

| FACILITY TYPE (by Mode) | REGION |  |
| --- | --- | --- |
|  | Eastern U.S. | Western U.S. |
| Rail/Highway | Waterville (Maine) |  |
| Rail/Highway/Port | Sears Island/Mack Point (Maine) | FAST Project (Seattle-Tacoma); Port of Oakland |
| Port/Rail |  | Alameda Corridor (Los Angeles); Port of Long Beach |
| Port/Highway |  | West Hayden Island (Portland, Oregon) |
| Airport/Highway | Logan Airport (Boston) |  |

FIGURE 1

LOCATIONS OF SELECTED INTERMODAL PROJECTS

## Initial Project Evaluation and Investigation

While the project selection process was underway, a matrix was developed to map projects by mode, geography, environmental factors, and other criteria.  Geography was represented as:  Northeast, South, Midwest/Plains, and West regions, although FHWA also considered whether projects had either urban or rural locations, and whether they were in residential or non-residential settings.  Modes and connections were categorized as ports/highway/rail, rail/highway, and airport/highway/rail facilities.  Intermodal facilities were further characterized by the type(s) of commodities transferred: dry bulk, trailer/container, liquid bulk, perishable, or hazardous materials.  Environmental factors included:

- Noise and vibration,

- Land use compatibility/zoning,

- Local transportation impacts,

- Socio-economics,

- Environmental justice

- Community impacts

- Air quality,

- Water quality,

- Hazardous waste contamination,

- Natural resources,

- Wildlife habitat,

- Vegetation,

- Cultural resources,

- Historic structures,

- Archaeological sites,

- Landscapes, traditional cultural properties, etc.

This comprehensive matrix is presented in Appendix B.

Following project selection, the matrix was refined and simplified.  Summary Table 2 illustrates the degree to which the selected projects are representative of different modes and environmental factors.

The project team employed a variety of means to collect the information to characterize the projects.  We identified initial contact persons (usually an individual representing the project sponsor) and asked questions (See Appendix C) to collect the basic information on projects that allowed us to apply the site selection criteria.  The project team’s previous knowledge of many intermodal projects, information provided by FHWA, and initial telephone and internet inquiries provided a first cut of information regarding which projects to investigate further.

## Implementation of Case Studies

After we selected the case studies, it was necessary to collect additional information on the environmental review process beyond information typically contained in public documents.  We developed a questionnaire and interviewed sponsoring agencies and the associated planning and regulatory agencies.  Appropriate interviewees were selected both through the recommendations of FHWA and the existing knowledge of the project team, and from referrals obtained in previous interviews or through other contacts.  Interviewed individuals included: those responsible for the NEPA process for the projects in question at the applicable lead agency, project sponsor agencies, FHWA field offices, EPA Regions, local MPOs, and other involved agencies.  Interviewees were also identified through contact lists in NEPA documents.  For the more detailed interviews, the project team sent the interviewees information regarding this study, including a description of the study’s goals and scope, as well as an advance copy of the interview questions to facilitate the interview.  Appendix D contains a copy of the questionnaire that was developed to ensure comprehensive, consistent coverage of the applicable issues

## Preparation of Case Study Summaries

Based on the results of the interviews and information gathered from public documents, project summaries were prepared.  These summaries were structured in a formal and consistent format to maximize their usefulness.  The full set of these project summaries is provided in Appendix E.

TABLE 2

MATRIX OF SELECTED CHARACTERISTICS FOR CASE STUDY PROJECTS

| Mode | Project | Environmental Factors |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Air Quality | Cultural Resources | Land Use Compatibility | Local Transportation | Natural Resources | Noise, Vibration | Haz. Waste Contamination | Socio- Economics | Water Quality |
| Rail/ Highway | Waterville (Maine) | X |  | X | X | X |  |  |  |  |
| Rail/ Highway/ Port | Oakland Marine Berths | X | X | X | X | X | X |  |  | X |
|  | Sears Island/Mack Point (Maine) |  |  |  | X | X |  | X | X |  |
|  | FAST Corridor (Seattle/Tacoma) | X | X |  | X | X |  |  |  |  |
| Port/Rail | Long Beach Naval Base Re-Use |  | X |  |  | X | X | X |  |  |
|  | Alameda Corridor (Los Angeles) | X | X | X | X |  | X |  | X | X |
| Port/ Highway | West Hayden Island Terminal (Portland, Oregon) |  | X | X | X | X | X |  |  |  |
| Airport/ Highway | Logan Airport (Boston) | X |  | X | X |  | X |  | X |  |

# SECTION 3.0	EVALUATION

## Overview

This section includes the evaluation of information collected from the sample of projects, as well as information on other intermodal projects that was obtained through the screening process.  The sample projects are summarized by project type, lead and cooperating agencies, level of NEPA documentation,  main environmental issues, and level of success that these projects had in the environmental review process.

## Summary of Selected Projects

Type of Projects Captured in Sample

The results of the review of planning activities and environmental constraints affecting the development and expansion of intermodal facilities is based on screening projects nationwide and a detailed review of selected projects.  For the selected projects studied in detail, Table 3 provides a brief project description, lead and cooperating agencies, funding sources, public/private partnership, whether an EA or EIS was prepared, main environmental issues, and length of the environmental review process.

The types of intermodal projects captured in this sample were determined largely by whether a federal agency had a funding, approval, or permitting role.  When agencies are involved in this way, it triggers an environmental review at the federal level.  Certain types of intermodal projects are more likely than others to involve a federal environmental review.  Six of the eight projects in the sample are port-related projects involving dredging, fill activities to expand ship and land side access, and land side improvements and/or access improvements.  One of the projects is a rail/highway intermodal facility and another is air/highway.

The water side of port improvement projects most frequently require NEPA activities in the form of EISs and EAs due to the Army Corps of Engineers permitting requirements and expenditures of the Harbor Maintenance Tax for capital improvements, such as dredging.  FHWA becomes involved with port improvements through land side access projects including: new access into and out of ports for federal-aid highways, rail/highway grade separations at ports, and installation of ITS technology to improve the efficiency of port-highway interfaces.

Inland rail/highway intermodal facilities are mostly owned by railroads and are not as likely to require federal permits and funding, and therefore tend not to trigger NEPA reviews (in the past).  Federal-aid funding is available through several FHWA programs for providing rail/highway improvements. These include:  highway access to and from rail yards, reconstruction of National Highway System (NHS) intermodal freight connectors, building NHS intermodal freight connectors, improved interstate access, double stack compatibility for trains, highway/rail grade separation projects at rail yards and along rail lines, improvements to rail facilities, and grade crossing improvements, and activities that provide air quality benefits in non-attainment areas (diversion from truck to rail and other types of projects).  These projects can require a variety of NEPA documents including a Categorical Exclusion (CE), an EA or an EIS.

TABLE 3

SUMMARY OF SELECTED PROJECTS

| Project / Type | Sponsoring Agencies | Project Description | Funding Sources | EA or EIS? | Main Environmental Issues | Length of Environmental Review Process |
| --- | --- | --- | --- | --- | --- | --- |
| Sears Island and Mack Point, ME Port/rail/highway and port/highway | Lead federal agency: FHWA for Sears Island and COE for Mack Point Cooperating federal agency: None State or local agency: Maine DOT | Renovate Mack Point in Penobscot Bay as an alternative to the unsuccessful Sears Island intermodal facility proposal. Maine DOT proposed Sears Island as the site of a multimodal facility with rail and highway access that would service containers and dry bulk products. Mack Point will have two berths available for the shipment of all commodity types, including petroleum. Cargo will be transferred to trucks, for which no new roads will be required. | Federal, State and Private | EA and EIS for Sears Island, and possibly an EA for Mack Point. | Marine and terrestrial habitat and visual impacts | For Sears Island, on and off for many years. Mack Point has been relatively brief thus far. |
| Waterville, ME Rail/highway | Lead federal agency: FHWA Cooperating federal agency: none State or local agency: Maine DOT | Facility transfers bulk and manufacturing goods from truck to rail. | Federal and private | EA | Avoided wetland impacts by selecting this site over another | Relatively brief |
| Logan Airport, Boston, MA Bird Island Flats and North Cargo Area Air/highway | Lead federal agency: FAA Cooperating federal agency: none. State or local agency: MassPort | Initial concepts included dual taxiways and multiple cargo facilities. Based on early public involvement, one taxiway was eliminated and office and hotel developments were added as well as a shoreline park. | MassPort | EA/EIR | Noise impacts and community opposition derailed fast-track environmental review | Relatively brief after changes in design |
| West Hayden Island, Portland, OR Port/highway/rail | Lead federal agency: COE Cooperating federal agency: FHWA, USCG State or local agency: Port of Portland | 600-acre facility with access to deep draft shipping and barge traffic on the Columbia River. It has direct access to a rail line and an interstate highway, but may still require an additional highway bridge. Facility plan includes grain, automotive and general marine cargo distribution capabilities. | Port of Portland, possibly state and federal for bridge | EIS | Dredge and fill impacts to wetlands, significant habitat loss and community concern over wetlands, noise and air pollution, and traffic | An additional year because of change in DEIS scope. Public and resource agency concerns may delay project. |
| FAST Corridor, WA Port/rail/highway | Lead federal agency: FHWA on a few projects and FTA on at least one project. Cooperating federal agency: none State or local agency: Washington State DOT, Puget Sound Regional Council, Ports of Tacoma, Seattle, and Everett, 11 cities, two counties, Burlington Northern Santa Fe and Union Pacific Railroads | Fifteen individual projects to improve mobility in the freight corridor stretching from Tacoma to Everett. Projects include twelve grade separations and three port access projects. | State, private investors, federal aid | Various EISs, EIRs, and EAs | Endangered species and wetlands | Normal timeframe |
| Alameda Corridor, Los Angeles, CA Port/rail | Lead federal agency: FHWA, FRA Cooperating federal agency: Surface Transportation Board State or local agency: Caltrans, Alameda Corridor Transportation Authority | Development of a consolidated freight railroad corridor below grade between the Ports of Los Angeles and Long Beach and downtown Los Angeles. | Private, local, state, and federal | EIS/EIR | Effects related to seismicity, vibration, acquisition and displacement identified. Beneficial long-term effects related to air quality, noise energy, transportation and circulation, public services, safety and security, aesthetics and economics. | Approximately four years. Followed by community law suits on both EIS and EIR. Project is under construction. |
| Long Beach, CA Naval Base re-use as marine terminal | Lead federal agency: Navy Cooperating federal agency: (none) State or local agency: Caltrans and Port of Long Beach | Developing the 525-acre former Naval facility as a container/rail/port facility that will transfer bulk (primarily lumber) and liquid bulk commodities, and operate as a ship repair facility. | Federal | EIS/EIR | Historic resources, endangered species habitat, and hazardous waste as well as air quality, noise and vibration, and hazardous material transport from trains. | Several years due to NEPA/CEQA coordination issues and multi-agency review. Followed by community law suit. |
| Oakland, CA Marine Terminal Dredging and Expansion | Lead federal agency: COE and Navy Cooperating federal agency: FHWA State or local agency: Port of Oakland, CalTrans | Adding four additional containership berths and one tug berth through widening and deepening of the existing inner harbor channel, bank excavation, fill land reclamation, and wharf construction. The project also involves realignment of Seventh Street and construction of a small access road to handle additional traffic anticipated as a result of the project. | Port of Oakland | EA and EIS/EIR | Marine habitat, endangered birds, air emissions, traffic, historic resources, noise and vibration, and community concerns. | Unavailable |

Like port facilities, airports are publicly owned and the FAA has to approve construction on airport property (e.g., the Logan Airport project in Boston, Massachusetts).  Therefore, airport freight facility construction could trigger the NEPA process.  However, other than the one project included in this sample, suitable air-freight projects were difficult to find.

For the six port projects in this sample, COE was the lead agency on the Mack Point portion of the Sears Island/Mack Point projects (Penobscot Bay, Maine), the Port of Oakland’s marine terminal dredging (Oakland, California), and the Port of Portland’s West Hayden project (Portland, Oregon).  The FHWA was the lead agency in the Sears Island project, Alameda Corridor project (the Los Angeles, California area), and the FAST Corridor project (the Seattle-Tacoma area), because they were funding access roads or separation of railroad/highway at-grade crossings.  The Navy was the lead federal agency in the reuse of a former Naval base as a marine terminal at both the Port of Long Beach (the Los Angeles, California area) and the FISCO portion of the Oakland project. The FHWA was a reviewing agency in the Port of Oakland, West Hayden, and Long Beach projects.

For the non-port projects, FHWA was the lead federal agency for the Waterville, Maine rail/highway intermodal facility.  The FAA was the lead agency for Logan Airport North Cargo Area project.

## Environmental Issues

Table 3 lists the main environmental issues associated with the sample of projects.  The projects encompassed a range of impacts.  Natural and cultural resources, noise, and local traffic were among the larger issues.

Natural Resources.  The natural resource issues included effects to wetlands, threatened and endangered species, and marine habitat.  In terms of impacts by modes, the Logan Airport and Waterville rail/highway projects did not have any natural resource impacts.  Potential impacts to wetlands were an issue for the Waterville, West Hayden, FAST Corridor, and Port of Oakland projects.  The Maine DOT selected the Waterville project to avoid wetland impacts at another site.  The West Hayden project would result in the filling of 40 acres of wetlands to accommodate landside intermodal facilities.  The Port of Portland has proposed greater than one-to-one mitigation of wetlands and forest loss.  Some of the projects that comprise the FAST Corridor have wetland impacts (e.g., grade separations that require additional right-of-way).  The specific details of the mitigation measures for the individual projects were not readily obtainable.

Two of the port projects, Sears Island and the Port of Oakland, had marine habitat issues.  The Port of Oakland project has a mitigation plan that will prevent significant adverse localized effects except on one eel grass bed.  The Sears Island project would have affected an area that did not actually contain eel grass, but had the right habitat for eel grass.  Potential impacts to threatened and endangered species were an issue for the FAST Corridor, Port of Oakland, and Port of Long Beach.  For the FAST Corridor, new species of salmon have been listed and damage to Puget Sound, the rivers or adjacent riparian habitat may threaten their habitat.  The regional governments have been consulting with USFWS and NMFS on long-range and short-range approaches to address the potential impacts.  The long-range approach is to prepare a recovery and conservation plan for each of the six river basins in the three-county area that will support the recovery of the salmon.  The short-range approach is to identify and pursue other actions likely to have an immediate beneficial effect.  These include capital investments, regulation of activities within habitat areas, the level of enforcement of various actions, and management practices of government agencies.  The construction of the Port of Oakland facility threatens potential feeding areas for the California least tern and nesting areas for the Brown Pelican.  Possible adverse impacts to several species could be caused by non-indigenous species invasion from increased ballast water discharges.  The Port will contribute $200,000 over four years (NMFS originally requested $2 million) to aid in the development and implementation of the State’s ballast water monitoring and treatment program.   The reuse of the Long Beach Naval Yard also has the potential to adversely effect potential feeding areas of the California least tern and nesting areas for the Black-crowned Night Heron.  The mitigation for the California least tern is to create replacement shallow-water foraging habitat within the vicinity of the Terminal Island nesting colony.  The mitigation for Black-crowned night heron would involve salvaging approximately 30 trees from the existing colony and planting them at Gull Park on the Navy property.

Cultural Resources.  Three of the port projects, Long Beach, Oakland, and Alameda Corridor, had cultural resource issues.  Both the Long Beach and Oakland projects involved the demolition of significant historic Navy buildings.  The mitigation for both projects involved establishing exhibits and the Oakland project designed portions of the historic structures into the new facilities.

Noise and Vibration.  The proximity to residential land use for the Logan Airport, Oakland, Long Beach, and Alameda projects created noise and vibration issues.  In the Logan airport project, a substantial mitigation program addressed the potential noise from a proposed taxiway.  The mitigation included a series of strategically placed and designed buildings that would act as noise and visual buffers.  In the Oakland, Long Beach, and Alameda projects, the adjacent communities were concerned about noise and vibration from increased rail and truck traffic.  All three projects included mitigation to reduce the noise and vibration impacts (the mitigation for the Alameda Corridor addresses the impacts of the Long Beach project).  Noise barriers will be constructed along the Alameda Corridor to reduce noise.  Various design and operational approaches will be used to reduce vibration potential, including relocation of trackwork away from sensitive areas, installation of ballast mats, and use of movable point frogs where needed.

Local Transportation.  Almost all of the projects have local transportation impacts.  The FAST Corridor and the Alameda Corridor have positive impacts because they improve access to intermodal facilities and thereby reduce congestion.  There are however, cases where local traffic and transportation have been viewed as negative impacts, as is the case with the Hayden Island Port expansion project.  Increasing truck traffic through communities and onto and off of interstate highways can be viewed as a problem rather then a benefit.  The expansion of the Port of Oakland initially generated neighborhood objections to increased truck and rail traffic, but these concerns were addressed through a range of mitigation measures.

Air Quality.  Most of the projects were anticipated to have beneficial air quality impacts because they reduce congestion.  The elimination of a large number of grade crossings on the Alameda Corridor is projected to have a substantial reduction in all criteria pollutants.  The analysis for the Waterville project indicated that it would have positive air quality impacts because it would reduce heavy truck traffic and emissions.  The project was therefore awarded CMAQ funding.  Neighborhood concerns over local air emissions associated with the Port of Oakland expansion led to mitigation that included a transfer of $660,000 from the Port to AC Transit (the local transit agency) for bus engine retrofitting, and some maritime terminal equipment will be retrofitted with emissions control devices.

Socioeconomics.  Several of the projects had potential socioeconomic impacts such as potential community impacts (Logan Airport and Alameda Corridor), displacement and disruption of businesses (Alameda Corridor), and job creation (Sears Island/Mack Point).  The construction of the Alameda Corridor will require up to 40 full acquisitions and up to 16 partial acquisitions of commercial properties.  Some businesses may have substantial difficulty relocating.  Construction of the project will have substantial impacts on businesses along the corridor.  They will experience reduced vehicular and pedestrian access, traffic detours, noise and other inconveniences.  Mitigation measures are expected to reduce the impacts to potentially substantial and include signs to direct customers along alternate routes to businesses; traffic management to maintain access; and a business outreach program.  Any relocated businesses would be compensated under the Uniform Relocation Assistance and Real Property Acquisition Policies Act.  The proposed action would result in only four residences having noise impacts after the implementation of noise attenuation walls.  The environmental justice analysis also considered the beneficial effects of the proposed action:  a 90 percent reduction in population exposure to railroad noise on all lines serving the ports.  Therefore there was no disproportionate adverse affect to low-income or minority communities.

Land Use.  One neighborhood adjacent to Logan Airport was concerned about the compatibility of the proposed cargo terminal development with the neighborhood, and with possible adverse impacts to the host community.  In addition to noise and vibration impacts, the community was concerned with the prospect of a view dominated by air cargo warehouses.  The development of more attractive office buildings and the hotel with restaurants and other amenities was deemed more compatible with existing land uses.  The EIS for the Alameda Corridor found that with the No Build alternative, increased train traffic could potentially have substantial incompatibility with some adjacent land uses.

Water Quality.  Water quality issues were addressed in the dredging projects (e.g., fill material produced by the dredging for the reuse of the Long Beach Naval Yard is contaminated) and in the de-watering of the Alameda Corridor, but there were no substantial water quality issues involved.

Hazardous Waste.  The only project with notable hazardous waste issues is the reuse of the Long Beach Naval Yard.  The fill material produced by the dredging, along with other materials on the island, is contaminated.  The Navy established two major restoration programs and has worked with the U.S. EPA to dispose of the contaminated dredge materials, and with the California Department of Toxic Substances Control to dispose of the contaminants on the island.

## Level of Success in the Environmental Review Process

NEPA, Including Agency Consultation.  Success in the NEPA process and in agency consultation can be measured in a number of ways, including the amount of time required to move through the process, compliance with procedural requirements, and the degree of proactive engagement of the appropriate agencies in consultation.  Other measures are discussed further below.

The projects in the sample involved five EISs and at least five EAs (the FAST Corridor is a series of projects and at least one was covered by an EA; the Sears Island project started as an EA before becoming an EIS and then back to an EA when it moved to Mack Point; the Oakland Project involved both an EA and an EIS).  Specific information on the length of time required to prepare the EAs was unavailable.  The Waterville EA, according to Maine DOT, did not encounter any delays.

The projects with EISs provided the best information on the timing of the environmental reviews within this sample.  Table 4 illustrates the timelines of these EISs.  The Long Beach EIS/EIR was the shortest in duration, but still required 19 months.  It appears that part of the time required was attributable to the Section 106 process, coordinating the NEPA and CEQA processes, and the Navy taking longer than the Port of Long Beach to reach conclusions regarding the magnitude of the impacts.  The Section 106 process alone took a year to complete.

The amount of time to prepare the Alameda Corridor EIS, 26 months, appears to have been attributable to several factors.  The size of the loan from FHWA required coordination with FHWA headquarters.  FRA was a joint lead agency and FHWA staff in California worked with FRA headquarters staff.  Both state and federal environmental documentation were required for this project.  While work done for the state requirements could be referenced in the federal documents, additional analysis not required at the state level had to be undertaken to satisfy federal needs (air quality, water quality, and historic preservation).  This included determining what was needed and where, as well as the complicated coordination contributed to the time it took to finish the review.  In addition, the complexity of the project no doubt contributed to the amount of time needed to get through those processes and requirements.

The COE issued the Notice of Intent (NOI) for the West Hayden Island EIS 17 months ago and it is still in the DEIS stage.  The Port of Portland lost an additional year because it began to prepare a DEIS addressing the first five years of development, but subsequently convinced the COE to allow it to address all 30 years of proposed development.

The environmental review for the Sears Island project encountered over 12 years of effort before it was cancelled.  Much of the delay came from the Sierra Club’s litigation over the initial EA, which led to the preparation of an EIS.  The EIS took two years to prepare, because, among other issues, the reviewing agencies had substantial disagreements with FHWA and Maine DOT.  The Sierra Club successfully litigated the EIS.  FHWA and Maine DOT prepared a Supplemental EIS before deciding that the use of Sears Island had become economically infeasible.

###### TABLE 4

###### EIS TIMELINES

| Project | Milestone | Date | Cumulative Duration |
| --- | --- | --- | --- |
| Alameda Corridor |  |  |  |
|  | NOI | 12/93 |  |
|  | DEIS | 1/95 | 13 months |
|  | FEIS | 2/96 | 26 months |
| Long Beach |  |  |  |
|  | NOI | 9/96 |  |
|  | EIS/EIR | 4/98 | 19 months |
| Sears Island |  |  |  |
|  | EA | 11/83 |  |
|  | Litigation | 1985 |  |
|  | NOI | 9/85 | 22 months |
|  | DEIS | 7/86 |  |
|  | FEIS | 10/87 | 45 months |
|  | ROD | 12/87 |  |
|  | Litigation | 1988 |  |
|  | Draft Suppl. EIS | 7/95 |  |
|  | Withdrawal of NOI | 2/96 | 12 years, 3 months |
| West Hayden |  |  |  |
|  | NOI | 10/98 | (on-going) |

Improving the agency consultation process is the focus of FHWA NEPA streamlining efforts, including the new Section 106 regulations, and MOUs on consultation regarding wetlands and endangered species.  These initiatives and requirements encourage consultation early in the NEPA process.  Counteracting this goal, FHWA, COE, EPA, FWS, and NMFS are often resource-constrained from providing sufficient input into projects during the early planning stages as lead, cooperating or reviewing agencies.  This situation can thwart meaningful consideration of a project’s purpose, need, and alternatives, as well as the timely discovery of fatal flaws.  Issues can arise when relying on another agency’s determination of a project’s purpose and need, and the alternatives that would meet those needs. The COE is greatly inhibited from reviewing projects at the conceptual stage, and its staff may only work at the permit stage; their budget correlates directly with the number of permits that it has to process.  In general, FWS does not have the staff resources to attend pre-application meetings and other advanced planning activities.  Some of the EPA regional offices also have resource constraints and cannot always attend pre-application or early planning meetings.  If COE and FWS could meet with applicants prior to filing applications they may have more influence on the process for selecting alternatives.  FHWA has developed MOUs with a number of agencies that integrate the 404 permitting process with NEPA and bring agencies into the consultation process in planning.  In some cases, funding has been provided to agencies where the work necessary is considered above and beyond their normal responsibilities.  This funding is not a uniform practice nor is it uniformly necessary.

Most of the projects in this sample involved consultation with one or more of the agencies discussed above as well as with the State Historic Preservation Officer (SHPO).  The success of these consultations has varied for any given resource area.  Sometimes the delays are beyond the control of the project sponsor.  For example, both of the lead agencies involved in the FAST Corridor projects, NMFS and FWS, are grappling with how to apply the Endangered Species Act consultation process to projects in urban watersheds given the new listings of salmon.  FHWA and Maine DOT held meetings with EPA, FWS, and NMFS during the scoping process for the Sears Island project and throughout the preparation of the EIS, those agencies had strong disagreements with FHWA and Maine DOT.  The disagreements centered on issues such as the selection of alternatives to be analyzed in the EIS and the analysis of secondary impacts.  Maine DOT has implemented an effort to better integrate the preliminary design and environmental review phases so that environmental issues are considered at the beginning of projects.

Use of a Structured Process for Environmental Review.  It appears that all of the three projects involving FHWA as the lead agency (Alameda Corridor, Waterville, and Sears Island/Mack Point) used FHWA’s structured review process.  Sears Island started with the FHWA structured review process, but as the project wore on and became more controversial it was difficult to apply.  FHWA and Maine DOT used a standardized approach to screen potential environmental impacts when choosing the Waterville site.  In addition, the projects that had to comply with the California Environmental Quality Act (CEQA) generally followed a structured approach, because CEQA is much more prescriptive than NEPA.  Following FHWA’s structured approach in the Alameda Corridor project may have been challenging because FHWA came in and out of the lead agency role as the nature of the federal funding changed.

Integration of NEPA and State Environmental Review Processes.  The President’s Council on Environmental Quality (CEQ) regulations for implementing NEPA require agencies to “cooperate with state and local agencies to the fullest extent possible to reduce duplication between NEPA and state and local requirements . . .”  (40 CFR Part 1506.2).  The projects analyzed in this sample encountered mixed results in terms of integrating NEPA and state review processes.  The Alameda Corridor would have been more integrated, but the CEQA process advanced without the NEPA process because it appeared that federal funding would not be available for the project.  The CEQA process had been underway for nine months when federal funding was identified and FHWA and FRA initiated NEPA.  The integration of NEPA and CEQA in the Long Beach project did not go as well as it could have because the Navy took longer to reach conclusions about the magnitude of impacts and had a more complex internal decision-making process than the Port of Long Beach.  For the Port of Oakland project, early coordination and consultation with the various state agencies during the NEPA process facilitated the project’s progress.  The FAST Corridor projects that involve NEPA have been and will be integrated with the Washington State Environmental Policy Act.

Affect of the Environmental Review Process on Project Design and Alternatives.  The environmental review process influenced project design and alternatives for several projects.  For the FAST Corridor project, the screening and ranking process used by WSDOT and the Regional Council (MPO) led to the selection of projects that had fewer assessed impacts relative to others.  Consultation with COE and FWS led FHWA and Maine DOT to select the Waterville site rather than a site in Fairfield, specifically because Fairfield contained wetlands.  In the Long Beach EIS/EIR, two of the alternatives analyzed are based on two potentially feasible adaptive reuse alternatives generated by the Historic Properties Adaptive Use Feasibility Study. The Sears Island structural designs and drainage patterns were altered because of concerns over wetlands.  After the project was cancelled, Maine DOT chose Mack Point as an alternative site, because the regulatory agencies in the Sears Island review had preferred it.  For the Logan Airport project, the community’s early entry into the planning and environmental review process had a strong influence on the formulation of alternatives and the change in the project’s initial design.

Multi-Agency Review.  Most of the sample projects have involved reviews with agencies such as EPA, COE, FWS, NMFS, and SHPOs.  As discussed above, structured processes have been used on some projects to consult with these agencies.  Even in the more controversial projects, it is not clear how much the multi-agency review process may have delayed a project.  With any controversial project, the reviewing agencies are likely to request additional information and analysis.

Public Involvement.  All of the projects, with the exception of the Waterville project, had public involvement processes and faced some public opposition.  The Waterville project received no substantial public comment, because it is located in an industrial area away from any residences or natural resources.

The Port of Oakland appeared to have successful results with its public involvement process, albeit litigation may have sped the discussions.  To address community concerns about air quality, noise, and vibration, and increased truck and rail traffic, the Port worked extensively with the community through an early outreach effort to develop a range of mitigation and enhancement actions.  Following a quickly agreed to Consent Decree, these efforts appear to have shifted public sentiment towards widespread local support for the project.

The Sears Island/Mack Point projects involved sporadic public meetings until the initiation of the supplemental EIS for Sears Island, for which formal public meetings were regularly held.  Initially, the project had public support attributable to the economic development potential of the project.  Eventually, however, summer residents, national and local environmental groups, and others strongly objected.  Environmental groups representing a summer resident successfully litigated the project for several years.  Although they were unsuccessful in their final legal challenge, the years of delay rendered the project economically infeasible on Sears Island.  Maine DOT moved the project to Mack Point.  The Mack Point project involves regular public meetings and a town oversight group.

The public involvement process for the West Hayden intermodal facility has been mixed.  To solicit community concerns about the proposed facility, the Port of Portland has presented its plans at town meetings for East Hayden. One neighborhood’s early discussions with FHWA and the Port led to formal inclusion of a new bridge as a Phase One project component in the NOI.  Community views were also integrated into the planning process through an Advisory Committee, which included local citizens, environmental groups such as the Audubon Society, and multi-function agencies.  However, some of the community and environmental groups have been dissatisfied with the public involvement process because they believe that the Port has not properly characterized their positions and they do not have appropriate representation on the Advisory Committee relative to the other stakeholders.  Negotiations are continuing to avoid litigation over the extent of wetland impact avoidance and mitigation.

The EIS for the Alameda Corridor leveraged the extensive public involvement that occurred under the CEQA process.  Under CEQA, the Alameda Corridor Transportation Authority implemented an extensive notification process and held numerous public meetings.  This may have been the reason that attendance was lower at the FHWA/FRA public meetings for the EIS.  Much of the opposition came from locally elected officials rather than individual citizens.  Attempts by local governments to block the project through CEQA and NEPA law suits were unsuccessful.

For the Long Beach reuse EIS, the Navy held public meetings, as did the City of Long Beach.  Residents remained concerned about air quality, noise and vibration, and hazardous materials transportation impacts from train traffic.  The neighboring communities were unsuccessful in blocking the project through CEQA and NEPA litigation.  The public involvement for the FAST Corridor has mainly occurred on a project-specific basis.  Most of the individual projects that comprise the Corridor do not appear to have been controversial.

For the Logan Airport cargo building and taxiway, MassPort recognized in advance the historical mistrust in the surrounding community and provided substantial funding to the community so that it could hire its own consultants to participate directly in developing the alternatives.  This gave the community joint ownership of the project and thereby lessened potential opposition.

# SECTION 4	CONCLUSIONS AND RECOMMENDATIONS

The information included in this report comes from eight case studies.  The data is restricted to what could be obtained through interviews with a variety of participants on the different projects.  The total number of intermodal freight transportation projects currently underway in the United States is unknown, and thus, this is not a statistical sample of all port, rail, highway, and airport facilities.  The information represents a first look at environmental issues affecting development of intermodal freight transportation facilities.  Enough information has been collected to make it clear that there are a variety of environmental concerns on intermodal freight transportation projects and they are not restricted to issues of air quality, noise, and community impacts.

## Conclusions

Initial conclusions that can be drawn from the information reviewed include, but are not limited to the following:

- Intermodal freight transportation projects, depending on federal funds or permits, frequently involve a variety of federal agencies as reviewers or that could be directly affected (port improvements and landside access issues).

- Clear communications and early involvement of federal and state agencies are critical to the successful completion of environmental analysis for projects (time, money spent, design of project, etc.)

- Conflicts between state and federal environmental requirements can cause delays on projects but can be overcome with early recognition of issues and agreements among agencies on how to proceed.

- The variety of environmental issues that can become a concern on a given project depend on the nature of the project and the location of the project.  They are not uniform for every project.

- Consideration of environmental resources (including avoidance and minimization of impacts through site selection and design) early in the planning and project design phases can result in simplified environmental review and avoidance of costly delays in project schedules.

- Early coordination with public interests on intermodal freight projects can lead to resolving concerns before they become a problem.

- NEPA streamlining through improved agency consultation may be difficult to achieve on many projects if the regulatory agencies do not have adequate resources to engage in early consultation.

- When questions or disagreements arise over the assumptions behind a project’s purpose and need, and alternatives, regulatory agencies do not always have the resources to independently verify cargo projections, market analyses, and facility land use needs.  They have to rely on the lead agency to comply with the NEPA requirement for independent verification of the information and analyses submitted by a permit or funding applicant.

- Port dredging, land side development, and land side access projects are sometimes covered by separate NEPA documents because funding is not always available to cover all three types of activity simultaneously and because different agencies take the lead on these projects.  On a related note, there does not appear to be any regional or national guidance or policies for project sponsor agencies and regulatory agencies to follow when considering the funding, permitting, and environmental review of projects in separate political or planning jurisdictions that compete in the same freight markets.

## Recommendations

Additional efforts in this area of environmental review might include the following next steps:

- Further research to confirm the preliminary conclusions discussed above.  This might include researching FHWA EAs and EISs for intermodal facilities; reviewing past funding of intermodal projects; and interviewing additional FHWA Division Office staff.

- Further research into how FHWA Division staff considers a project’s purpose and need, and alternatives when it is a cooperating or review agency.

- Further research into how other reviewing agencies (e.g., EPA, FWS, NMFS, and SHPOs) consider a project’s purpose and need and develop alternatives.  This research could include whether those agencies have the resources to independently verify a lead agency’s or applicant’s freight projections and market analysis, if they have reason to suspect them.

- Follow-up calls to determine whether some of the projects excluded from this report might be worth further review.  In addition, projects that were only in the early stages of review during the preparation of this report might be appropriate for review in a subsequent effort.

APPENDIX A

INTERMODAL PROJECTS CONSIDERED FOR DEVELOPMENT AS CASE STUDIES

# APPENDIX A - INTERMODAL PROJECTS CONSIDERED FOR DEVELOPMENT AS CASE STUDIES

## Part I – Projects advanced as case studies

| Project Name and Mode | Geography | Federal Funding or Permit? | Involvement of Intermodal Freight? | Project Development Status | Type and Magnitude of Impacts or Public Controversy | Advance as a case study? |
| --- | --- | --- | --- | --- | --- | --- |
| Alameda Corridor Los Angeles area Rail / Highway | West | Federal funding. Numerous federal permits and federal EIS. | Yes, facilitates highway and rail connections and access to maritime facilities | Under construction | Project involved brownfields, archaeological issues, Native Americans, probably local traffic and noise impacts during construction. Started as a CEQA document, because it was not in the SIP. FHWA wanted to streamline the NEPA document, but were unable to. Had one NEPA suit and several CEQA suits. | Yes |
| Oakland Marine Terminal Berths 55-58 Oakland Port/Rail/Highway | West | Army Corps of Engineers, Section 404 permit. Federal Environmental Assessment conducted. | Yes | Phase I under construction or complete. Later phases pending. | Dredging impacts. Local truck traffic, air quality, and noise. Endangered species issues. | Yes |
| West Hayden Island Marine Terminal Portland, Ore. Port/Highway | West | Army Corps of Engineers, Section 404 permit. Possible FHWA funding for new bridge. Draft EIS underway. | Yes | Environmental review is being conducted, having been reinitiated in 1998 following a revision to ACOE processes. | Local truck traffic, air quality, and noise. Potential endangered species issues. Potential wetland issues. | Yes |
| Logan Airport - Bird Island Flats Cargo Area Boston Rail/Aviation | Northeast | The Bird Island Flats cargo project involved FAA funding and federal environmental permits, as well as a federal Environmental Assessment | Yes - Air cargo operations and trucks; local transportation impacts on airport access. | Project effectively completed | Noise and vibration; air quality; socio-economics and neighborhood impacts. | Yes |
| Sears Island terminal development and access Sears Island, Maine Rail/Highway | Northeast | Required an EIS and probably other permits | Yes – port with rail and truck connections | The project was stopped in court by EDF, NRDC, and others six years ago after an EIS had been prepared and several million dollars spent on construction. | Impacts to eel grass were apparently involved in stopping the project. Public concern over coastal development probably played a role as well. | Yes |
| FAST-Corridor Puget Sound, WA Port/Rail/Highway | West | Federal funding | Yes – Improved truck access to ports and grade separations involving port, rail, and highway | Various stages of analysis and implementation | Appears to have positive air quality effects through reduced congestion. Positive safety impacts from grade separating highway/rail at-grade crossings. Appears to have neighborhood impacts. | Yes |
| Long Beach Naval Base Re-Use Long Beach, CA Port/Rail | West | Army Corps of Engineers permits for landfill, dyke work, use of dredged material. Is also a brownfield. | Yes. The new terminal will include an on-dock rail facility. | In construction | All sorts of environmental issues and considerations. Also relates to reuse of military terminals. | Yes |

## Part II – Projects strongly considered but not advanced as case studies

| Project Name and Mode | Geography | Federal Funding or Permit? | Involvement of Intermodal Freight? | Project Development Status | Type and Magnitude of Impacts or Public Controversy | Advance as a case study? |
| --- | --- | --- | --- | --- | --- | --- |
| OE&J Cherokee, Woodbridge, NJ Truck/Rail/Barge and Warehousing | Northeast | Army Corps of Engineers and other environmental permits | Yes. The site is being redeveloped as an intermodal distribution center with truck, rail, barge and warehousing. | Project is in preliminary stages. | Brownfields; private developer of an intermodal yard- reuse of dredged materials; neighborhood noise/light impacts (from current rail yard – Port Reading Yard on the site). | No |
| Red Hook Barge, NY Barge/Rail/Truck | Northeast | The project is funded in part with CMAQ grants. Only required a categorical exclusion under NEPA. | Yes. The barge transports containers from the Red Hook Container Terminal in Brooklyn to Port Newark, where it is moved inland by truck and rail. | Acquisition of two new barges and mobile cranes is nearly completed. The project is now several years old. | Air quality (reduction of VMT and truck emissions) - Was one of the first freight projects funded under CMAQ. | No – Only required a categorical exclusion under NEPA. |
| CSX 59th St Intermodal Yard Chicago | Midwest/ Plains | Reviewed under NEPA because of Conrail acquisition, but no Federal permit or funding | Yes | Operational | Mitigation for noise, traffic, and community impacts were identified in the EIS and City of Chicago permit. EIS said residences were 375 feet away but did not indicate the magnitude of the noise impacts. Project is located in an environmental justice community | No |
| Marine Cargo Terminal Complex Development, Daniel Island, Charleston, SC | South | Army Corps of Engineers, Section 404 Permit and Section 103 of the Marine Protection, Research and Sanctuaries Act. USCG (for two bridges), Section 9 of the Rivers and Harbors Act. US Forest Service (construction). Surface Transportation Board for rail construction | Yes | Army Corps of Engineers to issue Final EIS in near future. Too early to characterize the review process. | EIS covering “23 key issues,” including water quality, aquatic sediments, endangered species, light, parks and recreational opportunities, and environmental justice | No – High level of sensitivity due to on-going and anticipated litigation and political issues precludes necessary interviews |
| The EDC Sunset Park project Brooklyn, NY | East | Yes – Army Corps of Engineers, Section 404 Permit | New, state-of-the-art container terminal in Brooklyn with sprint trains and reduced need for trucks to come to terminal. | Concept and planning were completed. NYCEDC going to next steps now. | Numerous potential impacts. | No. The project is not advanced enough to fully identify environ-mental impediments to the development. |
| Cross Harbor Tunnel New York/New Jersey | Northeast | Federal permits are anticipated to be required. | Yes – rail, truck, maritime. | Early planning. DEIS is the next stage | Increase in rail movements in neighborhoods, removal of trucks from NYC and trans-Hudson routes, etc. | No – project is too early in the planning stage. |
| BNSF Alliance Intermodal Facility Fort Worth, Texas | Midwest/ Plains | Could not be determined | Yes | Operational | Aside from possible site specific impacts, rural facility that may have avoided adverse impacts at alternative locations | No – Insufficient information to judge applicability |

## Part III – Projects initially considered, but not advanced as worthy of consideration as case studies

Denver UPS project

Des Moines, UPS project

East-west corridor, Maine Judith

Western Transportation Trade Network (WTTN) project

Tucson, AZ intermodal NAFTA project

I-35 NAFTA Corridor – improvements through urban areas

PennDOT bridge replacement projects

Connecticut railroad bridge replacement

Bethlehem, PA - CSX or NS yard expansion

Reno, Nevada grade separation rail project

Other Chicago projects

Lackawanna Valley Industrial Highway

# APPENDIX B
INTERMODAL FACILITY DESCRIPTIVE MATRIX

# APPENDIX B – INTERMODAL FACILITY DESCRIPTIVE MATRIX

# APPENDIX C

# SELECTION AND EVALUATION CRITERIA

(Distributed to project team)

# APPENDIX C -- SELECTION AND EVALUATION CRITERIA

(Distributed to project team)

## Phase One Selection Criteria

To select projects for the development of case studies, we are using two phases of screening criteria.  The first phase involves a set of minimum requirements that we are applying to projects for which we lack sufficient prior information to make a case study recommendation.  These requirements are indicated below.  The second phase will examine how a project contributes insight across matrix categories (see criteria below).  For the projects selected as case studies, our interview questions are presented below.

Minimum Requirements:

Federal funding –or– federal permit – the project must have required one or the other.

Level of NEPA documentation – the project must have required an environmental assessment or environmental impact statement under Federal laws.

Involvement of intermodal freight – the project must have a clear relationship to intermodal freight operations.

Project development status – the project must be far enough along that the project proponents and agencies are able to discuss specifically the potential or actual impacts, the level of public concern, and any issues associated with agency coordination/permitting.  We want to avoid speculation on these issues because a project is in the early stages of project development.

Type and magnitude of impacts or public controversy – the project must have moderate to significant impacts (either negative or positive) across one or more subject areas under the natural and human environments.  The project could be included if it lacked these impacts but had generated substantial public opposition.

## Initial Screening Questions for Projects

We will use the following questions to collect basic information on projects that will allow us to apply the site selection criteria.

1.  Could you briefly describe the project, e.g., location, modes served. (Confirm a clear relationship to intermodal freight operations.)

2.  Is there federal funding or a federal permit involved?

3.  What is the project development status, e.g., feasibility stage, planning/NEPA stage, under construction, operational?

4.  What type and magnitude of impacts or public controversy has the project involved?

5.  Have there been any agency coordination or permitting problems?

Evaluation Criteria:  For Placement of Projects in Matrix and Final Selection

Regional location:

- Northeast

- South

- Midwest/Plains

- West

Privately- and publicly-owned facilities:

- Privately-owned

- Publicly-owned

Mode and commodity type / shipment means:

- Different intermodal combinations of rail, truck, aviation, inland waterway, and maritime

- Commodity type (e.g., perishables, high value, container/freight-all-kinds, bulk, liquid bulk, etc.)

Type and magnitude of impacts:

- Noise and vibration

- Land use compatibility

- Local transportation impacts

- Socioeconomics

- Air quality

- Water quality

- Hazardous waste contamination

- Natural resources

- Historical and cultural resources

- Environmental justice

Urban and rural:

- Residential and non-residential areas

- Urban and rural

Successes and failures:

- Successes (e.g., generated positive impacts or took environmental considerations into account during conceptual design phase and avoided project delays in the face of permitting requirements or public opposition)

- Failures (e.g., Mismanaged agency coordination or public involvement process, or suffered avoidable costs or delays due to environmental issues)

# APPENDIX D

# INTERVIEW QUESTIONS FOR SELECTED PROJECTS

# APPENDIX D  -- INTERVIEW QUESTIONS FOR SELECTED PROJECTS

The following questions have been developed to collect moderately detailed information regarding selected intermodal freight projects that have been influenced by environmental impacts or the environmental planning process.  Please note that not all questions will be used with each interviewee, both because of inapplicability and/or because of prior knowledge of the contractor.

1.  Could you briefly describe the project?

- What is the location, both in geographic region and immediate surroundings?

- What modes and carriers are served? (Re-confirm a clear relationship to

intermodal freight operations.)

- What are the key commodity types served (e.g., containers, bulk, liquid bulk)?

- What is the nature of facility ownership?

- Who is the project planning entity?

2.  Is there federal funding or a federal permit involved?

3.  What is the current project development status, (e.g., feasibility stage, planning/NEPA stage, under construction, operational)?

4.  At what point in the project development process did you begin to consider environmental issues?  For example, in the feasibility stage, conceptual design stage, or detailed design stage.

5.  Were there any project design or alternatives changes based on environmental issues?

6.  What were the main environmental impacts (positive and negative), in terms of the natural, physical, and human environments?

- Key impacts (prompt if necessary) might be in the areas of:

--	Noise and vibration

--	Land use competition

--	Local transportation impacts

--	Socioeconomics / employment

--	Emissions and air quality

--	Water quality

--	Wetlands permitting

--	Hazardous materials / hazardous waste contamination or dredge spoils

--	Natural resources and biodiversity

--	Cultural or historical resources

--	Other environmental justice considerations

- Were there any environmental impacts that the public or others perceived as potential impacts, but from an analytical standpoint were negligible?

7.  Did you prepare an Environmental Assessment or an Environmental Impact Statement?

- Was there an equivalent state or local environmental review process combined with the EA or EIS?

8.  Approximately how long did it take to prepare the EA or EIS and any associated state or local document?

- Were there any delays related to having to combine the NEPA process with a state or local review process?

- If so, what was the nature of that delay?

9.  Were there any project delays because of a consultation process or environmental permitting (e.g., 404 permit, Section 106 consultation with the SHPO, Section 7 consultation with US FWS)?

- If yes, what was the nature of the delay (e.g., insufficient information submitted during 	consultation, difficulty reaching agreement with the reviewing agency, or delay on the 	part of the reviewing agency)?

10.  Was there a multi-agency review?

- If yes, what agencies were involved and were there any associated problems?

- If there was a private entity as the action proponent or local government applying for federal funding, was the multi-agency review process clear to them?

11.  What was the public perception?

- How did you involve the public and how did the public involvement process work?

- For example, did you form a citizen advisory group?

# APPENDIX E

SELECTED INTERMODAL PROJECTS

## Appendix E -- Selected Intermodal Freight Projects

The length of the case studies for the selected intermodal freight projects varies depending on the magnitude of the impacts, the level of documentation available, and the ability to contact project proponents and reviewers.

In the summary box for each case study the lead agency is the lead federal agency for the purposes of the NEPA process and the cooperating agencies are the other agencies cooperating with the lead federal agency.  The reviewing agencies are the agencies with regulatory jurisdiction (e.g., FWS, COE, SHPO).  The state or local agencies are the action proponents in the state department of transportation or the local port authority.

The projects comprising the case studies include:

- Sears Island and Mack Point, Maine

- Waterville, Maine

- Logan Airport, Boston, Massachusetts

- FAST Corridor, Washington State

- West Hayden Island, Portland, Oregon

- Oakland, California

- Alameda Corridor, Los Angeles, California

- Long Beach, California

SEARS ISLAND/MACK POINT

Mode:  Marine, Highway, Rail	Commodity Type:  All

Ownership:  Public/Private	Location:  Rural, East

- Lead Federal Agency:  FHWA (Sears Island), COE (Mack Point)

- Cooperating Agencies:  FRA (Sears Island)

- Review Agencies:  USCG, EPA, FWS, NMFS

- State or Local Agencies:  Maine DOT

| Environmental Issues: |  |
| --- | --- |
| - Air Quality |  |
| - Cultural Resources |  |
| - Land Use |  |
| - Local Transportation |  |
| - Natural Resources |  |
| - Noise/vibration |  |
| - Hazardous Waste |  |
| - Socioeconomics |  |
| - Water Quality |  |
| Environmental Review Process: |  |
| - NEPA, including agency consultation |  |
| - Use of structured process |  |
| - Integration of NEPA and state processes |  |
| - Timing of environmental review initiation |  |
| - Effect of process on project design and alternatives |  |
| - Multi-agency review |  |
| - Public involvement |  |

- Issue

- Major Issue

Project Description

Initially, Maine DOT had proposed Sears Island, in Penobscot Bay, as their preferred alternative for an intermodal facility and nearby Mack Point eventually became an alternative site.

Subsequent to the termination of the Sears Island project, Maine DOT, in cooperation with private investors, is proposing to renovate an existing intermodal facility at Mack Point.  While the current Mack Point project is substantially different from the project originally proposed at Sears Island, the Sears Island EIS had addressed Mack Point and the regulatory agencies and environmental groups had urged its selection.  Therefore, both projects are described in this case study.

Under the Port Planning and Development Program, which began in 1976, MDOT targeted the Searsport area for potential development of a new port facility capable of competing with new port facilities outside Maine.  The proposed action in the original FHWA EIS for Sears Island was for a two-berth dry cargo port with the potential for future expansion to six berths.  At full build-out it would have required 160 acres of the mostly forested 940-acre island.  The port would have been connected to the mainland through the construction of a 2.3 mile-long, two-lane highway, including a 1,200 foot causeway and a 1.5 mile railroad spur along the length of a gravel bar connecting to the mainland.  The port was intended to supplement the existing petroleum and cargo port at nearby Mack Point with container and break-bulk capacity.  It would primarily service Maine’s northern hinterland, which mostly produces forest, paper, and agricultural products.  MDOT considered two alternative sites on Mack Point located across the harbor from Sears Island near the mainland end of the proposed causeway.  Mack Point is 50 percent developed with industrial and port facilities.  MDOT rejected both Mack Point alternatives as impractical given the projected need for six berths at full build-out.

MDOT constructed a causeway and highway connecting the port site to the mainland in 1982 with federal-aid highway funds.  Eventually, MDOT completed substantial clearing and grading at the proposed site and removal of approximately 303,000 cubic yards of dredged material before further construction and funding of the project were enjoined.  The dredging represented approximately 60 percent of the total required to complete the initial one-berth terminal in Phase I of the project.

The Mack Point facility currently proposed for redevelopment would create two modern piers with four fully serviceable berths for less than one quarter the public cost of the previously proposed Sears Island development.  “By constructing the two new piers within the footprints of the existing piers, environmental impacts have also been vastly minimized,” according to Maine Transportation Commissioner John Melrose.

The new berths would handle all commodity types, including petroleum, and be served by pipeline, road, and the Bangor and Aroostook Railroad Searsport Terminal.   No new roads would be required.  Increased traffic would require new stop lights in a neighboring town.

Mack Point renovation would be a $19 million joint public/private venture, for which the State of Maine has pledged $16 million from a combination of general fund bonds and appropriations.  The balance will be financed through a revenue bond paid by the Bangor and Aroostook Railroad (BAR) and Sprague Energy.  A unique provision was created to allow either the railroad or Sprague to buy back their pier site and pier when the state's full investment is paid back.  Both parties have agreed to payments over time that would allow ownership to revert to them.  According to Melrose, “We plan to have all BAR and Sprague payments go toward capitalizing a revolving loan fund for Maine ports and harbors that would be under the direction of the Maine Port Authority.”

The COE has not yet determined whether the dredging renovation or a new action that requires permitting.  If a permit is required, the Army Corps of Engineers will fund the dredging.

The engineering for Mack Point is 70 percent complete.  Necessary permit applications were supposed to have been filed by the end of December 1999, and bidding for construction was expected to begin in April 2000.

Environmental Issues of Concern

Local Transportation: The local transportation impacts created by the Mack Point facility will be mitigated through the installation of stoplights.

Natural Resources: The Sears Point facility would have damaged wetlands on the island and eelgrass habitat in the subtidal zone surrounding the island.  The access corridor’s division of the island also would have fragmented species populations, damaging the diversity and health of the island ecosystem.

The Mack Point renovation is estimated to affect less than one acre of wetlands.  There is local concern that increased shipping efficiency will stimulate trade in wood chips, increasing deforestation.

Hazardous Waste: The safeguards needed for the transport of hazardous materials, such as petroleum, are already in place at Mack Point.

Socioeconomics: Sears Island initially garnered public support for its potential job creation and other socioeconomic benefits.  Currently, the renovation of the Mack Point facility is also being championed as a source of new jobs.

Environmental Review Process

NEPA, including agency consultation: FHWA accepted the lead agency role for the Sears Island port project because FHWA had been involved in MDOT’s construction of a causeway and highway connecting the port site to the mainland in 1982 with federal-aid highway funds.  FHWA also had an ongoing relationship with MDOT and of the affected federal agencies, they had a local presence in Maine.  In the fourteen years from initial proposal to cancellation of Sears Island as an intermodal site, an EA, EIS, and Supplemental EIS were prepared.  The Sierra Club’s litigation over the initial EA led to the preparation of the EIS.  The EIS took two years to prepare, mainly because the reviewing agencies had substantial disagreements with FHWA and Maine DOT.  Subsequent to the EIS, the Sierra Club won a court ruling that USCG had unlawfully issued a permit for the proposed causeway under the General Bridge Act.   FHWA and Maine DOT prepared a Supplemental EIS, which took over three and a half years, before deciding that the use of Sears Island had become economically infeasible.

In terms of agency consultation, FHWA and MDOT held at least two scoping meetings with all of the agencies participating in the EIS process.  FHWA and MDOT also circulated a preliminary draft EIS among these agencies.  Several of the agencies criticized MDOT for rejecting both Mack Point sites as impracticable alternative sites for the project.  They suggested carrying the Mack Point alternatives through the full impact analysis at the same level as the Sears Island site.  There was also disagreement particularly from FWS and EPA, over the MDOT proposal for analyzing secondary impacts, which were being limited to currently viable development alternatives.  EPA’s written comments to FHWA on the preliminary draft EIS argued against FHWA and MDOT’s position that there were no viable alternatives to the Sears Island site.  They also strongly disagreed with only analyzing secondary growth likely to occur as a result of the port while not evaluating potential development due to the newly created access road to the island.  MDOT decided to fully analyze the Mack Point alternatives in the Final EIS.  Simultaneously, EPA hired their own consultant to prepare a study on the practicability of the Mack Point alternatives.  EPA and their consultants met with FHWA and MDOT to discuss the conflicts between the findings of their respective consultants.  There was a conflict among the consultants regarding the adequacy of two berths versus six berths for the twenty-year design life.

FHWA and MDOT circulated a preliminary Final EIS for Sears Island and issued the Final EIS in the face of continued opposition from FWS, NMFS, and EPA.  Those agencies and the Sierra Club submitted additional comments on the Final EIS before FHWA issued its ROD.

As part of the COE review of the Section 404 permit application for Sears Island, the COE met with EPA, FWS, and NMFS to discuss their opposition to the project.  The COE was unable to resolve their concerns and issued the COE ROD approving the MDOT application.  EPA pursued a formal review of the COE Division Engineer’s decision through the Assistant Secretary of the Army, who issued the final COE approval.  The USCG also issued its ROD permitting MDOT to construct the causeway.

FHWA and MDOT prepared a Supplemental EIS, because subsequent to the Final EIS, FHWA and MDOT determined that a six-berth facility would require 124 acres of upland rather than 50.  MDOT subsequently determined that Sears Island had become economically infeasible.

The identification of all necessary permits for the Mack Point renovation is pending the Army Corps of Engineer’s decision regarding the nature of the dredging.  Should a review be deemed necessary, an EA would most likely be completed, with the Army Corps of Engineers serving as the lead agency.

Use of a structured process: For Sears Island, Maine DOT started with FHWA’s standard approach to NEPA reviews, but over the course of the lengthy review process they had difficulty following the approach.  In addition, Sears Island was part of a “three port strategy” for the state, so there was a larger planning context.  Maine DOT has taken a standard approach to planning the Mack Point renovation.  Maine DOT has worked with FHWA to begin the NEPA process earlier in their planning activities and to better integrate the project planning and NEPA review processes for all projects.

Effect of process on project design and alternatives: The Sears Island project plans and alternatives were altered and eventually abandoned after review.  Prior to abandoning the Sears Island site, concerns over wetlands resulted in the reconfiguration of structural designs and drainage patterns.

Multi-agency review: The proposed Sears Island project triggered substantial multi-agency review efforts as discussed above.  Some of these reviews led to additional studies and NEPA documents.

Public involvement: Initially, Sears Island had public support.  Approximately 100 people attended the public hearing on the Draft EIS.  Most of the people who spoke were from the local community and expressed support for the project because of the potential for job creation in this economically depressed area.  The shipping interests believed that the Mack Point facilities were outmoded, overcrowded, and unsafe.  The Sierra Club’s opposition focused on the underlying assumptions for the facility rather than on environmental issues.  They argued that the project was unneeded and based on erroneous or misleading and/or incorrect data in the Draft EIS.  Eventually, other environmental groups, summer residents, and others strongly objected to the facility.  Public involvement in the planning and review of the Sears Island facility consisted of sporadic public meetings until the initiation of the supplemental EIS, for which formal public meetings were regularly held.  Maine DOT has incorporated the public into planning of the Mack Point renovation through regular public meetings and a town oversight group that acts as an intermediary between the local citizens and the project group.

WATERVILLE, MAINE INTERMODAL FACILITY

Mode: Rail, Highway 	Commodity Type: Bulk goods

Ownership: Private 	Location: Urban, East

- Lead Federal Agency: FHWA

- Cooperating Agencies: FRA

- Review Agencies: FHWA, Maine DOT

- State and Local Agencies: Maine DOT

| Environmental Issues: |  |
| --- | --- |
| - Air Quality |  |
| - Cultural Resources |  |
| - Land Use |  |
| - Local Transportation |  |
| - Natural Resources |  |
| - Noise/vibration |  |
| - Hazardous Waste |  |
| - Socioeconomics |  |
| - Water Quality |  |
| Environmental Review Process: |  |
| - NEPA, including agency consultation |  |
| - Use of structured process |  |
| - Integration of NEPA and state processes |  |
| - Timing of environmental review initiation |  |
| - Effect of process on project design and alternatives |  |
| - Multi-agency review |  |
| - Public involvement |  |

- Issue

- Major Issue

Project Description

Guilford Transportation Industries (parent of Guilford Rail System) constructed a truck-to-rail 


transfer facility, including storage areas, staging areas, and other facilities.  Six 3,000-foot tracks were removed from an existing rail yard, and a new 3,000-foot by 100-foot paved loading/unloading area was built along with two new tracks that connected the new loading/unloading area to the main line.  Waterville is located inland in mid-coast Maine, and the facility’s location near an Interstate highway allows central Maine products shipped in trailers and containers to move via rail, reducing heavy truck traffic and emissions.  The facility is operational, and the FHWA has maintained a continual role by leasing packers to Guilford.  The current site was selected when environmental impacts and subsequent mitigation costs at a site in Fairfield were too high.

Environmental Issues

Air Quality: Analysis showed that the facility would reduce heavy truck traffic and emissions.  As a result, Maine DOT requested $1.2 million in funding from the Federal-aid Congestion Mitigation and Air Quality program.

Land Use: Given the location of the Waterville facility within a brownfield, the Guilford rail  yard, the facility had essentially no negative impacts on the natural, physical, or human environment.  Using the brownfield is likely an environmental improvement.

Local Transportation: The increased local truck and rail traffic was estimated to have minimal impacts to local transportation and noise and vibration.

Environmental Review Process

NEPA, including agency consultation: The Waterville transfer facility required an EA, which was completed without delay.  Given the nature of the Waterville site, no issues related to agency consultations existed.  However, for the initial site in Fairfield, the consultation with the Army Corps of Engineers and FWS led Maine DOT to conclude that wetlands mitigation would have doubled the cost of the project from $2 million to $4 million.  The early identification of this issue led Maine DOT to select the Waterville site.

Multi-agency review: The Waterville site was chosen by a multi-agency review as the alternate to the failed Fairfield site.  Environmental issues were an important factor in the selection of the site.  The multi-agency review conducted by FHWA and Maine DOT used a standardized approach in order to screen potential environmental impacts.

LOGAN AIRPORT (BOSTON) – BIRD ISLAND FLATS PROJECT

Mode: Aviation, Highway 		Commodity Type: Various

Ownership: Public Authority 		Location: Urban, East

- Lead Federal Agency: FAA

- Cooperating Agencies:  Massachusetts Port Authority (MassPort)

- Review Agencies: U.S. EPA, U.S. Army Corps of Engineers, Massachusetts Executive Office of Transportation and Construction (EOTC), Massachusetts Department of Environmental Protection (DEP).

- State or Local Agencies: (As above)

| Environmental Issues: |  |
| --- | --- |
| - Air Quality |  |
| - Cultural Resources |  |
| - Land Use |  |
| - Local Transportation |  |
| - Natural Resources |  |
| - Noise/vibration |  |
| - Hazardous Waste |  |
| - Socioeconomics |  |
| - Water Quality |  |
| Environmental Review Process: |  |
| - NEPA, including agency consultation |  |
| - Use of structured process |  |
| - Integration of NEPA and state processes |  |
| - Timing of environmental review initiation |  |
| - Effect of process on project design and alternatives |  |
| - Multi-agency review |  |
| - Public involvement |  |

- Issue

- Major Issue

Project Description

The Massachusetts Port Authority (MassPort) wished to expand its air cargo facilities at Logan Airport by constructing new air cargo buildings and a new dual taxiway.  The project area is located in the southwest corner of the airport, on a reclaimed area known as Bird Island Flats. This area adjoins an older residential neighborhood (Jeffrey’s Point) established long before the airport.  Logan is built largely on reclaimed and filled portions of Boston Harbor, and is severely land constrained because it is surrounded by active harbor channels and by the historic neighborhoods of East Boston.

The 90-acre project area was originally envisioned as also receiving limited office development, and the dual taxiways were envisioned as also providing access to a potential new runway.

The project is now effectively completed and includes the air cargo buildings, several office buildings (including one housing most of MassPort’s staff), and a large hotel.  Only a single taxiway was built and a successful linear park (the “walk to the sea”) was included in the project.

Environmental Issues of Concern

The aviation facilities, other buildings, and taxiway were all constructed on Bird Island Flats, a former wetlands area that had been filled several decades ago.  Therefore, many potential concerns related to wetlands, natural resources, endangered species habitat, and historical resources had been previously addressed and were not an issue in this project.

Air Quality, Noise/Vibration: Some original (conceptual) versions of the project would have placed dual taxiways and air cargo facilities within a few hundred yards of a neighborhood that pre-dated the airport.

A substantial mitigation strategy was developed to address this potential impact.  All formally considered alternatives included only a single taxiway, rather than the dual taxiways originally contemplated, and a scaling back of air cargo buildings.  Further, a substantial commercial/office building component was added to the alternatives.  Reaching agreement with the community that “good fences make for good neighbors,” the project in effect included a series of strategically placed and designed buildings that would act as noise and view buffers. One of these buildings is a 100-plus foot high Hyatt hotel with a rooftop restaurant, despite explicit restrictions in the state environmental impact review (EIR), and FAA safety regulations that limit buildings in the applicable area to 70 feet (in case of missed landings).  Many in the region (including some in government, media, and the public) believe that the hotel was built at this location to ensure that an additional runway could not be built.  Therefore, the surrounding neighborhoods would receive no additional flight patterns and no new sources of aircraft noise.

Local transportation:  There was at least some concern that the project might affect access to some airport parking facilities and lower the level of service at certain local intersections.  MassPort’s initial analysis of the issue proved inadequate and the project was delayed for about two months by the EOTC until the analysis was redone.  Nevertheless, in the end, no significant impact was found regarding local transportation.  Additional highway and local access issues later arose due to the shift of the Ted Williams Tunnel portal to the project area.  However, these issues were addressed under the EIS for the Central Artery/Tunnel project.

Land Use, Socioeconomics:  The adjoining neighborhood was concerned about the compatibility of the proposed development with the neighborhood and the possible adverse impacts to the host community.  In addition to noise and vibration impacts, the community was concerned by the prospect of a view dominated by air cargo warehouses.

The development of more attractive office buildings and the hotel, with restaurants and other amenities, was deemed more compatible with existing land uses.  The linear park further helped shift the project’s image from that of an eyesore to an improvement to the community.  Finally, the development and jobs that came with the constructed alternative were viewed as being a greater local benefit than the air cargo facilities.  The cargo facilities were designed primarily for the small package express carriers and were considered primarily to benefit the metropolitan region and not the local area.

Environmental Review Process

NEPA, including agency consultation, and integration of NEPA and state environmental review processes: An early conceptual version of the project envisioned dual taxiways serving new air cargo hangers and possibly access to a new runway.  Although an expedited federal review of this version was possible, state environmental review requirements made federal review alone, expedited or not, insufficient to allow construction.

The federal EA was conducted at the level of an EIS for the purpose of maintaining a review process parallel to the state EIR.  MassPort believed they had to comply with both regardless.  At least two factors made MassPort focus more closely on the state process.  First, MassPort believed they would likely be sued under state law, and therefore decided to follow the state process most closely for defensive purposes.  Second, the state process explicitly would permit MassPort to progress to 30 percent of project design before permitting, minimizing the net delay to the project by continuing preparations while resolving permitting and litigation issues.

MassPort still ended up making considerable efforts to get the state EIR approved, as the Massachusetts EOTC denied approval and delayed some elements of the process (such as the approvals for the local transportation analysis, as discussed above).  Local political considerations also affected this process in complex ways.  For example, the EOTC was concerned that the project might preclude or constrain future transportation investments in the area.  At one point, MassPort was subject to litigation from both a citizen group opposing the project, and from the Massachusetts EOTC.

Effect of process on project design and alternatives: As soon as it became apparent at the conceptual level that airport expansion might occur, Jeffrey’s Point and East Boston were prepared to mobilize. A citizen’s group called Airport Impact Relief, Inc. (AIR, Inc.) was organized to work on this and other airport impact issues.  As a result, from the start of the project design and planning process, the airport was proactive in incorporating citizen concerns into the project and in formulating alternatives.

Public involvement: Community concerns regarding the project existed for years prior to the projects formal initiation due to previous impacts to the neighborhood from the airport operations.  MassPort staff recognized that the community did not trust them and that they would be sued regarding this project, regardless of how they proceeded.  To gain credibility with the community and to better ensure a legally defensible environmental review, MassPort provided the community with several hundred thousand dollars prior to the definition of alternatives (although at least one conceptual vision of the project had been informally “floated” prior to this formal community involvement).  This money was to be used to hire noise, air quality, and land use consultants, approved by MassPort, but selected by the citizens’ groups, to directly participate in developing the alternatives.  MassPort’s planning staff forcefully pursued this strategy with the Authority’s leadership, arguing “it would be better to pay for participation and consultants now than to have to pay for lawsuits later.”  Establishing this substantial community joint ownership of the project early on was highly effective in precluding the re-examination of issues.  For example, once the primary citizens’ group had spent considerable effort helping to design the office buildings to provide noise mitigation barriers, they could not credibly oppose the project based on insufficient noise reduction.

THE FREIGHT ACTION STRATEGY (FAST) CORRIDOR

Mode: Rail, Highway, Marine 		Commodity Type: Various

Ownership: Public/Private 		Location: Urban, Northwest

- Lead Federal Agency:  FHWA, FTA

- Review Agencies: NMFS, FWS, EPA

- Cooperating Agencies:  Not Applicable

- State or Local Agencies: Washington State DOT, Puget Sound Regional Council

| Environmental Issues: |  |
| --- | --- |
| - Air Quality |  |
| - Cultural Resources |  |
| - Land Use |  |
| - Local Transportation |  |
| - Natural Resources |  |
| - Noise/vibration |  |
| - Hazardous Waste |  |
| - Socioeconomics |  |
| - Water Quality |  |
| Environmental Review Process: |  |
| - NEPA, including agency consultation |  |
| - Use of structured process |  |
| - Integration of NEPA and state processes |  |
| - Timing of environmental review initiation |  |
| - Effect of process on project design and alternatives |  |
| - Multi-agency review |  |
| - Public involvement |  |

- Issue

- Major Issue

Project Description

The Transportation Equity Act for the 21st Century (TEA-21) establishes the National Corridor Planning and Development program.

This program cited the FAST Corridor as one of its 43 high priority corridors.  The FAST Corridor, stretching from Tacoma to Everett within the State of Washington, is a statewide initiative composed of fifteen individual projects.  These individual projects, twelve grade separations and three port access projects, are designed to function as an integrated unit.  The Puget Sound region is the second largest freight gateway for containerized cargo in North America, and the volume of container traffic is expected to double by 2015.  The FAST Corridor projects are intended to facilitate the transfer and transport of this increasing volume of trade commodities.  The fifteen projects have been planned at the corridor level by the Puget Sound Regional Council and the Washington State DOT (WSDOT), the fifteen cities where the individual projects will be completed, the ports, the Burlington Northern Santa Fe (BNSF) Railroad, and the Union Pacific (UP) Railroad.  All of the projects have begun the planning process, and a number of them (e.g., SR 519, 3rd St. SW, Port of Tacoma Road, E Marginal Way, and S 277th St.) are ready to begin construction imminently.  Funding for the projects varies and includes federal, state, and private (railroads and ports) financing.

Environmental Issues of Concern

Air Quality: The FAST Corridor is in an air quality maintenance area.  The Washington State DOT has indicated that by reducing congestion for both freight and general purpose movements, the fifteen projects will improve travel speeds around ports, rail yards, and grade crossings and thereby reduce air emissions.

Cultural Resources: Cultural and historical issues have been identified as a concern.  A number of the projects, for example SR 519, are being built on mud flats, where the potential for discovering Native American artifacts is high.  This issue will be better defined as studies progress.

Local Transportation:  All 15 projects are  designed to improve freight mobility in the corridor by improving local transportation.  The FAST Corridor partners will achieve this benefit by reducing delays at highway/rail grade crossings through grade separations and by improving rail and truck access to ports.

Natural Resources:  Some projects may have potential impacts to endangered species and some have had impacts to wetlands.  The recent addition of the Sockeye and Chinook Salmon to the list of threatened and endangered species has created new environmental review and consultation issues not usually encountered in urban projects.  Puget Sound and its surrounding river systems are habitat for the endangered Sockeye Salmon.  Damage to the Sound, the rivers, or to adjacent riparian habitats may threaten the Sockeye and their habitat.  Separately, additional land required to create grade separations has required filling in wetlands for some projects.

Environmental Review Process

NEPA, including agency consultation: The projects receiving federal funding have all begun the NEPA process.  Because each project has “independent utility” (i.e., they are not operationally dependent on each other to succeed), the Corridor as a whole did not require review under one NEPA document.  Instead, the projects are covered under separate EAs and EISs.  The FAST Corridor partners selected the projects because they scored high in a state technical ranking process that evaluates economic benefit and the feasibility of mitigating community impacts.  This approach helps to avoid lengthy environmental reviews.

To address the new endangered species consultations required by the recent listings of salmon, three counties have created a TriCounty ESA Response Team.  This Team is an informal association and has no independent powers.  Consultations with NMFS are coordinated with the Tri-County ESA Response Team and follow long-range and short-range approaches.  The long-range approach is to prepare a recovery and conservation plan for each of the six river basins in the three-county area that will support the recovery of the salmon.  The preparation of the plan is estimated to take between 18 months and three to four years.  The short-range approach is to identify and pursue other actions likely to have an immediate beneficial effect.  These include capital investments, regulation of activities within habitat areas, the level of enforcement of various actions, and management practices of government agencies.  Ideally, the Team would like NMFS to recognize their early, proactive, and beneficial actions as a basis for giving some umbrella coverage for activities rather than protracted project-by-project consultations.

The FAST Corridor partners have been grappling with several issues.  For example, they have had to address with NMFS the issue of how the salmon listings will affect projects that are already underway, as well as projects that are still in the planning and environmental review stages.  The ESA Response Team has been trying to determine what processes and procedures would be timely and give the level of review that is needed.  WSDOT has been proactive in negotiating, facilitating, and evaluating transportation projects, however, they believe that even this exemplary effort will involve project delays.  In addition, the FWS is responsible for the Bull Trout, which may be listed soon (FWS has jurisdiction over freshwater species).  They are concerned about having two processes and two biological assessments with two different agencies when both the salmon and trout are potentially affected.  As a possible mitigation strategy, the ESA Response Team is considering whether NMFS might approve the concept of basinwide habitat banking.  Under the banking approach, a pool of mitigation sites is preserved for use to offset impacts from individual projects within the basin.  Another issue is that Native American groups can bring treaty rights to bear if the salmon are not protected.

Integration of NEPA and state environmental review processes: Some of the projects are only receiving state funding and only trigger the State Environmental Policy Act (SEPA), and not NEPA.  For those projects that trigger both NEPA and SEPA, the two processes are very similar and their integration has not caused any problems.  On another level, while the independent nature of these projects did not require a NEPA review for the corridor, the Washington State Growth Management Act requires the Regional Council to review the projects as a whole, seeking consistency throughout the Corridor.  The fifteen projects were assembled and screened at the regional level by the Puget Sound Regional Council.  This higher level of screening and review under the Growth Management Act allowed the state and regional planners and decision-makers to balance the environmental impacts of each project with the regional transportation benefits.

Multi-Agency Review: Multiple agencies have been involved in the review of these projects and it appears that coordinating the review process and keeping it on schedule has not been an issue.

Effect of Process on Project Design and Alternatives: The screening and ranking process used by WSDOT and the Regional Council led to the selection of projects with fewer impacts.

Public Involvement:  No major issues or delays have been associated with the public involvement process. When a local community, such as the City of Auburn, opposes one of the projects, the local planners address the community’s concerns.

The fifteen cities involved in the Corridor projects are all host communities in the sense that they have the infrastructure that supports this flow of commodities.  However, over 70 percent of the imported containers at Puget Sound ports are headed to points elsewhere in the U.S.  Some host communities have voiced concerns over projects causing local impacts without appearing to create reciprocal benefits.  WSDOT and the Regional Council have had a public outreach campaign to raise public awareness about the value of facilitating this flow of commodities.  In their campaign they have indicated that many Washington State exports are bulk items (such as apples and grain), which have relatively low value per ton, while the imports passing through tend to be higher value goods.  Those higher value goods generate most of the shippers’ profits.  The State wants to attract and keep those shippers in Washington, because once they are there, they prefer to carry the State’s exports with them on backhaul trips.  Backhauling allows Washington farmers and manufacturers to reach markets that are otherwise unattainable.  They have pointed out to the public that without a large volume of high-value imports and an abundance of backhaul capacity for lower-value exports, it would be difficult to attract the freight companies that ship many of the State’s goods to international markets.  They estimate that Washington exporters save $150 to $500 per container because of this advantage.

| Environmental Issues: |  |
| --- | --- |
| - Air Quality |  |
| - Cultural Resources |  |
| - Land Use |  |
| - Local Transportation |  |
| - Natural Resources |  |
| - Noise/vibration |  |
| - Hazardous Waste |  |
| - Socioeconomics |  |
| - Water Quality |  |
| Environmental Review Process: |  |
| - NEPA, including agency consultation |  |
| - Use of structured process |  |
| - Integration of NEPA and state processes |  |
| - Timing of environmental review initiation |  |
| - Effect of process on project design and alternatives |  |
| - Multi-agency review |  |
| - Public involvement |  |

- Issue

- Major Issue

West Hayden Island, Portland, Oregon

Mode: Rail, Marine, Highway 		Commodity Type: Various

Ownership: Public/Private 		Location: Urban, West

- Lead Federal Agency: U.S. Army Corps of Engineers

- Cooperating Agencies:  U.S. DOT/FHWA, USCG

- Review Agencies: U.S. EPA, NMFS, FWS

- State or Local Agencies: Port of Portland, Portland Metro (Portland’s MPO), City of Portland, Oregon DOT, Oregon FWS

Project Description

Hayden Island is located in the Columbia River and is adjacent to the Port of Portland. Originally a set of two islands subject to seasonal river inundation, the 1920’s placement of groins by the Army Corps of Engineers, and the subsequent accretion of silt, created Hayden Island.  The damming of upstream portions of the Columbia River has controlled river level fluctuations, making the island permanently habitable.

In 1983, Portland Metro (the Portland MPO) designated Hayden Island as within its Urban Growth Boundary, and determined that the island was suitable for marine industrial uses. The eastern end of the island was subsequently developed with housing and commercial uses.  In 1991, Metro and the Port of Portland identified the western end of Hayden Island as one of the last remaining large locations in the metro area in which deep draft shipping could be developed.  In 1994, the Port purchased 827 acres on the western end of the island for deep draft shipping and as an environmental reserve.  These uses were confirmed in the 1995 Regional Comprehensive Plan prepared by Portland Metro.  It was also determined that the proposed land uses for Hayden Island would best be achieved were the island to be annexed by the City of Portland and re-zoned under its processes; this process is underway.  In addition to its expected use for deep draft shipping, the West Hayden Island facility would be able to service barge traffic from the Columbia River.  The West Hayden marine terminal site is immediately across the channel from other port facilities, is linked via a spur to a rail line that bisects Hayden Island, and has nearby access to an Interstate Highway that currently serves Hayden Island.  However, the bridge (Interstate-5) that serves the eastern end of Hayden Island is currently congested, with demand at capacity during peak periods.

The Port of Portland developed a three-phase plan for the development of the West Hayden Island intermodal facility. Depending on market demand, the development plan will be implemented over approximately a thirty-year period.  Phase One consists of the development of an intermodal grain facility.  Phases Two and Three include the establishment of automotive distribution and general marine cargo uses.  Integral to the feasibility of Phases Two and Three is the construction of a road bridge to link the western end of Hayden Island with the Port’s facilities on the mainland to avoid needing access to I-5.  Construction of this bridge still requires funding and would require a Supplemental EIS for the project.

The commodities transferred at the West Hayden facility under Phase One will primarily be transported by rail.  It is expected that peak truck traffic serving the Phase One facilities would be less than 60 vehicles per hour.  Under Phases Two and Three, rail will serve many cargo needs, but trucking will be increasingly important (for example, automobiles being distributed within the Pacific Northwest by truck).  However, the new bridge would meet the needs of the intermodal facility and alleviate traffic impacts on the eastern (I-5) bridge. The intermodal facility is projected to cost $120 million to construct (for all phases), and the bridge is estimated to cost an additional $44 million. The Port of Portland is involved in a concurrent federal and local permitting process, in which it is composing a Draft EIS of the full three-phase plan for the Army Corps of Engineers.  The Port is simultaneously seeking annexation of the site to the City of Portland and the consequential re-zoning and application of local zoning laws.

Environmental Issues of Concern

West Hayden Island was predominantly created, and its former wetlands impacted, under activities conducted during the 1920s and 1930s.  Subsequently, many dredge spoils were deposited on the island during the 1950s and 1960s.  Therefore, many potential concerns related to wetlands, natural resources, endangered species habitat, and historical resources were not directly at issue for this project, as they involved pre-existing conditions.  Nonetheless, there are several habitat, wetlands, and natural resources issues still of concern on this project and are discussed below.

Cultural Resources:  Hayden Island, which was once described by Lewis and Clark as the “canoe image island” was assumed to potentially have been a site of Native American activities. However, an archeological investigation found no evidence of artifacts.

Local Transportation and Noise/Vibration: The West Hayden facility has “host community issues” stemming from the East Hayden Island residents’ concerns that the intermodal facility will negatively impact their access to I-5. East Hayden Island’s sole highway access, the I-5 bridge, is already congested.  The trucks would pass through a commercial area, including some retail and a hotel, which could produce noise and vibration impacts.  Truck routes to the I-5 access ramps would not pass through any residential areas and under Phase I would not exceed 60 vehicles per hour.  Nonetheless, there is significant community concern regarding the impacts of the truck traffic.

The Port has proposed a (new) West Hayden Island Bridge as a condition for Phases Two and Three to commence.  However, there is some contention whether the Port would legally commit to not proceed with these Phases without construction of the bridge.  The Port is seeking federal funding (hopefully earmarked) for half of the $44 million cost of bridge construction.  The Port has offered to make $4.5 million in road improvements on the I-5 highway and bridge, in order to help mitigate highway and bridge impacts. It appears that most of the community believes that $4.5 million dollars in improvements would be inadequate to mitigate the ramp congestion and noise/vibration impacts the facility’s truck traffic would create.

Natural Resources and Wetlands: The 827 acres that the Port acquired is a riparian habitat composed of intermittent wetlands in the lowlands and black cottonwood forest in the uplands, with a variety of small mammals and nesting grounds for migratory neotropical birds.  A dispute among the parties over the size of these areas (for example, the cottonwood area is described by different parties at from 240 to over 400 acres).  The wetlands consist of an intermittent creek and lake.  EPA has suggested that a significantly greater portion of the island may be considered as wetlands, as the island’s mean 15-foot elevation makes much of it susceptible to periodic flooding despite the upriver dams.  No threatened or endangered species are present on the island.  Nonetheless, the riparian forests, particularly the cottonwood, are considered critical habitat.  Much of the area, including some of the cottonwood forest, includes dredge spoils that have been deposited for decades.

The Port plans to use eight million cubic yards of sand to raise much of their property’s mean elevation from 15 feet to 30 feet, which would affect approximately 600 acres.  This would include filling some wetlands and leveling some woodland. The remaining 227 acres of West Hayden Island would remain as open space and wooded wetlands with a 50-acre recreational area.  The Port has proposed greater than one-to-one mitigation of wetlands and forest loss.  However, there is considerable concern about habitat recovery time and the impacts of substantial habitat fragmentation.  Partially because of the effects of Portland’s Urban Growth Boundary, West Hayden Island represents one of the largest cottonwood forests in the area providing critical interior habitat for certain species.  Although not pristine, the location has been fenced off from people for approximately 15 years.

Through clean-up of dredge spoils, mitigation and restoration efforts, and protection of open space, the Port asserts that the proposed action would improve the island’s environmental condition.  This view is disputed by the resource agencies and some environmental groups because of the substantial habitat impacts, which they consider as outweighing the clean-up benefits.  Furthermore, the island remains far below its full environmental potential, as characterized by its condition prior to the deposition of dredge spoils.  Several environmental groups want the island restored to its circa 1940 environmental condition as an unspoiled, undeveloped habitat.  Some local citizens who oppose the degradation of wetlands have sued the Port and are pushing for the revitalization of the island’s historic wetlands through the resumption of seasonal natural inundation from the Columbia River.  Concern exists over the interdependence of the wetlands and the health of the Columbia River, and the implications for endangered fish stocks.

Environmental Review Process

The project is currently in the DEIS phase, which is expected to be completed soon.  In 1997, the Port of Portland anticipated initiating a DEIS for the first five years of development at the West Hayden intermodal facility (now known as Phase One).  At the Port’s request, the Army Corps of Engineers later decided to accept a DEIS for all thirty years (three phases) of proposed development at the facility, and the Notice of Intent (NOI) was issued on October 27, 1998. The change in the scope of the DEIS delayed project initiation by approximately one year, but will eliminate the need to prepare additional EISs in the future for Phases Two and Three.  While the new bridge is described as occurring in Phase One in the NOI, it is still unfunded and is currently proposed for Phase Two, and possibly may not be built.  Thus, when plans and funding for the West Hayden Island Bridge are finalized, it will likely require a supplemental EIS.

This aggregation of the three phases has been disputed by environmental groups, and may also be opposed by the resource agencies.  They believe that the three phases have independent utility, the phases are subject to independent timelines, and have little advantage from physical contiguity.  These parties believe that there may be a number of other potential sites for these facilities if sited independently, and that there is no compelling rationale for their co-location.  Among these sites are locations within already developed Port properties, or at the Port of Vancouver immediately across the channel.

Agency consultation: At an informal level, development of this site (including by a previous owner) has been an issue for a number of years, and interaction between agencies has at least occurred at the informal and preliminary level.  The Port also distributed scoping documentation early in project initiation. Metro has been coordinating with the Port for a number of years, which has facilitated the project’s continued progress.  For example, coordination with the MPO and the city has resulted in a coordinated process that is facilitating zoning and building permit issues.  Similarly, FHWA’s inclusion helped generate a viable solution (the new bridge) to more significant potential local transportation impacts.

However, a lack of internal resources prevented several agencies from engaging substantially in early action, and staff turnover may have negated institutional knowledge of earlier considerations.  The Army Corps has staff restrictions on involvement prior to the formal permit process; the FWS described that staff workload prevents their early involvement unless the proponent makes it clear that such involvement is needed to help develop a project.  FWS described the agency interaction as lacking genuine effort to engage in early discussions.  While all formal requirements were followed, the project substantially changed from the NOI, and the impression was received that the community and other agencies were already on board in support of the project.

Integration of NEPA and state environmental review processes:  The Port of Portland has concurrently pursued the NEPA and local processes. The Port intends to submit a Preliminary Draft EIS to the Army Corps of Engineers in four to five months, and anticipates that the Federal process will be complete in the fall of 2001. The Port estimates that the permits required for annexation to the City of Portland and the application of local zoning laws will be completed by September 2000.

Public involvement:  The characterizations of this process have been widely divergent.  The community of East Hayden Island has been aware of possible development for a number of years.  One neighborhood’s early discussions with FHWA and the Port led to formal inclusion of the new bridge as a Phase One project component in the NOI.  Community views were also integrated into the planning process through an Advisory Committee, which included local citizens, environmental groups such as the Audubon Society, and multi-function agencies such as Metro (which has responsibilities including land use planning, open space, parks, and salmon recovery). The Port of Portland has used public meetings to present the plans for the intermodal facility and to give the public a forum in which they can voice their concerns.  While not fully resolved, the Port hopes to be able to leverage its close coordination with the City and series of public participation activities into the successful resolution of environmental and community concerns.  Negotiations are continuing to avoid litigation over the extent of impact avoidance and mitigation.

Current Status:

This project has developed and the environmental review process and public involvement conducted in a manner that may substantially delay development of a new port facility.  The Port’s preference appears to be development that will allow maximum flexibility and expansion of their own facilities in future years.  Such an objective would be accomplished by maximizing development rights at West Hayden Island, still leaving several smaller existing port parcels vacant for future development.   However, to accomplish this objective, delays have already been encountered, such as an approximate one-year incremental delay due to shifting the scope of the DEIS to incorporate all three project phases.  The environmental review process has been considered by all parties to be a major influence shaping the project, including factors such as the size of the development and the possible inclusion of a bridge.  Based on misgivings about the process, the FWS is strongly leaning toward opposing the DEIS based on inadequate “Purpose and Need” and Alternatives Analysis; they believe they will be joined by several other agencies in this position.  Community and environmental groups have shifted from conditional acceptance to outright opposition of the project, and appear poised to litigate to prevent its occurrence.

Port of Oakland – Berths 55-58 and FISCO Disposal and Reuse Projects

Mode: Marine, Rail, Highway 		Commodity Type: Intermodal Containers

Ownership: Public Authority		Location: Urban, West

- Lead Federal Agency: COE, U.S. Navy

- Cooperating Agencies:  none

- Review Agencies: FHWA, FWS, NMFS, EPA, Bay Conservation and Development Commission (BCDC), State Lands Commission.

| Environmental Issues: |  |
| --- | --- |
| - Air Quality |  |
| - Cultural Resources |  |
| - Land Use |  |
| - Local Transportation |  |
| - Natural Resources |  |
| - Noise/vibration |  |
| - Hazardous Waste |  |
| - Socioeconomics |  |
| - Water Quality |  |
| Environmental Review Process: |  |
| - NEPA, including agency consultation |  |
| - Use of structured process |  |
| - Integration of NEPA and state processes |  |
| - Timing of environmental review initiation |  |
| - Effect of process on project design and alternatives |  |
| - Multi-agency review |  |
| - Public involvement |  |

- Issue

- Major Issue

Project Description

While these two NEPA actions are legally separate, for practical purposes they represent two elements of the same physical project.  The Port of Oakland is expanding its facilities by adding four additional containership berths and one tug berth through widening and deepening of the existing inner harbor channel, bank excavation, fill land reclamation, and wharf construction. The project also involves realignment of Seventh Street and construction of a short access road in order to handle additional traffic anticipated as a result of the project. Additionally, the project includes substantial demolition and reconstruction (containment dike construction and land fill) of a former U.S. Navy facility (the Fleet and Industrial Supply Center, Oakland, or “FISCO”) in the adjacent Middle Harbor, with conversion of the FISCO facility into container handling facilities, the Middle Harbor Shoreline Park and associated promenades, and restoration of natural habitat.  The overall project site covers approximately 250 acres of the former FISCO, approximately 105 acres of the Union Pacific (UP) Railyard, and 118 acres of water area. The Berths 55-58 Project and FISCO Disposal and Reuse Project are independent from, but associated with, the Oakland Harbor Navigation Improvement Project, which will further deepen some of the berths and channels from the 42 feet envisioned in this project to 50 feet, and will include additional restoration of natural habitats.

Environmental Issues of Concern

Cultural Resources: The extensive demolition and reconstruction of a former Navy base raised questions concerning historical resources. The FISCO complex was found to have some historical significance. In agreement with the State Historical Preservation Officer (SHPO), the facility’s historic training walls were incorporated into the new park as jetties, historic pilings will be left in place as a historic exhibit, and materials from demolished buildings will be reused.

Natural Resources, Wetlands, and Water Quality: The construction of the facility threatens potential feeding areas for the California Least Tern and nesting areas for the Brown Pelican. The FWS was responsible for these habitat issues, which fell under the Endangered Species Act and the Migratory Bird Act, respectively.  Light pollution mitigation will be undertaken, and container gantry cranes will be regularly inspected to insure they are not providing roosting/nesting habitats for predatory raptors.  There was additional concern about potential impacts to eelgrass beds, although this was found to be mitigable through offsetting plantings and sediment restoration in the Middle Harbor.

Dredging and dike reconstruction are required for the facility, for which the Army Corps of Engineers has provided the required permits.  The fill has not been found to be contaminated. The project was designed to create 30 new acres of port terminal area and 5 acres of new parkland, without involving any net fill increase in the Bay (this is possible through channel widening along the berths). A strong mitigation plan will prevent significant adverse localized effects except on one small eelgrass bed.

Ballast water discharge concerns by NMFS resulted in a Biological Opinion of possible adverse effects (nonindigenous species invasion) on several fish species from ballast water discharge increases associated with additional maritime traffic. NMFS negotiated with the Port regarding reasonable and prudent measures to mitigate the impact, which in the end did require the Port of Oakland to enter into an MOU with NMFS. As a result, the Port will contribute $200,000 over four years (NMFS originally requested $2 million) to aid in the development and implementation of the State’s ballast water monitoring and treatment program.

Air Quality, Local Transportation, Noise/Vibration, and Public Involvement:  Residents originally voiced concerns over air quality, noise and vibration, and increased truck and rail traffic. A lawsuit focused primarily on the air quality issues had been filed in October 1997 (in response to the FISCO EIS), but was settled through a Consent Decree in less than four months.   Both prior to the litigation and as a result thereof, the Port worked extensively with the community to develop a range of mitigation and enhancement actions. For example, $660,000 was transferred from the Port to AC Transit (the local transit agency) for bus engine retrofitting, and some maritime terminal equipment will be retrofitted with emissions control devices.  In total, $9,000,000 will be spent on the Port’s Air Quality Mitigation Program.  In addition, as described above, the Middle Harbor Shoreline Park and associated promenades were incorporated into the project at a very early date in response to community requests.  While the nearest community (West Oakland) is minority and low-income, they were found to be subject to no significant and disproportionate adverse impacts.  Public sentiment has shifted to widespread local support for the project.

Environmental Review Process

NEPA, agency consultation: The Army Corps of Engineers recently completed the Environmental Assessment of the project, having issued its Public Notice for comments regarding the Section 404 permit for the project on September 1, 1999.  A Finding of No Significant Impacts (FONSI) was made, and therefore no Environmental Impact Statement was found warranted for the Berths 55-58 Project (a state EIR was completed).  The FISCO Disposal and Reuse Project had its FEIS/EIR completed in July 1997.  On the basis of CEQA criteria, the Reduced Harbor Fill Alternative was found to be the environmentally superior reuse alternative, and was selected as the preferred alternative.  A FEIR/EIS/FS was also completed for the adjacent Harbor Navigation Project.  Although the Corps and Navy have been the official lead agencies for the project, the Port has effectively taken a lead role in much of the effort and has carried out the planning of the facility on behalf of the Corps and Navy.  The Corps has also issued a Section 404 permit, following the November 29 signing of the endangered species consultation by NMFS.

Multi-Agency Review:  The Corps had initiated a joint consultation for the Berths 55-58 Project and Harbor Navigation Project in June 1999, which FWS agreed to, but NMFS requested that the consultations be separated. The Corps, because of staff constraints, did not reinitiate the consultation with NMFS until September 27, 1999.  While NMFS did commence their work on their biological opinion prior to the formal reinitiation, their own staff constraints resulted in the opinion not being completed until mid-November.  This process resulted in an MOU between the Port of Oakland and NMFS, in which the Port agreed to help fund a state study and effort to minimize the potential impacts of nonindigenous species introduction from ballast water discharge.

Integration of NEPA and state processes:  The NEPA and California environmental review requirements include review roles for several state agencies.  In particular, the State Lands Commission and the Regional Water Quality Control Board were responsible for issuing permits regarding fill and water quality issues, respectively.  Furthermore, the Bay Conservation and Development Commission holds authority over all projects impacting San Francisco Bay, and undertook its own comprehensive review of the project prior to issuance of its permit.  Early coordination and consultation by the Port with each of these entities facilitated the project’s progress.

The Port Authority completed a Section 106 historical review process for the former FISCO facility, and arranged for a combination of illustrative preservation and adaptive reuse to mitigate the extensive demolition.  Arrangements for conversion of the FISCO Navy facility and property transfer have been made with relatively little difficulty with the completion of the FEIS/EIR, as well as certain facilitating legislation that simplified the property transfer.

ALAMEDA CORRIDOR

Mode: Rail, Marine, Highway 		Commodity Type: Various

Ownership: Public/Private 		Location: Urban, West

- Lead Federal Agency: FHWA, FRA

- Cooperating Agencies:  Surface Transportation Board

- Review Agencies: U.S. EPA, Surface Transportation Board, FWS, COE

- State or Local Agencies: Caltrans and Alameda Corridor Transportation Authority

Project Description

| The Alameda Corridor will be a twenty mile consolidated railroad link, centered along Environmental Issues: |  |
| --- | --- |
| - Air Quality |  |
| - Cultural Resources |  |
| - Land Use |  |
| - Local Transportation |  |
| - Natural Resources |  |
| - Noise/vibration |  |
| - Hazardous Waste |  |
| - Socioeconomics |  |
| - Water Quality |  |
| Environmental Review Process: |  |
| - NEPA, including agency consultation |  |
| - Use of structured process |  |
| - Integration of NEPA and state processes |  |
| - Timing of environmental review initiation |  |
| - Effect of process on project design and alternatives |  |
| - Multi-agency review |  |
| - Public involvement |  |

- Issue

- Major Issue

Alameda Street, extending from downtown Los Angeles to the Ports of Los Angeles and Long Beach. The ports comprise the largest seaport complex in the U.S. and the third largest in the world.  The project will consolidate the rail operations of four mainlines (one owned by Union Pacific (UP), two by Southern Pacific (SP), which have merged since the environmental analysis began, and one by Santa Fe (ATSF), which later merged with Burlington Northern). Currently, trains operating to and from the ports run on 90 miles of track.  In 1993, 32 trains per day operated to and from the ports.  The average speeds on these lines are in the range of 10 to 20 miles per hour because of a large number of grade crossings and other restrictions.  The four mainlines have 198 at-grade street crossings and have over 70,000 people living within 500 feet.  The ports are expected to experience a shift toward an increased reliance on containers with a commensurate increase in rail activity.  According to the EIS, part of this growth is attributable the development of on-dock or near-dock railyards that will result in an estimated 23 percent reduction in truck movements by the year 2020.  By the year 2020, an estimated 97 trains per day will be moving in and out of the ports.  The “Purpose and Need” as stated in the EIS is that utilization of existing unimproved corridors under this scenario will result in impairment of rail and street traffic flow and increased noise and air pollution.  The depressed trainway will have two mainline tracks in addition to an at-grade track serving local industries.  Alameda Street would be reconstructed to accompany the depressed track.  Overpasses configured to match existing street geometry would allow passage across the depressed trainway at designated streets.

Environmental Issues of Concern

Air Quality: For the purposes of CEQA, the construction of the corridor would produce emissions of criteria pollutants and fugitive dust in quantities above significance thresholds established by the South Coast Air Quality District.  These construction emissions were not considered substantial under NEPA.  Under the No Build alternative, locomotive, auto, and truck regional criteria emissions would increase substantially.  The proposed action was projected to have a substantial reduction in all criteria pollutants.  Car and truck emissions decline slightly.

Cultural Resources: The Corridor would avoid the Watson Station, which had been determined eligible for the National Register.  Findings of No Effect were reached for several structures and a Finding of No Adverse Effect was reached for the Redondo Junction Historic District.  The EIS indicated that the area between 109th and 111th Streets was sensitive for archaeological resources.  One site, located in the vicinity of the midpoint of the Corridor, was reported to have burials when it was discovered in 1969.  However, it is outside the area of potential effect.  The other site is located on the Dominquez Hills overlooking Compton Creek and the Los Angles River.  The site was discovered in 1969 and was described as a seasonal village or camp site which had already been effectively destroyed by roads and grading activity.  In addition, a Phase I Archaeological Study was conducted in 1992.  The results of the archaeological field reconnaissance revealed no surface evidence of prehistoric or historic archaeological resources within the project Area of Potential Effects.  Therefore, the EIS concluded that the APE is considered to contain no known important prehistoric or historic archaeological resources with the possible exception of the area in the vicinity of the site with the potential burials.  The EIS indicated that a qualified archaeologist would be contacted promptly if the construction of the project encountered unanticipated cultural resource remains.  The fact that burials have been found in the past indicates the possible presence of an important resource. Therefore, they planned to conduct archaeological monitoring in that area.  During the construction process 30 Native American skeletons were discovered.  This led to the preparation of a recovery plan.

Land Use: Under the No Build alternative, increased train traffic could potentially have substantial incompatibility with some adjacent land uses.  The construction of the Alameda Corridor does not represent a major change to existing uses and will not impede the achievement of local planning goals.

Local Transportation: The construction of the Alameda Corridor could result in potentially substantial traffic disruption at various locations throughout the construction period.  During the operations phase of the No Build alternative, the increased train volumes and deteriorated roadway conditions would result in increasing delays, slower speeds, and less capacity to handle future demands.  The operation of the Alameda Corridor is expected to improve overall traffic handling capacity.  Grade separated crossings over the depressed railroad, left turn pockets, and improved signalization would improve traffic conditions in the project area.  In terms of traffic capacity at intersections, the No Build alternative is estimated to have substantial impacts to three intersections in 2010 and 65 intersections in 2020.  The operation of the Alameda Corridor is estimated to result in substantial impacts at two intersections in 2020.  The addition of turning lanes would mitigate these impacts.  Under the No Build alternative, auto/train accidents would increase as the growth in freight trains increases.  The Alameda Corridor would reduce those accidents because conflicts would be eliminated along the Corridor and train volumes will be reduced on the other rail lines.  The state is required to implement traffic maintenance plans during construction to mitigate temporary impacts.

Although the project may increase the potential for accidents involving train derailments and spills by increasing the number of trains, the provision of improved tracks and equipment and cross-street grade separations would decrease the accident potential.  The likelihood of injuries or property damage would be substantially reduced due to containment provided by the trench.  The potential for accidents on the other lines would decrease as train activity decreased.

Noise/vibration: The construction of the corridor could produce intrusive noise at some locations.  Train operations under the No Build alternative would have substantial impacts for 69 residences.  For the portion of the Proposed Action within the Alameda Corridor, 92 residences and two community facilities would experience a substantial impact.  With the construction of noise barriers, the residual impacts would potentially effect eight residences and two community facilities.  The use of sound insulation for buildings will be explored and implemented where practicable.  Along the SP, UP, and ATSF branches the proposed project would reduce residential noise exposure from 29,800 to zero.  Potentially substantial vibration effects could occur during operation at certain points.  Various design and operational approaches will be used to reduce vibration potential, including relocation of trackwork away from sensitive areas, installation of ballast mats, and use of movable points frogs where needed.

Socioeconomics: The construction of the Alameda Corridor will require up to 40 full acquisitions and up to 16 partial acquisitions of commercial properties.  Under the Uniform Relocation and Assistance Act, comparable housing has been identified and assistance with relocation for both residents and business people has been provided.  In terms of effects on schools, the Alameda Corridor would greatly reduce train conflicts for students walking across Alameda Street.  However, the project would result in increased noise effects at two schools located along the corridor.  The use of sound insulation for buildings will be explored and implemented where practicable.  The residual impact is expected to be potentially substantial.  In addition, the project would result in noise impacts at one church.  The use of sound insulation for the building will be explored and implemented where practicable.  The residual impact is not substantial.

Construction of the project will have substantial impacts on businesses along the corridor.  They will experience reduced vehicular and pedestrian access, traffic detours, noise and other inconveniences.  Mitigation measures are expected to reduce the impacts to potentially substantial and include signs to direct customers along alternate routes to businesses; traffic management to maintain access; and a business outreach program.  Any relocated businesses would be compensated under the Uniform Relocation Assistance and Real Property Acquisition Policies Act.

The EIS addressed environmental justice.  Land uses surrounding the corridor are primarily industrial with only a small proportion consisting of residences.  Those residences were occupied by minorities.  The proposed action would result in only four residences having noise impacts after the implementation of noise attenuation walls.  The proposed action would result in a 90 percent reduction in population exposure to railroad noise on all lines serving the ports.  A number of mitigation measures involving landscaping and urban design will be implemented in response to perceived visual effects in one of the Central Business Districts (Compton) and in recognition of the need to apply urban design measures to the corridor as a whole.  The environmental justice analysis also considered the beneficial effects of the proposed action, especially the improved traffic circulation and reduced grade crossing accidents.  Based on the small number of minority residences that would be impacted and the substantial number of minority residences that would benefit from the noise reductions, The EIS determined that there were no disproportionate adverse impacts to minority or low-income populations.

Water Quality:  The EIS indicated that construction of the Corridor may require dewatering in some portions.  In addition, the addition of footings and columns for the crossings of the Los Angeles River, Compton Creek, and Dominquez Channel could affect the flood control capacity of these waters.  They planned to design the columns and footings for appropriate hydrology considerations in  coordination with the COE and the Los Angeles County Flood Control District.

Environmental Review Process

NEPA, including agency consultation: Planning for the Alameda Corridor began in 1981 when the Southern California Association of Governments (SCAG) created the Ports Advisory Committee.  The Committee conducted various planning activities which eventually led to the creation of the Alameda Corridor Task Force in 1985, which in turn led to the creation of the Alameda Corridor Transportation Authority (ACTA) in 1989.  ACTA began conceptual engineering in 1990, to more fully define the project.  Simultaneously, FHWA intended to be the lead federal agency and a joint EIR/EIS was envisioned.  FHWA started a NEPA scoping process in 1991.  Subsequently, FHWA funding was limited to specific grade crossing separations allowing individual categorical exclusions for these actions.  ACTA withdrew from the NEPA process and advanced the project under CEQA alone.

ACTA developed a range of conceptual engineering alternatives and reviewed them in a Draft EIR, which was issued in August, 1992, and a Final EIR, which was issued in January, 1993.  ACTA selected a locally preferred alternative.

After completion of the EIR, ACTA, Caltrans, and FHWA decided that additional federal funding should be applied for and that FHWA and FRA should prepare an EIS.  FHWA and FRA stated in the FEIS that they had decided to make maximum use of the analyses undertaken for the EIR.  Therefore, the EIS expanded on the EIR where it was necessary to address federal requirements that the EIR did not have to address.  Additional subjects requiring analysis included: additional documentation to address Clean Air Act requirements, including a conformity determination, the Section 106 process for cultural resources, COE requirements for hydrology and water quality, additional documentation for hazardous materials requested by FHWA and EPA, and coordination required for threatened and endangered species.

Prior to the re-initiation of the Alameda Corridor EIS by the FHWA and FRA, the COE and the Port of Los Angeles/Los Angeles Harbor Department prepared an EIS/EIR for the modification of the Port of Los Angeles Master Plan.  The EIS/EIR was completed in 1992.  The purpose of the Plan was to accommodate increased cargo throughput and the relocation of hazardous and other facilities.  The plan included dredging navigation channels and turning basins in Los Angeles Harbor and the creation of about 582 acres of new landfill to support new terminals and associated handling and storage facilities.  The facilities will be developed in four increments over time as needed.  Similarly, the Port of Long Beach was designing and building a comprehensive program of grade separation projects that were supposed to dramatically reduce train-related traffic blockages at the Port.  The program was slated for completion by 1997.  In addition, the Port was improving efficiency and expanding capacity of their on-dock rail facilities.  Those improvements were designed to speed flow of cargo through the Port and reduce Port-related truck traffic on roadways and freeways.  The Alameda Corridor EIS assumed that these projects would be in place for the purposes of the Alameda Corridor project, and were therefore also part of the No Build Alternative.

The FHWA and FRA reinitiated the NEPA process with a Notice of Intent in December 1993. They consulted with three federal agencies during the preparation of the EIS: EPA, FWS, and COE.  EPA submitted a comment letter during the scoping process in which they raised concerns about the selection of alternatives and air quality impacts.  In May 1994, subsequent to the scoping process, FHWA and EPA held a meeting at EPA’s Region 9 offices in San Francisco to discuss the project and its environmental documentation.  The meeting included staff from FHWA Region 9, FHWA California Division, Port of Los Angeles, and project consultants.  The key comments in EPA’s follow-up letter included air quality, train derailments and spills, and water quality.  Their comments were largely based on their review of the Final EIR, which they had not previously reviewed.  Regarding air quality, EPA commented on potential violations of the carbon monoxide and particulate matter standards and the application of the Conformity Rule to the project.  Their concerns over emergency response focussed on the need for a plan that addresses worst case scenarios.  They commented that, among other requirements, such a plan should be designed to address sensitive receptors and natural resources in a timely way.  The plan should be sent for review and comment to EPA, the Coast Guard, FWS, California Office of Emergency Services, California EPA, Los Angeles County, municipal fire departments, the Regional Water Quality Control Board, California Department of Fish and Game, and the Highway Patrol.  Their comments on water quality centered on the need for stormwater discharge permits for the construction and operational phases and as well as the need for nonpoint source controls.  In addition, EPA noted that the Executive Order on Environmental Justice had just been signed and that the DEIS should reflect its requirements.  FHWA addressed these comments in the Draft EIS.  FHWA also consulted with the COE on the proposed waterway crossings, which included two meetings.  The COE indicted that the crossings may meet the general terms and conditions for a nationwide permit.  Consultation with the FWS regarding the California least tern resulted in a response that potential effects are remote and therefore formal consultation is unnecessary.

They issued the Draft EIS in January 1995. The comment letters received during the scoping process came from: two federal agencies (EPA and the Surface Transportation Board), three regional agencies, five County of Los Angeles agencies, 17 local jurisdictions, eight private organizations, businesses and individuals.  Approximately 90 people attended the public hearing and 30 people spoke.

Among the written comments, EPA’s main concerns focussed on air quality.  EPA commented that although DEIS and conformity analysis suggest that the project would help reduce air pollution levels, there are opportunities to implement additional mitigation measures.  As an example they recommended a program to reduce vehicle miles traveled by construction workers.  They also had numerous comments on the technical aspects of the air quality modeling.  The Metropolitan Water District of Southern California strongly objected to the alternative preferred by the local entities because of the potentially significant costs and impacts upon existing water conveyance facilities.  The San Gabriel Valley Council of Governments and the Metropolitan Transportation Authority were concerned about the secondary or cumulative impacts from the increase in port-related rail traffic eastward of the Corridor (grade crossing delay, congestion, and air quality).  Several of their member governments also provided similar comments.  The Southern California Association of Governments commented that the project is consistent with the Regional Comprehensive Plan and Guide and is vital to the region’s future growth.  The Los Angeles Unified School District raised concerns about vibration during construction and operation of the Corridor, traffic circulation, air quality, and noise.  The City of Compton submitted over 140 pages of comments on a broad range of subjects and proposed a covered depressed trainway and roadway (a tunnel).  The City of Lynnwood commented on local transportation, utilities, mitigation of air pollution, and economic benefits (local hiring policy).  The City of Vernon supports the locally preferred alternative and among their other comments, noted that the “EIS should discuss the importance of the Alameda Corridor Project with regard to its mitigation of individual and cumulative” impacts which are anticipated for the port projects related to the Corridor.  They also commented that the EIS should recognize that the Alameda Corridor project is the mitigation for the impacts resulting from the other port projects.  The comments of the Cities of Long Beach and Los Angeles were generally supportive.  A family commented on existing grade crossing delays.  A citizen of Compton commented on property devaluation, emergency response access, increased noise, air pollution, and vibration.  Two oil companies commented on potential impacts to their pipelines and one commented on access for emergency response vehicles.  A land company, which owns over 450 acres and nearly 3 million square feet of office and light industrial space along the Corridor, commented on loss of access and impacts from noise and vibration.

Many of the issues raised at the public hearing pertained to the City of Compton and included: vehicle access, impacts on schools, law enforcement and public safety issues, concerns about graffiti, a perception that there would be a large increase in trench traffic, job creation and the need for employment outreach efforts, and project cost.  Other comments addressed: potential grade separations in the City of Lynnwood, the I-105/Imperial Highway Interchange, parking, landscaping, and business access along the corridor.

The Final EIS was issued in February 1996.  In May 1997, the Secretary of Transportation delegated to the Administrator of FHWA, the authority to manage DOT’s $400 million loan with ACTA.  Other related activities outside the Alameda Corridor include the Alameda Corridor East and a Southern California Association of Governments study to determine the best way of moving rail traffic eastward through Southern California.  The study addresses the potential for additional consolidated along one or more lines.  The Alameda Corridor East project involves a series of transportation safety improvements at 55 grade crossings along 35 miles of ROW throughout the San Gabriel Valley.

The FHWA and FRA reinitiated the NEPA process with a Notice of Intent in December 1993.  They issued the Draft EIS in January 1995 and the Final EIS in February 1996.  In May 1997, the Secretary of Transportation delegated to the Administrator of FHWA, the authority to manage DOT’s $400 million loan with ACTA.

Integration of NEPA and state environmental review processes: The CEQA process began about nine months before the NEPA process because federal funding was not identified, and thus NEPA was not triggered, until later in the planning process.  The locally preferred alternative under CEQA was also the federally preferred alternative under NEPA.  The FHWA wanted to streamline the NEPA process.  One way to have accomplished this would have been to adopt the CEQA document for the purposes of NEPA.  However, as mentioned above, FHWA needed to conduct additional analyses to meet federal requirements that were not required of the EIR.

Effect of process on project design and alternatives: The public involvement process and consultation with local governments led to certain mitigation measures on the preferred alternative.

Multi-Agency Review: There was an extensive multi-agency review process as described above.

Public Involvement:  Prior to the NEPA scoping process, the CEQA process involved an extensive public comment effort.  ACTA distributed the August 1992, Draft EIR to 120 government agencies and interested parties.  ACTA received 100 requests for additional copies during the public comment period.  ACTA held six public hearings, which were attended by 163 people, of whom 47 provided verbal comments.  ACTA announced the hearings through a number of means, including newspapers, direct mailing, radio and television public service announcements, flyers and door hangers.  In addition to the formal hearings, ACTA held four community meetings.  The 35 comment letters received during the scoping process came from: two state agencies, six regional agencies, three County of Los Angeles departments, eight local jurisdictions, eight private companies, and four individuals.

For the NEPA scoping process, the FHWA and FRA held a formal scoping meeting, which they advertised in seven local newspapers.  They also notified public agencies and known interested parties through a direct mailing.  In addition, they sent a direct mailing to five federal agencies and a general mailing to 465 addresses.  The FHWA and FRA conducted afternoon and evening sessions for the scoping meeting.  They gave attendees an information packet about the project and conducted a presentation to explain the project and the purpose of the meeting.  Fifty-one people attended the two sessions combined.  Six speakers provided comments at the sessions and 12 written comments were received.  During the scoping period, the FHWA and FRA received 14 comment letters, including one from EPA, two local agencies, the Cities of Compton and Vernon, seven private companies, and two citizens.  The agency letters are separate from the agency coordination and consultation letters discussed above.  The commenters raised issues concerning:  alternatives, accessibility, safety, air quality, noise and vibration, traffic and circulation, landscaping, and site-specific issues.  During the comment period for the DEIS, FHWA and FRA held a public hearing with an afternoon session and an evening session.  Approximately 90 people attended the two sessions combined.  Thirty people spoke at the two sessions combined.

REUSE OF THE LONG BEACH NAVAL YARD

Mode: Marine, Rail, Highway 		Commodity Type: Various

Ownership: Public/Private 		Location: Urban, West

- Lead Federal Agency: U.S. Navy

- Cooperating Agencies:  None

- Review Agencies: FHWA, COE, ACHP, U.S. EPA, California Department of Toxic Substances Control

- State or Local Agencies: City of Long Beach

| Project Description Environmental Issues: |  |
| --- | --- |
| - Air Quality |  |
| - Cultural Resources |  |
| - Land Use |  |
| - Local Transportation |  |
| - Natural Resources |  |
| - Noise/vibration |  |
| - Hazardous Waste |  |
| - Socioeconomics |  |
| - Water Quality |  |
| Environmental Review Process: |  |
| - NEPA, including agency consultation |  |
| - Use of structured process |  |
| - Integration of NEPA and state processes |  |
| - Timing of environmental review initiation |  |
| - Effect of process on project design and alternatives |  |
| - Multi-agency review |  |
| - Public involvement |  |

- Issue

- Major Issue

For the EIS/EIR, the purpose and need of the federal action was to dispose of the Long Beach Naval Station (NAVSTA) and the Long Beach Naval Shipyard (NSY) under the Base Realignment and Closure (BRAC) process.  The purpose and need for the proposed local action was to reuse the Navy property for expansion of the Port of Long Beach.

Located south of Los Angeles, the Port of Long Beach coupled with the Port of Los Angeles constitutes the San Pedro Bay Port System; together they are approximately twice as large as the next largest container port in North America.  The 525-acre island facility will serve as a container-rail/port facility that will also transfer bulk (primarily lumber) and liquid bulk commodities, and operate as a ship repair facility.  As part of the Port of Long Beach, the facility is linked by rail to the region and nation through the Alameda Corridor.  The Port of Long Beach is building one quarter-mile of new track to link with the Alameda Corridor.

The Port of Long Beach has carried out the planning of the facility on behalf of CALTRANS.  While the Navy still holds the title to the NAVSTA and NSY properties, pending clean-up of hazardous waste contamination, the Port of Long Beach has facilitated construction of the intermodal facility by leasing segments of the base until the property transfer is completed.  Completion of the construction of the intermodal facility is dependent upon the transfer of the property title to the Port of Long Beach.  The Navy is funding the clean-up of the naval complex; the FHWA has funded construction of a traffic interchange and grade separation; and the ACOE is funding dredging and dike repair.

Environmental Issues of Concern

Cultural Resources: The naval complex housed a Historic District, comprised of buildings designed by Paul Revere Williams, one of the first prominent African American architects. These historically significant buildings garnered attention from the local community and the State Historical Preservation Organization (SHPO) and national attention from the ACHP.  The local community wanted the complex to be preserved intact. In November 1997, the Navy completed a Historic Properties Adaptive Use Feasibility Study to identify potential realistic, economically feasible adaptive uses for the Historic District.  The Navy also reinitiated consultation under Section 106 of the National Historic Preservation Act (NHPA) with the SHPO and the ACHP.  Upon completion of a Section 106 Adaptive Use Feasibility Study, it was found that the only economically viable use for the complex is the conversion to an intermodal facility.  The Navy developed a Memorandum of Agreement (MOA) with the SHPO and the ACHP addressing the potential effects on the Historic District and identifying possible mitigation measures. The agreed upon mitigation plan included:  the preservation of selected items from the historical buildings, production of a historical documentary, and a $4.2 million allocation to the City of Long Beach for historic preservation.

Hazardous Waste: The fill material produced by the dredging, along with other materials on the island, is contaminated.  The Navy established two major restoration programs, an Installation Restoration Program (IRP) and a compliance program, in response to releases of hazardous substances, pollutants, contaminants, petroleum hydrocarbons, and hazardous solid wastes.  The IRP identifies, assesses, characterizes, and cleans up or controls contamination from past hazardous waste disposal operations and hazardous materials spills.  The Compliance Program addresses underground storage tanks, above ground storage tanks, oil/water separators, asbestos, polychlorinated biphenyls, radon, and lead-based paint.  The Navy has worked with the U.S. EPA to dispose of the contaminated dredge materials, and with the California Department of Toxic Substances Control to dispose of the contaminants on the island.

Natural Resources: The FWS raised concerns over impacts to potential feeding areas for the California least tern and nesting areas for the black crown night heron.  The EIS/EIR indicated that a significant and mitigable impact to the California least terns would occur due to the loss through dredging of the 26-acre shallow water area in the West Basin.  The mitigation is to create replacement shallow-water foraging habitat within the vicinity of the Terminal Island nesting colony.  The project would also have a significant and mitigable impact to the black-crowned night heron rookery because of the removal of ornamental trees on the NAVSTA, NSY, and surrounding Port of Long Beach properties.  The mitigation for this impact would involve salvaging approximately 30 trees from the existing colony and planting them at Gull Park on the Navy property.  Both mitigation measures are the responsibility of the Port of Long Beach.

Noise/vibration: The nearest private residences are located three miles from the intermodal facility, however, the increased train traffic that will result from the completed facility transects these neighborhoods.  The Alameda Corridor project will mitigate these impacts.

Environmental Review Process

NEPA, agency consultation: The disposal and conversion process has taken several years.  In 1991, the BRAC Commission recommended the closure of NAVSTA and in 1995, recommended the closure of NSY.  Most of NAVSTA closed operationally in 1994 and NSY closed in 1997.  The Navy began the NEPA process by choosing to evaluate the disposal and reuse of NAVSTA and NSY in separate NEPA documents because they closed under separate BRAC Commission actions and the Navy could reach independent decisions on the two facilities.  The Navy prepared and distributed a Final EIS in February 1997 for NAVSTA.  The Navy also published a Notice of Intent (NOI) to prepare an EIS for NSY in September 1996.  The City of Long Beach’s Harbor Department prepared an EIR for the reuse of NAVSTA in 1996.  The City’s Harbor Department published a Notice of Preparation (NOP) in 1996 for the preparation of an EIR under the California Environmental Quality Act (CEQA) for the development of NSY.  The Navy reevaluated its earlier decision and determined that they should address the disposal and reuse of NAVSTA and NSY in one EIS.  Their rationale was that: the properties are adjacent; the Port of Long Beach’s reuse plans for both properties were similar; the proposed disposal and reuse would now occur in the same general time frame; and there is the possibility that a combined analysis could identify mitigation measures to reduce impacts to the Historic District.  Therefore, the Navy and the City of Long Beach decided to prepare a joint EIS/EIR. They completed the Final EIS/EIR in April 1998.  In terms of agency consultation, the proposed destruction of the historic buildings generated controversy and the local preservation group and the SHPO involved the ACHP. The Section 106 process required one year to complete.

Integration of NEPA and state environmental review processes: The Navy and the Port of Long Beach initiated independent EISs and

EIRs, which they did not complete.  They moved forward with a joint EIS and EIR, which has been reviewed by FHWA, EPA, FWS, and the COE. They also worked jointly with the Navy to complete the Section 106 historic review process.  The Port believes that the EIS delayed the project.  The Port of Long Beach used a standard approach, has been through CEQA reviews many times, and has reached an understanding over how to characterize various types of impacts (e.g., negligible or significant). However, the Navy (especially their legal staff) had more difficulty determining levels of impact.

Effect of process on project design and alternatives: Two of the alternatives analyzed in the EIS/EIR are based on two potentially feasible adaptive use alternatives generated by the Historic Properties Adaptive Use Feasibility Study.

Multi-Agency Review: The Port and the Navy had to consult with several agencies, including the SHPO, ACHP, EPA, COE, DTSC, and FWS.  Apparently, the Navy’s ongoing consultations with DTSC have led to tensions between the two agencies.

Public Involvement: Residents are still concerned about air quality, noise and vibration, and hazardous materials transportation impacts from train traffic.  The neighboring communities sued over the EIR and EIS.

Siting of some of the proposed development across the river where a more appropriate site may be already available has been encouraged by the Port of Vancouver, community groups, and the FWS, but dismissed by the Port of Portland as their may not be sufficient space to site all three potential phases.