## Section 156. — Public Traffic

12/15/15– FP14

Construction Requirements

WFL Specification 01/01/14

Note: Edit as required to meet project requirements delaying or restricting PUBLIC travel.

Examples:

Accommodate traffic according to the following schedule:

6:00 a.m. to 8:00 a.m. Open road

8:00 a.m. to 11:30 a.m. 30 minute delays permitted

11:30 a.m. to 2:30 p.m. Close road for rock blasting

2:30 p.m. to 4:00 p.m. 30 minute delays permitted

4:00 p.m. to 5:00 p.m. Open road

5:00 p.m. to 6:00 a.m. 30 minute delays permitted

During open road intervals, do not perform work which interferes with public travel.

One-lane, two-way traffic control between Stations \_\_\_\_\_\_\_ and \_\_\_\_\_\_\_ will be permitted during open road intervals.

During 30 minute delay intervals, all construction caused delays to a vehicle passing through the project (including delays for lane closures) shall not exceed 30 minutes.

Road closures will only be permitted for rock blasting. Comply with the following requirements before closing the road:

(1) At least 2 days in advance of road closures, publish notices of the road closure in local newspapers and notify local radio stations. Provide notices on a weekly basis and continue until no longer applicable.

(2) Uncover Sign Number \_\_\_ at least 12 hours before closures. See Plan Sheet No. \_\_\_. On days the road will not be closed, cover the sign.

Immediately open the road to emergency vehicles.

The road may be closed from [INSERT DATE] to [INSERT DATE].

### 156.04 Accommodating Traffic During Work.

Add the following:

[INSERT REQUIREMENTS]

WFL Specification 01/01/14

Note: Edit as required to meet project requirements. Include limitations on activities which affect public travel under Subsection 156.07. Cross-reference with Subsection 108.01. Begin labeling paragraph with (k).

### 156.07 Limitations on Construction Operations.

Amend as follows:

WFL Specification 01/01/14

Include the following in all projects requiring flaggers, pilot cars, or Traffic Control Supervisors.

Delete paragraph (g) and substitute the following:

**(g)** Provide two-way radio communications between Traffic Control Supervisor, flaggers, and pilot cars. Provide two-way radio communications between flaggers unless flaggers are able to see each other and communicate. Citizen band radios are not acceptable. Make radio equipment available to the CO as necessary.

WFL Specification 01/01/14

Include the following when uneven lane elevations are not allowed (coordinate with plan detail and note).

Add the following:

**( )** Complete paving of adjacent traffic lanes to the same elevation by the end of each day.

WFL Specification 01/01/14

Include the following when weekend or holiday work is not allowed. Edit as required.

Add the following:

**( )** Do not perform construction operations which interfere with public travel on the roadway on any holiday or between 6 p.m. Friday and 6 a.m. the following Monday, unless approved by the CO.

WFL Specification 01/01/14

Include the following if there will be part-width construction requiring flaggers and/or pilot cars.

Add the following:

**( )** For purposes of facilitating traffic, perform grading or surfacing part-width at a time. Make the width not under construction available to public traffic under alternate one-way control. Furnish pilot car and driver, or flaggers, or both, as ordered by the CO, to direct traffic through sections of road under one-way control.

WFL Specification 12/15/15

Include the following on all projects. Edit as required.

### 156.09 Traffic Control Supervisor.

Add the following:

**(l)** Transport personnel, construction signs, barricades, drums, cones, tubular markers, and other traffic control devices.