# DIVISION 150 PROJECT REQUIREMENTS

## Section 151. — MOBILIZATION

Description

151.01  This work consists of moving personnel, equipment, material, and incidentals to the project and performing all work necessary before beginning work at the project site.  Mobilization includes the obtaining of permits, insurance, and bonds.

Measurement

151.02  Measure mobilization according to Subsection 109.02.

Payment

151.03  The accepted quantity, measured as provided in Subsection 109.02, will be paid at the contract price per unit of measurement for the Section 151 pay item shown in the bid schedule.  Payment will be full compensation for the work prescribed in this Section.  See Subsection 109.05.

Progress payments for mobilization lump sum will be paid as follows:

(a) Bond premiums will be reimbursed according to FAR Clause 52.232-5 Payments Under Fixed-Price Construction Contracts, after receipt of the evidence of payment.

(b) When 5 percent of the original contract amount is earned from other bid items, 50 percent of the mobilization item, or 5 percent of the original contract amount, whichever is less, will be paid.

(c) When 10 percent of the original contract amount is earned from other bid items, 100 percent of the mobilization item, or 10 percent of the original contract amount, whichever is less, will be paid.

(d) Any portion of the mobilization item in excess of 10 percent of the original contract amount will be paid after final acceptance.

## Section 152. — CONSTRUCTION SURVEY AND STAKING

Description

152.01  This work consists of furnishing qualified personnel and necessary equipment and material to survey, stake, calculate, and record data for the control of work.  See FAR Clause 52.236-17 Layout of Work.

Personnel, equipment, and material shall conform to the following:

(a) Personnel.  Furnish technically qualified survey crews experienced in highway construction survey and staking.  Provide personnel capable of performing in a timely and accurate manner.  An acceptable crew supervisor shall be on the project whenever surveying/staking is in progress.

(b) Equipment.  Furnish survey instruments and supporting equipment capable of achieving the specified tolerances.

(c) Material.  Furnish acceptable tools, supplies, and stakes of the type and quality normally used in highway survey work and suitable for the intended use.  Furnish stakes and hubs of sufficient length to provide a solid set in the ground with sufficient surface area above ground for necessary legible markings.

Construction Requirements

152.02 General.  Include staking activities in the construction schedule submitted according to Section 155.  Include the dates and sequence of each staking activity.  The Government will set initial reference lines, will set horizontal and vertical control points, and will furnish the data for use in establishing control for completion of each element of the work.  Data relating to horizontal and vertical alignment, theoretical slope stake catch points, and other design data will be furnished.

Before beginning construction, notify the CO of any missing initial reference lines, control points, or stakes.  The Government will reestablish initial reference lines, control points, and stakes missing before the beginning of construction.

Perform additional calculations for convenient use of Government-furnished data.  Provide immediate notification of apparent errors in the initial staking or in the furnished data.

Preserve all initial reference and control points.  After beginning construction, replace all destroyed or disturbed initial reference or control points necessary to the work.

Before surveying or staking, discuss and coordinate the following with the CO:

(a) Surveying and staking methods;

(b) Stake marking;

(c) Grade control for courses of material;

(d) Referencing;

(e) Structure control; and

(f) Any other procedures and controls necessary for the work.

Survey and establish controls within the tolerances shown in Table 152-1.

Prepare field notes in an approved format.  Furnish all survey notes at least weekly.  All field notes and supporting documentation become the property of the Government upon completion of the work.

Start work only after staking for the affected work is accepted.

The construction survey and staking work may be spot-checked for accuracy, and unacceptable portions of work may be rejected.  Resurvey rejected work, and correct work that is not within the tolerances specified in Table 152-1.  Acceptance of the construction staking does not relieve the Contractor of responsibility for correcting errors discovered during the work and for bearing all additional costs associated with the error.

Remove and dispose of all flagging, lath, stakes, and other staking material after the project is complete.

152.03  Survey and Staking Requirements.  Perform all survey, staking, recording of data, and calculations as necessary to construct the project from the initial layout to final completion.  Reset stakes as many times as necessary to construct the work.

(a) Control points.  Relocate initial horizontal and vertical control points in conflict with construction to areas that will not be disturbed by construction operations.  Furnish the coordinates and elevations for the relocated points before the initial points are disturbed.

(b) Roadway cross-sections.  Take roadway cross-sections normal to centerline.  When the centerline curve radius is less than or equal to 150 meters, take cross-sections at a maximum centerline spacing of 10 meters.  When the centerline curve radius is greater than 150 meters, take cross-sections at a maximum centerline spacing of 20 meters.  Take additional cross-sections at significant breaks in topography and at changes in the typical section.  Along each cross-section, measure and record points at breaks in topography, but no further apart than 5 meters.  Measure and record points to at least the anticipated slope stake and reference locations.  Reduce all cross-section distances to horizontal distances from centerline.

(c) Slope stakes and references.  Set slope stakes and references on both sides of centerline at the cross-section locations.  Establish slope stakes in the field as the actual point of intersection of the design roadway slope with the natural ground line.  Set slope stake references outside the clearing limits.  Include all reference point and slope stake information on the reference stakes.  When initial references are provided, slope stakes may be set from these points with verification of the slope stake location with field measurements.  Recatch slope stakes on any section that does not match the staking report within the tolerances established in Table 152-1.  Take roadway cross-section data between centerline and the new slope stake location.  Set additional references even when initial references are provided.

(d) Clearing and grubbing limits.  Set clearing and grubbing limits on both sides of centerline at roadway cross-section locations.

(e) Centerline reestablishment.  Reestablish centerline from instrument control points.  The maximum spacing between centerline points is 10 meters when the centerline curve radius is less than or equal to 150 meters.  When the centerline curve radius is greater than 150 meters, the maximum distance between centerline points is 20 meters.

(f) Grade finishing stakes.  Set grade finishing stakes, for grade elevations and horizontal alignment, on centerline and on each shoulder at roadway cross-section locations.  Set stakes at the top of subgrade and the top of each aggregate course.

Where turnouts are constructed, set stakes on centerline, on each normal shoulder, and on the shoulder of the turnout.  In parking areas, set hubs at the center and along the edges of the parking area.  Set stakes in all ditches to be paved.

The maximum longitudinal spacing between stakes is 10 meters when the centerline curve radius is less than or equal to 150 meters.  When the centerline curve radius is greater than 150 meters, the maximum longitudinal spacing between stakes is 20 meters.  The maximum transverse spacing between stakes is 5 meters.  Use brushes or guard stakes at each stake.

(g) Culverts.  Stake culverts to fit field conditions.  The location of culverts may differ from the plans.  Perform the following:

(1) Survey and record the ground profile along the culvert centerline.

(2) Determine the slope catch points at the inlet and outlet.

(3) Set reference points and record information necessary to determine culvert length and end treatments.

(4) Plot-to-scale the profile along the culvert centerline.  Show the natural ground, the flow line, the roadway section, and the culvert including end treatments and other appurtenances.  Show elevations, grade, culvert length, and degree of elbow.

(5) Submit the plotted field-design cross-section for approval of final culvert length and alignment.

(6) When the field design has been approved, set drainage structure survey stakes, reference stakes, and stake inlet and outlet ditches to make the structure functional.

(7) Stake or grade ditches to make the culvert functional.

(h) Bridges.  Set adequate horizontal and vertical control and reference points for all bridge substructure and superstructure components.  Establish and reference the bridge chord or the bridge tangent.  Also establish and reference the centerline of each pier, bent, and abutment.

(i) Retaining walls.  Survey and record profile measurements along the face of the proposed wall and 2 meters in front of the wall face.  Every 5 meters along the length of the wall and at all major breaks in terrain take cross-sections within the limits designated by the CO.  For each cross-section, measure and record points every 5 meters and at all major breaks in terrain.  Set adequate references and horizontal and vertical control points.

(j) Borrow and waste sites.  Perform the work essential for initial layout and measurement of the borrow or waste site.  Establish a referenced baseline, site limits, and clearing limits.  Survey and record initial and final cross-sections.

(k) Permanent monuments and markers.  Perform all survey and staking necessary to establish permanent monuments and markers.  Set permanent monuments according to Section 621.

(l) Miscellaneous survey and staking.  Perform all surveying, staking, and recording of data essential for establishing the layout and control of the following, as applicable:

(1) Approach roads and trails;

(2) Curb and gutter;

(3) Guardrail;

(4) Parking areas;

(5) Paved waterways;

(6) Special ditches;

(7) Turf establishment;

(8) Utilities;

(9) Signs, delineators, and object markers; and

(10) Pavement markings.

Table 152-1

Construction Survey and Staking Tolerances(1)

| Staking Phase | Horizontal | Vertical |
| --- | --- | --- |
| Existing Government network control points | ±20 mm | ±8 mm*K (2) |
| Local supplemental control points set from existing Government network points | ±10 mm | ±3 mm*N (3) |
| Centerline points (4) — (PC), (PT), (POT), and (POC) including references | ±10 mm | ±10 mm |
| Other centerline points | ±50 mm | ±50 mm |
| Cross-section points and slope stakes (5) | ±50 mm | ±50 mm |
| Slope stake references (5) | ±50 mm | ±50 mm |
| Culverts, ditches, and minor drainage structures | ±50 mm | ±20 mm |
| Retaining walls and curb and gutter | ±20 mm | ±10 mm |
| Bridge substructures | ±10 mm (6) | ±10 mm |
| Bridge superstructures | ±10 mm (6) | ±10 mm |
| Clearing and grubbing limits | ±500 mm | — |
| Roadway subgrade finish stakes (7) | ±50 mm | ±10 mm |
| Roadway finish grade stakes (7) | ±50 mm | ±10 mm |

(1) At 95% confidence level.  Tolerances are relative to existing Government network control points.

(2) K is the distance in kilometers.

(3) N is the number of instrument setups.

(4) Centerline points:  PC - point of curve, PT - point of tangent, POT - point on tangent, POC - point on curve.

(5) Take the cross-sections normal to the centerline ±1 degree.

(6) Bridge control is established as a local network and the tolerances are relative to that network.

(7) Includes paved ditches.

152.04  Acceptance.  Construction survey and staking will be evaluated under Subsections 106.02 and 106.04.

Measurement

152.05  Measure the Section 152 items listed in the bid schedule according to Subsection 109.02 and the following as applicable.

Measure grade finishing stakes one time for the subgrade and one time for each aggregate course.

Do not measure resetting stakes.

For miscellaneous survey and staking paid by the hour, the minimum survey crew size is 2 persons.  Do not measure time spent in making preparations, traveling to and from the project site, performing calculations, plotting cross-sections and other data, processing computer data, and other efforts necessary to successfully accomplish construction survey and staking.

Payment

152.06  The accepted quantities, as provided above, will be paid at the contract price per unit of measurement for the Section 152 pay items listed in the bid schedule.  Payment will be full compensation for the work prescribed in this Section.  See Subsection 109.05.

Payment for lump sum items will be prorated based on the total work completed.

## Section 153. — CONTRACTOR QUALITY CONTROL

Description

153.01  This work consists of obtaining samples for Contractor quality control testing, performing tests for Contractor quality control, providing inspection, and exercising management control to ensure that work conforms to the contract requirements.  See FAR Clause 52.246-12 Inspection of Construction.

Construction Requirements

153.02  Contractor Quality Control Plan.  Before the start of the work, submit a written quality control plan for acceptance.  With prior approval, submission of a quality control plan for items of work not immediately scheduled to begin may be deferred.

Submit the following with the quality control plan:

(a) Process control testing.  List the material to be tested by pay item, tests to be conducted, the location of sampling, and the frequency of testing.

(b) Inspection/control procedures.  Address each of the following subjects in each phase of construction:

(1) Preparatory phase.

(a) Review all contract requirements.

(b) Ensure compliance of component material to the contract requirements.

(c) Coordinate all submittals including certifications.

(d) Ensure capability of equipment and personnel to comply with the contract requirements.

(e) Ensure preliminary testing is accomplished.

(f) Coordinate surveying and staking of the work.

(2) Start-up phase.

(a) Review the contract requirements with personnel performing the work.

(b) Inspect start-up of work.

(c) Establish standards of workmanship.

(d) Provide training as necessary.

(e) Establish detailed testing schedule based on the production schedule.

(3) Production phase.

(a) Conduct intermittent or continuous inspection during construction to identify and correct deficiencies.

(b) Inspect completed work before requesting Government inspection acceptance.

(c) Provide feedback and system changes to prevent repeated deficiencies.

(c) Description of records.  List the records to be maintained.

(d) Personnel qualifications.

(1) Document the name, authority, relevant experience, and qualifications of person with overall responsibility for the inspection system.

(2) Document the names, authority, and relevant experience of all personnel directly responsible for inspection and testing.

(e) Subcontractors.  Include the work of all subcontractors.  If a subcontractor is to perform work under this Section, detail how that subcontractor will interface with the Contractor's and other subcontractor's organizations.

Modifications or additions may be required to any part of the plan that is not adequately covered.  Acceptance of the quality control plan will be based on the inclusion of the required information.  Acceptance does not imply any warranty by the Government that the plan will result in consistent contract compliance.  It remains the responsibility of the Contractor to demonstrate such compliance.

Do not begin the work until the quality control plan covering that work is accepted.

Supplement the plan as work progresses and whenever quality control or quality control personnel changes are made.

153.03  Testing.  Perform testing according to the accepted quality control plan.  Keep laboratory facilities clean and maintain all equipment in proper working condition.  Allow unrestricted access for inspection and review of the facility.

153.04  Records.  Maintain complete testing and inspection records by pay item number and make them accessible to the CO.

For each day of work, prepare an "Inspector's Daily Record of Construction Operations" (Form FHWA 1413) or an approved alternate form.  Detail inspection results including deficiencies observed and corrective actions taken.  Include the following certification signed by the person with overall responsibility for the inspection system:

"It is hereby certified that the information contained in this record is accurate and that all work documented herein complies with the requirements of the contract.  Any exceptions to this certification are documented as a part of this record."

Submit the record and certification within one working day of the work being performed.  If the record is incomplete, in error, or otherwise misleading, a copy of the record will be returned with corrections noted.  When chronic errors or omissions occur, correct the procedures by which the records are produced.

Maintain linear control charts that identify the project number, pay item number, test number, each test parameter, the upper and lower specification limit applicable to each test parameter, and the test results.  Use the control charts as part of the quality control system to document the variability of the process, to identify production and equipment problems, and to identify potential pay factor adjustments.

Post control charts in an accessible location and keep them up-to-date.  Cease production and make corrections to the process when problems are evident.

153.05  Acceptance.  The Contractor's quality control system will be evaluated under Subsection 106.02 based on the demonstrated ability of the quality control system to result in work meeting the contract requirements.

If the Government's testing and inspection indicate that the Contractor's quality control system is ineffective, make immediate improvements to the system to correct these inadequacies.  Furnish notification in writing of improvements and modifications to the system.

Measurement and Payment

153.06  Do not measure Contractor quality control for payment.

## Section 154. — CONTRACTOR SAMPLING AND TESTING

Description

154.01  This work consists of obtaining samples for testing.  When there is a contract pay item for Contractor testing included in the bid schedule, it also consists of testing and reporting required test results.  It does not include Contractor quality control testing required under Section 153.  However, include the work required under this Section in the Section 153 quality control plan.

Construction Requirements

154.02  Sampling.  Sample material to be tested according to the Sampling and Testing Requirements tables included at the end of each section.  The sampling schedules and times will be provided by the CO using a random number system.  In addition, sample any material that appears defective or inconsistent with similar material being produced unless such material is voluntarily removed and replaced or corrected.

Sample and split samples according to AASHTO or other acceptable procedures.  Allow the CO the opportunity to witness all sampling.  Immediately perform splits when required.  Deliver the Government’s portion of the sample or split sample in an acceptable container suitable for shipment.  Label all samples with the following information:

(a) Project number;

(b) Source of material;

(c) Pay item number;

(d) Sample number;

(e) Date sampled;

(f) Time sampled;

(g) Location sample taken;

(h) Name of person sampling;

(i) Name of person witnessing sampling; and

(j) Type of test required on sample.

154.03  Testing.  When there is a contract pay item for Contractor testing included in the bid schedule, perform all tests required by the Sampling and Testing Requirements tables at the end of each section.  Allow the CO the opportunity to witness all testing.  Testing of trial samples may be required to demonstrate testing competence.

154.04  Records.  Report test results on forms containing all sample information required by Subsection 154.02.  Label clearly all interim measurements used to determine the results.  Attach work sheets used to determine test values to the test result forms when submitted.  When tests are on material being incorporated in the work, report test results within 24 hours except as specified in the Sampling and Testing Requirements tables.  Payment for work may be delayed or the work suspended until test results are provided.

154.05  Acceptance.  Contractor sampling and testing will be evaluated under Subsections 106.02 and 106.04 based on Government verification testing.

Measurement

154.06  Measure the Section 154 items listed in the bid schedule according to Subsection 109.02.

Payment

154.07  The accepted quantities will be paid at the contract price per unit of measurement for the Section 154 pay item listed in the bid schedule.  Payment will be full compensation for the work prescribed in this Section.  See Subsection 109.05.

Progress payments for Contractor testing will be paid as follows:

(a) 25 percent of the item amount, not to exceed 0.5 percent of the original contract amount, will be paid after all the testing facilities are in place, qualified sampling and testing personnel are identified, and the work being tested has started.

(b) Payment for the remaining portion of the item amount will be prorated based on the total work completed.

Payment for all or part of this item may be retained if Government verification testing invalidates the Contractor testing.

## Section 155. — SCHEDULES FOR CONSTRUCTION CONTRACTS

Description

155.01  This work consists of scheduling and monitoring all construction activities.  See FAR Clause 52.236-15 Schedules for Construction Contracts.

Construction Requirements

155.02  General.  Submit 3 copies of a preliminary construction schedule at least 7 days before the preconstruction conference.

A preliminary construction schedule is a written narrative with a detailed breakdown of all contract activities for the first 45 days after the notice to proceed is issued.  Within 7 days after the preconstruction conference, the preliminary construction schedule will be accepted or rejected.  If rejected, submit a revised schedule within 3 days.  Do not begin work, except mobilization, traffic control, and Section 637 work, without an accepted preliminary construction schedule.

Use either the Bar Chart Method (BCM) or the Critical Path Method (CPM) described below to develop the construction schedule for the total contract work.  Preface each construction schedule as follows:

(a) Project name;

(b) Contract number;

(c) Contractor;

(d) Original contract time allowed or completion date;

(e) Type of construction schedule (initial or update);

(f) Effective date of the schedule;

(g) Percent work complete; and

(h) Percent time used.

Submit 3 copies of the construction schedule within 30 days after the notice to proceed is issued.  Allow 14 days for acceptance or rejection of the construction schedule or a revised schedule.  If rejected, submit a revised schedule within 7 days.  No progress payment will be made for any work until a construction schedule is submitted to the CO and accepted by the CO.

Do not show conflicts with any scheduled activities, limits on operations, order of work requirements, interim or final completion dates, or other contract restrictions.

Show completion of the work within the contract time.

155.03  Bar Chart Method (BCM).  The BCM construction schedule consists of a progress bar chart and a written narrative.

(a) Progress bar chart.  The following applies to the initial submission and all updates:

(1) Use a time scale to graphically show the percentage of work scheduled for completion during the contract time.

(2) Define and relate activities to the contract pay items.

(3) Show all activities in the order the work is to be performed including submittals, submittal reviews, fabrication, and delivery.

(4) Show all critical (major) activities that are controlling factors in the completion of the work.

(5) Show the time needed to perform each activity and its relationship in time to other activities.

(6) Show the total expected time to complete all work.

(7) Provide enough space for each activity to permit 2 additional plots parallel to the original time span plot.  Use one space for revision of the planned time span, and one for showing actual time span achieved.

(b) Written narrative.  Furnish a written narrative of the activities displayed in the progress bar chart.

155.04  Critical Path Method (CPM).  The CPM construction schedule consists of a diagram, a tabulated schedule, and a written narrative.

(a) Diagram.  Use the "activity-on-arrow" format for the arrow diagrams or the "activity-on-node" format for precedence diagrams.  The following applies to the initial submission and all updates:

(1) Use a time scale to graphically show the percent of work scheduled for completion by any given date during the contract time.

(2) Define and relate activities to the contract pay items.

(3) Show the sequence and interdependence of all activities including submittals, submittal reviews, fabrication, and deliveries.

(4) Show all activity nodes, activity descriptions, and durations.

(5) Show all network dummies (for arrow diagrams only).

(6) Identify the critical path.

(b) Tabulated schedule.  The following requirements apply to the tabulated schedule:

(1) For arrow diagrams, show activity beginning and ending node numbers.  For precedence diagrams, list activities and show lead or lag times.

(2) Show activity durations.

(3) Show activity descriptions.

(4) Show early start and finish dates.

(5) Show late start and finish dates.

(6) Show status (critical or not).

(7) Show total float.

(c) Written narrative.  Furnish a written narrative of the activities displayed in the schedule diagram.

155.05  Written Narrative.  The following applies to the written narrative:

(a) Estimate starting and completion dates of each activity.

(b) Describe work to be done within each activity including the type and quantity of equipment, labor, and material to be used.

(c) Describe the location on the project where each activity occurs.

(d) Describe planned production rates by pay item quantities (e.g., cubic meters of excavation per day/week).

(e) Describe work days per week, holidays, number of shifts per day, and number of hours per shift.

(f) Estimate any periods during which an activity is idle or partially idle.  Show the beginning and end dates for reduced production or idle time.

(g) Describe expected and critical delivery dates for equipment or material that can affect timely completion of the project.

(h) Describe critical completion dates for maintaining the construction schedule.

(i) Identify the vendor, supplier, or subcontractor to perform the activity.  State all assumptions made in the scheduling of the subcontractor's or supplier's work.

155.06  Schedule Updates.  Review the construction schedule to verify finish dates of completed activities, remaining duration of uncompleted activities, any proposed logic, and time estimate revisions.  Keep the CO informed of the current construction schedule and all logic changes.

Submit 3 copies of an updated construction schedule for acceptance at least every 8 weeks or when:

(a) A delay occurs in the completion of a critical (major) activity;

(b) A delay occurs which causes a change in the critical path for CPM schedules or a change in a critical activity for BCM schedules;

(c) The actual prosecution of the work is different from that represented on the current construction schedule;

(d) There is an addition, deletion, or revision of activities caused by a contract modification; or

(e) There is a change in the schedule logic.

Allow 7 days after receipt for acceptance of the updated construction schedule or a return for revisions.

No progress payment will be made for any work until an updated construction schedule has been submitted to, and accepted by, the CO.

155.07  Acceptance.  Construction schedules will be evaluated under Subsection 106.02.

Measurement

155.08  Measure the Section 155 items listed in the bid schedule according to Subsection 109.02.

Payment

155.09  The accepted quantities will be paid at the contract price per unit of measurement for the Section 155 pay item listed in the bid schedule.  Payment will be full compensation for the work prescribed in this Section.  See Subsection 109.05.

Progress payments for construction schedule will be paid as follows:

(a) 25 percent of the item amount, not to exceed one percent of the original contract amount, will be paid after the construction schedule is accepted.

(b) Payment of the remaining portion of the lump sum will be prorated based on the total work completed.

## Section 156. — PUBLIC TRAFFIC

Description

156.01  This work consists of controlling and protecting public traffic adjacent to and within the project.  See FAR Clause 52.236-13 Accident Prevention.

Material

156.02  Conform to the following Section:

Temporary traffic control	635

Construction Requirements

156.03  Accommodating Traffic During Work.  Accommodate traffic according to the contract traffic control plan, MUTCD, Section 635, and this Section.  The Contractor may submit an alternate traffic control proposal.  Submit alternate traffic control proposals according to Subsection 104.03 for acceptance at least 30 days before intended use.

Perform work in a manner that ensures the safety and convenience of the public and protects the residents and property adjacent to the project.  Accommodate public traffic on roads adjacent to and within the project until the project is accepted according to Subsection 106.07(b).

156.04  Maintaining Roadways During Work.  Perform roadway maintenance as follows:

(a) Construct and remove diversion roads and bridges as required by the traffic control plan.

(b) Maintain intersections with trails, roads, streets, businesses, parking lots, residences, garages, farms, and other features.

(c) Snow removal to facilitate the work is the Contractor’s responsibility.  Snow removal to provide public access is the responsibility of the maintaining agency and will be performed at the maintaining agency’s discretion.  Allow the maintaining agency access to perform snow removal.

(d) Maintain a dust-free traveled way such that visibility and air quality are not affected and a hazardous condition is not created.

(e) Remove accumulations of soil and other material from traveled way.

(f) Maintain the roadway, detours, and diversions in a safe and acceptable condition.  If corrective action is requested and the corrective action is not taken immediately, the condition may be corrected and the cost of the corrective action deducted from monies due the Contractor.

156.05  Maintaining Roadways During Non-Work Periods.  Maintain roadways and traffic control for public traffic during all periods when work is not in progress.  Snow removal to provide public access is the responsibility of the maintaining agency.

156.06  Limitations on Construction Operations.  When the roadway is open to public traffic, restrict operations as follows:

(a) Operate equipment in the direction of traffic, where practical.

(b) For shoulder drop-offs in excess of 50 millimeters, provide "Low Shoulder" warning signs.  For shoulder drop-offs in excess of 100 millimeters, provide a 1:3 fillet with "Low Shoulder" warning signs.  Complete the construction of shoulders adjacent to traffic lanes to the same elevation within 14 days.

(c) Provide minimum lane widths of 3.0 meters.  Use barricades, drums, or other acceptable devices to delineate traffic lanes through areas where the edge of pavement or intended path has been obliterated by construction operations.

(d) Locate staging areas at least 10 meters from the traveled way or behind acceptable traffic barriers.  Obtain approval of the location and access to staging areas.  Store unused traffic control devices at staging areas.

(e) Park equipment at least 10 meters from the traveled way or behind acceptable traffic barriers.

(f) Provide parking areas for employees' personal vehicles in approved areas.

(g) Provide two-way radio communications between flaggers and also between flaggers and pilot cars unless flaggers are able to see each other and communicate.  Citizen band radios are not acceptable.  Make radio equipment available to the CO as necessary.

(h) Where switching traffic to a completed lane, provide adequate personnel and equipment to set or relocate traffic control devices.

(i) Limit construction-caused delays to public traffic to a maximum of 30 minutes per passage through the project.

(j) Maintain existing guardrails, barriers, and bridge railings until removal is necessary for construction.  Use a temporary barrier or appropriate channelizing devices while the guardrails and bridge rails are absent.  Install permanent barriers, guardrails, and bridge rails as soon as possible to minimize risk to the public.

156.07  Nighttime Operations.  Perform construction operations during the hours of daylight (½ hour after sunrise to ½ hour before sunset).

Where night operations are permitted, submit a night lighting system for approval.  Include the light types, locations, and the manner in which the lights will be moved.  Submit the proposed system at least 14 days before use.  Use an independent source other than vehicle headlights.  Do not use incandescent lights.  Furnish and install the approved system to illuminate the entire work area.  Position the lights so they do not shine directly at motorists traveling from any direction.  If the operation is moving, move the lighting with the operation.  Provide lighting at each flagger location.  Equip all vehicles with an exterior flashing yellow dome light.

156.08  Traffic and Safety Supervisor.  Provide a traffic and safety supervisor who is certified by a State highway agency or other acceptable certification program.  Do not designate the superintendent as the traffic safety supervisor.  Furnish the traffic safety supervisor's name, address, and 24-hour telephone number(s) at the preconstruction conference.  At all times during the contract, including periods of suspensions and work stoppages, perform all of the following:

(a) Implement the traffic control plans.

(b) Coordinate traffic control operations, including those of subcontractors and suppliers.

(c) Ensure the condition, position, and applicability of traffic control devices in use.

(d) Immediately correct traffic control deficiencies.

(e) Coordinate traffic control maintenance operations with the CO.

(f) Ensure unused traffic control devices are properly handled and stored.

(g) Conduct weekly traffic safety meetings for construction workers, and invite the CO to these weekly meetings.

(h) Furnish a weekly certification that inspections and reviews were conducted and that the traffic control devices meet contract requirements. Include the number and types of devices in use.  Report with the weekly certification, all changes or corrective actions taken to ensure the safe passage of public traffic through the project.

156.09  Acceptance.  Public traffic work will be evaluated under Subsection 106.02.

Traffic control devices and services will be evaluated under Section 635.

Measurement and Payment

156.10  See Subsection 109.05.

Measure traffic control under Section 635.

Measure dust abatement under Section 158 or 306.

Measure diversion construction, required by the contract, under the applicable Sections.

## Section 157. — SOIL EROSION CONTROL

Description

157.01  This work consists of furnishing, constructing, and maintaining permanent and temporary erosion and sediment control measures.

Material

157.02  Conform to the following Subsections:

Backfill material	704.03

Erosion control bales, wattles, logs, and rolls	713.13

Erosion control culvert pipe	713.15

Fertilizer	713.03

Geotextile	714.01

Mulch	713.05

Plastic lining	725.19

Riprap	251.02

Sandbags	713.14

Seed	713.04

Silt fence	713.16

Water	725.01

Construction Requirements

157.03  General.  Provide permanent and temporary erosion control measures to minimize erosion and sedimentation during and after construction according to the contract erosion control plan, contract permits, Section 107, and this Section.  Contract permits amend the requirements of this Section.  Do not modify the type, size, or location of any control or practice without approval.

The contract erosion control plan reflects special concerns and measures to protect resources.  An alternate erosion control proposal, with all necessary permits, may be submitted for acceptance according to Subsection 104.03.  Submit alternate erosion control proposals at least 30 days before their intended use.

When erosion control measures are not functioning as intended, immediately take corrective action.

157.04  Controls and Limitations on Work.  Before grubbing and grading, construct all erosion controls around the perimeter of the project including filter barriers, diversion, and settling structures.

Limit the combined grubbing and grading operations area to 30,000 square meters of exposed soil at one time.

Construct erosion control and sediment control measures as follows:

(a) Construct temporary erosion controls in incremental stages as construction proceeds.

(b) Construct temporary slope drains, diversion channels, and earth berms to protect disturbed areas and slopes.

(c) Unless a specific seeding season is identified in the contract, apply permanent turf establishment to the finished slopes and ditches within 14 days according to Sections 624 and 625.

(d) Apply temporary turf establishment, mulch, or other approved measures on disturbed areas within 14 days after the last disturbance except where:

(1) The area will be disturbed within 21 days after last disturbance.

(2) When initial stabilization is precluded by snow cover or by seasonal arid conditions in arid or semi-arid areas (average annual rainfall of 500 millimeters or less).

(e) Construct outlet protection as soon as culverts or other structures are complete.

(f) Construct permanent erosion controls including waterway linings and slope treatments as soon as practical or upon completion of the roadbed.

(g) Construct and maintain erosion controls on and around soil stockpiles to prevent soil loss.

(h) Following each day's grading operations, shape earthwork to minimize and control erosion from storm runoff.

157.05  Filter Barriers.  Construct silt fence, bales, wattles, logs, rolls, and brush barriers for filtering sediment from runoff and reducing the velocity of sheet flow.  Conserve brush from clearing operations to construct brush barriers.

157.06  Sediment Retention Structures.  Construct sediment retention structures of the following types:

(a) Temporary sediment traps.  Construct temporary sediment traps to detain runoff from disturbed areas and settle out sediment.  Provide outlet protection.

(b) Sediment basins.  Construct sediment basins to store runoff and settle out sediment for large drainage areas.  Excavate and construct sediment basins according to Section 204.  Construct riser pipes according to Section 602.  Provide outlet protection.

157.07  Outlet Protection.  Construct riprap aprons or basins to reduce water velocity and prevent scour at the outlet of permanent and temporary erosion control measures.  Construct riprap according to Section 251.

157.08  Water Crossings.  Construct temporary culvert pipe at temporary crossings where construction vehicles cross a live waterway.

157.09  Diversions.  Construct temporary channels, temporary culverts, earth berms, or sandbags to divert water around disturbed areas and slopes.  Use temporary channels, temporary culverts, pumps, sandbags, or other methods to divert the flow of live streams for permanent culvert installations and other work.  Stabilize channels according to Subsection 157.10.  Provide outlet protection.

157.10  Waterway and Slope Protection and Stabilization.  Use plastic lining, riprap, check dams, erosion control blankets and mats, and temporary slope drains as follows:

(a) Plastic lining.  Use plastic lining to protect underlying soil from erosion.  Place the plastic lining loosely on a smooth soil surface free of projections or depressions that may cause the liner to puncture or tear.  Lap transverse joints a minimum of 1 meter in the direction of flow.  Do not use longitudinal joints.  Anchor the lining in place using riprap.

(b) Riprap.  Construct riprap for channel lining according to Section 251.

(c) Check dams.  Construct riprap, sandbags, or earth berms for temporary dams to reduce the velocity of runoff in ditches and swales.

(d) Rolled erosion control products.  Use rolled erosion control products to stabilize waterways and slopes before or after temporary or permanent seeding.  Install according to Section 629.

(e) Temporary slope drains.  Use drainpipe, riprap, or plastic lined waterway for temporary slope drains to channel runoff down slopes.  Channel water into the slope drain with an earth berm constructed at the top of a cut or fill.  Anchor slope drains to the slope.  Provide outlet protection.

157.11  Temporary Turf Establishment.  Apply seed, fertilizer, and mulch for soil erosion protection at the rates shown in Table 157-1.  Protect and care for seeded areas, including watering, until permanent turf establishment is in place.

Table 157-1

Application Rates for Temporary Turf Establishment

| Material | Application Rate kg/ha |
| --- | --- |
| Seed | 40 |
| Fertilizer | 375 |
| Mulch | 1500 |

157.12  Inspection and Reporting.  Inspect all erosion control facilities at least every 7 days, within 24 hours after more than 10 millimeters of rain in a 24-hour period, and as required by the contract permits.

Within 24 hours, furnish inspection reports to the CO which include all of the following:

(a) Summary of the inspection;

(b) Names of personnel making the inspection;

(c) Date and time of inspection;

(d) Observations made; and

(e) Corrective action necessary, action taken, and date and time of action.

157.13  Maintenance and Cleanup.  Maintain temporary erosion control measures in working condition until the project is complete or the measures are no longer needed.  Clean erosion control measures when half full of sediment.  Use the sediment in the work, if acceptable, or dispose of it according to Subsection 204.14.

Replace erosion control measures that cannot be maintained and those that are damaged by construction operations.

Remove and dispose of temporary erosion control measures when the vegetation is satisfactorily established and drainage ditches and channels are lined and stabilized.  Remove and dispose of erosion control measures according to Subsection 203.05.

Restore the ground to its natural or intended condition and provide permanent erosion control measures.

157.14  Acceptance.  Material for soil erosion control measures will be evaluated under Subsections 106.02 and 106.03.

Construction, maintenance, and removal of soil erosion control measures will be evaluated under Subsections 106.02 and 106.04.

Geotextile will be evaluated under Section 207.

Measurement

157.15  Measure the Section 157 items listed in the bid schedule according to Subsection 109.02 and the following as applicable.

Do not measure replacement items.

Measure temporary turf establishment by the hectare on the ground surface.  When measurement is by the kilogram, weigh the seed in kilograms.

Measure excavation for diversion channels and sediment basins under Section 204.

Measure riprap under Section 251.

Measure permanent paved waterways under Section 608.

Measure permanent slope paving under Section 616.

Measure topsoil under Section 624.

Measure permanent turf establishment under Section 625.

Measure rolled erosion control products under Section 629.

Payment

157.16  The accepted quantities will be paid at the contract price per unit of measurement for the Section 157 pay items listed in the bid schedule.  Payment will be full compensation for the work prescribed in this Section.  See Subsection 109.05.

Progress payments for erosion control measures will be made as follows:

(a) 50 percent of the unit bid price will be paid upon installation.

(b) An additional 25 percent of the unit bid price will be paid following completion of 50 percent of the contract amount.

(c) Payment of the remaining portion of the unit bid price will be paid when the temporary erosion control measures are removed from the project.

## Section 158. — WATERING FOR DUST CONTROL

Description

158.01  This work consists of furnishing and applying water for the control of dust caused by the work and public travel.

Material

158.02  Conform to the following Subsection:

Water	725.01

Construction Requirements

158.03  General.  Provide an adequate water supply and apply water needed at all hours (including nights, weekends, and periods of nonwork) as necessary to control dust.  Uniformly apply water using pressure-type distributors, pipelines equipped with spray systems, or hoses with nozzles.

(a) Project dust control for public benefit.  Control dust within the construction limits at all hours when the project is open to public traffic.  When the project is not open to public traffic, control dust in areas of the project which neighbor inhabited residences or places of business.  Control dust on approved, active detours established for the project.  Apply water at the locations, rates, and frequencies ordered by the CO.

(b) Other dust control.  Control dust on active haul roads, in pits and staging areas, and on the project during all periods not covered in (a) above.

158.04  Acceptance.  Furnishing and placing water will be evaluated under Subsection 106.02.

Measurement

158.05  Measure the Section 158 items listed in the bid schedule according to Subsection 109.02 and the following as applicable.

Measure water for dust control by the cubic meter in the hauling vehicle or by metering.

Do not measure water for dust control applied according to Subsection 158.03(b).

Payment

158.06  The accepted quantities will be paid at the contract price per unit of measurement for the Section 158 pay item listed in the bid schedule.  Payment will be full compensation for the work prescribed in this Section.  See Subsection 109.05.