Acquisition Management System Guidance

Implementation Strategy and Planning Document Template

July 2016

Implementation Strategy and

Planning Document Template

(ISPD)

Initial ISPD:

An initial ISPD is required for the initial investment decision and is not to exceed 15 pages for all acquisition category (ACAT) levels.  The initial ISPD contains only the following sections:

Overview

Acquisition Planning

Systems Engineering, Development, and Production

Physical and Functional Integration

Integrated Logistics Support

System Safety Management

Information in the initial ISPD is a comparative analysis of the alternatives for each of the six sections above (for example, the pros and cons of each alternative with respect to physical and functional integration into the anticipated operating environment). The initial ISPD is NOT an initial strategy for the preferred alternative.

Final ISPD:

A final ISPD is required for the final investment decision.  The final ISPD has the following page limits based on the ACAT level:

ACAT 1 and 2:  should be no more than 35 pages

ACAT 3 and 4:  should be no more than 25 pages

ACAT 5:  should be no more than 15 pages

The final ISPD is the overall implementation strategy for the alternative selected for implementation at the initial investment decision.

Joint Resources Council (JRC) members sign the final ISPD at the time the investment is approved.

Updates to the ISPD:

The ISPD is updated when a major change to the acquisition program baseline (performance, cost, or schedule) results in a significant change to the investment strategy approved by the Joint Resources Council. Contact the JRC Secretariat for instructions concerning the ISPD change process.

Relationship between the ISPD and the Program Management Plan:

The ISPD and program management plan are complementary documents. The ISPD specifies the overall strategy for obtaining, fielding, and supporting over its service life the capability approved and funded for implementation by the Joint Resources Council at the final investment decision. The program management plan defines how the service organization will manage the investment program to execute the strategy recorded in the ISPD. It defines the relationships and responsibilities of key organizations that will contribute to the implementation and fielding of this initiative.

Joint Resources Council

Signature Page

IMPLEMENTATION STRATEGY AND

PLANNING DOCUMENT

for

(Program Name)

ISPD Approved by:

_______________________________________	Date:_____________

FAA Acquisition Executive /

Deputy Assistant Administrator Acquisition

and Business Services, ACQ-1

_______________________________________	Date:_____________

Chief Financial Officer /

Deputy Assistant Administrator

Financial Services, ABA-1

_______________________________________	Date:_____________

Chief Information Officer, AIT-1

Deputy Assistant Administrator for

Information & Technology

SIGNATURE PAGE

ISPD Approved by:

_____________________________________ 	Date:_____________

Chief Operating Officer / Deputy Chief Operating Officer, AJO-0 (ATO programs only)

ISPD Approved by:

_____________________________________ 	Date:_____________

For ATO programs: Vice President of the organization that will execute the program in solution implementation

For non-ATO programs:  Second-level executive of the organization that will execute the program in solution implementation

ISPD Section 2 Approved by:

_____________________________________	Date:_____________

Director, Acquisition and Contracting, AAQ-1

_____________________________________	Date:_____________

Director of Financial Analysis, AFA-1

ISPD Sections 5, 6, and 10 Approved by:

_____________________________________	Date:_____________

Vice President for Technical Operations, AJW-0 (NAS and Non-NAS)

Director, AIT Infrastructure & Operations (Non-NAS)

ISPD Sections 1, 4, and 5 Approved by:

_____________________________________	Date:_____________

Director, Engineering Services, ANG-B (NAS programs)

Director, AIT Strategy & Performance Service (Non-NAS programs)

ISPD Section 6.7, 7.1, 9.2, and 10.2 Approved by:

_____________________________________	Date:_____________

Vice President, Safety and Technical Training, AJI-0

ISPD Submitted by:

_____________________________________	Date:_____________

Program manager of the organization that will execute the program in solution implementation

Implementation Strategy and Planning Document

Table of Contents

EXECUTIVE SUMMARY	1

1 OVERVIEW	2

1.1 Service Need	2

1.2 Description	2

1.3 Key Outputs & Outcomes	2

2 ACQUISITION PLANNING	3

2.1 Purpose of Contract(s)	3

2.2 Sources	3

2.3 Competition	3

2.4 Contract Type & Incentives	3

2.5 Source Selection	3

2.6 Government-Furnished Property and Information	3

2.7 Warranties and Data Rights	3

3 PROGRAM & CONTRACT MANAGEMENT	4

3.1 Program Management	4

3.2 Contract Management	4

4 SYSTEMS ENGINEERING, DEVELOPMENT, & PRODUCTION	5

4.1 Systems Engineering	5

4.2 Hardware and Software	5

4.3 Reliability, Maintainability & Availability	5

4.4 Configuration Management	5

4.5 Human Factors	5

4.6 Specialty Engineering	6

4.7 Production	6

5 PHYSICAL & FUNCTIONAL INTEGRATION	7

5.1 Real Property	7

5.2 Physical Space and Integration	7

5.3 Operational Integration	7

5.4 Environmental Requirements	7

5.5 Telecommunications	8

5.6 Spectrum Management	8

5.7 Information Interoperability	8

6   Integrated Logistics Support  (ILS)	9

6.1 Maintenance Planning	9

6.2 Supply Support	9

6.3 Packaging, Handling, Storage, and Transportation	10

6.4 Support Equipment	10

6.5 Maintenance Support Facilities	10

6.6 Direct-Work Maintenance Staffing	10

6.7 Training, Training Support, and Personnel Skills	10

6.8 Technical Data	10

6.9 Computer Resources Support	11

7 SAFETY & HEALTH	12

7.1 System Safety Management	12

7.2 Employee Health & Safety	13

7.3 Hazardous Materials	13

8 SECURITY & PRIVACY	14

8.1 Physical Security	14

8.2 Information Security	14

8.3 Personnel Security	14

8.4 Privacy	14

9 TEST & EVALUATION	15

9.1 Test Strategy Overview	15

9.2 Independent Operational Assessment	15

10 DEPLOYMENT	16

10.1 Deployment Strategy	16

10.2 In-Service Decision Strategy	16

10.3 Disposition Strategy	16

11 PROGRAM SCHEDULE	17

- ACAT 1 - 4

- Should be no more than 2 pages

# EXECUTIVE SUMMARY

Summarize the information in this document highlighting those elements most relevant for the investment decision authority to make a final investment decision.

- All ACATs

- Should be no more than 5 pages

# 1 OVERVIEW

## 1.1 Service Need

Cite the program requirements document and other appropriate higher level documents (such as FAA Strategic Plan, FAA enterprise architecture, and organizational business plan) from which this service need is derived.

Briefly characterize the need this initiative is intended to resolve or the opportunity it will fulfill and explain why this investment is required.

## 1.2 Description

Briefly summarize the service or operational capability this initiative is intended to provide. Briefly describe how it relates to the overall NAS or Non-NAS enterprise architecture and other interfacing systems or products.

Identify key implementation features of this initiative (e.g., development of hardware or software, procurement of systems or equipment, modification or construction of facilities, changes in the physical infrastructure, development of functional interfaces, or procurement of installation or support services).

Briefly characterize the level of development envisioned for this initiative (e.g., integration of commercial items, modified COTS, COTS hardware with developmental software, full-scale development).

## 1.3 Key Outputs & Outcomes

Briefly summarize the primary capabilities this initiative is intended to provide including key outputs and outcomes. Be consistent with the program requirements document and shortfall analysis report.

2 ACQUISITION PLANNING

- All ACATs

- Should be no more than 4 pages

## 2.1 Purpose of Contract(s)

Describe the purpose, scope of work, period of performance, and estimated price of each contract planned to be awarded or used for this initiative. Explain how each supports the products and outcomes of Section 1. Include any support contract requirements and interagency agreements, as applicable.

## 2.2 Sources

Characterize the prospective sources that can satisfy the need as identified by market research and other means. State whether a Qualified Vendors List will be used. Discuss how small and small disadvantaged businesses will participate.

## 2.3 Competition

Identify whether competition will be sought and explain how it will be achieved. If competition is not planned, explain the decision-making process and rationale used to reach that conclusion. Identify what streamlining actions will be used (e.g., release of draft information to industry for comment, use of oral proposals, pre-qualification of contractors, etc.).

## 2.4 Contract Type & Incentives

Identify the contract type(s) you will use and explain why the correct choice is appropriate for the level of anticipated program risk. Discuss the use of contract incentives to achieve key program goals such as performance, quality, and cost and schedule control.

## 2.5 Source Selection

Identify any special or unique considerations to be used in source selection(s). Identify key source selection participants.

## 2.6 Government-Furnished Property and Information

Identify any key property or information the FAA must provide to the contractor.

## 2.7 Warranties and Data Rights

Identify any key warranties or data rights that will be obtained.

# 3 PROGRAM & CONTRACT MANAGEMENT

## 3.1 Program Management

Identify key individuals responsible for management and control of program cost, schedule, and technical performance baseline. This includes the program manager, contracting officer, and contracting officer representative, as applicable. Summarize the certifications/accreditations for all three, as applicable.

Describe the strategy for planning, integrating and managing all resources and tasks supporting the execution of this initiative. Explain the strategy for planning, measuring, coordinating, reporting, evaluating, and revising program activity.

Describe how key technical measures of program success will be monitored, reported, and evaluated throughout solution implementation including developmental and operational testing.

## 3.2 Contract Management

Describe the strategy for managing prime and support contracts. Include contract administration and review or oversight of contractor capability, evaluation, and appraisal processes. Identify what kind of cost, schedule, and technical performance tracking will be used to monitor contractor status and progress. Identify whether earned value management will be applied consistent with AMS policy.

Identify what quality assurance controls will be applied to the contractor. Identify what government entity will perform quality assurance on contract activities. Examples include in-plant Quality Reliability Officers and independent verification and validation.

# 4 SYSTEMS ENGINEERING, DEVELOPMENT, & PRODUCTION

As appropriate, use the standard FAA work breakdown structure as a guide in addressing the following sub-sections.

## 4.1 Systems Engineering

Describe the systems engineering strategy for this investment initiative. For example, define government and contractor roles for applying systems engineering to operational requirements and maintenance concepts, functional analysis and allocation, product analysis and trade-off studies, product design, and test and evaluation. Identify whether program requirements will be allocated to different solution providers and describe how they will be transformed into specifications for prime contractor(s).

## 4.2 Hardware and Software

Using the framework of section 3 of the FAA standard work breakdown structure, define the strategy for the design, development, and production of hardware and software configuration items. Describe the software and hardware development process that will be applied to this investment initiative; for example, whether software development will follow an evolutionary, spiral, incremental, or combination process. Discuss the level and scope of design, development, or procurement of hardware that will be applied.

Non-NAS investment programs that are IT-centric should work with the AIT Solutions Delivery Service, Solution Architecture & Design Group when defining the hardware and software strategy or task them to do it.

## 4.3 Reliability, Maintainability & Availability

Explain the strategy to incorporate reliability, maintainability, availability, and usability into the design, development, and production of the solution.

## 4.4 Configuration Management

Define the strategy for managing the configuration of requirements, hardware, software, data documentation, interfaces, and tools throughout their service life. Differentiate between vendor and in-house organic configuration management responsibilities. Identify whether and when product configuration will transfer from contractor management to formal FAA control.

## 4.5 Human Factors

Define how human factors requirements associated with operation and maintenance of the solution will be derived and integrated into product design.

## 4.6 Specialty Engineering

Identify what specialty engineering disciplines apply to this initiative and define the strategy for integrating them into the solution.

## 4.7 Production

As applicable, define the strategy for transforming the engineering design to into a product that can be manufactured efficiently. Define FAA and contractor roles associated with production feasibility and producibility of the engineering design including resources, processes, tooling, materials, testing, and deployment.

# 5 PHYSICAL & FUNCTIONAL INTEGRATION

5.1 Real Property

- All ACATs

- Should be no more than 2 pages

Real property includes owned and leased land and space and other structures under FAA control. Define the strategy for acquiring needed land, including completion of the National Environmental Protection Act process, appropriate Environmental Due Diligence Audits, and any other applicable environmental law before agreement to acquire property. This includes initial analysis, market search, identifying and analyzing candidate sites, appraisals, title searches, and acquisition. Be aware the lead-time for acquisition of real estate can be very long and should begin soon after the investment decision and in close coordination with the appropriate region or center that will acquire the real estate. If existing land is being replaced, an Environmental Due Diligence Audit needs to be completed prior to disposal of property.

Note that this section will typically not apply to Non-NAS investment programs that are IT-centric.

## 5.2 Physical Space and Integration

Define the strategy for acquiring the physical space needed to accommodate systems, auxiliary equipment, and personnel both for end-state operations and during transition to the new capability. As applicable, define the strategy for satisfying power system and commercial power requirements and for achieving heating, ventilation, and air-conditioning requirements.

Non-NAS investment programs that are IT-centric should work with the AIT Data Center Infrastructure & Operations Service, Performance & Planning Group when defining the physical space and integration strategy.

## 5.3 Operational Integration

Define the strategy for implementing interface requirements with other NAS and Non-NAS systems, subsystems, networks, facilities, and organizations, including all states and modes of operation (e.g., primary and back-up).

## 5.4 Environmental Requirements

Other than for real property (Section 5.1), define the strategy for satisfying environmental requirements for this initiative or its products that minimize lifecycle environmental impact of systems, facilities, and equipment. This may involve Environmental Impact Statements, Assessments, and Due Diligence Audits.

An example of environmental needs that Non-NAS investment initiatives may need to plan for is cooling for large-scale IT installations.

## 5.5 Telecommunications

Identify any changes to the NAS or information technology infrastructure necessary to accommodate the telecommunications needs of this investment. Define the strategy for achieving any telecommunications capabilities not in the current infrastructure both for end-state operations and during transition to the new capability.

Non-NAS IT investment programs will always need to consider telecommunications. Where does your information need to go? How will it be transferred? What FAA data transfer system will you use? What protocols will you use to transfer data?

## 5.6 Spectrum Management

Define the strategy for satisfying spectrum management requirements for this initiative and ensuring spectrum compatibility with other National Airspace System elements.

Non-NAS IT spectrum needs will typically be commercial spectrum versus NAS spectrum. If you need spectrum, make sure your solution provider understands your requirements.

## 5.7 Information Interoperability

If this initiative is required to be compliant with the FAA’s System-Wide Information Management (SWIM) infrastructure, describe the strategy for using SWIM products and standards to ensure information interoperability with other NAS and Non-NAS systems.

Non-NAS investment programs that are IT-centric, should work with the AIT Data Center Infrastructure & Operations Service, Performance & Planning Group when defining the information interoperability strategy.

# 6   Integrated Logistics Support (ILS)

- All ACATs

- Should be no more than 2 pages

NAS programs work with the AJW NAS Integrated Support Group to form an integrated logistics support management team that will establish and implement a support strategy to sustain the products of this investment initiative (system, service, facility, equipment) throughout their service life. Refer to AMS Section 4.3 for ILS policy guidance.

Non-NAS investment programs that are IT-centric should also work with the AIT Solution Delivery Service, Building & Management Group when defining their maintenance and integrated logistics support strategy. Typically, Non-NAS IT investments do not require a lifecycle support strategy for every logistics element since they often are deployed at a single site.

During initial investment analysis, you will develop an initial logistics support strategy for each alternative solution to the service need as a basis for estimating service life support cost for inclusion in the initial business case. The work associated with each ILS element is found in Section 3.6 (for solution implementation) and Section 4.6 (for in-service management) of the FAA Standard Work Breakdown Structure.

During final investment analysis, you will develop a final logistics support strategy for the alternative selected for implementation by the Joint Resources Council. Refer to details required in the paragraphs that follow.

## 6.1 Maintenance Planning

Describe how you will sustain, restore, and maintain the operational capability of your solution (system, service, equipment, or facility) throughout its service life in compliance with FAA Order 6000.30. Include your strategy for preventive and corrective maintenance, repair, second-level engineering, enterprise monitoring, modifications to software and hardware, and resolution of technical problems. Summarize your strategy for complying with the 6000 series of FAA Orders to include certification, reliability-centered maintenance, and remote maintenance logging support.

Define FAA's role in certification, coordination of interruptions, event management, and overall operational oversight of the solution, service, and service providers. Also explain your strategy for periodically modernizing key elements of the product or service to sustain or improve service delivery.

## 6.2 Supply Support

Summarize your strategy for planning and acquiring supply support for newly fielded systems and equipment. This includes initial spares and repair parts to support field and depot repair, maintenance of training classrooms and labs, test and measurement equipment, support equipment, and second-level engineering labs and equipment.

## 6.3 Packaging, Handling, Storage, and Transportation

Summarize your strategy for planning and establishing a packaging, handling, storage, and transportation capability for prime mission product components, assemblies, and subassemblies. This includes packaging, handling, storage, and transportation of initial spares and repair parts to support and maintain newly fielded systems or subsystems during initial service at all levels of maintenance and support.

## 6.4 Support Equipment

Summarize your strategy for identifying, acquiring, and delivering test and measurement equipment, common support equipment, and peculiar support equipment.

## 6.5 Maintenance Support Facilities

Summarize your strategy for planning and establishing space in a site or facility for first-level maintenance, technical data repository, depot repair, second-level engineering, training classrooms and labs, supply support, and other facilities as required for you investment program.

## 6.6 Direct-Work Maintenance Staffing

Summarize your strategy for defining qualitative FAA first-level touch labor requirements, their supervision, and support functions required to maintain NAS systems and equipment that your investment initiative will deploy. For leased services, address staffing impacts of coordination, certification, event management, and operational oversight of service providers.

## 6.7 Training, Training Support, and Personnel Skills

Summarize your strategy for establishing training for operators and maintainers and enterprise operations personnel; deport repair technicians; maintenance of common and peculiar support equipment and test and measurement equipment; second-level engineering support; computer resources support; and packaging, handling, storage, and transportation of systems and equipment.

## 6.8 Technical Data

Summarize your strategy for obtaining, reviewing, and storing program and contractor technical data. Technical data includes items such as engineering drawings, notebooks, maintenance handbooks, operator manuals, maintenance manuals, installation drawings, configuration management plans and all contract data deliverables. This includes delivery and maintenance of documentation in place by contractors with government access, as well as activity related to treatment of intellectual property rights and third-party retention of data and documentation.

## 6.9 Computer Resources Support

Summarize your strategy for planning and establishing second-level engineering support for computer resources associated with deployed systems, services and equipment.

# 7 SAFETY & HEALTH

## 7.1 System Safety Management

Describe your strategy for conducting safety management as required by FAA Order 8040.4A Safety Risk Management (non-ATO acquisitions only), ATO JO 1000.37A Air Traffic Organization Safety Management System, ATO SMS Manual, and the Safety Risk Management Guidance for System Acquisitions (SRMGSA) including safety strategy meetings with the Safety and Technical Training, Safety Management Group, as necessary.

System safety management may not apply to Non-NAS investment initiatives; you must coordinate with Safety and Technical Training to determine required actions.

For the initial investment decision, explain your strategy for:

- Developing a preliminary program safety plan that identifies significant safety concerns and is not solution specific; and

- Conducting a comparative safety assessment to determine the safety risk ratings of each alternative. Include any critical safety issues identified from this or other safety assessments.

Include:

- Safety risk differences among the investment alternatives and the development assurance level for each; and

- How you will track safety hazards in the ATO safety management tracking system.

For the final investment decision, explain your strategy for:

- Developing or updating the program safety plan;

- Conducting a preliminary hazard analysis for the selected alternative;

- Conducting additional safety assessments during solution implementation as determined in safety strategy meetings, e.g., system hazard analysis, sub-system hazard analysis, operational and support hazard analysis and system safety assessment report; and

- Ensuring solution contractors develop appropriate system safety plans to support the program safety plan.

Include:

- The development assurance level for the selected alternative; and

- How you will track safety hazards in the safety management tracking system.

Refer to system safety management program guidance in FAST, the Safety Management System Manual, and the SRMGSA to find detailed requirements.

## 7.2 Employee Health & Safety

Define the strategy for satisfying requirements related to Occupational Safety and Health Administration, the National Fire Protection Association, and other safety and health regulations, as well as for avoiding conditions that degrade performance. Define the strategy for achieving operating environment requirements associated with such factors a light, temperature, fire protection, stairs and ladders. Specify how you will update the Occupant Emergency Plan when implementation will affect facility egress routes or fire safety.

## 7.3 Hazardous Materials

Define the strategy for achieving requirements associated with hazardous materials both for end-state operations and during transition to the new capability. Be sure to consider disposal of replaced assets that contain silicon or other hazardous material.

# 8 SECURITY & PRIVACY

## 8.1 Physical Security

Explain how you will satisfy requirements related to security of the physical plant both for end-state operations and during transition to the new capability.

## 8.2 Information Security

Define your strategy for ensuring information security (including security related to system integration into the NAS) throughout the lifecycle of this initiative and identify key risks.

Non-NAS IT-centric initiatives should work with the AIT Information Security & Privacy Service when developing the information security and privacy strategy.

## 8.3 Personnel Security

If applicable, explain how you will satisfy requirements related to personnel, security clearances, security training, and access control.

## 8.4 Privacy

If applicable, describe how you will secure personally identifiable information used by or stored in any product of this initiative.

# 9 TEST & EVALUATION

## 9.1 Test Strategy Overview

Define the test strategy for each stage (e.g., capability demonstration, prototype development, full-scale development, production, deployment, as appropriate) of solution implementation. Explain how test objectives will be established for each stage of testing and how operational issues and requirements will be integrated into test objectives. Explain your strategy for obtaining test plans, procedures, and reports, as well as test personnel, tools, training, and other test resources for both government and contractor personnel. Identify whether independent software verification and validation will be used.

If this is a commercial or non-developmental investment, describe the use of commercial product testing or historical usage data in place of government testing. Identify any completed testing including operational capability tests and demonstrations. Identify any other test streamlining approaches that will be used (e.g., Operational Capability Demonstration as an element of source selection).

Explain why this test strategy is appropriate for the risk associated with the products or capability to be provided. State the plan and requirements for the delivery of a test and evaluation master plan.  State whether a Verification Requirements Traceability Matrix will be used to trace critical performance requirements and critical operational issues from the program requirements document to test activities throughout solution implementation. Identify any field testing that will be part of developmental or operational testing.

Non-NAS IT-centric investment initiatives should work with the AIT Quality Assurance Group when developing the test strategy.

## 9.2 Independent Operational Assessment

If this investment is anticipated to be designated for independent operational assessment, the IOA program manager will develop this section of the ISPD. It will include the IOA approach; criteria for selecting the site for IOA; how critical operational issues will be resolved; and prerequisites for starting the assessment.

# 10 DEPLOYMENT

## 10.1 Deployment Strategy

Define the strategy for fielding and bringing the new capability into operational use. This typically involves deployment planning, implementation contract(s) award and administration, site engineering and physical integration, installation and checkout, system shakedown, dual operations, joint acceptance and inspection, commissioning, and the removal and disposal of replaced systems, equipment, land, facilities, and other items.

Non-NAS IT-centric initiatives should work with the AIT Infrastructure & Operations Service, Transition & Operations Group when developing the deployment strategy.

## 10.2 In-Service Decision Strategy

Explain the strategy for the in-service decision. Describe whether there are segments, phases, or several, major software releases that will have separate in-service decisions. Identify any shipment to sites other than the key site before the in-service decision. This section should be coordinated with the In-Service Decision Executive Secretariat.

If as a program progresses, a major portion of the solution will not be ready at the time of the in-service decision, the decision may have to be delayed or additional in-service decisions may be required. Significant changes to the in-service decision strategy must be reviewed by the in-service decision authority and approved by the Joint Resources Council.

Non-NAS and Non-NAS IT initiatives do not require an in-service decision nor a waiver from the In-Service Decision Executive Secretariat.  Acceptance criteria will be agreed upon by the customer and the service delivery organization.

## 10.3 Disposition Strategy

Explain the strategy for the reuse or disposition of all property and equipment replaced or affected by this initiative. FAA Order 4600.27 specifies FAA disposition policy and ISR checklist items 10.1 and 10.2 identify disposition factors that need to be considered.

11 PROGRAM SCHEDULE

- All ACATs

- Tailored by ACAT

Non-NAS IT-centric investment programs should work with the AIT Enterprise Program Management Service to develop the program schedule.

Display your integrated program schedule by month after contract award for key program events, milestones, and activities necessary to design, produce, and deliver the product(s) of this initiative. Integrate all activity by the government, contractors, and others who will complete the work. Display anticipated timeframes for design, development, production, test, site preparation, deployment, and shakedown, as appropriate. Use the FAA work breakdown structure found under “Special Topics” on the FAST homepage.

If implementation will occur in segments or builds, include them in your integrated schedule. Section 3 (solution implementation) of the standard FAA work breakdown structure contains representative planning elements and events that may be applicable. Be sure to build contractor activity (WBS Section 3.1) into your integrated schedule. Include real estate acquisition and all key program elements such as airspace design and rulemaking, as appropriate. Be aware that real estate acquisition can be the most time-consuming aspect of program implementation.

The schedule should be consistent with the schedule in the business case and acquisition program baseline for the selected alternative.

The integrated master schedule should include logic, predecessor and successor relationships, and constraints.