Section 109. — MEASUREMENT AND PAYMENT

Revised 23 September 2008

ASPHALT CEMENT Price Adjustment Provision Coordination on the use of this provision must be sought with Acquisitions, Construction, and Materials. The use of this price adjustment provision must be evaluated on a project-by-project basis and is only applicable when included by the Government for a specific project. Use this price adjustment provision on single or multiple season contracts/projects, when (1) the contract involves an extended period of performance with significant costs to be incurred beyond one year after performance begins, (2) the contract amount subject to adjustment is substantial, (3) the economic variables for materials and supplies are too unstable to permit a reasonable division of risk between the Government and the Contractor, without this type of provision; (4) the price of materials and/or supplies is extremely volatile, (5) suppliers are unable to provide price quotations for the usual term of the contract, (6) price quotes are based on the date of delivery or spot market conditions and (7) shortages are expected. The price adjustment provision should only be applied to the specific price volatile materials and/or supplies called out below.

109.06  Pricing of Adjustments.  Add the following:

ASPHALT CEMENT PRICE ADJUSTMENT PROVISION

GENERAL  The Asphalt Cement Price Adjustment Provision provides for a price adjustment in the form of a payment to the Contractor or a rebate to the Government for fluctuations in the cost of asphalt cement used in the performance of applicable construction work.  The price adjustment provisions are applicable only to the asphalt cement, as defined in Subsection 702.01, and incorporated in the following eligible contract pay items:

- 40101 Superpave pavement

- 40102 Superpave pavement, wedge and leveling course

- 40201 Hot asphalt concrete pavement, Marshall or Hveem test

- 40202 Hot asphalt concrete pavement, Marshall or Hveem test, wedge and leveling course

- 40301 Hot asphalt concrete pavement

- 40302 Hot asphalt concrete pavement, wedge and leveling course

- 40501 Open-graded asphalt friction course

Select appropriate eligible pay items and delete those that do not apply. For each of the eligible contract pay items chosen above, a corresponding statement should be added to the applicable SCR payment subsection, which indicates that “A price adjustment will be made for fluctuations in the cost of asphalt cement used in the performance of any eligible pay items according to Subsection 109.06 Pricing of Adjustments Asphalt Cement Price Adjustment Provision.” See end of provision for additional direction.

The price adjustment provisions are also applicable when the Government adds extra work to the eligible pay items already existing under the Contract.

The provision will remain in effect throughout the duration of the contract.  Enactment of the Asphalt Cement Price Adjustment Provision will only be considered when the increase or decrease in the price of asphalt cement as defined herein exceeds 10 percent.

The Asphalt Cement Price Adjustment Provision is intended to reduce but not eliminate the cost effects of price uncertainty to the Contractor and the Government for asphalt cement used in the construction of this contract.  It provides for sharing by the Government in a portion of the Contractor’s risk, which could result from unusual price fluctuations.  The provision is not intended to compensate the Contractor for normal day-to-day fluctuations and seasonal changes or to serve as a guarantee of full compensation for asphalt cement price fluctuations.

EFLHD will revise the following policy/procedures. The Construction Branch is responsible for (1) purchasing the Asphalt Weekly Monitor (AWM) newsletter; (2) selecting the applicable region and states; (3) calculating and posting price indexes on an accessible web page and; (4) calculating and paying price adjustment compensations. In order to establish a reference for the base and monthly performance price indexes, the Poten and Partners, Inc newsletter (i.e. Asphalt Weekly Monitor) should be surveyed and an applicable region and state inserted below. A website address must also be inserted below where the Contractor and other interested parties can check Government postings of monthly price indexes. There could potentially be one web page for each project unless projects are in the same state. The Base and Monthly Performance Price Indexes for Asphalt Cement must also be calculated using weekly high and low selling price data obtained from the Asphalt Weekly Monitor for the applicable state. Weekly high and low selling price data from four consecutive reports will be averaged to obtain a Base Price Index as well as a Monthly Performance Price Index. The Base Price Index (BPI) must be inserted below by Acquisitions in the conformed set. The Monthly Performance Price Index must be posted monthly by Construction on the website.

PRICE INDEXES  The Government will generate a monthly performance price index for asphalt cement using price data obtained from Poten and Partners, Inc. (PPI), which publishes a weekly report (Asphalt Weekly Monitor) on high and low selling prices for states in five regions throughout the United States including the East Coast/Northeast, the Mid-Continent/Midwest, the Gulf Coast/Mid South, the Rocky Mountains and the West Coast/Northwest.  Weekly high and low selling price data reported for (insert the applicable region and states) will be averaged and used to establish a base price index, BPI, for this project and a monthly performance price index, MPPI, for the duration of the contract.  These indexes are defined as follows:

- BASE PRICE INDEX  The base price index, BPI, is the price index determined by the arithmetic average, as specified above, shown in the four weekly publications immediately preceding the bid opening.  The BPI will be provided by the Government after contract award.  It is as follows:

BASE PRICE INDEX (BPI) FOR ASPHALT CEMENT

PER SHORT TON (TON) (or PER METRIC TON) = $

- MONTHLY PERFORMANCE PRICE INDEX  The monthly performance price index, MPPI, is the monthly price index at the time of performance of applicable work as determined by the arithmetic average, as specified above, shown in the four weekly publications issued prior to the last Wednesday of the month (i.e. the monthly performance price index during which asphalt cement is used in the performance of applicable construction work).

PRICE ADJUSTMENTS  Price adjustments are calculated by the Government for average conditions and are not intended to reflect the Contractor’s actual purchase price.  The ratio of the monthly performance price index and the base price index (MPPI/BPI) is calculated and used to determine price adjustments for eligible pay items as follows:

- No Price Adjustment – When the ratio MPPI/BPI falls within the range of 0.90 to 1.10, no price adjustment will be made for any asphalt cement used in construction work performed during the relevant month.

- Government Rebate – When the ratio MPPI/BPI is calculated to be less than 0.90, the Government is due a rebate determined in accordance with the following formula:

Government Rebate = [0.90 – (MPPI/BPI)] (BPI) (Q)

- Contractor Payment – When the ratio MPPI/BPI is calculated to be greater than 1.10, the Contractor is due additional payment determined in accordance with the following formula:

Contractor Payment = [(MPPI/BPI) – 1.10] (BPI) (Q)

The following definitions are applicable to both the Government Rebate and the Contractor Payment formulas:

MPPI	=	Monthly Performance Price Index for the month during which asphalt cement is used in the performance of applicable construction work.

BPI	=	Base Price Index that is established immediately preceding the bid opening.

Q	=	Quantity in tons of asphalt cement for eligible pay items that were used on the project during the progress payment period.  The quantity will be calculated using the asphalt content of the approved mix design and the following formula:

Q	=	Asphalt Concrete Pavement tons placed x (% Asphalt/100)

PRICE ADJUSTMENT COMPENSATION  Monthly adjustments will be accrued.  The final price adjustment will be paid, or rebated, after completion of all work for eligible pay items.  The Contractor may request in writing a partial price adjustment payment once every 12 months, or when the unpaid accrued increase exceeds $10,000.  The Government will take a rebate when the deductive accrual exceeds $10,000.

No price adjustments will be made for work performed beyond the Government-approved Contract completion date.

The maximum allowable monthly and final price adjustment to the Contractor or rebate to the Government is limited to a (MPPI/BPI) ratio of 1.6 and 0.4, respectively.

Cut and insert the following into the appropriate Section (delete the non-applicable Subsections):

401.19.  402.19.  403.19.  405.13.  Add the following:

A price adjustment will be made for fluctuations in the cost of asphalt cement used in the performance of any eligible pay items according to Subsection 109.06 Pricing of Adjustments Asphalt Cement Price Adjustment Provision.