## Instructions
Better Building Residential Program Implementation Plan Template
Overview
The Better Building Residential Program Implementation Plan Template will help you develop a strategy for planning, operating, and evaluating a successful residential energy efficiency program. This document identifies the key implementation steps involved with the six program components typically overseen by a program administrator:
® | Market Position & Business Model
® | Program Design and Customer Experience
® | Evaluation & Data Collection
® | Marketing & Outreach
® | Financing
® | Contractor Engagement & Workforce Development
How to Use this Template
Each tab in this workbook is dedicated to one of the six program components required to successfully launch or improve a residential energy efficiency upgrade program. The first column of each worksheet provides the important stages for successful program administrators to follow, as well as links to the individual handbooks in the Better Buildings Residential Program Solution Center. The second column provides a high-level description of each stage. The third column lists implementation steps to consider in each stage of your planning process. Note: Launching and improving an energy efficiency upgrade program is an iterative process that may not always lend itself to concrete start and end dates for each step provided in the template. Additionally, each worksheet contains a Gantt chart for you to plan and monitor the progression of your program's key acitivities.
Additional Information
Detailed information on specific steps can be found in the Better Buildings Residential Program Solution Center at: energy.gov/rpsc.

## MarketPosition
Market Position & Business Model |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
Identify your organization’s optimal market position by understanding existing market actors, gaps, competitors, and potential partners. Develop a business model that will allow you to sustainably deliver energy efficiency products and services. |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Stage | Stage Description | Step-by-Step | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Assess the Market | Survey existing and potential demand for energy efficiency products and services based on an understanding of policies, housing and energy characteristics, demographics, related initiatives and other market actors. | • Assess potential market demand for energy efficiency products and services
• Assess how the market is served by other organizations and what gaps exist for your organization to fill
• Assess your strengths and capabilities to provide products and services in the market
Set Goals & Objectives | Establish or update your organizational mission, vision, and goals to encompass energy efficiency programs. | • Examine your organization’s existing vision, mission, and goals
• Define your organization’s vision
• Define the organization’s mission
• Develop S.M.A.R.T. goals
• Get buy-in from your organization’s stakeholders
Identify Partners | Identify and engage organizational partners in your business model design. | • Understand the business models of potential partners
• Approach potential partners and develop a partnership framework
Develop a Business Model | Define your business model, including market position, products and services, type of customers, financial model, governance structure, and the assets and infrastructure your organization needs. | • Determine what services to provide
• Determine how you will deliver program services
• Determine the customers to whom you will provide services
• Determine what assets and infrastructure you will need to implement your program
• Identify sources of funding and operation costs to develop your financial model
• Determine your governance structure
• Outline your business model
• Decide whether to proceed based on the viability of the business model
Create a Business Plan | Create your organization’s business plan, which describes how your operational and financial structure will support the delivery of energy efficiency services. | • Describe your assets and infrastructure
• Describe your products and services
• Describe your market and customers
• Describe your partners and competitors
• Summarize your organization’s governance
• Describe your financial structure
• Write your executive summary
Develop Evaluation Plans | Develop processes to evaluate your organization’s strengths, weaknesses, and market position on a regular basis. | • Reassess your market position
• Reconsider your vision, mission, and goals
• Revisit your business model
• Review key policies
• Identify risks and uncover new opportunities
• Gather sufficient information for decision-making
Develop Resources | Identify and develop needed resources to position your organization in the market and maintain a viable business model. | • Define resources to help you reach your goals
• Assess current resources and identify gaps
• Take action to fill resource gaps
Assess & Improve Processes | Develop processes, strategies, and procedures to continuously improve your organization’s operations and position in the market. | • Track and collect data on your organization’s performance
• Review and assess the data you have collected
• Make decisions and implement solutions based on your data analysis
• Regularly review and re-evaluate your data to ensure continuous improvement
Communicate Impacts | Publicize benefits and lessons learned resulting from your organization’s success in the market. | • Link events, milestones, and activities to your communications strategy
• Define the purpose of your communication
• Identify audiences
• Decide on key information and messages
• Choose and develop products
• Choose and use communication channels
• Assess and refine your communication strategy

## ProgramDesign
Program Design & Customer Experience |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
Design a residential energy efficiency program that provides customers with a positive experience by integrating marketing and outreach, contractor coordination, incentives, financing, and program evaluation in a streamlined way. |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Stage | Stage Description | Step-by-Step | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Assess the Market | Research and analyze the specific barriers, needs, and opportunities for a residential energy efficiency program in your community. | • Understand market demand, local policies, and building stock
• Assess your potential customers’ motivations for home energy upgrades
• Assess your potential customers’ need for loans and other financial products
• Assess your local contractor network and workforce development resources
• Analyze program strengths, weaknesses, opportunities, and threats (SWOT) to inform design
Set Goals & Objectives | Establish program goals and objectives to clarify what you want your program to achieve and to guide program design and implementation over time. | • Set long-term program goals
• Set specific and measurable program objectives
• Set objectives for individual program components
• Get input from stakeholders
Identify Partners | Establish relationships with organizations that can help deliver your program by enhancing your knowledge, resources, capabilities and access to customers and contractors. | • Identify areas where your program would benefit from added strength
• Identify potential partners that can strengthen your program
• Recruit partners by understanding their goals and motivations
• Establish ongoing coordination and communication with partners
Make Design Decisions | Solidify your program strategy and decide which customers you will focus on; what products, services, and support you will provide; and how you will partner with contractors and others to deliver services to your customers. | • Select your target market sector(s)
• Identify barriers to overcome with customers
• Select your products and/or services for customers
• Determine how you will deliver services
• Select and design key program coordination and communication activities
• Get feedback on your program design
Develop Implementation Plans | Develop a detailed plan for launching and operating your program that integrates all program components into a process that is customer-friendly and efficient for contractors and other partners. | • Identify the program components your program will undertake
• Use workflow diagrams to illustrate and refine program processes
• Establish staffing requirements, roles, and responsibilities for all aspects of program implementation
• Develop a program budget
• Use a project management approach to integrate and sequence program pre-launch, launch, and operational activities
Develop Evaluation Plans | Establish metrics and measurement strategies for understanding whether you are effectively achieving your program goals and meeting your customers’ needs, while identifying areas that can be improved. | • Establish program metrics that reflect your goals and objectives
• Establish direct and indirect customer experience metrics
• Document measurement strategies for collecting data
• Establish responsibilities for internal review of evaluation results
Develop Resources | Develop the necessary materials, tools, and staff capacity to effectively deliver and manage your program | • Decide who will implement the program
• Hire and train a program team
• Develop project tracking systems
• Develop customer care resources
• Develop customer intake process templates and forms
• Develop financial processing systems for incentives (as needed)
Deliver Program | Ensure a positive customer experience with your program from launch through implementation over time. | • Before launch, ensure that all resources and processes are in place for delivering the program
• Consider a soft launch to test systems, workflows, and processes
• Launch the program
• Manage the program effectively over time
Assess & Improves Processes | Improve your program’s efficiency and effectiveness through regular information collection, assessment, decision-making, adaptation, and communication | • Track quantitative and qualitative information for assessing program process and impacts
• Establish internal and external processes for reviewing and communicating program performance
• Regularly review and assess program metrics and feedback to determine what is working well and what is not
• Make decisions about program design changes and communicate them
Communicate Impacts | Develop a strategy for communicating program impacts and benefits to key audiences to create and sustain support and engagement. | • Determine communications requirements and purpose
• Develop a communications strategy
• Gather quantitative and qualitative information, including customer feedback
• Evaluate communications channels
• Develop communications products
• Evaluate and refine your communications strategy

## DataCollection
Evaluation & Data Collection |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
Develop evidence-based insights into your program’s performance through thirdparty process and impact evaluations. Craft effective data collection strategies and timely evaluations to identify important program achievements as well as opportunities for making improvements. |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Stage | Stage Description | Step-by-Step | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Develop Evaluation Plans | Identify the right questions to ask, appropriate metrics to collect, and the processes needed to initiate third-party impact and process evaluations. | • Determine the type(s) of evaluation
• Determine the scope of the evaluation(s)
• Develop a timeline for evaluation activities
• Decide how to determine your program’s cost-effectiveness
• Solicit proposals for evaluation services
• Evaluate proposals
• Negotiate and execute the contract
Develop Resources | Identify and implement systems and tools that will support data collection and data quality necessary for effective evaluation. | • Identify the types of data you need and how you will collect the data
• Identify the processes and tools for collecting and assessing program data
• Test your tools and processes before program launch
Conduct Evaluation | Manage third-party impact and process evaluation activities by coordinating with evaluators, transferring data, and overseeing evaluation deliverables. | • Oversee evaluation activities
• Review evaluation deliverables
• Identify and mitigate potential risks
• Adjust scope and timeline to accommodate evaluation changes
• Communicate progress throughout the evaluation process
Communicate Impacts | Communicate pertinent results of evaluations to program staff, partners, and stakeholders. | • Understand and interpret evaluation results
• Choose appropriate communications products and channels to reach your stakeholders
• Determine how to present pertinent evaluation results in your communications products
• Share evaluation results with program managers

## Marketing
Marketing and Outreach |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
Spur customer demand for your program’s services by understanding your target audience and motivating them to act using effective messaging, marketing and outreach tactics, and attractive program offers. |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Stage | Stage Description | Step-by-Step | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Assess the Market | Identify and prioritize potential target audiences based on their likely receptivity to your program’s services | • Develop a market research plan based on available resources and research techniques
• Conduct audience research to determine who should be the focus of your marketing and outreach
• Categorize your target audiences to narrow the focus of your marketing and outreach efforts
Set Goals & Objectives | Establish specific marketing and outreach goals, objectives, targets, and timeframes. | • Review program goals
• Set marketing and outreach objectives that tie to your program goals
• Obtain management and stakeholder buy-in and approvals
Identify Partners | Establish relationships with organizations that will assist with program marketing and outreach. | • Assess gaps that marketing and outreach partners could help fill
• Determine and evaluate potential partners
• Recruit marketing and outreach partners
• Develop a partnership agreement
• Engage partners early and often
Make Design Decisions | Decide on priority target audience segments, messages, and incentives that will motivate customers. | • Finalize your priority target audiences
• Articulate your value proposition for customers
• Develop messages to motivate action
• Build a consistent brand platform
• Design financial and non-financial incentives
• Communicate your decisions to partners
Develop Implementation Plans | Develop a marketing and outreach plan that details your strategies and tactics, workflows and timelines, staff roles and responsibilities, and budget. | • Develop marketing and outreach strategies and tactics
• Define marketing and outreach staff needs, roles, and responsibilities
• Create a marketing and outreach workplan
• Establish a marketing budget
• Communicate your plan with stakeholders
Develop Evaluation Plans | Develop a plan and metrics to evaluate the effectiveness of your marketing and outreach strategies. | • Identify metrics and evaluation criteria for each marketing and outreach objective
• Draft a marketing and outreach evaluation plan
• Share your evaluation plan with partners
Develop Resources | Create your program's branding guidelines and materials to elevate program visibility and support your marketing and outreach efforts. | • Staff and plan to develop marketing and outreach resources
• Create a distribution plan
• Develop materials that motivate with a call to action
• Brand your outreach consistently
• Use traditional and modern materials
• Share your materials internally and with partners
Deliver Program | Implement marketing and outreach activities in coordination with other program components to generate demand for your program's services. | • Assess your marketing program’s readiness
• Consider a pilot or “soft launch”
• Launch your marketing efforts
• Build on what works and adjust as needed
Assess & Improves Processes | Monitor the effectiveness of marketing and outreach strategies and adapt as needed. | • Track progress using key metrics
• Collect customer and partner feedback
• Review and evaluate data
• Decide how to improve marketing efforts mid-stream and reconsider overall marketing strategies if necessary
• Communicate decisions to partners
Communicate Impacts | Communicate marketing and outreach results internally and to partners. | • Collect marketing and outreach successes and lessons learned as you go
• Share marketing and outreach impacts internally and with partners

## Financing
Financing |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
Ensure that your program’s customers have access to affordable financing, so they can pay for the products and services you offer. |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Stage | Stage Description | Step-by-Step | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Assess the Market | Determine how your target audience currently funds energy efficiency services, to what extent upfront cost is a barrier, and whether improvements to their financing options would increase the uptake of energy efficiency measures. | • Assess the characteristics of target customers and identify gaps
• Identify lenders and understand available loan products
Set Goals & Objectives | Establish goals, objectives, and timeframes for your financing activities. | • Review program goals
• Set financing objectives that tie to your program goals
• Reach out to stakeholders for insight and refinement
Identify Partners | Identify and partner with financial institutions that can provide capital, underwriting, and other functions to enable your customers to access financing. | • Identify lenders
• Engage lenders
• Determine the process for soliciting proposals from prospective lending partners
• Evaluate proposals
• Negotiate and execute the lending agreement
Make Design Decisions | Determine if enhancements to existing financing products or the development of new products are necessary to allow you to achieve your goals and objectives. | • Define the financing problem or opportunity that you intend to address
• Decide on your program’s financing activities
• Determine which functions your program will perform and which functions your partners or subcontractors will perform
• Plan for the long-term
Develop Implementation Plans | Develop a plan to implement your financing activities, with defined roles for financial institution partners, contractors, customers, and your program. | • Identify steps relevant to your financing model to implement your financing activities
• Document the flow of funds
• Establish internal staffing requirements and roles/responsibilities
• Develop a timeline for key milestones and a budget for implementing your financing activities
• Share your implementation plan with your lending partners
Develop Evaluation Plans | Establish an evaluation plan that will allow you to determine how your financing activities are impacting the market. | • Establish metrics based on your goals and objectives
• Design the measurement strategies relevant to your financing model
• Establish how data will be transferred, stored, and managed
• Design the process and the schedule for data review and assessment
Develop Resources | Develop the procurement, outreach, and loan support resources required to perform your financing activities. | • Hire and train staff
• Identify the resources needed to implement your financing activities
• Develop internal and external resources that conform to your program’s brand
Deliver Program | Launch your financing activities in coordination with other program components. | • Prepare to implement your financing activities
• Consider a soft launch or pilot to test systems, workflows, and processes
• Launch your financing activities and manage them over time, including adjustments to program design based on feedback from stakeholders
Assess & Improves Processes | Focus on the continuous improvement of your financing activities by tracking and evaluating data, responding to feedback, and modifying strategies when needed. | • Collect and track data
• Review and evaluate data
• Make decisions to improve your financing activity processes
• Communicate process change decisions to your partners
Communicate Impacts | Communicate the results of your financing activities to internal and external partners. | • Collect examples, stories, lessons learned, best practices, and data trends that highlight financing successes
• Communicate program impacts with your lending partners

## WorkforceDevlopment
Contractor Engagement & Workforce Development |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
Engage your most important partners, the workforce that delivers your program’s products and services in customers’ homes. Identify what kinds of support local contractors need to help achieve your program’s goals. |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Stage | Stage Description | Step-by-Step | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Assess the Market | Assess the quantity and capacity of available contractors and workforce development providers to meet market needs. | • Identify existing home performance contractors in your market
• Find other contractors that could expand their services to include energy upgrades
• Assess the need for new skills and certifications for contractors
• Evaluate existing training and education providers who could become workforce development partners
• Identify organizations that can help find workers and match them to jobs
Set Goals & Objectives | Establish or refine specific workforce and contractor engagement goals, objectives, targets, and time frames. | • Review program goals related to contractor engagement and workforce development
• Establish specific contractor engagement and workforce development objectives
• Discuss and refine the goals and objectives with potential contractor and workforce development partners
Identify Partners | Establish relationships with contractors and organizations that recruit, train, and certify workers. | • Assess potential contractor partners
• Develop strategies for contractor recruitment
• Establish ongoing relationships with contractors
• Engage and recruit workforce development partners
• Evaluate potential workforce development and employment partners
• Establish partnership agreements with workforce development partners
Make Design Decisions | Decide on strategies for training, workforce standards, and contractor coordination. | • Establish standards for ensuring quality work
• Determine contractor participation requirements
• Set guidelines for how your program will interact with contractors
• Decide on contractor incentives and financial support
• Outline contractor engagement and support activities
• Decide on the content and approach for training
• Outline workforce development activities
• Collaborate with contractors and workforce development partners to develop program design
Develop Implementation Plans | Develop workforce development, contractor coordination, and quality assurance plans. | • Plan contractor recruitment and enrollment activities
• Plan for program process and business support for contractors
• Outline contractor training, incentives, and financial support
• Establish contractor participation procedures
• Define the quality assurance plan for your program
• Create a workforce development plan
• Plan for ongoing coordination and feedback with contractors and workforce development partners
• Develop a staffing plan, timeline, and budget
Develop Evaluation Plans | Develop a workforce quality assurance and quality control plan. | • Establish metrics and qualitative evaluation questions based on goals and objectives
• Design measurement strategies and a process and schedule for data review and assessment
• Design an approach for managing and sharing data internally and with partners
• Integrate these metrics and strategies into your overall evaluation plan
Develop Resources | Develop workforce and contractor engagement procedures, forms, and materials. | • Hire and train program staff
• Create program forms and materials for contractors
• Create contractor recruitment and enrollment materials
• Plan for regular contractor meetings
• Develop training resources for participating contractors
• Create other resources and processes to support contractors
• Develop contractor marketing support materials
• Develop process evaluation materials
Deliver Program | Implement contractor coordination and workforce recruitment and training in concert with other program components. | • Ensure that your program partners, procedures, plans, and resources are ready
• Consider a soft launch or pilot to test systems, workflows, and processes
• Recruit and bring contractors onboard
• Provide program delivery support for participating contractors
• Verify the quality of your program services
• Integrate workforce development with contractor engagement
Assess & Improves Processes | Monitor the effectiveness of workforce efforts, motivate continuous improvement, address low performers, and adapt as needed. | • Track program operations and external feedback from program partners, contractors, and customers
• Review and evaluate the collected data
• Share performance data and feedback
• Make improvement decisions with relevant partners and stakeholders
• Communicate decisions and changes to contractors
Communicate Impacts | Communicate program results to workforce stakeholders and contractor partners. | • Highlight contractor and workforce development successes
• Communicate program impacts to contractors and training provider partners