## Instructions
COVID-19 72-Hour Response Plan Checklist
Background: Many countries and organizations have asked for recommendations on what actions to take during the first 72 hours of a large-scale COVID-19 outbreak to establish a coordinated multi-sectoral response. This tool is based off of a 72-hour response plan developed by the CDC Kenya Office and Ministry of Health Kenya and adapted to incorporate emergency management and rapid response team principles. This checklist should be adapted to each country’s existing response structure and response context. While full measures to establish a comprehensive Public Health Emergency Management program cannot occur during an active response, there are certain areas that can be anticipated and planned for in advance, to facilitate a coordinated response in real time. This plan was created to help countries and sub-national administrative units such as regions and districts implement initial emergency response functions while responding to COVID-19. CDC SMEs are also available to provide further technical assistance as needed.
How to Use: This plan is in a checklist format and contains recommendations on national and sub-national level activities that should be considered during a given time period. The tool is intended to be flexible; countries may re-prioritize, add, or omit activities based on their internal response plans. Read the document in its entirety, mark any activities that have been completed, prioritize remaining activities and begin working through the tool. As activities are initiated, update the “started” column and as items are completed, mark the “completed” column. Assign each activity to a responsible person or team and if possible, determine an alternate point of contact.
Target Audience: Intended for officials from countries’ CDC Country offices, Ministries of Health, National Public Health Institutes, and Disaster Management entities at the national or subnational levels. Can include:
a. Emergency response manager/coordinator positions
b. Individuals involved in public health emergency response decision-making at national and subnational levels
c. Graduates of the CDC Public Health Emergency Management Fellowship
d. PHEOC managers, if they exist in the country’s response structure
e. Risk communication experts
Ideally a lead point of contact and alternate (when lead is not available) will maintain and update the form, after the priority activities have been identified and assigned.
References:
WHO Handbook for Developing a Public Health Emergency Operations Center (2015)
WHO Handbook for Developing a PHEOC Part A: Policies, Plans, and Procedures
WHO Handbook for Developing a PHEOC Part C: Training and Exercises
Questions? Please contact the COVID-19 CDC International Task Force eocevent223@cdc.gov

## Prior to Response
Prior to Large Scale COVID19 Response Activation
Time & Date Tracker: __ __ : __ __ , ____ / ____ / 2020 to __ __ : __ __ , ____ / ____ / 2020
Status | Level of Coordination | Activity | Responsible | Alternate | Notes/Comments
| National | Engage with national authorities to identify appropriate coordination mechanism.
| National | Initiate initial capacity assessment and risk analysis, including mapping of vulnerable populations. Note: If event meets WHO grading criteria, notify WHO, National IHR focal point and international partners.
| National | Begin engaging with national authorities and key partners to begin developing a country-specific operational plan with estimated resource requirements for COVID-19 preparedness and response which addresses and identifies POCs for the following: • Country-level coordination, planning, and monitoring • Risk communication and community engagement • Epidemiology and surveillance • Points of entry • National laboratories • Infection prevention and control • Case management, isolation and quarantine • Operations support and logistics • Multidisciplinary rapid response teams or GO Team |  |  | Per WHO guidance, strategies should address • Coordination and planning • Engage and mobilize communities to limit exposure • Find, test, isolate and care for cases and quarantine contacts to control transmission • Provide clinical care and maintain essential health services to reduce mortality Reference: WHO COVID Strategy Update: https://www.who.int/publications-detail/strategic-preparedness-and-response-plan-for-the-new-coronavirus
| National | Establish/Activate (if pre-existing) a COVID-19 multidisciplinary rapid response team to be on-call for immediate deployment if a case is identified. Consider technical areas to be represented: • Infection prevention and control • Epidemiology/surveillance (including case investigation and contact tracing) • Risk communication and community engagement Readiness for responders should include: • COVID-19 -specific information/just-in-time training • Provision of national (or WHO) guidelines/standardized forms • Equipment/travel bag packed
| National | Convene preliminary assessment with initial coordination team of COVID19 impact to determine if a national level response is required. During this meeting the team should: • Recommend activation of the National level PHEOC/ Coordination Center • Identify the Lead Ministry/Agency for the Response • Identify Incident Manager to provide strategic direction to COVID response staff |  |  | If yes, proceed through checklist. If no, continue to monitor the situation and prepare to respond. The Incident Manager should have leadership experience and access to subject matter experts in respiratory Illness. This IM also has the authority to lead and provide strategic direction to national level response.
| National | Identify a central location or PHEOC (Public Health Emergency Operations Center) to serve as information hub and coordination center for response. Identify any equipment and IT needs (computers, meeting space, and area to display response data, video-teleconferencing capability).
| Sub-National | Identify a central location (Public Health Emergency Operations Center) to serve as information hub and coordination center for response. Recommend: If no sub-national PHEOC is available; • Identify a location to establish an Emergency Response Coordination Center (ERCC) to serve as the information hub and coordination center for response.
| National | Identify Technical/Pillar Leads to provide technical direction to COVID response staff on • Risk communication and community engagement • Epidemiology/surveillance • Points of entry • National laboratories • Infection prevention and control • Case management • Operations support and logistics • Multidisciplinary rapid response teams or GO team
| Sub-National | Appoint a local Incident Manager in each affected district and/or region to manage and coordinate local level response efforts. Appoint Technical/Pillar Leads at local level will lead implement direct response interventions in: • Epidemiology/surveillance (including case investigation and contact tracing) • Laboratory • Case management • Infection prevention and control • Risk communication and social mobilization Ensure this structure is shared with the national level Coordination Team
| Sub-National | Provides information to national level on technical assistance, guidance, and resources needed

## Hours 0-12
Response Checklist (0-12 Hours)
Time & Date Tracker: __ __ : __ __ , ____ / ____ / 2020 to __ __ : __ __ , ____ / ____ / 2020
Status | Level of Coordination | Activity | Responsible | Alternate | Notes/Comments
| National | Appoint an Incident Manager (or equivalent position) from the Lead Agency to provide strategic direction and coordination of response actions which address: • Coordination and planning • Engagement and mobilization of communities to limit exposure • Finding, testing, isolating and caring for cases and quarantine contacts to control transmission • Providing clinical care and maintain essential health services to reduce mortality |  |  | IM facilitations the creation of common outcome measures, common vision, goals, and objectives, and coordination of actions. The appointment of IM and activation of the Incident Management Structure are one of three criteria the PHEOC is activated. The other two criteria are notification of the activation, and development of an Incident Action Plan or tool that manages the response using common objectives. Reference: WHO COVID Strategy Update: https://www.who.int/publications-detail/strategic-preparedness-and-response-plan-for-the-new-coronavirus
| National | Appoint Technical Experts to serve as Technical/Pillar Leads for the following areas and identify any staffing gaps • Risk communication and community engagement • Epidemiology/ surveillance • Points of entry • National laboratories • Infection prevention and control • Case management • Rapid response teams
| National | Appoint IMS Section Leads or equivalent Pillars for the following areas and identify any staffing gaps: • Operations • Planning • Logistics • Finance and Administration |  |  | • Operations/Scientific Section Lead- Ensures coordination between technical/pillar groups This position would be filled by someone within Ministry of Health. • Planning Section Lead- collection of data, analysis, and planning of future actions based on the likely course of the incident and the resources available for the response This position would be filled by someone within Ministry of Health. • Logistics Section Lead- acquires, tracks, stores, stages, maintains, and disposes of material resources required for the response. This position would be filled by someone within MoH or National Pharmacy. • Finance/Admin Lead- cash flow management; tracking of material and human resource costs; budget preparation and monitoring; and production and maintenance of administrative records. This position would be filled by someone within MoH or Ministry of Finance. References: WHO Handbook for Developing a Public Health Emergency Operations Center (2015) https://www.who.int/ihr/publications/9789241565134_eng/en/
| National | Identify and Appoint Staff for IMS Management Functions: •Public Information Officer (Spokesperson) • Liaison Officer • Safety/ Security |  |  | •Public Information Officer (Spokesperson) - Develops messages and manages communications for media and the general public. This person could be the Lead from the Health Communications Pillar • Liaison Officer (or equivalent)- coordinates with other ministries/agencies/donors supporting response activities. This position would be filled by someone within Ministry of Health. • Safety/Security Officer-assess risk and develops messages for health and safety of responders. Note: Worker safety during COVID19 response efforts is very important. This position could be filled by someone within MoH or Ministry of Defense or National Police. References: WHO Handbook for Developing a Public Health Emergency Operations Center (2015) https://www.who.int/ihr/publications/9789241565134_eng/en/
| National | Incident Manager, Technical/Pillar and IMS Section Leads will develop initial response objectives and priority activities for the next operational period. |  |  | Operational period is defined as the time required to achieve a specific set of objectives. WHO recommends developing a plan for the initial 3 months.
| National & Sub-National | Deploy initial multidisciplinary RRT for immediate deployment after pre-deployment briefing, providing equipment and any just-in-time training. Prepare for additional rapid response teams. |  |  | To provide investigation assistance and glean information for the PHEOC to start initial response actions.
| National | Develop organogramme for the initial Incident Management System and/or coordination mechanism which incorporates the following functions. MS Management Functions: • Incident Manager • Public Information Officer (Spokesperson) • Liaison Officer • Safety/Security Operations Section composed of Technical Pillars: • Risk communication and community engagement • Epidemiology/ Surveillance • Points of entry • National laboratories • Infection prevention and control • Case management • Rapid response teams • Planning Section • Logistics Section • Finance and Administration Section |  |  | References: WHO Handbook for Developing a Public Health Emergency Operations Center (2015) https://www.who.int/ihr/publications/9789241565134_eng/en/
| National | Planning Team develops and distribute organigramme of initial response structure and response objectives/priorities. (Initial Incident Action Plan) |  |  | Share with sub-national PHEOCs or Coordination Centers.
| National & Sub-National | Establish mechanism to coordinate, communicate and provide technical and operational support to field sites. |  |  | This could be a desk within the PHEOC to receive and disseminate information to and from sub-national coordination centers.

## Hours 12-24 (Day 1)
Response Checklist (12-24 Hours)
Time & Date Tracker: __ __ : __ __ , ____ / ____ / 2020 to __ __ : __ __ , ____ / ____ / 2020
Status | Level of Coordination | Activity | Responsible | Alternate | Notes/Comments
| National & Sub-National | Technical/Pillar Leads establish initial meetings with respective teams to determine initial response activities and a list of resources needed for the next 30 days. |  |  | Once established this information can be shared with the Operations and Planning Section Leads to incorporate in the Incident Action Plan.
| National & Sub-National | Establish communication and coordination mechanisms/ structure with all deployers at National and regional levels to obtain real-time data and information from field teams.
| National | Establish initial response talking points and messaging for media and public. Continue developing and refining messages for the public throughout the response. |  |  | •Public Information Officer (Spokesperson) - Develops messages and manages communications for media and the general public, however, the Incident Manager must approve all response messaging. References: WHO Framework for a PHEOC https://www.who.int/ihr/publications/9789241565134_eng/en/
| National & Sub-National | Deploy multidisciplinary RRT(s) to hotspot for additional support to initial RRT expanding technical expertise. |  |  | Define RRT Mission, purpose, and objectives.
| National | Identify and establish initial PHEOC information systems for response. |  |  | For Example: 1. Resources (leadership, policies, financial and human resources, infrastructure) 2. Indicators (e.g. morbidity, mortality, environmental risks, health resources availability and readiness, vaccine coverage) 3. Data sources (e.g. common operational datasets, health facilities data, reports from subnational health management teams and coordination meetings, health workforce, human and animal surveillance, laboratories, data on stockpiles of medicines and commodities, financial data, etc.) More information can be found in the WHO Framework for a Developing a PHEOC on (p.27). References: WHO Handbook for Developing a PHEOC (2015) https://www.who.int/ihr/publications/9789241565134_eng/en/
| National | Establish Common Operating Picture/Situational Awareness area in PHEOC to display real time data and response information. |  |  | Once established, this information can be shared with the Operations and Planning Section Leads to incorporate in the Incident Action Plan.
| National | Review and utilize all existing Standard Operating Procedures (SOPs) for: IMS Management Functions • Incident Manager •Public Information Officer (Spokesperson) • Liaison Officer • Safety/Security Officer IMS Sections Include: Planning Section Logistics Section Finance and Administration Section Operations Section (composed of Technical Pillars) • Risk communication and community engagement • Epidemiology/surveillance, • Points of entry • National laboratories • Infection prevention and control • Case management • Rapid response teams |  |  | Note if SOPs are needed and don’t exist mark this as a gap and assign to relevant groups to create SOPs if needed. References: WHO Framework for a PHEOC: Part A Policies, Plans, and Procedures https://www.who.int/activities/coordinating-a-global-network-of-emergency-operations-centres
| National & Sub-National | Technical Pillars refer to Country Operational Plan or WHO Guidance on Operational Plans to develop strategies for their area of focus. https://www.who.int/docs/default-source/coronaviruse/covid-19-sprp-unct-guidelines.pdf?sfvrsn=81ff43d8_4
| National | Conduct first Incident Manager Briefing. Each IMS Section and Technical Pillars will share their reports with IM and determine priorities for next 24 hours. |  |  | These meetings should occur daily during the initial stages of response. Establish regular briefing schedule. Priorities should fall in line with the IM's response objectives. Sub-national Coordination Centers should participate virtually.
| National & Sub-National | Create and display list of all response related meetings and briefings (staff rhythm) in the PHEOC/Coordination Center. |  |  | Operations Section should develop with the input from each Section and Pillar lead. Section and Pillar leads should forward list of their scheduled functional meetings with time, location, purpose, and attendees to Operations.
| National & Sub-National | Identify surge staff to support national and sub-national responses efforts for next 30 days.
| National | Planning Team begins compiling response data, and objectives for each technical working group to create an operational response plan or Incident Action Plan for the next operational period (30-90 days) to include but not limited to: Situation Overview Epidemiological Data Response Objectives by Technical Area for next operational period Organigramme of current IMS.
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: End sentence with a period.
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: End last sentence with a period.

## Hours 24-48 (Day 2)
Response Checklist (24-48 Hours)
Time & Date Tracker: __ __ : __ __ , ____ / ____ / 2020 to __ __ : __ __ , ____ / ____ / 2020
Status | Level of Coordination | Activity | Responsible | Alternate | Notes/Comments
| National & Sub-National | Data and Information from last 24hrs displayed in the PHEOC/Coordination Center.
| National | Establish contact lists, distribution lists and mechanisms to communicate with all responders. |  |  | Operations Section should develop list with input from other sections and pillars.
| National & Sub-National | Establish Points of Contact Lists for: • Laboratories • Points of entry • Hospitals • Media • NGOs • Police/security |  |  | Operations Section should compile list with input from other sections and pillars. Include (Name, Position, Phone, E-mail and Location).
| National & Sub-National | Technical Pillar Leads create mechanism for data collection from field teams.
| National & Sub-National | Establish regular calls with RRTs, field teams, and local leadership in affected areas. |  |  | All Technical Pillar Leads with field teams should do this, the Logistics and Operations Sections should be involved in these calls to identify additional staffing or resource needs.
| National & Sub-National | Risk and safety messages for responders are established based on risk assessments of impacted areas and input from field teams. |  |  | Typically done by the Safety Officer(s) at field and national level.
| National | Develop and disseminate first Incident Situation Report (SITREP) addressing: • A record of the event • Evolving analysis • Updates on progress toward major goals and objectives • Status of resources • Public risk management message |  |  | A SITREP is a routinely produced report that provides current information about an emergency response and immediate and future response actions, with analysis of the impact of the emergency and identification of related management issues. Input is gathered from field reports provided by technical leads and national level PHEOC Section Leads. Reference: WHO Handbook for developing a PHEOC Part A: Plans, Policies, Procedures (page 37) https://www.who.int/activities/coordinating-a-global-network-of-emergency-operations-centres

## Hours 48-72 (Day 3)
Response Checklist (48-72 Hours)
Time & Date Tracker: __ __ : __ __ , ____ / ____ / 2020 to __ __ : __ __ , ____ / ____ / 2020
Status | Level of Coordination | Activity | Responsible | Alternate | Notes/Comments
| National & Sub-National | Determine whether current supply chain procedures can be used for COVID-19 response, and if not, identify new sites and establish plan for distribution of COVID-19 medical supplies and equipment. |  |  | Logistics Section is responsible for conducting these assessments. Review Medical Counter Measures Plans if available (GHSA countries)
| National & Sub-National | Begin strengthening supply chain (forecasting, procurement, warehousing, transportation, distribution, partner coordination).
| National & Sub-National | Compile input from last 24 hours: • Significant Accomplishments • Objectives/Next Steps • Challenges • Resources needed
| National & Sub-National | Continue updating Common Operating Picture/Situational Awareness area in PHEOC to display real time data and response information. |  |  | Once established this information can be shared with the Operations and Planning Section Leads to incorporate into the Incident Action Plan.
| National & Sub-National | Initial staffing plan for next 30 days is established for central and field level support. |  |  | Technical Pillars provide input to Operations and Planning Section. Logistics supports mobilization of staff.
| National | Establish terms of reference for IMS general and technical positions.
| National | Finalize and distribute the Incident Action Plan or Response Plan for the next operational period (30,60 or 90 days). |  |  | Planning Section develops and distributes the Incident Action Plan or Response Plan among all responders and partners at the national and subnational level.